## Most Likely
| Year | Month | Data
| 2016 | [21 empty] | 2016 Cost | 2016 Cumulative Cost | 2017 | [23 empty] | 2017 Cost | 2017 Cumulative Cost | 2018 |  |  |  | 2018 Cost | 2018 Cumulative Cost | Total Cost | Total Cumulative Cost
| February |  | March |  | April |  | May |  | June |  | July |  | August |  | September |  | October |  | November |  | December |  |  |  | January |  | February |  | March |  | April |  | May |  | June |  | July |  | August |  | September |  | October |  | November |  | December |  |  |  | January |  | February
| Cost | Cumulative Cost | Cost | Cumulative Cost | Cost | Cumulative Cost | Cost | Cumulative Cost | Cost | Cumulative Cost | Cost | Cumulative Cost | Cost | Cumulative Cost | Cost | Cumulative Cost | Cost | Cumulative Cost | Cost | Cumulative Cost | Cost | Cumulative Cost |  |  | Cost | Cumulative Cost | Cost | Cumulative Cost | Cost | Cumulative Cost | Cost | Cumulative Cost | Cost | Cumulative Cost | Cost | Cumulative Cost | Cost | Cumulative Cost | Cost | Cumulative Cost | Cost | Cumulative Cost | Cost | Cumulative Cost | Cost | Cumulative Cost | Cost | Cumulative Cost |  |  | Cost | Cumulative Cost | Cost | Cumulative Cost
Total | 8456 | 8456 | 12654.6 | 21110.6 | 141283653.4 | 141304764 | 10211.3 | 141314975.3 | 18009.29 | 141332984.59 | 18618.508 | 141351603.098 | 19466.122 | 141371069.22 | 19154.2181 | 141390223.4381 | 17772.8949 | 141407996.333 | 18620.509 | 141426616.842 | 18618.509 | 141445235.351 | 141445235.351 | 141445235.351 | 18618.509 | 141463853.8599 | 16927.2809 | 141480781.1408 | 19466.123 | 141500247.2638 | 16927.2809 | 141517174.5447 | 19466.123 | 141536640.6677 | 18618.509 | 141555259.1767 | 17772.8949 | 141573032.0716 | 19466.123 | 141592498.1946 | 322284.7069 | 141914782.9016 | 476632.436 | 142391415.3375 | 5086680.0105 | 147478095.348 | 6153070.672 | 153631166.02 | 12185930.669 | 153631166.02 | 65229.21 | 153696395.23 | 9625.4 | 153706020.63 | 74854.61 | 153706020.63 | 153706020.63 | 153706020.63
|  |  | Cost | Planned Value
| 2016 | August | 0.13318 | 0.13318 |  |  | 9513 | 9513
|  | September | 0.16977 | 0.30295 |  |  | 12126.1 | 21639.1
|  | October | 330.0545 | 330.3574 |  |  | 23575320.0667 | 23596959.1667
|  | November | 1450.3096 | 1780.6671 |  |  | 103593544.6333 | 127190503.8
|  | December | 198.002 | 1978.6691 |  |  | 14143002.826 | 141333506.626
| 2017 | January | 0.26066 | 1978.9298 |  |  | 18618.508 | 141352125.134
|  | February | 0.23698 | 1979.1667 |  |  | 16927.28 | 141369052.414
|  | March | 0.27253 | 1979.4393 |  |  | 19466.122 | 141388518.536
|  | April | 0.24448 | 1979.6837 |  |  | 17462.9908 | 141405981.5268
|  | May | 0.2725 | 1979.9562 |  |  | 19464.123 | 141425445.6499
|  | June | 0.26069 | 1980.2169 |  |  | 18620.509 | 141444066.1588
|  | July | 0.24882 | 1980.4657 |  |  | 17772.8949 | 141461839.0538
|  | August | 0.27253 | 1980.7383 |  |  | 19466.123 | 141481305.1768
|  | September | 0.24882 | 1980.9871 |  |  | 17772.8949 | 141499078.0717
|  | October | 0.26066 | 1981.2478 |  |  | 18618.509 | 141517696.5807
|  | November | 0.26069 | 1981.5084 |  |  | 18620.509 | 141536317.0896
|  | December | 0.24882 | 1981.7573 |  |  | 17772.8949 | 141554089.9846
| 2018 | January | 0.2725 | 1982.0298 |  |  | 19464.123 | 141573554.1076
|  | February | 0.23698 | 1982.2667 |  |  | 16927.2809 | 141590481.3885
|  | March | 0.59737 | 1982.8641 |  |  | 42669.2526 | 141633150.641
|  | April | 8.6695 | 1991.5336 |  |  | 619247.593 | 142252398.234
|  | May | 49.7268 | 2041.2604 |  |  | 3551916.658 | 145804314.892
|  | June | 109.5523 | 2150.8127 |  |  | 7825162.135 | 153629477.027
|  | July | 0.31403 | 2151.1267 |  |  | 22430.382 | 153651907.409
|  | August | 1.1065 | 2152.2332 |  |  | 79037.252 | 153730944.661
|  | September | 0.55588 | 2152.7891 |  |  | 39705.4138 | 153770650.0748
|  | October | 0.61534 | 2153.4044 |  |  | 43952.6052 | 153814602.68
|  | November | 0.11616 | 2153.5206 |  |  | 8297.1 | 153822899.78
December
| 2019 | January
February
March
April
Contingency Reserve (163 days)
Contingency Reserve (IDR 568,090,436,000)
Management Reserve (IDR 272,000,000,000)

## Pessimistic
| Year | Month | Data
| 2016 | [9 empty] | 2016 Cost | 2016 Cumulative Cost | 2017 | [23 empty] | 2017 Cost | 2017 Cumulative Cost | 2018 | [23 empty] | 2018 Cost | 2018 Cumulative Cost | 2019 | [15 empty] | 2019 Cost | 2019 Cumulative Cost | Total Cost | Total Cumulative Cost
| August |  | September |  | October |  | November |  | December |  |  |  | January |  | February |  | March |  | April |  | May |  | June |  | July |  | August |  | September |  | October |  | November |  | December |  |  |  | January |  | February |  | March |  | April |  | May |  | June |  | July |  | August |  | September |  | October |  | November |  | December |  |  |  | January |  | February |  | March |  | April |  | May |  | June |  | July |  | August
| Cost | Cumulative Cost | Cost | Cumulative Cost | Cost | Cumulative Cost | Cost | Cumulative Cost | Cost | Cumulative Cost |  |  | Cost | Cumulative Cost | Cost | Cumulative Cost | Cost | Cumulative Cost | Cost | Cumulative Cost | Cost | Cumulative Cost | Cost | Cumulative Cost | Cost | Cumulative Cost | Cost | Cumulative Cost | Cost | Cumulative Cost | Cost | Cumulative Cost | Cost | Cumulative Cost | Cost | Cumulative Cost |  |  | Cost | Cumulative Cost | Cost | Cumulative Cost | Cost | Cumulative Cost | Cost | Cumulative Cost | Cost | Cumulative Cost | Cost | Cumulative Cost | Cost | Cumulative Cost | Cost | Cumulative Cost | Cost | Cumulative Cost | Cost | Cumulative Cost | Cost | Cumulative Cost | Cost | Cumulative Cost |  |  | Cost | Cumulative Cost | Cost | Cumulative Cost | Cost | Cumulative Cost | Cost | Cumulative Cost | Cost | Cumulative Cost | Cost | Cumulative Cost | Cost | Cumulative Cost | Cost | Cumulative Cost
Total | 6615.36 | 6615.36 | 8444.24 | 15059.6 | 8081.92 | 23141.52 | 7082.24 | 30223.76 | 64068571.8233 | 64098795.5833 | 64098795.5833 | 64098795.5833 | 82879248.9067 | 146978044.49 | 75344771.7333 | 222322816.2233 | 3777992.0861 | 226100808.3094 | 12617.8353 | 226113426.1447 | 14510.4106 | 226127936.5553 | 13878.2188 | 226141814.7741 | 13248.0271 | 226155062.8012 | 15297.6107 | 226170360.4118 | 13541.4321 | 226183901.844 | 14185.5956 | 226198087.4396 | 14187.5956 | 226212275.0352 | 13541.4321 | 226225816.4673 | 162127020.884 | 226225816.4673 | 14831.759 | 226240648.2263 | 12897.2687 | 226253545.495 | 14185.5956 | 226267731.0906 | 13541.4321 | 226281272.5228 | 14831.759 | 226296104.2818 | 13541.4321 | 226309645.7139 | 14185.5956 | 226323831.3095 | 14831.759 | 226338663.0685 | 18572.2987 | 226357235.3672 | 261820.9157 | 226619056.2829 | 643601.4237 | 227262657.7067 | 4570915.0333 | 231833572.74 | 5607756.2727 | 231833572.74 | 7576625.2011 | 239410197.9411 | 16286.7778 | 239426484.7189 | 56300.0111 | 239482784.73 | 9727.44 | 239492512.17 | 10170.96 | 239502683.13 | 8844.4 | 239511527.53 | 10137.7733 | 239521665.3033 | 6989.8667 | 239528655.17 | 7695082.43 | 239528655.17 | 239528655.17 | 239528655.17
|  |  | Cost | Planned Value
| 2016 | August | 0.092615 | 0.092615 |  |  | 6615.36 | 6615.36
|  | September | 0.11822 | 0.21083 |  |  | 8444.24 | 15059.6
|  | October | 0.11315 | 0.32398 |  |  | 8081.92 | 23141.52
|  | November | 0.099151 | 0.42313 |  |  | 7082.24 | 30223.76
|  | December | 896.96 | 897.3831 |  |  | 64068571.8233 | 64098795.5833
| 2017 | January | 1160.3095 | 2057.6926 |  |  | 82879248.9067 | 146978044.49
|  | February | 1054.8268 | 3112.5194 |  |  | 75344771.7333 | 222322816.2233
|  | March | 52.8919 | 3165.4113 |  |  | 3777992.0861 | 226100808.3094
|  | April | 0.17665 | 3165.588 |  |  | 12617.8353 | 226113426.1447
|  | May | 0.20315 | 3165.7911 |  |  | 14510.4106 | 226127936.5553
|  | June | 0.1943 | 3165.9854 |  |  | 13878.2188 | 226141814.7741
|  | July | 0.18547 | 3166.1709 |  |  | 13248.0271 | 226155062.8012
|  | August | 0.21417 | 3166.385 |  |  | 15297.6107 | 226170360.4118
|  | September | 0.18958 | 3166.5746 |  |  | 13541.4321 | 226183901.844
|  | October | 0.1986 | 3166.7732 |  |  | 14185.5956 | 226198087.4396
|  | November | 0.19863 | 3166.9719 |  |  | 14187.5956 | 226212275.0352
|  | December | 0.18958 | 3167.1614 |  |  | 13541.4321 | 226225816.4673
| 2018 | January | 0.20764 | 3167.3691 |  |  | 14831.759 | 226240648.2263
|  | February | 0.18056 | 3167.5496 |  |  | 12897.2687 | 226253545.495
|  | March | 0.1986 | 3167.7482 |  |  | 14185.5956 | 226267731.0906
|  | April | 0.18958 | 3167.9378 |  |  | 13541.4321 | 226281272.5228
|  | May | 0.20764 | 3168.1455 |  |  | 14831.759 | 226296104.2818
|  | June | 0.18958 | 3168.335 |  |  | 13541.4321 | 226309645.7139
|  | July | 0.1986 | 3168.5336 |  |  | 14185.5956 | 226323831.3095
|  | August | 0.20764 | 3168.7413 |  |  | 14831.759 | 226338663.0685
|  | September | 0.26001 | 3169.0013 |  |  | 18572.2987 | 226357235.3672
|  | October | 3.6655 | 3172.6668 |  |  | 261820.9157 | 226619056.2829
|  | November | 9.0104 | 3181.6772 |  |  | 643601.4237 | 227262657.7067
|  | December | 63.9928 | 3245.67 |  |  | 4570915.0333 | 231833572.74
| 2019 | January | 106.0728 | 3351.7428 |  |  | 7576625.2011 | 239410197.9411
|  | February | 0.22801 | 3351.9708 |  |  | 16286.7778 | 239426484.7189
|  | March | 0.7882 | 3352.759 |  |  | 56300.0111 | 239482784.73
|  | April | 0.13618 | 3352.8952 |  |  | 9727.44 | 239492512.17
|  | May | 0.14239 | 3353.0376 |  |  | 10170.96 | 239502683.13
|  | June | 0.12382 | 3353.1614 |  |  | 8844.4 | 239511527.53
|  | July | 0.14193 | 3353.3033 |  |  | 10137.7733 | 239521665.3033
|  | August | 0.097858 | 3353.4012 |  |  | 6989.8667 | 239528655.17
September
October
November
December

## Optimistic
| Year | Month | Data
| 2016 | [9 empty] | 2016 Cost | 2016 Cumulative Cost | 2017 | [23 empty] | 2017 Cost | 2017 Cumulative Cost | 2018 | [15 empty] | 2018 Cost | 2018 Cumulative Cost | Total Cost | Total Cumulative Cost
| August |  | September |  | October |  | November |  | December |  |  |  | January |  | February |  | March |  | April |  | May |  | June |  | July |  | August |  | September |  | October |  | November |  | December |  |  |  | January |  | February |  | March |  | April |  | May |  | June |  | July |  | August
| Cost | Cumulative Cost | Cost | Cumulative Cost | Cost | Cumulative Cost | Cost | Cumulative Cost | Cost | Cumulative Cost |  |  | Cost | Cumulative Cost | Cost | Cumulative Cost | Cost | Cumulative Cost | Cost | Cumulative Cost | Cost | Cumulative Cost | Cost | Cumulative Cost | Cost | Cumulative Cost | Cost | Cumulative Cost | Cost | Cumulative Cost | Cost | Cumulative Cost | Cost | Cumulative Cost | Cost | Cumulative Cost |  |  | Cost | Cumulative Cost | Cost | Cumulative Cost | Cost | Cumulative Cost | Cost | Cumulative Cost | Cost | Cumulative Cost | Cost | Cumulative Cost | Cost | Cumulative Cost | Cost | Cumulative Cost
Total | 13031.92 | 13031.92 | 84763656.88 | 84776688.8 | 56518942.8478 | 141295631.6478 | 23590.5422 | 141319222.19 | 23906.011 | 141343128.201 | 141343128.201 | 141343128.201 | 23219.9032 | 141366348.1042 | 21111.0938 | 141387459.198 | 24277.3079 | 141411736.5059 | 21111.0938 | 141432847.5998 | 24277.3079 | 141457124.9077 | 23219.9032 | 141480344.8109 | 107675.9991 | 141588020.81 | 7120000.6167 | 148708021.4267 | 45148.3533 | 148753169.78 | 0 | 7490557.47 | 0 | 7490534.47 | 0 | 7490517.47 | 7410041.579 | 148753169.78 | 0 | 7490517.47 | 0 | 7490517.47 | 0 | 7490517.47 | 0 | 7490517.47 | 0 | 7017038.13 | 0 | 6970094.55 | 0 | 275677.48 | 0 | 220742.04 | 0 | 7490517.47 | 148753169.78 | 148753169.78
|  |  | Cost | Planned Value
| 2016 | August | 0.18245 | 0.18245 |  |  | 13031.92 | 13031.92
|  | September | 1186.6912 | 1186.8736 |  |  | 84763656.88 | 84776688.8
|  | October | 791.2652 | 1978.1388 |  |  | 56518942.8478 | 141295631.6478
|  | November | 0.33027 | 1978.4691 |  |  | 23590.5422 | 141319222.19
|  | December | 0.33468 | 1978.8038 |  |  | 23906.011 | 141343128.201
| 2017 | January | 0.32508 | 1979.1289 |  |  | 23219.9032 | 141366348.1042
|  | February | 0.29556 | 1979.4244 |  |  | 21111.0938 | 141387459.198
|  | March | 0.33988 | 1979.7643 |  |  | 24277.3079 | 141411736.5059
|  | April | 0.29556 | 1980.0599 |  |  | 21111.0938 | 141432847.5998
|  | May | 0.33988 | 1980.3997 |  |  | 24277.3079 | 141457124.9077
|  | June | 0.32508 | 1980.7248 |  |  | 23219.9032 | 141480344.8109
|  | July | 1.5075 | 1982.2323 |  |  | 107675.9991 | 141588020.81
|  | August | 99.68 | 2081.9123 |  |  | 7120000.6167 | 148708021.4267
|  | September | 0.63208 | 2082.5444 |  |  | 45148.3533 | 148753169.78
October
November
December
| 2018 | January
February
March
April
May
June
July
August
September
October
November
December
| 2019 | January
February
March
April
May
June
July
August
September
October
November
December

## Monte Carlo Input
Planned Value
|  | Optimistic | Most Likely | Pessimistic
2016 | August | 0.18245 | 0.13318 | 0.092615
| September | 1186.8736 | 0.30295 | 0.21083
| October | 1978.1388 | 330.3574 | 0.32398
| November | 1978.4691 | 1780.6671 | 0.42313
| December | 1978.8038 | 1978.6656 | 897.3831
2017 | January | 1979.1289 | 1978.9263 | 2057.6926
| February | 1979.4244 | 1979.1632 | 3112.5194
| March | 1979.7643 | 1979.4358 | 3165.4113
| April | 1980.0599 | 1979.6802 | 3165.588
| May | 1980.3997 | 1979.9527 | 3165.7911
| June | 1980.7248 | 1980.2134 | 3165.9854
| July | 1982.2323 | 1980.4622 | 3166.1709
| August | 2081.9123 | 1980.7348 | 3166.385
| September | 2082.5444 | 1980.9836 | 3166.5746
| October |  | 1981.2443 | 3166.7732
| November |  | 1981.5049 | 3166.9719
| December |  | 1981.7538 | 3167.1614
2018 | January |  | 1982.0263 | 3167.3691
| February |  | 1982.2632 | 3167.5496
| March |  | 1985.5609 | 3167.7482
| April |  | 1993.0555 | 3167.9378
| May |  | 2041.2569 | 3168.1455
| June |  | 2150.8092 | 3168.335
| July |  | 2151.1232 | 3168.5336
| August |  | 2151.9082 | 3168.7413
| September |  |  | 3169.0013
| October |  |  | 3172.6668
| November |  |  | 3181.6772
| December |  |  | 3245.67
2019 | January |  |  | 3351.7428
| February |  |  | 3351.9708
| March |  |  | 3352.759
| April |  |  | 3352.8952
| May |  |  | 3353.0376
| June |  |  | 3353.1614
| July |  |  | 3353.3033
| August |  |  | 3353.4012
September
October
November
December