## Utk dicopy
Utk dicopy | [6 empty] | 568090436000
Schedule Three Point Estimation |  |  |  |  | Cost Three Point Estimation
44.17%
[5 empty] | Resource Name | Cost
WBS | Task Name | Duration |  |  |  | Optimistic | Most-likely | Pessimistic
|  | Optimistic | Most-Likely | Pessimistic | Total | 1291739716400 | 2151909564000 | 3.3534e+12
1 | ITF Establishment in Cilincing | 296 | 538 | 795 | Project Manager | 871486560 | 1210398000 | 1267924000
1.1 | Construction Planning | 4 | 8 | 11 | Project Engineer | 871214400 | 1210020000 | 1229200000
1.1.1 | Business Requirements List | 2 | 6 | 7 | Main Contractor | 155453760 | 215908000 | 227892000
1.1.1.1 | System Engineering | 2 | 6 | 7 | Sub-Contractor | 124992000 | 173600000 | 183190000
1.1.1.2 | Site Development | 2 | 6 | 7 | Finance and Administration | 774406080 | 1075564000 | 1087548000
1.1.1.3 | Civil Structures | 2 | 6 | 7 | Surveyor | 16863840 | 23422000 | 30618000
1.1.1.4 | Electrical Systems | 2 | 6 | 7 | Procurement | 155453760 | 215908000 | 227892000
1.1.1.5 | Thermal Systems | 2 | 6 | 7 | Architect | 231840000 | 322000000 | 331590000
1.1.1.6 | Storage Systems | 2 | 6 | 7 | Engineer | 353304000 | 490700000 | 500290000
1.1.1.7 | Mechanical Systems | 2 | 6 | 7 | MSW Recycling Package | 90014794800 | 150024658000 | 162879990000
1.1.1.8 | Instrumentation and Control Systems | 2 | 6 | 7 | Extruding Machine | 1203694800 | 2006158000 | 2102044000
1.1.1.9 | Auxiliary Systems | 2 | 6 | 7 | Leftover Waste Dryer | 1203694800 | 2006158000 | 2234554000
1.1.1.10 | Security System | 2 | 6 | 7 | Forklift | 1295221200 | 2158702000 | 2213666000
1.1.1.11 | Flow Systems | 2 | 6 | 7 | Building Material (Site Development) | 118784400 | 197974000 | 203014000
1.1.1.12 | Environmental Systems | 2 | 6 | 7 | Building Material (Civil Structures) | 370213200 | 617022000 | 696136000
1.1.2 | Process Models Design | 4 | 8 | 11 | Bailing Machine | 423696000 | 706160000 | 725662000
1.1.2.1 | System Engineering | 4 | 8 | 11 | Wire Machine | 507696000 | 846160000 | 942914000
1.1.2.2 | Site Development | 4 | 8 | 11 | Fertilizer Packaging System | 193536000 | 322560000 | 368788000
1.1.2.3 | Civil Structures | 4 | 8 | 11 | Fix Fence | 360502800 | 600838000 | 616434000
1.1.2.4 | Electrical Systems | 4 | 8 | 11 | CCTV | 15304800 | 25508000 | 29218000
1.1.2.5 | Thermal Systems | 4 | 8 | 11 | Personal Computer | 72718800 | 121198000 | 138488000
1.1.2.6 | Storage Systems | 4 | 8 | 11 | Security System | 14103600 | 23506000 | 25102000
1.1.2.7 | Mechanical Systems | 4 | 8 | 11 | Electricity Installment | 15002400 | 25004000 | 26096000
1.1.2.8 | Instrumentation and Control Systems | 4 | 8 | 11 | Generator Set | 534576000 | 890960000 | 955444000
1.1.2.9 | Auxiliary Systems | 4 | 8 | 11 | Communication Package | 16800000 | 28000000 | 32172000
1.1.2.10 | Security System | 4 | 8 | 11 | Conveyor | 675696000 | 1126160000 | 1241506000
1.1.2.11 | Flow Systems | 4 | 8 | 11 | Sorting Machine Package | 3914786400 | 6524644000 | 7419650000
1.1.2.12 | Environmental Systems | 4 | 8 | 11 | Plumbing System | 410407200 | 684012000 | 713258000
1.2 | Construction | 244 | 432 | 518 | Smart Thermal System | 118196400 | 196994000 | 202020000
1.2.1 | Site Development | 45 | 85 | 102 | Land and Land Acquisition | 1186700810400 | 1977834684000 | 3.1645e+12
1.2.2 | Civil Structures | 162 | 272 | 326 | Documentation | 2156000 | 2436000 | 3024000
1.2.3 | Electrical Systems | 4 | 10 | 12 | Report Writing | 868000 | 938000 | 1092000
1.2.4 | Thermal Systems | 5 | 15 | 18 | Report Publishing | 1442000 | 1610000 | 2002000
1.2.5 | Storage Systems | 3 | 5 | 6
1.2.6 | Mechanical Systems | 10 | 20 | 24
1.2.7 | Instrumentation and Control Systems | 18 | 30 | 36
1.2.8 | Auxiliary Systems | 5 | 7 | 8
1.2.9 | Security System | 5 | 7 | 8 | 296 | 4 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 244 | 45 | 162 | 4 | 5 | 3 | 10 | 18 | 5 | 5 | 10 | 15 | 46 | 30 | 5 | 11 | 14 | 14 | 14 | 14 | 5 | 1 | 15 | 15 | 13 | 5 | 2 | 3 | 3 | 7 | 5 | 1 | 1 | 4 | 1 | 2 | 1 | 5 | 2 | 1 | 1 | 250 | 4 | 3 | 1
1.2.10 | Flow Systems | 10 | 20 | 24 | 538 | 8 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 432 | 85 | 272 | 10 | 15 | 5 | 20 | 30 | 7 | 7 | 20 | 25 | 86 | 59 | 7 | 22 | 30 | 30 | 30 | 30 | 14 | 3 | 30 | 30 | 18 | 7 | 3 | 4 | 4 | 18 | 14 | 3 | 1 | 12 | 2 | 8 | 2 | 6 | 6 | 3 | 3 | 452 | 14 | 12 | 2
1.2.11 | Environmental Systems | 15 | 25 | 30 | 795 | 11 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 518 | 102 | 326 | 12 | 18 | 6 | 24 | 36 | 8 | 8 | 24 | 30 | 159 | 69 | 9 | 25 | 35 | 35 | 35 | 40 | 30 | 10 | 60 | 60 | 37 | 12 | 5 | 10 | 10 | 37 | 25 | 10 | 2 | 34 | 10 | 14 | 10 | 20 | 100 | 50 | 50 | 636 | 18 | 15 | 3
1.3 | Legal and Regulatory | 46 | 86 | 159
1.3.1 | Licensing | 30 | 59 | 69
1.3.1.1 | Waste Treatment | 5 | 7 | 9 | WBS | Task Name
1.3.1.2 | Machinery | 11 | 22 | 25 | 1.2.9 | Security System
1.3.1.3 | Plumbing | 14 | 30 | 35 | 1.2.10 | Flow Systems
1.3.1.4 | Electricity | 14 | 30 | 35 | 1.2.11 | Environmental Systems
1.3.1.5 | Land and Building | 14 | 30 | 35
1.3.2 | Government Permitting and Agreement | 14 | 30 | 40
1.3.2.1 | Acceptance Criteria | 5 | 14 | 30
1.3.2.2 | Issuance of Permit | 1 | 3 | 10
1.3.3 | Land Acquisition | 15 | 30 | 60
1.3.3.1 | Financing | 15 | 30 | 60
1.3.4 | Sustainability Impact Assessment | 13 | 18 | 37
1.3.4.1 | Preliminary Assessment | 5 | 7 | 12
1.3.4.2 | Impact Review | 2 | 3 | 5
1.3.4.3 | Magnitude Assessment | 3 | 4 | 10
1.3.4.4 | Mitigation Plan | 3 | 4 | 10
1.3.5 | Contractor Agreements | 7 | 18 | 37
1.3.5.1 | Tender Auctions | 5 | 14 | 25
1.3.5.2 | Bargaining | 1 | 3 | 10
1.3.5.3 | Contract Agreement | 1 | 1 | 2
1.3.6 | Work Agreements | 4 | 12 | 34
1.3.6.1 | Initial Agreement | 1 | 2 | 10
1.3.6.2 | Bargaining | 2 | 8 | 14
1.3.6.3 | Final Agreement | 1 | 2 | 10
1.3.7 | Other Legal/Regulatory Requirements | 5 | 6 | 20
1.4 | Testing | 2 | 6 | 100
1.4.1 | System Test | 1 | 3 | 50
1.4.2 | Acceptance Test | 1 | 3 | 50
1.5 | Reporting and Documentation | 250 | 452 | 636
1.5.1 | Annual Project Report | Repetitive during construction
1.5.1.1 | Project Documentation
1.5.1.2 | Report Writing
1.5.1.3 | Report Publishing
1.5.2 | Final Project Report | 4 | 14 | 18
1.5.2.1 | Report Writing | 3 | 12 | 15
1.5.2.2 | Report Publishing | 1 | 2 | 3

## Schedule output
Min | 471 |  |  | 67
Max | 752 |  | 44 | 538 | 8% |  |  | Min | 458 |  |  | CP | 0 |  | 40%
Iteration | 1200 |  |  | -214 |  | 701 | 163 | Max | 756 |  | 49 |  | 701 | 95%
[8 empty] | Iteration | 1200
| Duration Range | Hit | Cumulative Percentage
| 470.1-476 | 2 | 0.1667% | [5 empty] | Duration Range | Hit | Cumulative Percentage
| 476.1-481 | 1 | 0.25% | [5 empty] | 457.1-463 | 2 | 0.0016667
| 481.1-486 | 0 | 0.25% | [5 empty] | 463.1-468 | 1 | 0.0025
| 486.1-491 | 3 | 0.5% | [5 empty] | 468.1-473 | 0 | 0.0025
| 491.1-496 | 2 | 0.6667% | [5 empty] | 473.1-478 | 0 | 0.0025
| 496.1-501 | 4 | 1% | [5 empty] | 478.1-483 | 1 | 0.0033333
| 501.1-506 | 8 | 1.667% | [5 empty] | 483.1-488 | 3 | 0.0058333
| 506.1-511 | 6 | 2.167% | [5 empty] | 488.1-493 | 7 | 0.011667
| 511.1-516 | 13 | 3.25% | [5 empty] | 493.1-498 | 1 | 0.0125
| 516.1-521 | 11 | 4.167% | [5 empty] | 498.1-503 | 4 | 0.015833
| 521.1-526 | 17 | 5.583% | [5 empty] | 503.1-508 | 5 | 0.02
| 526.1-531 | 10 | 6.417% | [5 empty] | 508.1-513 | 1 | 0.020833
| 531.1-536 | 14 | 7.583% | [5 empty] | 513.1-518 | 14 | 0.0325
| 536.1-541 | 17 | 9% | [5 empty] | 518.1-523 | 8 | 0.039167
| 541.1-546 | 23 | 10.92% | [5 empty] | 523.1-528 | 22 | 0.0575
| 546.1-551 | 34 | 13.75% | [5 empty] | 528.1-533 | 23 | 0.076667
| 551.1-556 | 26 | 15.92% | [5 empty] | 533.1-538 | 11 | 0.085833
| 556.1-561 | 37 | 19% | [5 empty] | 538.1-543 | 16 | 0.099167
| 561.1-566 | 33 | 21.75% | [5 empty] | 543.1-548 | 29 | 0.12333
| 566.1-571 | 26 | 23.92% | [5 empty] | 548.1-553 | 27 | 0.14583
| 571.1-576 | 40 | 27.25% | [5 empty] | 553.1-558 | 26 | 0.1675
| 576.1-581 | 32 | 29.92% | [5 empty] | 558.1-563 | 31 | 0.19333
| 581.1-586 | 32 | 32.58% | [5 empty] | 563.1-568 | 37 | 0.22417
| 586.1-591 | 31 | 35.17% | [5 empty] | 568.1-573 | 27 | 0.24667
| 591.1-596 | 37 | 38.25% | [5 empty] | 573.1-578 | 41 | 0.28083
| 596.1-601 | 42 | 41.75% | [5 empty] | 578.1-583 | 31 | 0.30667
| 601.1-606 | 34 | 44.58% | [5 empty] | 583.1-588 | 25 | 0.3275
| 606.1-611 | 40 | 47.92% | [5 empty] | 588.1-593 | 49 | 0.36833
| 611.1-616 | 44 | 51.58% | [5 empty] | 593.1-598 | 30 | 0.39333
| 616.1-621 | 36 | 54.58% | [5 empty] | 598.1-603 | 40 | 0.42667
| 621.1-626 | 41 | 58% | [5 empty] | 603.1-608 | 44 | 0.46333
| 626.1-631 | 42 | 61.5% | [5 empty] | 608.1-613 | 29 | 0.4875
| 631.1-636 | 36 | 64.5% | [5 empty] | 613.1-618 | 45 | 0.525
| 636.1-641 | 40 | 67.83% | [5 empty] | 618.1-623 | 49 | 0.56583
| 641.1-646 | 35 | 70.75% | [5 empty] | 623.1-628 | 42 | 0.60083
| 646.1-651 | 37 | 73.83% | [5 empty] | 628.1-633 | 37 | 0.63167
| 651.1-656 | 29 | 76.25% | [5 empty] | 633.1-638 | 34 | 0.66
| 656.1-661 | 27 | 78.5% | [5 empty] | 638.1-643 | 35 | 0.68917
| 661.1-666 | 23 | 80.42% | [5 empty] | 643.1-648 | 40 | 0.7225
| 666.1-671 | 39 | 83.67% | [5 empty] | 648.1-653 | 34 | 0.75083
| 671.1-676 | 22 | 85.5% | [5 empty] | 653.1-658 | 35 | 0.78
| 676.1-681 | 26 | 87.67% | [5 empty] | 658.1-663 | 20 | 0.79667
| 681.1-686 | 26 | 89.83% | [5 empty] | 663.1-668 | 34 | 0.825
| 686.1-691 | 21 | 91.58% | [5 empty] | 668.1-673 | 24 | 0.845
| 691.1-696 | 16 | 92.92% | [5 empty] | 673.1-678 | 24 | 0.865
| 696.1-701 | 14 | 94.08% | [5 empty] | 678.1-683 | 23 | 0.88417
| 701.1-706 | 18 | 95.58% | [5 empty] | 683.1-688 | 32 | 0.91083
| 706.1-711 | 10 | 96.42% | [5 empty] | 688.1-693 | 17 | 0.925
| 711.1-716 | 10 | 97.25% | [5 empty] | 693.1-698 | 18 | 0.94
| 716.1-721 | 9 | 98% | [5 empty] | 698.1-703 | 15 | 0.9525
| 721.1-726 | 8 | 98.67% | [5 empty] | 703.1-708 | 11 | 0.96167
| 726.1-731 | 5 | 99.08% | [5 empty] | 708.1-713 | 9 | 0.96917
| 731.1-736 | 4 | 99.42% | [5 empty] | 713.1-718 | 7 | 0.975
| 736.1-741 | 1 | 99.5% | [5 empty] | 718.1-723 | 9 | 0.9825
| 741.1-746 | 5 | 99.92% | [5 empty] | 723.1-728 | 7 | 0.98833
| 746.1-751 | 0 | 99.92% | [5 empty] | 728.1-733 | 5 | 0.9925
| 751.1-756 | 1 | 100% | [5 empty] | 733.1-738 | 3 | 0.995
| 756.1-761 | 0 | 100% | [5 empty] | 738.1-743 | 1 | 0.99583
| 761.1-766 | 0 | 100% | [5 empty] | 743.1-748 | 3 | 0.99833
| 766.1-771 | 0 | 100% | [5 empty] | 748.1-753 | 1 | 0.99917
| 771.1-776 | 0 | 100% | [5 empty] | 753.1-758 | 1 | 1
| 776.1-781 | 0 | 100% | [5 empty] | 758.1-763 | 0 | 1
| 781.1-786 | 0 | 100% | [5 empty] | 763.1-768 | 0 | 1
| 786.1-791 | 0 | 100% | [5 empty] | 768.1-773 | 0 | 1
| 791.1-796 | 0 | 100% | [5 empty] | 773.1-778 | 0 | 1
| 796.1-801 | 0 | 100% | [5 empty] | 778.1-783 | 0 | 1
| 801.1-806 | 0 | 100% | [5 empty] | 783.1-788 | 0 | 1
| 806.1-811 | 0 | 100% | [5 empty] | 788.1-793 | 0 | 1
| 811.1-816 | 0 | 100% | [5 empty] | 793.1-798 | 0 | 1
| 816.1-821 | 0 | 100% | [5 empty] | 798.1-803 | 0 | 1
| 821.1-826 | 0 | 100% | [5 empty] | 803.1-808 | 0 | 1
| 826.1-831 | 0 | 100% | [5 empty] | 808.1-813 | 0 | 1
| 831.1-836 | 0 | 100% | [5 empty] | 813.1-818 | 0 | 1
| 836.1-841 | 0 | 100% | [5 empty] | 818.1-823 | 0 | 1
| 841.1-846 | 0 | 100% | [5 empty] | 823.1-828 | 0 | 1
| 846.1-851 | 0 | 100% | [5 empty] | 828.1-833 | 0 | 1
| 851.1-856 | 0 | 100% | [5 empty] | 833.1-838 | 0 | 1
| 856.1-861 | 0 | 100% | [5 empty] | 838.1-843 | 0 | 1
| 861.1-866 | 0 | 100% | [5 empty] | 843.1-848 | 0 | 1
| 866.1-871 | 0 | 100% | [5 empty] | 848.1-853 | 0 | 1
[9 empty] | 853.1-858 | 0 | 1

## Cost Input & Output
| Resource Name | Project Manager | Project Engineer | Main Contractor | Sub-Contractor | Finance and Administration | Surveyor | Procurement | Architect | Engineer | MSW Recycling Package | Extruding Machine | Leftover Waste Dryer | Forklift | Building Material (Site Development) | Building Material (Civil Structures) | Bailing Machine | Wire Machine | Fertilizer Packaging System | Fix Fence | CCTV | Personal Computer | Security System | Electricity Installment | Generator Set | Communication Package | Conveyor | Sorting Machine Package | Plumbing System | Smart Thermal System | Land and Land Acquisition | Documentation | Report Writing | Report Publishing | train | trial
| Type | Work | Work | Work | Work | Work | Work | Work | Work | Work | Material | Material | Material | Material | Material | Material | Material | Material | Material | Material | Material | Material | Material | Material | Material | Material | Material | Material | Material | Material | Material | Cost | Cost | Cost
| Cost | $86,457 | $86,430 | $15,422 | $12,400 | $76,826 | $1,673 | $15,422 | 23000 | 35050 | $10,716,047 | $143,297 | $143,297 | $154,193 | $14,141 | $44,073 | $50,440 | $60,440 | $23,040 | $42,917 | $1,822 | $8,657 | $1,679 | $1,786 | $63,640 | $2,000 | $80,440 | $466,046 | $48,858 | $14,071 | $141,273,906 | $174 | $67 | $115 | 77350 | 2813
| Ovt. Rate | $24/hr | $8/hr | $5/hr | $4/hr | $5/hr | $3/hr | $5/hr | $4/hr | $4/hr
| Overtime Cost | 4109 | 1370 | 856 | 685 | 856 | 514 | 856 | 685 | 685 | 272802 | 3648 | 3648 | 3926 | 360 | 1122 | 1285 | 1539 | 587 | 1093 | 47 | 221 | 43 | 46 | 1621 | 51 | 2048 | 11865 | 1244 | 359 |  | 5 | 2 | 3
| Outsorcing cost | [9 empty] | 918238 | 6849 | 16314 | 1762 | 140 | 5651 | 1393 | 6911 | 3302 | 1114 | 265 | 1235 | 114 | 78 | 4606 | 298 | 8239 | 63929 | 2089 | 86 |  | 21 | 1 | 7
| Resource Name | Project Manager | Project Engineer | Main Contractor | Sub-Contractor | Finance and Administration | Surveyor | Procurement | Architect | Engineer | MSW Recycling Package | Extruding Machine | Leftover Waste Dryer | Forklift | Building Material (Site Development) | Building Material (Civil Structures) | Bailing Machine | Wire Machine | Fertilizer Packaging System | Fix Fence | CCTV | Personal Computer | Security System | Electricity Installment | Generator Set | Communication Package | Conveyor | Sorting Machine Package | Plumbing System | Smart Thermal System | Land and Land Acquisition | Documentation | Report Writing | Report Publishing |  |  |  | Total
Cost $ | Optimistic | 62249.04 | 62229.6 | 11103.84 | 8928 | 55314.72 | 1204.56 | 11103.84 | 16560 | 25236 | 6429628.2 | 85978.2 | 85978.2 | 92515.8 | 8484.6 | 26443.8 | 30264 | 36264 | 13824 | 25750.2 | 1093.2 | 5194.2 | 1007.4 | 1071.6 | 38184 | 1200 | 48264 | 279627.6 | 29314.8 | 8442.6 | 84764343.6 | 154 | 62 | 103 | 77347 | 2806 | -2 | 92267122.6 | 1291.7397
| Most-likely | 86457 | 86430 | 15422 | 12400 | 76826 | 1673 | 15422 | 23000 | 35050 | 10716047 | 143297 | 143297 | 154193 | 14141 | 44073 | 50440 | 60440 | 23040 | 42917 | 1822 | 8657 | 1679 | 1786 | 63640 | 2000 | 80440 | 466046 | 48858 | 14071 | 141273906 | 174 | 67 | 115 | 77350 | 2813 | 0 | 153707826 | 2151.9096
| Pessimistic | 90566 | 87800 | 16278 | 13085 | 77682 | 2187 | 16278 | 23685 | 35735 | 11634285 | 150146 | 159611 | 158119 | 14501 | 49724 | 51833 | 67351 | 26342 | 44031 | 2087 | 9892 | 1793 | 1864 | 68246 | 2298 | 88679 | 529975 | 50947 | 14430 | 226038249.6 | 216 | 78 | 143 | 77420 | 2988 | 438 | 239528136.6 | 3353.3939
Cost (IDR) | Optimistic | 871486560 | 871214400 | 155453760 | 124992000 | 774406080 | 16863840 | 155453760 | 231840000 | 353304000 | 90014794800 | 1203694800 | 1203694800 | 1295221200 | 118784400 | 370213200 | 423696000 | 507696000 | 193536000 | 360502800 | 15304800 | 72718800 | 14103600 | 15002400 | 534576000 | 16800000 | 675696000 | 3914786400 | 410407200 | 118196400 | 1186700810400 | 2156000 | 868000 | 1442000 | 1082858000 | 39284000 | -28000 | 1291739716400
| Most-likely | 1210398000 | 1210020000 | 215908000 | 173600000 | 1075564000 | 23422000 | 215908000 | 322000000 | 490700000 | 150024658000 | 2006158000 | 2006158000 | 2158702000 | 197974000 | 617022000 | 706160000 | 846160000 | 322560000 | 600838000 | 25508000 | 121198000 | 23506000 | 25004000 | 890960000 | 28000000 | 1126160000 | 6524644000 | 684012000 | 196994000 | 1977834684000 | 2436000 | 938000 | 1610000 | 1082900000 | 39382000 | 0 | 2151909564000
| Pessimistic | 1267924000 | 1229200000 | 227892000 | 183190000 | 1087548000 | 30618000 | 227892000 | 331590000 | 500290000 | 162879990000 | 2102044000 | 2234554000 | 2213666000 | 203014000 | 696136000 | 725662000 | 942914000 | 368788000 | 616434000 | 29218000 | 138488000 | 25102000 | 26096000 | 955444000 | 32172000 | 1241506000 | 7419650000 | 713258000 | 202020000 | 3.1645e+12 | 3024000 | 1092000 | 2002000 | 1083880000 | 41832000 | 6132000 | 3.3534e+12
| Mean | 1163500426.6667 | 1156749066.6667 | 207829626.6667 | 167097000 | 1027368346.6667 | 23528306.6667 | 207829626.6667 | 308571666.6667 | 469399000 | 142165569466.6667 | 1888395133.3333 | 1910480133.3333 | 2023949200 | 185615733.3333 | 589072866.6667 | 662333000 | 805875000 | 308760666.6667 | 563381466.6667 | 24425800 | 115999800 | 22204933.3333 | 23519066.6667 | 842310000 | 26828666.6667 | 1070307000 | 6238835400 | 643285533.3333 | 184698733.3333 | 2043762506800 | 2487333.3333 | 952000 | 1647333.3333 | 1083056333.3333 | 39774000 | 1017333.3333
| Var | 4365628995382044 | 3559824716871111 | 145758294841600 | 9.4084e+13 | 2723829501702400 | 5254914369600 | 145758294841600 | 276390625000000 | 6.0014e+14 | 1.4748e+20 | 22417535698351108 | 29518630284017776 | 23431690295751116 | 1.9707e+14 | 2950713098884444 | 2532874032111111 | 5261519653444444 | 8.5315e+14 | 1819466087040000 | 5.3771e+12 | 1.2016e+14 | 3.3601e+12 | 3.4186e+12 | 4920274261777778 | 6563844000000 | 8892804336111112 | 3.4122e+17 | 2547739085017778 | 195177664360000 | 1.0866e+23 | 20928444444.4444 | 1393777777.7778 | 8711111111.1111 | 29013444444.4444 | 180341777777.7778 | 1.054e+12
| Alpha | 4.4084 | 3.8376 | 4.4894 | 4.4871 | 3.707 | 3.8722 | 4.4894 | 4.1465 | 3.9301 | 4.5268 | 4.2114 | 4.6345 | 3.888 | 3.8879 | 4.661 | 3.925 | 4.6357 | 4.6728 | 3.8966 | 4.6734 | 4.6726 | 4.4084 | 4.1609 | 4.4426 | 4.6737 | 4.6008 | 4.6698 | 4.1492 | 3.8889 | 3.3973 | 2.8615 | 2.7891 | 2.6987 | 0.89862 | 0.88302 | 0.69107
| Beta | 1.5764 | 0.97374 | 1.7197 | 1.715 | 0.88189 | 4.1192 | 1.7197 | 1.2439 | 1.0457 | 1.798 | 1.3141 | 2.125 | 1.0122 | 1.0122 | 2.2801 | 1.0416 | 2.1305 | 2.4344 | 1.019 | 2.4554 | 2.4278 | 1.5765 | 1.259 | 1.6333 | 2.4902 | 1.996 | 2.3726 | 1.2467 | 1.0129 | 4.4427 | 4.6348 | 4.6484 | 4.6613 | 3.7319 | 3.7087 | 3.3813
Sim
| Mean | 1166716087.378 | 1158305831.2664 | 207343960.1826 | 167095665.2373 | 1030249153.6009 | 23599299.4649 | 208042257.1009 | 308877567.0009 | 468671389.3914 | 142006096581.0166 | 1890281449.981 | 1905806518.9101 | 2024275990.2746 | 185755120.0109 | 589255654.9029 | 662050390.5427 | 806455489.7572 | 308757314.0193 | 562587042.1211 | 24464357.3218 | 116320041.6977 | 22118195.9903 | 23589346.3288 | 838768885.7195 | 26853392.4147 | 1069667117.6216 | 6251185841.7594 | 640844940.7281 | 184680198.2472 | 2.0508e+12 | 2491552.4872 | 950726.2934 | 1647919.8827 | 1082871983.2212 | 39402724.882 | 2.2157e+12
| Var | 4.3476e+15 | 3564689678295462 | 1.4173e+14 | 1.001e+14 | 2734950957078931 | 5.0752e+12 | 1.4835e+14 | 2.5537e+14 | 5.9313e+14 | 1.4199e+20 | 21498273326028616 | 29448148822738648 | 25082395479418560 | 1.877e+14 | 3.0635e+15 | 2510711172712072 | 4903591483711747 | 8.7305e+14 | 1.7814e+15 | 5.1519e+12 | 1.2254e+14 | 3.5529e+12 | 3.2291e+12 | 4884047055889200 | 6.714e+12 | 8945606165192810 | 3.4712e+17 | 2.7896e+15 | 2.0195e+14 | 1.0897e+23 | 20523629431.9924 | 1389784666.9378 | 8372091127.1211 | #DIV/0! | #DIV/0! | 1.0908e+23
| Min | 884748155.8395 | 918045862.1838 | 161554263.2813 | 135249255.1589 | 820513897.4538 | 17657853.2581 | 166335905.1382 | 245201155.0016 | 375635010.9451 | 98683842404.0243 | 1290046134.1986 | 1341012247.813 | 1360242047.1712 | 127970959.4455 | 401863517.0491 | 456434139.0391 | 554474043.8399 | 218895487.6414 | 398550695.2063 | 16912891.534 | 79983143.4353 | 15218238.9944 | 17469415.4627 | 596478662.6052 | 18454853.0309 | 722767306.2097 | 4370360298.8542 | 443805123.5713 | 126747127.9432 | 1.2978e+12 | 2166168.731 | 870868.3789 | 1452009.2339 | 1082871983.2212 | 39402724.882 | 1.4545e+12
| Max | 1266192907.0407 | 1229187301.112 | 227510495.7743 | 183033650.4394 | 1087547532.2932 | 29777164.5018 | 227514768.5333 | 331382687.6056 | 500259060.3233 | 162741249354.7233 | 2101111143.1958 | 2221335766.2989 | 2213659252.9312 | 203002779.0425 | 695498570.3001 | 725603632.8229 | 938922161.5028 | 366780864.7428 | 616223609.7653 | 29025404.2121 | 137835875.1817 | 25056763.7262 | 26083778.7808 | 953281745.5927 | 31936495.8938 | 1236436533.9187 | 7398099821.9448 | 713101213.7005 | 202010686.7041 | 2.9379e+12 | 2876909.1499 | 1068086.263 | 1931540.2238 | 1082871983.2212 | 39402724.882 | 3.1122e+12
Summary
| Min | 1.4545e+12 |  |  | Most-likely | 2151909564000 | 44.17%
| Max | 3.1122e+12 |  |  |  | 648090436000 | 95% | 2800000000000
| Iterations | 1199
Min | Max | Range (Billion IDR) | Hit | Cumulative Percentage
1.45e+12 | 1460000000000 | 1450.1-1460 | 1 | 0.0834%
1.46e+12 | 1480000000000 | 1460.1-1480 | 2 | 0.2502%
1.48e+12 | 1500000000000 | 1480.1-1500 | 1 | 0.3336%
1.5e+12 | 1520000000000 | 1500.1-1520 | 2 | 0.5004%
1.52e+12 | 1540000000000 | 1520.1-1540 | 7 | 1.084%
1.54e+12 | 1560000000000 | 1540.1-1560 | 5 | 1.501%
1.56e+12 | 1580000000000 | 1560.1-1580 | 3 | 1.751%
1.58e+12 | 1600000000000 | 1580.1-1600 | 5 | 2.168%
1.6e+12 | 1620000000000 | 1600.1-1620 | 2 | 2.335%
1.62e+12 | 1640000000000 | 1620.1-1640 | 11 | 3.253%
1.64e+12 | 1660000000000 | 1640.1-1660 | 9 | 4.003%
1.66e+12 | 1680000000000 | 1660.1-1680 | 11 | 4.921%
1.68e+12 | 1700000000000 | 1680.1-1700 | 2 | 5.088%
1.7e+12 | 1720000000000 | 1700.1-1720 | 14 | 6.255%
1.72e+12 | 1740000000000 | 1720.1-1740 | 12 | 7.256%
1.74e+12 | 1760000000000 | 1740.1-1760 | 11 | 8.173%
1.76e+12 | 1780000000000 | 1760.1-1780 | 12 | 9.174%
1.78e+12 | 1800000000000 | 1780.1-1800 | 17 | 10.59%
1.8e+12 | 1820000000000 | 1800.1-1820 | 14 | 11.76%
1.82e+12 | 1840000000000 | 1820.1-1840 | 21 | 13.51%
1.84e+12 | 1860000000000 | 1840.1-1860 | 18 | 15.01%
1.86e+12 | 1880000000000 | 1860.1-1880 | 25 | 17.1%
1.88e+12 | 1900000000000 | 1880.1-1900 | 20 | 18.77%
1.9e+12 | 1920000000000 | 1900.1-1920 | 21 | 20.52%
1.92e+12 | 1940000000000 | 1920.1-1940 | 19 | 22.1%
1.94e+12 | 1960000000000 | 1940.1-1960 | 23 | 24.02%
1.96e+12 | 1980000000000 | 1960.1-1980 | 26 | 26.19%
1.98e+12 | 2000000000000 | 1980.1-2000 | 21 | 27.94%
2e+12 | 2020000000000 | 2000.1-2020 | 25 | 30.03%
2.02e+12 | 2040000000000 | 2020.1-2040 | 28 | 32.36%
2.04e+12 | 2060000000000 | 2040.1-2060 | 30 | 34.86%
2.06e+12 | 2080000000000 | 2060.1-2080 | 19 | 36.45%
2.08e+12 | 2100000000000 | 2080.1-2100 | 24 | 38.45%
2.1e+12 | 2120000000000 | 2100.1-2120 | 23 | 40.37%
2.12e+12 | 2140000000000 | 2120.1-2140 | 23 | 42.29%
2.14e+12 | 2160000000000 | 2140.1-2160 | 32 | 44.95%
2.16e+12 | 2180000000000 | 2160.1-2180 | 31 | 47.54%
2.18e+12 | 2200000000000 | 2180.1-2200 | 26 | 49.71%
2.2e+12 | 2220000000000 | 2200.1-2220 | 30 | 52.21%
2.22e+12 | 2240000000000 | 2220.1-2240 | 20 | 53.88%
2.24e+12 | 2260000000000 | 2240.1-2260 | 27 | 56.13%
2.26e+12 | 2280000000000 | 2260.1-2280 | 37 | 59.22%
2.28e+12 | 2300000000000 | 2280.1-2300 | 19 | 60.8%
2.3e+12 | 2320000000000 | 2300.1-2320 | 27 | 63.05%
2.32e+12 | 2340000000000 | 2320.1-2340 | 24 | 65.05%
2.34e+12 | 2360000000000 | 2340.1-2360 | 26 | 67.22%
2.36e+12 | 2380000000000 | 2360.1-2380 | 28 | 69.56%
2.38e+12 | 2400000000000 | 2380.1-2400 | 19 | 71.14%
2.4e+12 | 2420000000000 | 2400.1-2420 | 15 | 72.39%
2.42e+12 | 2440000000000 | 2420.1-2440 | 21 | 74.15%
2.44e+12 | 2460000000000 | 2440.1-2460 | 18 | 75.65%
2.46e+12 | 2480000000000 | 2460.1-2480 | 15 | 76.9%
2.48e+12 | 2500000000000 | 2480.1-2500 | 17 | 78.32%
2.5e+12 | 2520000000000 | 2500.1-2520 | 23 | 80.23%
2.52e+12 | 2540000000000 | 2520.1-2540 | 22 | 82.07%
2.54e+12 | 2560000000000 | 2540.1-2560 | 14 | 83.24%
2.56e+12 | 2580000000000 | 2560.1-2580 | 15 | 84.49%
2.58e+12 | 2600000000000 | 2580.1-2600 | 15 | 85.74%
2.6e+12 | 2620000000000 | 2600.1-2620 | 18 | 87.24%
2.62e+12 | 2640000000000 | 2620.1-2640 | 18 | 88.74%
2.64e+12 | 2660000000000 | 2640.1-2660 | 15 | 89.99%
2.66e+12 | 2680000000000 | 2660.1-2680 | 20 | 91.66%
2.68e+12 | 2700000000000 | 2680.1-2700 | 7 | 92.24%
2.7e+12 | 2720000000000 | 2700.1-2720 | 8 | 92.91%
2.72e+12 | 2740000000000 | 2720.1-2740 | 7 | 93.49%
2.74e+12 | 2760000000000 | 2740.1-2760 | 9 | 94.25%
2.76e+12 | 2780000000000 | 2760.1-2780 | 9 | 95%
2.78e+12 | 2800000000000 | 2780.1-2800 | 10 | 95.83%
2.8e+12 | 2820000000000 | 2800.1-2820 | 4 | 96.16%
2.82e+12 | 2840000000000 | 2820.1-2840 | 5 | 96.58%
2.84e+12 | 2860000000000 | 2840.1-2860 | 10 | 97.41%
2.86e+12 | 2880000000000 | 2860.1-2880 | 3 | 97.66%
2.88e+12 | 2900000000000 | 2880.1-2900 | 4 | 98%
2.9e+12 | 2920000000000 | 2900.1-2920 | 6 | 98.5%
2.92e+12 | 2940000000000 | 2920.1-2940 | 3 | 98.75%
2.94e+12 | 2960000000000 | 2940.1-2960 | 6 | 99.25%
2.96e+12 | 2980000000000 | 2960.1-2980 | 3 | 99.5%
2.98e+12 | 3000000000000 | 2980.1-3000 | 2 | 99.67%
3e+12 | 3020000000000 | 3000.1-3020 | 2 | 99.83%
3.02e+12 | 3040000000000 | 3020.1-3040 | 1 | 99.92%
3.04e+12 | 3060000000000 | 3040.1-3060 | 0 | 99.92%
3.06e+12 | 3080000000000 | 3060.1-3080 | 1 | 100%
3.08e+12 | 3100000000000 | 3080.1-3100 | 0 | 100%

## Cost Montecarlo
Resource Name/Iteration | Project Manager | Project Engineer | Main Contractor | Sub-Contractor | Finance and Administration | Surveyor | Procurement | Architect | Engineer | MSW Recycling Package | Extruding Machine | Leftover Waste Dryer | Forklift | Building Material (Site Development) | Building Material (Civil Structures) | Bailing Machine | Wire Machine | Fertilizer Packaging System | Fix Fence | CCTV | Personal Computer | Security System | Electricity Installment | Generator Set | Communication Package | Conveyor | Sorting Machine Package | Plumbing System | Smart Thermal System | Land and Land Acquisition | Documentation | Report Writing | Report Publishing |  |  | Sum
1 | 1250694671.7181 | 1173719496.1093 | 205306945.5635 | 169175564.5598 | 1033686555.3893 | 19577237.2352 | 214865310.3476 | 309318707.1962 | 488440389.4039 | 150377935295.0887 | 1781472666.7415 | 1913576723.6248 | 1976261013.9855 | 189345238.8412 | 632896896.0425 | 641353190.2462 | 700761416.1072 | 341943135.4512 | 590675153.6145 | 25673978.2825 | 119550690.8086 | 20453102.1911 | 20461794.6611 | 770829612.09 | 22954785.1497 | 1118856296.9971 | 6687969350.465 | 675813167.3488 | 198037856.7996 | 2.1373e+12 | 2565689.0359 | 937970.2474 | 1719676.4073 | 1082871983.2212 | 39402724.882 | 2.3109e+12
2 | 1199920336.9974 | 1082043446.9775 | 221016051.3445 | 174821474.3748 | 1086439070.1639 | 24342639.6653 | 209320596.5801 | 293268828.9816 | 450144535.8567 | 143328961319.0593 | 1718731498.1514 | 1995128696.0996 | 1965156220.4883 | 200096248.0645 | 614054972.8382 | 724808057.2769 | 793476178.3561 | 347910447.3396 | 601028705.7018 | 27379485.2744 | 119252303.4133 | 21414349.1035 | 20805119.1782 | 905671328.9975 | 29954498.693 | 1085374549.8528 | 6422902810.038 | 576698061.6664 | 193290813.4278 | 1.9472e+12 | 2548331.6763 | 930377.809 | 1609990.789 |  |  | 2.1136e+12
3 | 1217965787.762 | 1199800379.4352 | 204578823.52 | 177075211.485 | 1079917180.7434 | 23042462.4435 | 210065251.7641 | 299047740.3402 | 493084980.5511 | 143434104304.1882 | 1997726973.2337 | 2143602596.9189 | 2108023707.2129 | 201823883.1865 | 620158884.6772 | 667329791.7262 | 799860626.9361 | 343064101.6013 | 517360138.2511 | 25559383.8443 | 103688836.8764 | 21856167.0422 | 23680923.9049 | 808793153.0772 | 26303600.5016 | 1170133979.8669 | 5853512954.7528 | 674036078.4198 | 188062943.3141 | 2.058e+12 | 2558562.3978 | 918128.2582 | 1819017.2471 |  |  | 2.2246e+12
4 | 1192333917.2202 | 1169339342.611 | 201686013.3652 | 173372913.2712 | 1081668541.5932 | 19448749.6669 | 217700249.3265 | 325766677.0544 | 459692705.0221 | 128792257220.8096 | 1691961085.2542 | 2049528484.1714 | 1732350658.4069 | 177886324.1225 | 610544756.94 | 704123228.1835 | 710689546.0887 | 324741979.4713 | 600821338.9368 | 25910339.9589 | 120719362.4565 | 21336126.2751 | 23309469.0583 | 907942780.0117 | 20571480.8213 | 1068961011.1996 | 7254347000.8633 | 676449203.4737 | 166166069.8278 | 1.6008e+12 | 2234386.7303 | 925765.6471 | 1666059.7585 |  |  | 1.7533e+12
5 | 1215406233.9147 | 1119333408.2402 | 215783162.2562 | 155008754.2621 | 1005470051.5579 | 22752048.7008 | 204716425.634 | 315850200.3919 | 497754429.2995 | 140207668956.0375 | 1639579471.2218 | 1672338133.4996 | 2077383152.7859 | 160486518.6919 | 651705135.6239 | 709781686.9997 | 679530721.2893 | 321325888.0425 | 534233212.3545 | 25236788.4957 | 122409343.5254 | 22284561.1792 | 23570549.3454 | 641707396.0167 | 30659762.1678 | 1220946164.581 | 6541599701.5688 | 578437037.1868 | 174772038.4104 | 2.3538e+12 | 2273834.3103 | 888043.3092 | 1673887.2208 |  |  | 2.5166e+12
6 | 1122333972.8549 | 1226611395.2928 | 216795207.1839 | 161534378.7482 | 986229994.5533 | 23544182.8881 | 212882659.87 | 304866347.6774 | 479207360.1014 | 133615785609.8152 | 2024436647.6481 | 1938453424.9923 | 2077768072.6238 | 199429272.5891 | 483800246.6351 | 550550094.745 | 849910033.0504 | 267406687.6854 | 535802038.5139 | 24715693.8519 | 123567626.8584 | 22377690.3946 | 24594971.028 | 804055750.9441 | 20774536.0981 | 1007455783.7843 | 6205277460.2006 | 710971639.5798 | 173510085.9718 | 1.8577e+12 | 2608480.3763 | 929743.4456 | 1554994.4333 |  |  | 2.0141e+12
7 | 1249071951.1945 | 1037154403.5775 | 221761726.276 | 154882341.1538 | 924721790.4525 | 29012328.585 | 197572299.0377 | 313116498.0453 | 485730994.7252 | 150191547238.1165 | 1839791784.219 | 1679188243.9087 | 1975140712.9012 | 202350688.969 | 626093345.9223 | 672754594.8665 | 794583747.2535 | 313573564.8237 | 584622371.0904 | 24994331.5235 | 116345753.3068 | 24229205.1084 | 23848472.0294 | 889464522.3788 | 29628024.4122 | 1178438756.2049 | 5553376173.7567 | 621777880.2708 | 191327555.4688 | 1.5046e+12 | 2662383.1696 | 937592.4053 | 1647377.7908 |  |  | 1.6767e+12
8 | 1213605622.5096 | 1199527499.7599 | 215560792.121 | 164583262.9214 | 1067451834.3175 | 24417646.9393 | 182237300.0082 | 306186264.956 | 490598958.7626 | 152942562171.557 | 2017148566.8445 | 2056073290.2408 | 1886417629.7359 | 181075700.696 | 693422628.5389 | 645120049.7585 | 830995110.8427 | 293591241.6317 | 604736934.7638 | 24191073.4726 | 125308753.1567 | 17860647.8406 | 23337899.4549 | 767355101.0018 | 30017679.0218 | 1055596776.8608 | 6360496015.0398 | 657599849.0386 | 190812628.0553 | 2.1756e+12 | 2618551.637 | 916421.0061 | 1593570.3681 |  |  | 2.3519e+12
9 | 1242620620.2788 | 1222474023.1737 | 221866417.8931 | 181782541.8662 | 1075800511.1928 | 25998464.4339 | 204575369.5737 | 273972461.5151 | 462117605.894 | 153343606800.5515 | 1659582983.1027 | 2147664080.7188 | 2008518470.546 | 201672566.0211 | 576929432.4431 | 542071304.3389 | 734864742.6798 | 310673548.5596 | 595968568.5784 | 24878230.833 | 119265198.4471 | 24815940.215 | 24857138.8872 | 859174705.7659 | 28332730.0457 | 1112537628.3179 | 5994180995.3814 | 688565255.7802 | 172599519.8203 | 1.6965e+12 | 2457421.0074 | 979414.0081 | 1784496.5735 |  |  | 1.8726e+12
10 | 1220960510.3369 | 1192713872.3266 | 220945855.9686 | 169108916.2898 | 1056062258.062 | 22387212.375 | 219144410.1953 | 314468100.7261 | 491851224.5048 | 145005146250.2993 | 1982707681.6521 | 2172736506.3836 | 2207038973.2856 | 190937828.5967 | 556062233.1998 | 722117240.6687 | 711621116.2969 | 289049051.0484 | 516681956.1464 | 27662073.9735 | 119346511.8416 | 22280098.6133 | 22273831.6196 | 895675531.9226 | 26982212.9862 | 1020181757.6863 | 5743191209.8077 | 658438902.9826 | 173279854.2931 | 2.6516e+12 | 2473624.5453 | 930207.5462 | 1657939.0137 |  |  | 2.8196e+12
11 | 1048226996.2272 | 1217349107.322 | 207671942.6075 | 166890992.4314 | 1001898323.1885 | 25528390.9894 | 193515105.3514 | 310448519.2265 | 466889851.7547 | 151909372508.046 | 1957274777.2584 | 2021122678.9886 | 2015062195.6238 | 165877468.2234 | 670419885.3587 | 723416111.7219 | 699468939.8033 | 289536357.1836 | 520504199.178 | 27650423.6898 | 119021639.6363 | 23617606.8652 | 24615559.4105 | 834552471.4394 | 21792281.3198 | 1204151580.8145 | 6578157131.0175 | 595033208.6812 | 172656107.7354 | 2.1237e+12 | 2663584.7159 | 982957.5057 | 1675880.1026 |  |  | 2.2989e+12
12 | 1221885841.9662 | 1149629135.5911 | 187707527.9136 | 170614516.128 | 1057043491.1715 | 25242681.5382 | 214299408.5458 | 329778159.5598 | 497459228.1006 | 158459848238.1486 | 1688305985.5131 | 2053139648.2438 | 2116296085.563 | 184217781.61 | 599378422.5395 | 638167076.1276 | 770875335.6611 | 246644333.0503 | 487799484.147 | 23382321.8184 | 115128518.8771 | 23385250.9422 | 23888875.2482 | 597241835.4875 | 25475668.6914 | 980112677.5066 | 6256916660.4416 | 598649259.8957 | 194412127.928 | 2.3231e+12 | 2284660.0136 | 948094.4679 | 1821011.0304 |  |  | 2.504e+12
13 | 1029101388.5658 | 1182903187.8142 | 179455781.7058 | 171900706.9235 | 1076852706.2978 | 20805652.3784 | 220626534.5728 | 322465754.4045 | 485004420.7072 | 147874017826.929 | 1657503521.7496 | 1813372614.6497 | 2194059530.2744 | 166305118.4873 | 693960324.5922 | 725603632.8229 | 850705571.9841 | 285101179.5554 | 578492477.74 | 24288740.6389 | 99148231.3961 | 22193205.9848 | 22787762.3271 | 905454510.447 | 30409613.3358 | 842286200.8968 | 7278228497.6472 | 450468196.5118 | 182670504.1884 | 1.7917e+12 | 2270324.166 | 932251.8602 | 1809458.6762 |  |  | 1.9631e+12
14 | 1200784572.0891 | 1075921809.0312 | 217591540.5431 | 175663078.6578 | 997460608.8149 | 25955629.6342 | 194214562.4716 | 308984593.7789 | 490669343.8318 | 126391596989.6991 | 1791586357.38 | 2142840962.2713 | 2005891462.5078 | 192807337.7437 | 694466648.3344 | 665233466.7472 | 838500119.7012 | 325957623.9859 | 511104760.0218 | 21815283.182 | 133197690.7093 | 23367085.7944 | 24380008.7003 | 858826947.7637 | 28707885.1146 | 918485272.2743 | 6207108786.1312 | 673491317.5135 | 199470850.2545 | 1.9753e+12 | 2476689.4532 | 999726.4176 | 1680026.5322 |  |  | 2.1247e+12
15 | 1250303202.7055 | 1219225197.5159 | 210992015.153 | 176283615.1221 | 1067258407.5555 | 22384027.9936 | 211027360.1428 | 321269071.2518 | 478752678.7942 | 148760748753.6579 | 2041533886.6497 | 2049023787.1273 | 1744793697.9541 | 199199439.1276 | 556600372.5723 | 683764292.5562 | 750434841.7674 | 286376697.9224 | 583797167.1308 | 27172933.0681 | 121048617.1193 | 21582975.0038 | 25456076.3408 | 924676904.3936 | 26041829.3331 | 1028702286.3097 | 6960898280.5768 | 680572908.7136 | 165407809.9595 | 2.15e+12 | 2424026.6323 | 916095.9861 | 1498674.6819 |  |  | 2.3226e+12
16 | 1165387363.1013 | 1188456518.2722 | 195491862.175 | 146742451.0995 | 1061478634.4757 | 27545527.8727 | 220695081.0611 | 314144106.3014 | 455027889.114 | 150118750167.8275 | 1935993711.4782 | 1884256515.1759 | 1968278290.5284 | 160134363.638 | 639634041.3084 | 720770103.7438 | 819618713.6903 | 325118890.3291 | 499152401.4805 | 25916819.211 | 112139197.3906 | 22437803.229 | 24759617.8477 | 874381909.0393 | 23416552.6285 | 986086598.1155 | 5133419698.3368 | 676939504.7549 | 189213470.2873 | 2.3229e+12 | 2669153.7162 | 1009561.8919 | 1670730.7085 |  |  | 2.4949e+12
17 | 1254137447.5945 | 1105236151.3993 | 205241135.81 | 165049702.9339 | 974701315.7237 | 19438546.4552 | 201285500.2419 | 320076530.7738 | 456064500.7752 | 120164340648.3526 | 1928148673.1341 | 1995503976.7302 | 2011322309.4306 | 178155329.1598 | 621372192.7209 | 560453338.5286 | 938922161.5028 | 332020983.8586 | 566976170.2522 | 27225979.3927 | 99315521.4592 | 22085908.9129 | 25507467.4654 | 812491120.9385 | 28133629.6081 | 1121515087.2577 | 6559792577.5317 | 697954648.6194 | 196854839.3805 | 2.1849e+12 | 2649641.9444 | 933592.0096 | 1528904.4867 |  |  | 2.3285e+12
18 | 1234680095.0771 | 1166398964.019 | 220340221.7635 | 169781761.938 | 1084693596.0974 | 20927439.7955 | 198531818.6443 | 298496546.5412 | 415284580.6121 | 159795773334.0901 | 1996744359.7274 | 2021391504.6588 | 1988276565.427 | 160250563.5111 | 629301277.5635 | 645505201.6363 | 846966483.1226 | 305756502.388 | 481649353.0811 | 20874675.6986 | 105781158.5285 | 24159296.5285 | 24118752.4113 | 756499965.3398 | 28978813.0683 | 996658325.8345 | 7048237342.1077 | 699683095.5621 | 198168052.2783 | 1.6707e+12 | 2471900.7458 | 915406.6607 | 1658678.877 |  |  | 1.8543e+12
19 | 1156179346.8225 | 1114626467.9314 | 178259362.9699 | 172273598.172 | 1019899755.0096 | 24388160.4574 | 220208865.134 | 308648728.5966 | 471102102.1295 | 133049253552.8505 | 2091518797.673 | 1855097109.5602 | 2195571893.3065 | 191228215.6983 | 659813048.6656 | 714466333.3144 | 762854477.6994 | 315583505.4665 | 504587642.1712 | 22208300.9362 | 115570531.575 | 23102805.3385 | 24028037.0754 | 901750965.101 | 23222895.6481 | 1094346354.4519 | 6357694133.3026 | 548875366.1466 | 198433883.9233 | 2.1891e+12 | 2645078.7919 | 976218.7438 | 1568299.4345 |  |  | 2.3454e+12
20 | 1214986893.0062 | 1147826598.2547 | 206011934.7838 | 175310441.5556 | 1053099853.0973 | 21519202.5691 | 196284053.1878 | 317268249.3999 | 491658875.8028 | 147936196330.0273 | 2031656148.9237 | 1992343678.4453 | 2096982762.6383 | 188242442.2102 | 576904618.4898 | 629093858.8747 | 902671426.6288 | 250645974.8831 | 585125071.731 | 26495229.1046 | 109651244.8938 | 23437150.0103 | 22089325.3719 | 898684226.6804 | 25804175.3814 | 1143407941.5564 | 5977932376.1446 | 548835330.0811 | 187792558.0152 | 2.2416e+12 | 2375016.7875 | 905206.2687 | 1695743.8277 |  |  | 2.4126e+12
21 | 1138860365.3572 | 1223367701.8531 | 197160117.9022 | 165378042.7664 | 953570066.5951 | 25516722.0703 | 215455795.3263 | 282650323.3225 | 489589312.0209 | 135061625361.3728 | 1800076667.1474 | 2072140399.459 | 2195837898.3356 | 170752742.9898 | 543412354.8865 | 659046441.1771 | 859710409.6659 | 271726599.8784 | 563643022.0619 | 20050724.4742 | 103407559.8473 | 22282263.9427 | 20628551.1249 | 791047838.6257 | 21898285.0907 | 1112053659.158 | 6692826325.8101 | 584397885.9161 | 199376654.7684 | 2.3136e+12 | 2661689.5309 | 1007193.2075 | 1694596.5588 |  |  | 2.472e+12
22 | 1205920046.2649 | 1144970046.633 | 190786394.6848 | 166764194.2107 | 1081945473.7652 | 28055669.6711 | 216041758.0181 | 315122247.8893 | 484635290.0962 | 149632300690.7482 | 2058149045.7581 | 1950496500.9209 | 1910930036.0684 | 188931620.9706 | 662413468.5101 | 575339364.7568 | 756632780.1849 | 320551244.2464 | 542832022.3089 | 26219040.2041 | 106130447.2972 | 19082402.2318 | 25766435.9836 | 762641381.3568 | 27724751.6711 | 1179442457.6002 | 7019855036.1433 | 565792215.804 | 201753478.6548 | 1.8684e+12 | 2685425.6296 | 880630.0519 | 1603217.8236 |  |  | 2.0418e+12
23 | 1169508406.6247 | 1202114910.9127 | 221191837.9105 | 173049352.4014 | 1081891682.802 | 27968842.6428 | 225361511.1472 | 327170986.7951 | 475110441.3138 | 152303836482.0119 | 2041551523.0467 | 2013879629.0018 | 2159591262.1219 | 183656294.916 | 572852503.6863 | 713746588.0382 | 746668981.9968 | 345238341.1352 | 468375957.9644 | 20668416.9196 | 123933732.6367 | 24379424.9815 | 24378869.0401 | 682633030.2278 | 30941518.3568 | 1004560753.0536 | 5406996157.4382 | 670284465.4882 | 184887788.292 | 2.1631e+12 | 2471847.1062 | 942085.2776 | 1633489.2899 |  |  | 2.3377e+12
24 | 1191974441.8484 | 1175351445.8364 | 222076426.7682 | 144740036.3916 | 1074776418.1735 | 24534939.9681 | 186246428.3412 | 317129689.1653 | 452028305.2249 | 124761025460.8029 | 1705380070.7101 | 1635479101.0936 | 2010088677.2461 | 197943138.0785 | 654241763.3016 | 708573638.218 | 785330691.3981 | 299787354.0985 | 510980121.8128 | 24368645.7974 | 116697251.749 | 18934325.3068 | 21997092.3797 | 863542639.1439 | 25233829.2576 | 1179966173.5079 | 5633525709.1389 | 547385106.3159 | 191762891.8967 | 2.3514e+12 | 2532825.3222 | 893520.9053 | 1532432.1457 |  |  | 2.4981e+12
25 | 1219796132.5342 | 1185336455.0415 | 219843741.2397 | 158930051.9487 | 1055034761.2722 | 25376693.371 | 221811512.14 | 327620681.7468 | 450097669.61 | 128295550768.2816 | 1937750587.2131 | 1831200135.7549 | 2147266303.5042 | 196700934.901 | 467893276.9495 | 696052629.2788 | 926598766.4573 | 328598763.1287 | 596643842.3889 | 26450168.2358 | 111865443.5013 | 24268160.3736 | 22911665.8408 | 878183446.9289 | 28968073.5526 | 1160641117.5391 | 5884113856.2793 | 700034812.7262 | 193150065.8413 | 2.7496e+12 | 2560447.7166 | 899538.9437 | 1559091.3243 |  |  | 2.9009e+12
26 | 1180110677.2307 | 1213593741.3705 | 209545412.6284 | 167750451.2865 | 1055097467.2783 | 21883237.5054 | 175682264.1775 | 296074607.8166 | 477959103.7282 | 132949425723.6111 | 1884558702.7154 | 1634407088.4028 | 2202848019.7292 | 200973230.4446 | 548562969.8086 | 677946351.4984 | 774674003.7306 | 304776085.9671 | 573070426.2627 | 25779911.3892 | 117918788.5692 | 16857710.0252 | 22021905.6023 | 882958591.0152 | 26958679.489 | 1013147215.7719 | 6312880240.9268 | 570955430.0897 | 179414022.3914 | 2.1666e+12 | 2381322.0127 | 967318.6979 | 1728192.6946 |  |  | 2.3223e+12
27 | 1184324186.8889 | 1221974400.5274 | 214834520.5278 | 176519251.1447 | 932945513.3566 | 26443325.4341 | 219664264.7354 | 323096230.0202 | 449179266.6831 | 125831426578.6916 | 1803091575.4291 | 1620312103.0428 | 2070115710.7291 | 197470465.2835 | 665861644.2655 | 702817794.5451 | 821917327.8701 | 283422926.4759 | 588738191.1625 | 26111041.4535 | 130538425.2121 | 20113411.0257 | 18517888.6017 | 728553018.7168 | 23471536.4548 | 983277465.0494 | 5165458619.7124 | 686965505.6818 | 194166693.5827 | 1.8612e+12 | 2840633.8274 | 1014625.2871 | 1649989.699 |  |  | 2.0085e+12
28 | 1223741384.3149 | 1226943540.6621 | 209611326.409 | 161884657.2194 | 1064042327.208 | 23342047.271 | 226608759.5797 | 322168830.9135 | 475642607.6978 | 150197260970.5699 | 1807012055.8684 | 1692407710.2848 | 2080288966.2948 | 188874890.137 | 592575666.323 | 691244571.5577 | 847952550.0727 | 275607912.2503 | 577279136.5181 | 23480635.3766 | 121958711.3144 | 22826881.5628 | 24291410.7968 | 856402534.3462 | 26589501.3197 | 1078604830.293 | 6689979102.1977 | 678843253.4732 | 195903636.6475 | 1.6143e+12 | 2487188.3995 | 977749.222 | 1752706.0872 |  |  | 1.7879e+12
29 | 1159891960.253 | 1210143176.5851 | 222435557.6893 | 174685007.5009 | 940704949.8803 | 23920484.5672 | 190531745.7687 | 319235544.7551 | 458627333.4335 | 156055221678.9608 | 1464778532.4875 | 2007443031.1012 | 2025516326.1486 | 192529066.599 | 465095472.5849 | 721698724.7753 | 727470292.2396 | 326813837.9394 | 598823383.9725 | 25507693.2374 | 131199184.0586 | 20736492.8446 | 25121908.7811 | 930139166.7373 | 22795221.9222 | 1174153174.6698 | 6693942905.7715 | 587361769.3599 | 171908456.0018 | 2.396e+12 | 2282646.5922 | 927432.0062 | 1765231.6468 |  |  | 2.5751e+12
30 | 1095781666.9856 | 1224279836.4016 | 220794798.9126 | 167615503.2441 | 1042355531.2758 | 25833957.0223 | 207664605.9339 | 318009384.705 | 478888811.5405 | 142258425366.0455 | 1570941488.6706 | 2016427718.7878 | 2211897148.9601 | 200231834.5848 | 595970253.9054 | 625680485.2254 | 919342074.2871 | 297544401.9498 | 574197203.1757 | 22133759.6447 | 114267123.1091 | 21991129.0401 | 22317662.546 | 863778433.3893 | 28494673.6326 | 1089927740.1528 | 6756289422.4557 | 570383743.3411 | 200423716.4796 | 2.2254e+12 | 2542628.7485 | 932078.1839 | 1515716.1927 |  |  | 2.3911e+12
31 | 1193009613.5824 | 1077336510.1023 | 216611217.3127 | 149871116.3559 | 1086093603.6184 | 20408832.6161 | 196235624.6504 | 324692655.4539 | 452750756.5653 | 155936468242.8848 | 1990185515.9933 | 1488303817.7381 | 1872697354.3384 | 199141785.6174 | 635896775.1497 | 553084932.4954 | 722490839.0128 | 351288601.2992 | 610363821.4276 | 23770336.9168 | 111174932.8844 | 23379170.1794 | 21342291.8587 | 817263587.6635 | 24290386.0477 | 844471789.1191 | 6649847838.9498 | 706390901.2336 | 186872253.9289 | 2.0281e+12 | 2478748.9594 | 919121.7547 | 1744594.9758 |  |  | 2.2066e+12
32 | 1263406315.5127 | 1153348110.772 | 220006417.5588 | 163421190.6829 | 1039042882.5573 | 25567047.8427 | 215561707.2002 | 307667104.5134 | 495335528.6028 | 147297916781.2655 | 1685445193.0679 | 1908088346.1353 | 2071889135.9181 | 193016362.918 | 483561343.2722 | 689675388.2431 | 786094834.7405 | 331883924.0353 | 524071110.3671 | 28182894.737 | 121345005.1949 | 18554930.1318 | 24300247.0991 | 679643144.3953 | 28974455.8748 | 1164043141.5873 | 5876019558.9313 | 674844456.5814 | 193585290.0696 | 2.1696e+12 | 2594644.278 | 887823.2378 | 1535038.8449 |  |  | 2.3392e+12
33 | 1078288737.5698 | 1141031609.7979 | 205086158.6628 | 162019005.471 | 1059140018.1559 | 23931946.2467 | 206394408.0392 | 273122561.411 | 467666710.5655 | 154899222739.9704 | 2077104108.4388 | 1800578452.3826 | 1749303705.847 | 186094205.4828 | 533971666.5952 | 636568772.9991 | 802297982.0904 | 303989018.4348 | 605488039.3575 | 25694970.9108 | 123199648.833 | 19699548.3799 | 24479016.6638 | 854626301.4613 | 28893764.7193 | 973054271.9369 | 6212007662.3865 | 640708074.8622 | 164165890.4693 | 2.0072e+12 | 2370303.5219 | 967259.8925 | 1767505.4687 |  |  | 2.1845e+12
34 | 1050692083.5834 | 1124402298.1415 | 218537345.8918 | 150177800.3274 | 1051038277.3668 | 24925387.9817 | 209732145.046 | 291093374.1982 | 498772517.3746 | 141326767292.202 | 1683947714.2072 | 2177912119.089 | 1973461988.0473 | 192798901.6822 | 587542606.1666 | 697350722.0601 | 918879577.7139 | 315898156.7691 | 587050239.3296 | 27198688.4877 | 107775585.2038 | 23971296.2368 | 21691820.1215 | 763208310.0305 | 25021551.0298 | 1174728033.1324 | 6214286622.8087 | 655820750.0041 | 200142376.9703 | 2.1994e+12 | 2275203.7558 | 960222.7484 | 1864880.3658 |  |  | 2.3637e+12
35 | 1226641197.8537 | 1227961990.4935 | 220517635.8657 | 166522177.0093 | 1028871058.6649 | 27680393.6278 | 208007465.6742 | 307808781.0146 | 447324559.5049 | 121933064411.2775 | 1945866016.3438 | 1759235903.7436 | 2138279679.8258 | 199129499.3044 | 588216498.3269 | 634828034.7108 | 872925357.9541 | 312860581.1435 | 437489603.3609 | 25784893.6142 | 132234289.5207 | 21280806.5982 | 25666297.9482 | 837090327.5305 | 24811137.5081 | 1079223088.1618 | 6890094100.3597 | 557323932.7218 | 200802656.7196 | 2.769e+12 | 2638917.8132 | 981287.8682 | 1625925.6053 |  |  | 2.9145e+12
36 | 1212707074.2606 | 1143448612.2428 | 226830194.53 | 166294563.9751 | 961470140.7167 | 21790998.512 | 209396583.4124 | 292424666.1424 | 482104621.1978 | 130322478622.407 | 1814328889.0995 | 1940059670.4882 | 2000391154.6955 | 188531856.2604 | 544978397.5777 | 661522723.8426 | 839349296.7409 | 333282598.3403 | 557349083.4563 | 23459091.0959 | 118561799.5309 | 22227834.0088 | 25388661.5272 | 924231371.0231 | 30153761.7423 | 1153609035.4973 | 6514612218.225 | 635002157.4119 | 196312203.7525 | 2.2534e+12 | 2350986.8292 | 1010810.8184 | 1584456.5349 |  |  | 2.407e+12
37 | 1064075154.5058 | 1149025455.0082 | 215566418.2389 | 181253482.3729 | 1033289580.1546 | 24801360.2956 | 211476472.9867 | 276398912.9903 | 408592672.3404 | 120821930238.7438 | 1932457796.4689 | 1855686869.7519 | 2162169078.1502 | 193685452.9051 | 558021772.747 | 611147241.8684 | 816141930.8079 | 343840833.0577 | 589150663.0134 | 27939738.3539 | 107398227.5581 | 20630228.4801 | 25979330.1501 | 936371929.6832 | 26723539.7795 | 989353076.0102 | 5138840731.7491 | 662918221.1035 | 182776173.1973 | 2.1387e+12 | 2581271.7523 | 949510.6232 | 1614968.4316 |  |  | 2.2812e+12
38 | 1219264503.2268 | 1216710851.35 | 207721159.8352 | 168187948.8136 | 1084125896.9217 | 23866007.5562 | 213154185.7395 | 307202020.1912 | 486825819.9842 | 150551037360.388 | 2061336118.704 | 1917397936.1388 | 2103635992.3118 | 189095124.0886 | 502418449.9503 | 718073163.328 | 750393775.166 | 340729901.1047 | 586879077.9164 | 26855348.9175 | 124986265.7021 | 21200690.529 | 21586053.5561 | 915208607.3616 | 30177163.8266 | 973256812.841 | 6497448143.3198 | 663635479.2409 | 200205620.7731 | 2.3839e+12 | 2446086.9547 | 999362.8293 | 1695529.9361 |  |  | 2.558e+12
39 | 1264598744.2632 | 1183802062.364 | 219124194.9443 | 165096760.4183 | 958328045.9353 | 20416568.5554 | 198699121.5931 | 294828845.4046 | 473753475.6899 | 145923680750.6272 | 1889064403.7026 | 1904369220.2092 | 2155028520.9098 | 194358861.7782 | 576183439.3804 | 663319619.6385 | 732544883.0556 | 279055786.0286 | 550483453.8825 | 26827124.9713 | 105175239.8685 | 20879133.1824 | 25133056.1019 | 830517447.4543 | 26909877.9558 | 922006926.2359 | 6222109522.2017 | 674937250.4127 | 197151994.3959 | 1.6265e+12 | 2413269.1141 | 947151.0501 | 1689760.4593 |  |  | 1.7952e+12
40 | 1221506655.2137 | 1202523962.7865 | 213996301.5363 | 147108554.5994 | 934298784.3947 | 23625841.2495 | 206183855.2026 | 289336706.9227 | 456018141.1396 | 114064352629.7159 | 1853314110.2036 | 1948988517.2468 | 2088212054.3279 | 186788206.2501 | 606702218.643 | 660668272.2146 | 766290865.1288 | 322589557.3824 | 556752283.923 | 16912891.534 | 113295577.9522 | 21346902.6894 | 22143336.1136 | 858183979.3613 | 27696289.4153 | 1020792241.1556 | 5574378353.2386 | 601176467.611 | 188162395.9618 | 2.4653e+12 | 2446489.9338 | 976833.0966 | 1775788.6151 |  |  | 2.6015e+12
41 | 1111419055.587 | 1197595956.4987 | 203077257.2143 | 135249255.1589 | 1047831540.5441 | 27630203.7546 | 188994952.1295 | 288984709.5534 | 469161291.5243 | 143923077367.9896 | 2037680440.9545 | 1668595191.6985 | 2127121688.733 | 202564068.1412 | 568041009.9615 | 680022864.655 | 680395531.8271 | 335442167.1383 | 564234069.3148 | 27346442.167 | 134169104.1035 | 23754553.3439 | 25216388.423 | 681440379.1519 | 27239369.9008 | 1083616909.2885 | 5792696631.5346 | 605413332.2764 | 170036768.823 | 2.0782e+12 | 2443321.9453 | 956526.3628 | 1519228.6427 |  |  | 2.2442e+12
42 | 1047127636.7377 | 1224261071.3315 | 196955568.6337 | 162728593.724 | 1050287475.7308 | 24358925.4598 | 198239455.526 | 301044359.3806 | 471448737.3425 | 156905334162.4822 | 1832962471.934 | 1972727235.381 | 2115021509.2455 | 195310122.9703 | 663515456.724 | 668793087.5404 | 919337727.6947 | 299815510.1197 | 574709750.7981 | 23043278.2079 | 103814303.5336 | 22901191.2883 | 25374319.645 | 928319665.2943 | 29192308.1884 | 1168730584.4731 | 6943375961.1701 | 548285301.7835 | 155331151.5987 | 1.8122e+12 | 2438713.6234 | 965283.5895 | 1720236.224 |  |  | 1.993e+12
43 | 1238152327.5589 | 1126475999.4401 | 206522875.8823 | 164898660.231 | 1059923664.8329 | 22725106.4164 | 216876111.1589 | 314456030.2161 | 495125887.7682 | 151419884533.0695 | 1569623677.9598 | 1926765565.8911 | 1696317264.758 | 188298980.8886 | 576814305.0691 | 628260110.5912 | 731928850.6916 | 305607435.7758 | 601728338.8907 | 20934425.1645 | 109514953.3329 | 20808943.7898 | 24224488.4678 | 850467002.2219 | 30844304.7988 | 1115417523.5617 | 6251862379.4908 | 646984092.1765 | 201143963.106 | 2.0831e+12 | 2371595.7594 | 973665.9813 | 1710637.5459 |  |  | 2.2569e+12
44 | 1054791741.1591 | 1203130729.0895 | 207750292.8661 | 160120758.458 | 1087374698.8138 | 23196779.8765 | 213122185.7397 | 308125103.2619 | 406737663.5237 | 124779637558.8423 | 1801949092.5176 | 1812548752.8783 | 2011426132.6668 | 194995560.2412 | 613596273.4673 | 608300548.6598 | 625248234.41 | 337621157.9059 | 557104515.1155 | 24232830.7271 | 111932218.4028 | 21897349.1711 | 21900298.6757 | 812496247.8281 | 27632926.0376 | 1160606976.1787 | 6718708525.9822 | 685792095.7817 | 191661544.6261 | 1.7543e+12 | 2456528.7233 | 953078.0755 | 1659004.2508 |  |  | 1.9021e+12
45 | 1245547897.0665 | 1149939306.832 | 190210887.0642 | 170006574.7609 | 1049694645.0001 | 23738004.3111 | 226749467.3253 | 309369090.7605 | 470253702.6024 | 148816023951.5883 | 1908796463.5197 | 2123703217.7572 | 2135441567.178 | 182288312.2663 | 516422235.3858 | 720167812.1501 | 901254996.7344 | 293729456.4132 | 601927658.8931 | 25488596.7798 | 131097664.2353 | 24334508.5659 | 21873295.5279 | 808206323.5934 | 29560617.9109 | 1042487368.6875 | 5543631455.4662 | 626139888.9855 | 190422362.1384 | 2.8195e+12 | 2447528.4841 | 905138.2395 | 1506567.8074 |  |  | 2.991e+12
46 | 1243425833.6624 | 1173055623.5702 | 226833304.8148 | 177183834.8605 | 1047257292.2523 | 23439784.0303 | 211337613.7791 | 316370377.7621 | 487128722.2237 | 138942828640.3983 | 1971695997.9545 | 1938790713.5769 | 1804699340.0737 | 169215518.8154 | 624631486.3063 | 700290568.8967 | 910433347.8806 | 298194516.4849 | 581365309.2589 | 28872948.3593 | 122334808.9408 | 19814192.6721 | 17469415.4627 | 752783717.4728 | 30044753.2713 | 1069085228.8314 | 7034020127.1884 | 601486183.2341 | 195798372.1571 | 1.9686e+12 | 2479641.2126 | 978580.2348 | 1654198.5935 |  |  | 2.1314e+12
47 | 1207262355.5835 | 1203255501.1231 | 202396593.7007 | 174566917.3503 | 1004542424.7445 | 24936784.4539 | 223179092.6128 | 329317209.4061 | 442917075.4539 | 150397536804.1434 | 1533984720.7453 | 2105872181.7584 | 2149368383.9604 | 197996294.0637 | 626428760.9866 | 677500541.1483 | 861340993.5863 | 329494155.3623 | 557995373.7962 | 25146950.0978 | 116994881.1169 | 20555411.0677 | 24724184.7284 | 926559305.0691 | 26859686.6077 | 1128637373.4678 | 6859925509.0036 | 627996991.2252 | 178623112.0758 | 2.4044e+12 | 2651296.068 | 939562.2358 | 1751301.3369 |  |  | 2.5785e+12
48 | 1248282479.0052 | 1184413671.3888 | 192727190.768 | 153845956.0247 | 945551517.0511 | 20898115.9661 | 214027397.9849 | 302954859.6914 | 458650830.4864 | 135687233143.379 | 1884700371.3681 | 2007313015.7273 | 1674686973.4082 | 200918584.8554 | 553823840.7549 | 711348700.7618 | 794622302.2235 | 296263487.3912 | 531261947.3546 | 25341387.9741 | 107859436.4437 | 23338215.6191 | 23250167.2688 | 720263025.6937 | 29991459.5957 | 900597194.9708 | 5901853787.2999 | 650399628.8001 | 180724648.3727 | 2.3441e+12 | 2730313.0783 | 931458.4189 | 1685136.1664 |  |  | 2.5018e+12
49 | 1202491259.2902 | 1027234897.4745 | 195841334.4508 | 163865682.6158 | 1032547228.0416 | 21681450.4077 | 224567381.0807 | 327878675.1366 | 416708271.0135 | 154153312149.5038 | 1754167584.8076 | 1673993815.4137 | 2130987409.4693 | 190209606.1402 | 666536297.3997 | 711068914.4308 | 785666382.8159 | 330360675.4709 | 479178494.742 | 25448537.3249 | 119828408.6032 | 22017097.5801 | 19613780.1096 | 806278135.5253 | 29714765.2601 | 1072240756.4631 | 6726739619.7014 | 632040024.1112 | 199622069.346 | 2.1652e+12 | 2402877.0404 | 1037295.027 | 1634336.3811 |  |  | 2.3424e+12
50 | 1106581617.6746 | 1116088427.1179 | 219186115.7373 | 181345303.8778 | 1034980418.6229 | 23677136.4111 | 197894930.4453 | 324977299.7577 | 478795442.4876 | 137783438011.3409 | 1957566786.0852 | 2157179645.6327 | 1933057503.8431 | 193972111.4812 | 577896683.3914 | 499576738.9708 | 789075701.0836 | 335655490.8096 | 539410731.6755 | 23188673.3717 | 122578552.1343 | 23122979.0693 | 25777770.0386 | 876293560.4035 | 28751828.8937 | 1059465902.8734 | 6273178901.037 | 597228498.5689 | 200238117.3689 | 2.2234e+12 | 2823939.7945 | 934728.8742 | 1674200.8372 |  |  | 2.3841e+12
51 | 1216422200.7777 | 1156280397.1537 | 213895674.6441 | 167154962.7483 | 937024428.2358 | 23489344.7351 | 212663799.9763 | 303426559.5847 | 422908226.248 | 137733224376.5864 | 2085729465.1744 | 1897075185.1908 | 2016650243.263 | 196135142.1972 | 607581194.855 | 694763353.5404 | 712520109.8402 | 272373973.7861 | 574223814.8184 | 24903731.3567 | 132786306.1728 | 24163840.3519 | 17537453.0023 | 814763438.3426 | 29138205.3539 | 1028014029.2469 | 6023734523.242 | 669703005.1445 | 170040653.59 | 2.0051e+12 | 2344347.2395 | 960767.0981 | 1770196.3918 |  |  | 2.1655e+12
52 | 1000845300.5847 | 1154475909.7703 | 215300503.6662 | 165380580.5996 | 1080810809.114 | 25331557.005 | 188065595.385 | 303948563.8507 | 430472558.5454 | 131012550841.7898 | 1774681044.0023 | 2051371479.4656 | 1876488649.049 | 181145513 | 606369513.0989 | 722248053.8562 | 738376770.2298 | 353514760.1163 | 612327414.2699 | 21600876.3289 | 112728254.4436 | 22536033.75 | 23955747.3374 | 856292612.4964 | 30673603.7127 | 1069186119.2049 | 6204573947.0661 | 711349858.7069 | 178346868.9358 | 1.9976e+12 | 2609636.6578 | 987131.8553 | 1560458.5853 |  |  | 2.1514e+12
53 | 1162405232.3344 | 1222417547.6079 | 214926353.5325 | 166489630.3562 | 1008033117.331 | 26071382.4512 | 213170018.0817 | 325762562.2899 | 486621349.9498 | 144894694335.7415 | 2049462312.3025 | 1802001202.697 | 2067709081.2857 | 193632731.4107 | 536643370.0695 | 658774580.2946 | 870582538.0489 | 341790618.4504 | 496413045.9197 | 23244139.2175 | 104032417.0479 | 23225789.6784 | 23936107.3905 | 922544497.5279 | 25216805.8033 | 1181311779.1043 | 6069065792.9241 | 645387670.4835 | 184009639.6605 | 2.2243e+12 | 2294255.2982 | 933424.7568 | 1656590.8476 |  |  | 2.3922e+12
54 | 1230205322.1536 | 1207918552.6575 | 220936120.1615 | 168053050.3844 | 1026821819.4763 | 27968200.6691 | 207267491.1304 | 299396245.2828 | 455854860.1049 | 148232987774.3288 | 1746940589.3613 | 1828508414.9094 | 1447645209.497 | 172894252.6679 | 597233519.3037 | 643008641.2733 | 861284569.183 | 279414854.0245 | 484262273.429 | 22231282.6408 | 113581992.5058 | 22932901.8934 | 20957616.9696 | 841330477.2254 | 27053595.9935 | 1027851538.55 | 6230887543.7529 | 607272661.567 | 179171162.7412 | 1.7664e+12 | 2680813.047 | 936271.7274 | 1654294.2866 |  |  | 1.9366e+12
55 | 1090814263.74 | 1121675382.7576 | 209407387.7935 | 174348699.6368 | 1085544634.8563 | 23069348.677 | 201565498.9087 | 308832572.917 | 430454315.0279 | 117723694608.1495 | 1858541830.6673 | 1755389713.0197 | 2168863458.8703 | 168468285.1914 | 617762106.8773 | 635944357.4469 | 922337974.0655 | 321772376.87 | 599008830.9477 | 26209529.3898 | 106495482.7363 | 21409943.2287 | 25686318.9475 | 905587267.8665 | 27642387.1513 | 1139773269.0115 | 6942753719.0554 | 679848778.9011 | 189233739.5565 | 2.071e+12 | 2569022.7485 | 908903.1049 | 1737711.6803 |  |  | 2.2125e+12
56 | 968237991.8178 | 1210767000.1026 | 197285783.0695 | 168834709.4283 | 919695671.9631 | 23887238.904 | 177528859.0357 | 289904368.4656 | 480033826.2606 | 155122114597.935 | 1807359683.3045 | 1788377473.2185 | 2210002842.6853 | 193997775.2031 | 560351902.0883 | 679513270.5339 | 821497120.6709 | 308692125.5458 | 502066590.4627 | 21689931.3857 | 115998786.2768 | 19340285.5698 | 22551982.5666 | 847377935.0417 | 29422048.1478 | 1092600241.4862 | 5181236477.8866 | 658565154.1735 | 199795486.2094 | 2.2654e+12 | 2313233.0591 | 887962.6702 | 1711288.8777 |  |  | 2.4421e+12
57 | 1255923031.0291 | 1204360574.4252 | 223911539.3505 | 176185325.5802 | 1018178534.2962 | 21833142.3873 | 208778685.1725 | 308136694.9772 | 403483254.3146 | 150589550759.8232 | 2072959443.2769 | 2050046275.9353 | 2204886471.6271 | 194775618.374 | 574744792.7133 | 676513756.0277 | 646075102.8288 | 338889375.0039 | 595034447.3511 | 23758828.2859 | 121590124.2853 | 24260024.9614 | 25758562.0448 | 805262696.513 | 24270790.4989 | 1144330271.4577 | 6506873732.6807 | 605243629.5643 | 197805405.3092 | 1.5765e+12 | 2710315.5376 | 900784.6678 | 1639465.6762 |  |  | 1.7508e+12
58 | 1169944612.7571 | 1225120919.7949 | 194052505.1577 | 178552642.4411 | 1082160570.9035 | 20226154.2816 | 221209117.1456 | 322441135.9936 | 475612862.6791 | 111004587216.228 | 2036686543.7662 | 2095268302.6932 | 1969396091.5158 | 160592657.8192 | 661635560.9853 | 715050429.7205 | 823838445.0089 | 302018215.0379 | 613555366.0363 | 26230997.6822 | 114506333.6866 | 22806016.6044 | 24103679.1245 | 918284597.4243 | 24284837.5928 | 1128172841.1597 | 6567470781.4215 | 659138147.7477 | 188003427.0643 | 2.8725e+12 | 2580656.1961 | 927930.3805 | 1664628.6098 |  |  | 3.0075e+12
59 | 1182576325.0871 | 1111527856.5694 | 218049061.4102 | 171748569.8708 | 980145983.7205 | 21968934.0139 | 198325339.2992 | 285013902.5937 | 478686255.3383 | 162160627030.6426 | 2008553471.6575 | 2016856833.246 | 2027996205.1697 | 196825935.6007 | 553852673.6127 | 710892916.7628 | 817765216.1916 | 362298162.2036 | 511040514.4584 | 23803814.3721 | 110530446.6637 | 23227151.9863 | 20751162.6553 | 833737666.415 | 29250815.6985 | 915941063.4146 | 6388506692.3803 | 608445604.5136 | 179917986.1802 | 2.5866e+12 | 2570453.9552 | 1016744.0063 | 1523369.7079 |  |  | 2.7717e+12
60 | 1223217846.8791 | 971318602.3711 | 219591652.0829 | 169286148.2434 | 975738457.9042 | 24955718.6743 | 223520278.4445 | 320286404.0149 | 435656466.4615 | 148576608700.4887 | 1983996914.417 | 1951570115.4552 | 2157367306.8329 | 191135495.9005 | 613960680.2325 | 643219256.4254 | 777862188.2795 | 293622129.8505 | 443057452.8397 | 22338627.3697 | 107983557.0638 | 22614942.1115 | 24556311.5949 | 861587496.0002 | 25533199.6561 | 1160672692.3527 | 6858975995.5191 | 618734171.4283 | 186385645.1494 | 1.5847e+12 | 2622022.3489 | 979741.0537 | 1568761.8853 |  |  | 1.7568e+12
61 | 1253294594.5756 | 1173534191.8775 | 212846048.3148 | 164512003.4467 | 1073622263.5361 | 27143563.4563 | 206661268.8323 | 302394047.1302 | 486772281.3427 | 159996775028.4047 | 1805434967.3255 | 1687536379.1533 | 2174416807.8617 | 170415827.7189 | 633043754.8065 | 696672461.6957 | 784270378.4733 | 312186917.3067 | 562321892.007 | 19245108.12 | 128700893.1118 | 21219115.6235 | 24654522.9559 | 890948258.126 | 25838702.4213 | 1212735389.1392 | 5873596620.98 | 701734452.0394 | 193314359.9223 | 1.3753e+12 | 2288766.8939 | 916180.9573 | 1648133.5786 |  |  | 1.5581e+12
62 | 1189766011.6698 | 1208160943.553 | 202384898.5181 | 175248273.0361 | 961752136.9047 | 21904089.9734 | 198403789.1731 | 305001187.0703 | 458644319.7332 | 155728684556.7624 | 1608867104.9013 | 1928881080.4268 | 1697543408.6743 | 179384326.6195 | 615014121.6488 | 695890565.7108 | 773873340.7619 | 340334307.3166 | 590357536.5219 | 25099359.8559 | 98005663.977 | 22506003.8672 | 22817304.3552 | 783543141.3207 | 24760179.3477 | 883433291.6366 | 6031852548.9464 | 675810758.8776 | 200768575.2251 | 1.8763e+12 | 2691302.8855 | 1015826.6993 | 1721915.4525 |  |  | 2.0539e+12
63 | 1115131416.531 | 1179238409.8645 | 199027073.2053 | 173351427.8391 | 1069298047.7252 | 22608496.3942 | 212336167.647 | 324355796.2265 | 477830687.1131 | 156991074462.3794 | 1859973316.337 | 1888340930.2181 | 2210214893.8268 | 175681263.411 | 511907034.1447 | 696790673.607 | 891714814.9245 | 268827459.7969 | 519919484.628 | 21795593.4118 | 97547308.9244 | 21601545.1429 | 21818069.4483 | 711263815.1212 | 29832444.9203 | 1095226951.6911 | 6022973145.3876 | 691907022.8681 | 188854649.9914 | 2.1281e+12 | 2424493.4333 | 953373.9774 | 1797553.0669 |  |  | 2.3078e+12
64 | 1175588528.2497 | 1030506960.5507 | 221795568.1682 | 152204779.0286 | 993198978.2445 | 22446394.4922 | 222245747.6741 | 327634997.4057 | 486210696.9873 | 132533812810.7975 | 2006278309.2694 | 1596437197.7769 | 1920233674.3705 | 179631212.9089 | 626706866.2705 | 696704014.7443 | 775535448.7548 | 299578614.0741 | 576937529.8531 | 26514550.2309 | 125745195.2258 | 22774133.6495 | 25806698.0958 | 936100480.7691 | 29839066.2375 | 1126031142.4433 | 6927221830.3198 | 711874830.0144 | 180914297.8443 | 1.4049e+12 | 2286917.1432 | 953309.6633 | 1592757.4365 |  |  | 1.5608e+12
65 | 1240542622.0258 | 1228618619.1652 | 215736296.1507 | 180278731.193 | 1059976466.0215 | 25944105.7741 | 203757130.2155 | 327223559.4959 | 480339772.8304 | 160485423402.3417 | 2006707240.0281 | 2010474927.3226 | 2079160498.8927 | 172996446.359 | 627934239.8413 | 724562701.8232 | 614894140.436 | 329946719.3159 | 588004632.3459 | 25712920.3687 | 124311544.9255 | 23512936.8216 | 20453001.4093 | 863579612.9282 | 24063169.0183 | 1236436533.9187 | 5856657702.4398 | 635541653.6572 | 195922145.8657 | 2.056e+12 | 2604935.7014 | 929219.7863 | 1509618.7489 |  |  | 2.2396e+12
66 | 1135477636.492 | 1206687371.5292 | 190086944.514 | 161650608.7915 | 1061028527.743 | 24947950.703 | 190309986.8159 | 316516839.3474 | 485204504.2052 | 139423806240.5495 | 1500042052.5789 | 1669720702.1484 | 2180230127.7043 | 183824079.3704 | 520915385.8962 | 691678311.0053 | 924049301.4119 | 319106610.1895 | 554653119.4963 | 20744136.145 | 122877165.4293 | 22625331.9995 | 23288373.086 | 731505124.561 | 30943994.1257 | 1182581973.3833 | 6507353462.3276 | 692315002.4838 | 194860882.8263 | 2.2815e+12 | 2532878.1253 | 966508.9482 | 1556828.149 |  |  | 2.4438e+12
67 | 1059478120.7404 | 1222603194.8781 | 180673895.7637 | 182064258.5619 | 981253854.8625 | 24745411.8347 | 211616295.981 | 316055021.5183 | 443843110.0327 | 127759442697.0196 | 2089469590.619 | 2071871995.727 | 2153015735.378 | 194634816.2804 | 563483491.7952 | 661380659.0041 | 887488912.2599 | 310486852.4591 | 594777373.1133 | 27768051.1724 | 101022980.9272 | 20998595.6453 | 24075215.8247 | 906395319.5289 | 27816368.1466 | 1147925880.3633 | 6889726650.6595 | 688832335.2141 | 190288052.9267 | 2.4575e+12 | 2586618.3443 | 960115.7451 | 1772137.6931 |  |  | 2.6095e+12
68 | 1137748622.4428 | 1226625684.3576 | 212058220.0434 | 170450260.7623 | 1079646196.6333 | 22371399.8841 | 189494101.4272 | 327913148.4182 | 466024439.4452 | 156749242008.8199 | 2006866359.4566 | 1600056692.468 | 1968362540.6804 | 182115169.6696 | 561401678.8383 | 696867546.8432 | 837855396.9192 | 327892557.6405 | 602943141.8575 | 21739556.9066 | 119923649.8389 | 23588789.8308 | 20396369.6156 | 887338735.508 | 30917774.7064 | 915458450.0332 | 6644979832.1384 | 649344053.95 | 199242941.1822 | 1.3548e+12 | 2650070.6932 | 947518.2014 | 1584913.2465 |  |  | 1.5347e+12
69 | 1252082075.4653 | 1221839931.5026 | 195247606.0254 | 178792881.6544 | 1033021714.3266 | 25544419.5415 | 202338706.4886 | 315043812.8301 | 487459583.471 | 151822509704.1216 | 1948863576.5679 | 1952633060.91 | 2047229250.3799 | 152450344.9594 | 545202700.0736 | 719767548.4948 | 816853776.3421 | 315483472.8905 | 520032562.1627 | 23485497.7643 | 88981061.0209 | 22338477.3556 | 22848785.5032 | 744135389.3137 | 26026357.841 | 1198121539.0349 | 4774180418.1087 | 706237901.1072 | 165151120.4413 | 1.8964e+12 | 2616074.1637 | 971541.5719 | 1512784.7059 |  |  | 2.0699e+12
70 | 1249344839.3503 | 1226523494.0112 | 197025950.6009 | 143822534.3312 | 1035631909.1203 | 23580642.3761 | 214190353.6301 | 319645843.6096 | 485744792.1983 | 130780885329.7854 | 1914697276.0111 | 1883511982.6368 | 2194124067.9067 | 190928018.509 | 547450284.4638 | 720614176.3077 | 822191750.7224 | 293636302.1243 | 607285185.6771 | 25530142.8401 | 111809656.4448 | 17690051.7717 | 25026421.2191 | 828341450.6192 | 29708465.8793 | 1022636260.6912 | 6301798757.7075 | 585738947.3749 | 174583285.1891 | 1.9603e+12 | 2647071.8809 | 998610.2065 | 1671457.6811 |  |  | 2.1143e+12
71 | 1122746518.6415 | 1214392512.6653 | 193322734.6951 | 178065663.6534 | 1062913190.2476 | 22874489.0806 | 183158206.6576 | 329927032.0937 | 498715832.3635 | 144728107853.8631 | 1868860405.5845 | 2050726931.2226 | 1882094505.5923 | 198563124.8084 | 626638407.4029 | 607824578.7946 | 919652057.9826 | 325138383.5031 | 578396455.2355 | 25527382.8732 | 119185308.3719 | 18920885.3996 | 23526884.2344 | 870898926.609 | 28421061.5362 | 874677580.5497 | 5842366649.1214 | 521039589.4448 | 194464933.2034 | 1.9449e+12 | 2528675.4574 | 1046463.4796 | 1529709.7057 |  |  | 2.112e+12
72 | 1233973832.2242 | 1170740962.702 | 223557312.1738 | 155851279.7003 | 1041122554.9176 | 25771304.7646 | 211894582.0764 | 281061058.8398 | 495198245.6146 | 148124897115.1677 | 1644515208.3794 | 1517114872.1715 | 2117413987.2956 | 168259983.495 | 677972044.4091 | 686499839.7015 | 822635868.7118 | 350461861.283 | 596287473.8375 | 23500890.3369 | 124602780.4574 | 20871095.1683 | 25539083.2238 | 887933542.454 | 29911717.4282 | 1200815613.8366 | 6083152784.0236 | 693644655.5003 | 179048790.5047 | 1.8651e+12 | 2363280.8717 | 929897.2268 | 1607770.8248 |  |  | 2.0359e+12
73 | 1115932938.6902 | 1108547732.1502 | 209240093.7385 | 171237132.747 | 999760613.3385 | 22581583.2453 | 211162086.0974 | 315057858.712 | 488017051.7046 | 148127770660.7424 | 1890406506.2146 | 2066721291.1245 | 2200908325.6032 | 176264394.9121 | 592307285.3467 | 627143812.1062 | 821385710.6975 | 303176600.9911 | 609258485.6853 | 26855645.8335 | 128532207.972 | 22372824.0799 | 24994316.46 | 823116335.6234 | 28611969.7726 | 1118677690.8396 | 5753042531.2553 | 572966789.6661 | 165900882.7249 | 2.4013e+12 | 2529439.3766 | 955662.3895 | 1557080.9066 |  |  | 2.572e+12
74 | 1108768539.9105 | 1135142536.6301 | 186184218.5749 | 159945632.0041 | 1053125907.2551 | 25443477.7657 | 205381405.8483 | 320970976.823 | 459879313.4068 | 152459817009.8751 | 2010591002.1015 | 1939622319.5522 | 1861585218.6598 | 181439010.3059 | 608809335.1444 | 671855518.3701 | 850373215.4133 | 264142765.7168 | 601836145.8392 | 28241260.7409 | 98918268.2031 | 23158127.4074 | 25239523.9913 | 856901607.0485 | 25467450.9679 | 1151162918.876 | 4941998148.8951 | 615159192.6738 | 196108263.0506 | 2.539e+12 | 2181466.3818 | 966823.3777 | 1543578.4999 |  |  | 2.7131e+12
75 | 1116380374.194 | 1033024430.5859 | 203893725.0465 | 165596205.8278 | 1063588924.6527 | 24283367.9279 | 218194401.8672 | 307261861.7558 | 449461184.6914 | 155777979098.4468 | 2000567952.5969 | 1867883976.8047 | 2074782698.9221 | 199692357.8297 | 546936072.9199 | 648877029.1692 | 842322446.0304 | 308131728.412 | 513646839.6709 | 22221807.3747 | 123567067.6659 | 21727906.3391 | 25505354.1963 | 803136214.1753 | 31086230.9256 | 1119922091.8635 | 4754538393.2862 | 628179779.6917 | 165687739.9051 | 1.6893e+12 | 2466778.5317 | 919993.9291 | 1537583.4846 |  |  | 1.8663e+12
76 | 1247756955.2432 | 1138066325.4875 | 199841676.6219 | 182354848.0004 | 948093729.8977 | 20863748.4043 | 211458859.8099 | 313110068.7815 | 487842528.7182 | 141770638473.3429 | 1903292662.9463 | 2202056063.2134 | 2175694615.7645 | 164938047.5632 | 609165640.476 | 616552862.618 | 800090497.8963 | 294347584.7093 | 598722390.2716 | 25578164.0056 | 116439140.7842 | 22956013.4471 | 24361052.466 | 925018564.5726 | 26264120.8543 | 1116658478.4037 | 6033797495.1634 | 571037542.3988 | 167630779.9905 | 1.7116e+12 | 2401447.0569 | 953022.7482 | 1619739.1423 |  |  | 1.8765e+12
77 | 1138842555.1389 | 1032698142.2186 | 215310940.4411 | 174634502.4226 | 1060535677.0802 | 20580217.5933 | 195326427.3847 | 283293365.8812 | 500092470.6278 | 141954773956.5173 | 2049990275.6568 | 1896795547.9407 | 1866939984.1277 | 187300605.8951 | 594066325.949 | 703962480.0684 | 863925700.1443 | 358055605.9313 | 598951950.2322 | 23509698.1478 | 110882674.5173 | 23838347.0659 | 26062767.5731 | 866267526.4327 | 27863738.6226 | 988707015.4807 | 6971801177.5582 | 705880949.4828 | 197126757.8718 | 2.1231e+12 | 2710508.9517 | 940722.4741 | 1554977.4451 |  |  | 2.2887e+12
78 | 1193672295.9066 | 1227951481.636 | 223318221.0434 | 173847116.053 | 1015372323.9497 | 23594720.8636 | 199228655.554 | 320059738.1599 | 471196387.3198 | 147492675329.1589 | 1827418993.6263 | 2020530773.9014 | 1966473195.6954 | 182491307.2264 | 574668991.121 | 714605643.7033 | 802743244.0321 | 334757587.8927 | 560683061.1626 | 25003904.7169 | 117371191.7114 | 22876216.0818 | 22184621.3085 | 764110218.9129 | 29315540.8124 | 1143741983.6777 | 5527762663.5168 | 708639926.0405 | 170232676.9325 | 2.0831e+12 | 2399066.1894 | 939711.2592 | 1723892.6489 |  |  | 2.253e+12
79 | 1106705628.8631 | 1138963844.6826 | 209464277.2377 | 154373722.3846 | 1043360305.9912 | 22232857.689 | 221538958.4433 | 306635368.6516 | 481051772.4209 | 121323459131.994 | 2098683025.7917 | 1856692951.0979 | 2079369062.1799 | 202202943.8456 | 580478760.0218 | 679321311.0685 | 719236481.3601 | 335663680.5615 | 592205018.2995 | 24637795.8009 | 105370372.2854 | 18022165.2658 | 24088433.7114 | 807962739.2004 | 26548240.8506 | 950363024.1985 | 6892140770.1162 | 633015928.7042 | 194818274.8977 | 1.3096e+12 | 2487051.7166 | 978273.5988 | 1684694.0467 |  |  | 1.4545e+12
80 | 1066874342.5868 | 1199834686.4641 | 203630592.1731 | 166170542.0758 | 1083223543.7696 | 22987045.6421 | 213690298.8823 | 327990662.3145 | 469452710.8178 | 128082022019.0197 | 2009549398.2097 | 1783443048.7581 | 2208221262.2307 | 195605019.4748 | 490983196.2751 | 704090294.9224 | 868896397.6422 | 326660220.8159 | 605198155.8146 | 21768483.1048 | 111796360.5481 | 22555956.5739 | 24729858.5189 | 801833130.8165 | 29090843.6576 | 997793446.2046 | 5054333090.8791 | 602231028.299 | 190788855.3397 | 1.4791e+12 | 2423135.9477 | 905824.4631 | 1674013.0799 |  |  | 1.629e+12
81 | 1188634469.5661 | 1085446406.5021 | 222723385.3964 | 150562768.1101 | 977143546.8219 | 23147982.8409 | 203177527.0474 | 286862746.6238 | 492343623.4849 | 124622320697.5077 | 1952004180.6528 | 1853978106.5549 | 2168751037.6179 | 178688347.3276 | 575850481.0366 | 707684942.3508 | 799488236.2898 | 346607420.5602 | 578517130.4853 | 24083100.6233 | 110703253.8727 | 23957775.6715 | 22279606.2633 | 787725239.0924 | 28820650.048 | 1208413374.7196 | 6293919903.3535 | 662786438.0618 | 191602450.3425 | 1.7219e+12 | 2495036.8759 | 916360.9067 | 1608638.2843 |  |  | 1.8697e+12
82 | 1153675290.7104 | 1179937105.1315 | 218861276.6443 | 173187794.8372 | 1041675378.4046 | 23320486.4357 | 210746501.7405 | 280772199.5182 | 465913242.1982 | 160717482928.1562 | 1815353478.0088 | 1634381736.6195 | 2196374209.7027 | 199892061.1223 | 555956751.0888 | 530899463.9234 | 869459538.4882 | 317968012.0418 | 568019379.3054 | 27823022.3421 | 132485244.1357 | 24352042.9762 | 21623445.949 | 830492352.7372 | 29381263.8394 | 1118163502.4906 | 6440012405.7359 | 638593669.0602 | 189556644.9497 | 1.9417e+12 | 2682995.6485 | 929583.4606 | 1511109.2876 |  |  | 2.1253e+12
83 | 1167784703.7745 | 1209874524.3852 | 223198848.7225 | 156924754.1115 | 972150709.868 | 26088055.7282 | 174700384.4522 | 292378061.2119 | 411853387.908 | 151030872361.6617 | 1901439427.1275 | 1732783029.7899 | 2174558669.7482 | 195596956.3583 | 661139498.0198 | 690588932.9643 | 741737456.3077 | 310638795.1718 | 598857448.1425 | 25534856.1321 | 103487859.6442 | 21762862.7658 | 23790173.3169 | 897554219.4922 | 28082602.9395 | 1146440383.9554 | 5939395804.2387 | 700805223.4103 | 170879531.4174 | 1.9395e+12 | 2534127.9279 | 986087.6651 | 1513647.2647 |  |  | 2.1133e+12
84 | 1195924174.51 | 1133571771.6499 | 185366728.5158 | 174805186.2768 | 1022374169.9895 | 22604145.4779 | 218677894.4983 | 319648544.1362 | 444796739.3576 | 140102756553.4578 | 2022599388.217 | 1916360815.6444 | 2180453664.6971 | 195037111.682 | 625171535.7803 | 691717943.4454 | 789179479.3316 | 306138375.7898 | 541740753.022 | 25879266.3736 | 131985436.0178 | 24180115.4881 | 20863841.0502 | 909522558.1397 | 28915659.8179 | 1183864870.0731 | 5252659342.1889 | 636314545.242 | 177175467.1082 | 2.1934e+12 | 2248685.7416 | 968705.6538 | 1562072.743 |  |  | 2.3559e+12
85 | 1241526972.6098 | 1093278567.7256 | 218310446.5621 | 168961435.0889 | 1081747867.238 | 19855357.8599 | 209590024.9776 | 325525523.023 | 494188592.2332 | 151862622954.8305 | 1992486588.6875 | 1973338780.6255 | 2149324632.6314 | 202327197.2363 | 474648174.0249 | 675704178.3307 | 741983389.3427 | 297513691.9737 | 538148443.4316 | 27084011.999 | 111943002.2677 | 23617070.5864 | 25279700.8101 | 733506362.9073 | 22982471.7949 | 912295952.1695 | 6593121397.406 | 608739778.0329 | 191166451.8939 | 2.4513e+12 | 2231430.9647 | 927092.0704 | 1511470.492 |  |  | 2.6263e+12
86 | 1258153760.5611 | 1196485155.5709 | 221505378.5 | 158895747.3254 | 1036534910.3466 | 22732612.9044 | 192042357.0216 | 326307371.0218 | 410638503.5456 | 148454983220.2176 | 2034827202.9485 | 1873583926.6065 | 1953253283.3391 | 171219515.7796 | 597225069.0201 | 596692391.7561 | 689877741.9474 | 328476752.2237 | 575198154.294 | 26443149.9425 | 122190582.0099 | 19118127.9323 | 24303113.2134 | 895054693.4395 | 24530491.1318 | 1106858711.5433 | 6389389528.3444 | 676914637.2397 | 194552582.7499 | 2.5126e+12 | 2572886.3963 | 1005767.7762 | 1506966.3065 |  |  | 2.6842e+12
87 | 1168315702.4483 | 1111101293.7106 | 218047611.5107 | 150303564.646 | 1040498468.5138 | 20915989.818 | 211667073.0123 | 329438625.4368 | 492636927.3695 | 118432652012.8164 | 1793847809.6293 | 2083829906.1645 | 1746254202.9359 | 177163865.0418 | 559299868.9559 | 670346925.5351 | 791243374.7595 | 281189001.832 | 610321843.5438 | 21812950.2627 | 128623832.1561 | 20726830.3588 | 24937700.108 | 883701855.1066 | 29572436.7652 | 1212035731.046 | 5894789618.6519 | 644088861.1819 | 196809821.4679 | 1.8e+12 | 2282848.4293 | 936617.2501 | 1600467.4289 |  |  | 1.941e+12
88 | 1080010773.1129 | 1028137479.6238 | 197474114.4695 | 167683058.4982 | 1076981771.062 | 22576390.1664 | 196928395.5392 | 318531873.919 | 419888548.8986 | 121451319286.3277 | 1956299210.2829 | 1944413085.4219 | 2201432847.8879 | 180726455.8073 | 623777555.1665 | 687050160.4375 | 882373717.4179 | 359643859.6027 | 565287024.0774 | 25484228.4675 | 135569247.0381 | 23929536.5212 | 25442531.4067 | 873963765.7268 | 25000929.7923 | 983205156.896 | 6661408294.4744 | 705163887.2946 | 185062541.7542 | 2.0996e+12 | 2388580.2638 | 974704.4868 | 1749406.6325 |  |  | 2.2446e+12
89 | 1150216384.8321 | 1164312984.8144 | 209126627.3154 | 169611239.4839 | 1064400060.4307 | 25332794.1624 | 192949773.0046 | 306107205.0947 | 423616735.9874 | 141612031114.6017 | 1720648522.4332 | 1759996887.6352 | 1547464610.4066 | 171475304.4604 | 597580978.073 | 677353882.5995 | 627414592.3239 | 336535381.4103 | 534703334.0605 | 27812657.3884 | 113199113.2222 | 24107826.3464 | 23015974.5687 | 920659358.6449 | 29662066.6759 | 1123342760.9356 | 6066454460.4722 | 684175742.9011 | 200682103.7094 | 1.72e+12 | 2613034.3417 | 931161.893 | 1556681.1613 |  |  | 1.8835e+12
90 | 1101602917.5157 | 1229019864.0078 | 195415405.4037 | 175944299.5992 | 1004784461.3326 | 21051522.524 | 206872935.0998 | 321624244.589 | 481601981.5018 | 123619284032.0736 | 2070142843.9209 | 1440673360.1278 | 1606770310.7442 | 200680734.8842 | 493605889.0432 | 705934909.5561 | 884958621.937 | 353365562.8259 | 612516074.3394 | 21721407.0527 | 104478634.6061 | 19174433.0314 | 23265409.0471 | 792766010.4469 | 27832411.8883 | 947154305.6272 | 6252505704.8012 | 546216132.4493 | 194801571.0519 | 2.3484e+12 | 2608598.7385 | 1020264.0086 | 1827737.9132 |  |  | 2.4941e+12
91 | 1228550626.1964 | 1228061225.2064 | 213242707.1089 | 166542434.9737 | 1069012310.8067 | 27054623.8486 | 220605530.8523 | 317620003.1114 | 481809158.7295 | 134840724884.9659 | 1976044989.5072 | 2038496293.6862 | 2027854956.2191 | 196161036.7436 | 530508384.0167 | 613055760.7112 | 883801255.7118 | 311740108.3558 | 592796151.2416 | 24610843.7512 | 122688873.3977 | 24094924.4133 | 21753373.4537 | 808969273.2781 | 28179279.367 | 1142717324.1693 | 6287093943.458 | 599751395.3579 | 176782534.7709 | 1.8719e+12 | 2552795.9582 | 929065.0494 | 1517965.9731 |  |  | 2.0301e+12
92 | 1216781936.9662 | 1170559694.9979 | 215289293.5364 | 140215207.7794 | 1052206160.9071 | 24628055.2941 | 196737907.4444 | 323115592.0075 | 490648788.3221 | 153072851151.2362 | 2030386234.6656 | 1782570663.339 | 2208645321.5787 | 202482259.5964 | 612057641.1135 | 698871586.4707 | 776867404.7185 | 242821056.8388 | 547230305.3819 | 26279775.5428 | 105094517.7299 | 22926560.1299 | 23163049.9254 | 804505561.3181 | 31207222.2444 | 1054180603.4321 | 6169433757.6129 | 656844286.295 | 192183080.9934 | 1.7743e+12 | 2409644.6256 | 934582.1601 | 1674869.2602 |  |  | 1.9504e+12
93 | 1075672920.603 | 1158126318.7897 | 214254096.7728 | 147145341.6456 | 1077382583.1768 | 23167692.865 | 214101215.61 | 306875560.2812 | 484750278.4323 | 152963981571.3856 | 2062918985.272 | 1931722579.1207 | 2041082110.2594 | 172207194.8822 | 607279181.3951 | 715535966.5956 | 729726841.2801 | 296318269.6027 | 561528689.5849 | 23668969.6213 | 101289596.8107 | 23308976.1909 | 20191067.1452 | 911637244.7521 | 27329094.4509 | 1051380733.6034 | 5783353065.5314 | 623310714.8284 | 162826600.9614 | 2.2825e+12 | 2553520.4068 | 968229.0301 | 1782916.3632 |  |  | 2.458e+12
94 | 1143404558.7415 | 1184019952.5966 | 199715175.5155 | 151629753.4465 | 1038162403.122 | 22438080.8153 | 219545332.6267 | 288738306.2378 | 461461826.7118 | 152535657251.721 | 1956439122.3916 | 2149537998.424 | 1953512617.9089 | 165985230.5978 | 620653002.6743 | 668918247.206 | 723702243.6486 | 316287965.2938 | 596829089.9087 | 28423093.5928 | 111173176.8744 | 22874664.1031 | 25113109.0063 | 927106137.8943 | 25950825.0018 | 1175017841.8643 | 5140805041.8342 | 681911055.6591 | 200724386.983 | 1.3565e+12 | 2476416.2743 | 958104.9411 | 1642294.5229 |  |  | 1.5312e+12
95 | 1161637631.275 | 1223746472.9876 | 224312175.0456 | 172907263.1667 | 971279732.2051 | 20360100.2001 | 210929760.0923 | 331261833.5194 | 493242579.0992 | 157706899155.9771 | 2012988195.1516 | 1945895269.3116 | 2207494179.7651 | 192557468.4378 | 537223976.0864 | 634478171.7366 | 799006042.8091 | 303500290.9614 | 586177417.7453 | 23290416.6534 | 90441359.2674 | 21611476.4173 | 22058670.3537 | 745976704.9281 | 25999817.624 | 1076712843.2731 | 6763061057.6272 | 671088164.7936 | 196244293.5915 | 1.6777e+12 | 2567991.1772 | 941127.5814 | 1712009.9527 |  |  | 1.8591e+12
96 | 1239988581.9267 | 1089502331.0882 | 199006898.4292 | 166646573.8937 | 1010686706.5826 | 27882965.514 | 227413151.7176 | 274714691.4707 | 462647417.7958 | 135199152774.2979 | 2013871534.5875 | 2068851304.8246 | 2165840116.6733 | 153835607.6025 | 577698914.3709 | 564382568.337 | 894233737.5488 | 346580300.2681 | 541905021.3227 | 23740952.8384 | 104383106.3916 | 20553351.4421 | 23733237.6427 | 889726436.6333 | 20239859.5227 | 996452295.5514 | 5673556837.0338 | 667042486.9013 | 186174847.5278 | 2.6715e+12 | 2664776.3639 | 954402.4261 | 1719238.4829 |  |  | 2.8293e+12
97 | 1018842212.8184 | 965720262.6507 | 213946729.7364 | 170751872.4268 | 999013059.1518 | 22704249.2582 | 176907767.3224 | 312279867.3733 | 485475786.8086 | 144006118257.1467 | 1963179444.0028 | 1960606649.0056 | 1696199066.2464 | 168416193.2156 | 584965643.9671 | 588780014.0796 | 674339061.7543 | 337699699.8346 | 604063880.357 | 23108543.5031 | 118716892.9716 | 23469816.5431 | 24408482.99 | 681929333.109 | 27073385.6315 | 1123968141.6185 | 6930043153.4268 | 574839688.9379 | 194946776.9503 | 2.5052e+12 | 2548713.2798 | 976164.7276 | 1650510.0631 |  |  | 2.6718e+12
98 | 1232009607.2116 | 1149213216.5506 | 213839416.7505 | 163588153.6719 | 1004205429.8723 | 23382158.7298 | 208074805.6526 | 319177766.3523 | 375635010.9451 | 135794022890.7791 | 2051940906.7582 | 1799022124.4777 | 2146002238.0583 | 175934786.5297 | 558506504.4247 | 715028087.6029 | 765724254.3298 | 269875731.0777 | 560617811.8221 | 20908353.827 | 114261267.9669 | 22964275.9548 | 21446416.8549 | 804216658.2521 | 27978328.2471 | 1178132390.1137 | 6683773012.2015 | 686615713.0188 | 163226721.9173 | 1.8966e+12 | 2442767.4942 | 971459.8739 | 1600184.1249 |  |  | 2.0558e+12
99 | 1184274582.2222 | 1106304835.7678 | 206133058.0135 | 169608947.2157 | 1067658830.8123 | 19391101.8999 | 218285523.7077 | 327784768.8544 | 436885747.0466 | 160062100746.1265 | 1658034619.1049 | 2108157648.2717 | 2100867881.7989 | 181984321.1096 | 613849001.5791 | 587144911.1825 | 857021486.5938 | 272281263.7719 | 591084784.9019 | 23045280.1194 | 107462604.4205 | 23878901.0072 | 24209268.072 | 916388091.9553 | 26810238.7956 | 863791071.5216 | 6749226108.911 | 670127653.1918 | 188997328.8237 | 2.7109e+12 | 2460992.9758 | 917690.8614 | 1583237.9652 |  |  | 2.8943e+12
100 | 1184630673.4001 | 1192415136.8238 | 208112241.856 | 178405409.4399 | 978384197.0898 | 25574861.8747 | 218362446.183 | 303846880.9375 | 468795811.7876 | 138190049593.7217 | 1717177006.4534 | 1844866402.7876 | 2149685164.2558 | 179193275.8174 | 608773537.6623 | 596696149.2671 | 700919421.8417 | 348423674.2108 | 597920474.4492 | 27663844.8016 | 129462914.6874 | 21068259.8433 | 23164152.5299 | 795495869.8752 | 21976532.9536 | 944775218.631 | 6616801752.7091 | 593967177.8619 | 192444852.7205 | 2.4643e+12 | 2507657.0507 | 898123.4222 | 1551515.3449 |  |  | 2.6254e+12
101 | 1170776922.6901 | 1160125054.8437 | 207080293.5179 | 162443035.8283 | 896880246.5877 | 23930021.6844 | 205169528.9137 | 308149911.2957 | 496029283.9491 | 146268202879.1639 | 1875229321.0525 | 1976348581.4156 | 1945827466.0381 | 196649973.6031 | 590010044.9599 | 571590336.9299 | 909275329.9004 | 327058896.1406 | 593433351.498 | 22764126.6021 | 115884504.2372 | 24668502.4154 | 24373567.596 | 884623355.9441 | 27342414.3821 | 1062646415.5572 | 5769357837.2681 | 686903311.0353 | 194943801.4146 | 1.9107e+12 | 2440791.151 | 924077.9921 | 1634041.2336 |  |  | 2.0794e+12
102 | 1242250220.5243 | 1220872295.7645 | 171855706.0382 | 164911163.4992 | 1032539040.4343 | 23708480.7779 | 224434888.7719 | 317109903.0789 | 456964579.9303 | 155137011823.9759 | 1951098077.2506 | 2131522259.419 | 2114623425.4234 | 182125595.6165 | 586609409.8086 | 608598049.8926 | 693869096.1684 | 314059985.2394 | 606243548.0542 | 26380312.9543 | 127241629.8691 | 23323453.353 | 22834584.2126 | 912786317.0196 | 29616704.5415 | 955854199.5129 | 5484487154.446 | 573489771.5342 | 197460624.5375 | 2.1277e+12 | 2525894.0699 | 977027.2481 | 1665196.4321 |  |  | 2.3053e+12
103 | 1130783585.9966 | 1210872813.3835 | 203341350.156 | 178355960.8659 | 1071851443.015 | 22308848.675 | 204943828.6149 | 286076696.0905 | 424539781.0241 | 147547150218.9771 | 1793669700.7638 | 1974551372.8723 | 2034983598.5352 | 181724328.773 | 621619269.0307 | 694024797.0633 | 819057177.5868 | 325680082.9127 | 578600209.2831 | 25755315.0264 | 135307324.6719 | 22499848.8887 | 24857478.4986 | 916814405.9018 | 29263272.6917 | 1130854805.541 | 5320332384.2409 | 661135501.1172 | 175360185.568 | 1.7519e+12 | 2231861.0805 | 959845.6966 | 1720576.8791 |  |  | 1.9217e+12
104 | 1118107547.3399 | 1224697524.4542 | 198220998.8707 | 170098608.6098 | 1070234021.4172 | 21483455.4306 | 196926312.9173 | 326741116.8967 | 468095784.8553 | 151186594848.0735 | 1733373334.898 | 2097606865.0734 | 2091909213.3569 | 183780251.98 | 575822297.081 | 722738481.2828 | 752517681.1337 | 262550277.0828 | 550132968.599 | 27841233.0675 | 123894488.4921 | 21282515.1107 | 25078670.2565 | 787192971.5938 | 21654176.4991 | 1052503058.8596 | 6205597993.6744 | 666017708.11 | 201145293.5379 | 1.8746e+12 | 2510746.6565 | 985050.1335 | 1700693.8752 |  |  | 2.0487e+12
105 | 1078786952.1888 | 1211522252.4938 | 200385078.266 | 173181225.5406 | 972500484.0789 | 27047064.3688 | 216227553.8535 | 258502643.2953 | 422182258.0108 | 149744604906.034 | 1922643383.0616 | 1621554136.4424 | 2158051284.1711 | 201853149.6839 | 612110743.5457 | 586545922.0018 | 812455368.6578 | 300874339.8221 | 574992136.8573 | 26602304.6847 | 124428032.5408 | 23912756.3806 | 22486215.2234 | 685292895.6565 | 25853815.7593 | 972340736.0767 | 6333413386.9696 | 696614936.9668 | 179904659.5799 | 2.2038e+12 | 2744227.8623 | 979356.7121 | 1670161.3837 |  |  | 2.376e+12
106 | 1186593453.8086 | 1137754532.1197 | 197253660.175 | 181656097.44 | 1006358004.2612 | 22067821.6352 | 216238525.9514 | 320968004.8814 | 478157854.6218 | 150612542001.2136 | 2028467650.8906 | 1798018459.2326 | 2114156789.19 | 187453947.0224 | 565623726.0756 | 711920272.0973 | 699360328.6246 | 366359820.1261 | 605190068.9784 | 26979632.6606 | 105028055.3602 | 20009209.1751 | 26029150.7734 | 849750586.3464 | 30337927.7737 | 1224287806.0532 | 6528550162.9576 | 656970238.6677 | 192194391.073 | 2.1795e+12 | 2263490.888 | 900366.27 | 1692214.7649 |  |  | 2.3536e+12
107 | 1257284431.1801 | 1183983291.0251 | 201666116.0456 | 158613076.895 | 1021898280.6782 | 23367146.3901 | 214881208.2359 | 311784048.2019 | 447873093.5742 | 149589093516.271 | 1851967930.6249 | 2174271778.8585 | 2203433363.9872 | 187006040.672 | 637321827.5912 | 684088451.609 | 744604009.1368 | 305994940.1666 | 492471716.5745 | 24096901.6308 | 115026195.2739 | 24544165.9579 | 22488236.5641 | 829568467.0363 | 29448665.6493 | 1093385026.043 | 6389413523.0574 | 649103578.742 | 192728735.6481 | 1.8857e+12 | 2427895.7547 | 942047.3711 | 1628974.4681 |  |  | 2.0587e+12
108 | 1113278290.2278 | 1077053763.2459 | 213442996.5111 | 178773178.8705 | 1006661368.6213 | 25717060.1388 | 189496073.5653 | 312003297.8265 | 470597169.3904 | 150966072869.2496 | 1800258842.544 | 1804119614.3448 | 2160811542.3171 | 165234555.7089 | 685331181.1811 | 692672394.1748 | 886058805.952 | 317183312.9517 | 572306626.905 | 22483130.9049 | 127659714.49 | 24380072.6487 | 24714396.7273 | 860250300.7789 | 28318774.7507 | 944787702.9503 | 7398099821.9448 | 656345047.9647 | 171171953.9222 | 1.6958e+12 | 2334749.9337 | 999004.4736 | 1719895.8757 |  |  | 1.8707e+12
109 | 1162346967.3908 | 1153378990.5556 | 220949401.7952 | 178454326.6736 | 994569018.5859 | 25897447.0361 | 218030050.4896 | 331382687.6056 | 474327637.877 | 118625934239.4969 | 1885483255.4622 | 1756194438.2444 | 2202050188.5318 | 195603401.1161 | 612864664.8142 | 490692788.3657 | 807333994.5383 | 270261693.9943 | 606257078.4933 | 24264232.8044 | 101044428.4108 | 21142856.7554 | 24540897.4534 | 918677005.0972 | 24911847.1034 | 1219660321.3541 | 6572957070.1204 | 640205766.7261 | 193381355.9021 | 1.9989e+12 | 2380267.6082 | 997201.6545 | 1682217.2829 |  |  | 2.1409e+12
110 | 1192257165.9931 | 1190342578.3329 | 213369229.7705 | 176081783.0951 | 1008287248.0389 | 23897398.0247 | 215311980.3728 | 292906190.4002 | 417038899.3593 | 140964739797.2524 | 1812441978.8385 | 1772154451.0135 | 1499923797.4333 | 180697465.0652 | 651537421.745 | 654801894.6169 | 837893202.6282 | 305214320.1019 | 599298479.2547 | 23460496.2414 | 99501744.0824 | 20943683.8447 | 24118412.8996 | 799561945.1066 | 22069329.6232 | 1138155135.5328 | 6447329097.7187 | 670047307.4989 | 190669960.4113 | 1.7202e+12 | 2753711.0727 | 992989.2157 | 1633046.2855 |  |  | 1.8836e+12
111 | 1129812229.1137 | 1129767867.7191 | 211956151.837 | 142193804.9422 | 950023875.5646 | 24886935.3715 | 218099759.6063 | 316288062.3949 | 496471712.6962 | 128443207776.0172 | 1974542395.9207 | 2064960735.6761 | 1999342584.5069 | 175825234.4958 | 560878303.3138 | 712772412.8463 | 736803740.2517 | 340048184.3546 | 492444159.2841 | 18111637.4845 | 135459723.8229 | 24734265.9419 | 25969087.3885 | 928896932.785 | 28126566.0902 | 1173545437.4718 | 6015643677.4066 | 710123949.8826 | 198786785.3844 | 2.4714e+12 | 2776624.0913 | 964146.9524 | 1732939.9342 |  |  | 2.6228e+12
112 | 1227416091.7374 | 1219500054.5516 | 216856557.5698 | 153563392.6653 | 979545943.7367 | 24353474.2682 | 203483189.4171 | 324939761.322 | 457759936.7167 | 141735933554.6478 | 1936970093.4873 | 2058130636.6893 | 2204096984.0422 | 202383945.6845 | 594560703.9497 | 575663936.7651 | 668820773.1951 | 294945302.1968 | 603083687.6898 | 25718414.2991 | 107906732.5099 | 24257784.6402 | 26072228.8656 | 819805864.9796 | 29186161.452 | 969735990.539 | 5867018812.513 | 547656469.0648 | 192121482.6042 | 1.9157e+12 | 2219702.4392 | 988860.3709 | 1688645.0017 |  |  | 2.08e+12
113 | 1107974518.0502 | 1093666396.4721 | 219988961.0009 | 172062458.7002 | 1080949093.7965 | 22503720.2113 | 226193641.4938 | 305687505.8638 | 466528419.8435 | 128231592837.4009 | 1577816015.1209 | 1715294011.3891 | 2056107060.8119 | 189990467.3224 | 589001199.4116 | 569402839.7678 | 740969901.106 | 295476091.0294 | 540502151.6148 | 25215284.0906 | 102488042.6137 | 23991455.8927 | 22549346.7816 | 728773034.4861 | 25649867.2268 | 1096370153.2371 | 6922209565.6677 | 607834871.9516 | 192968820.3758 | 2.0649e+12 | 2356674.4407 | 985003.2875 | 1601252.755 |  |  | 2.2159e+12
114 | 1114229056.3955 | 1228093174.8421 | 194041316.2432 | 163798535.7644 | 1078370241.4257 | 20098971.2914 | 209431553.3392 | 321037601.3472 | 490910249.2463 | 157287107446.8918 | 1735264651.5868 | 1888906313.215 | 1979911768.435 | 154790150.4306 | 635951593.421 | 721039128.5135 | 755898028.7942 | 325297475.068 | 545673951.7981 | 24824565.3558 | 127243207.9256 | 20399615.7756 | 24382938.9274 | 897728657.7713 | 23672179.7409 | 1175545741.5851 | 5833347289.1269 | 686130893.907 | 199980119.1682 | 1.5853e+12 | 2260257.4536 | 896565.7907 | 1490800.3123 |  |  | 1.7652e+12
115 | 1175086522.1923 | 1132471732.6876 | 212201020.1984 | 179491806.7734 | 1064822933.2958 | 25471196.1129 | 215435875.4736 | 309372305.9738 | 481318912.3932 | 142412656142.5239 | 1949575463.8533 | 1809550387.3983 | 1910460696.717 | 201996825.0874 | 442672953.0065 | 699592804.0556 | 847867031.4266 | 334404147.4476 | 612154482.8263 | 24808882.651 | 104151151.5397 | 23368394.3199 | 25803020.1335 | 826301146.607 | 23747090.3587 | 886933665.6446 | 5296350102.3844 | 604870632.8348 | 194486265.9708 | 1.9003e+12 | 2433777.5875 | 887092.8401 | 1824327.8099 |  |  | 2.0644e+12
116 | 1231835109.0105 | 1181410379.0182 | 211745110.7312 | 175762096.3975 | 920146023.0655 | 23287705.9191 | 217197141.9126 | 329227712.672 | 457100692.7448 | 135207990601.1114 | 1963610780.3293 | 1901934431.8929 | 2087971665.9136 | 179062405.7131 | 655473499.3502 | 705262950.0042 | 799933040.6602 | 338214504.343 | 553093939.9797 | 21308268.5982 | 119754426.1984 | 21637846.2071 | 21846812.1757 | 851019939.0405 | 24129514.1185 | 958050426.5261 | 5895587999.1443 | 686441332.4224 | 188510731.6598 | 2.008e+12 | 2501842.5035 | 973282.1298 | 1687454.6811 |  |  | 2.166e+12
117 | 1182983124.0161 | 1135488212.1772 | 193613866.4117 | 166162506.4611 | 1030915508.597 | 22536408.5316 | 209507500.7027 | 328705953.0203 | 465894410.6932 | 148045934967.9812 | 1934542292.5049 | 2068597809.6082 | 2004091453.1958 | 194829895.8746 | 453378301.655 | 703813129.3718 | 873601634.4098 | 256324159.5717 | 578471869.7662 | 25856193.1156 | 120881782.272 | 23451505.7347 | 24628566.321 | 922375288.7723 | 28115252.3093 | 1219999699.161 | 6061576454.4017 | 710267209.0274 | 192411077.7446 | 1.7237e+12 | 2253494.012 | 926450.9139 | 1515112.6992 |  |  | 1.8949e+12
118 | 1197768189.9763 | 1125368524.5197 | 203391090.0219 | 173071586.3462 | 930410047.5919 | 22298533.543 | 195327298.9183 | 308508026.5784 | 472956696.5947 | 136776772261.1028 | 1645985983.0807 | 1472584644.9393 | 2076019678.1549 | 182323371.1375 | 596999134.4645 | 645743380.1106 | 858913350.3655 | 349038930.2631 | 583623432.6056 | 19909267.91 | 121415886.3801 | 21997445.8208 | 25963731.4516 | 911854241.651 | 21468458.1174 | 1097962926.432 | 6795875573.2953 | 591370798.7443 | 194134433.1434 | 2.6402e+12 | 2569255.7771 | 882939.3758 | 1708385.4778 |  |  | 2.7998e+12
119 | 1239048655.9969 | 1220207592.1401 | 201599262.6771 | 169478933.8752 | 1026812901.2655 | 23026586.1854 | 204367265.2692 | 302002011.4783 | 450591238.0272 | 139922120443.3851 | 1624097142.1415 | 1605289251.8013 | 2189016502.4847 | 194084443.6907 | 606736950.8906 | 647232934.3838 | 781329442.9883 | 339736791.9245 | 607054263.3692 | 27961809.5784 | 124585648.6703 | 21012714.0786 | 22827604.3267 | 775688987.2402 | 24968797.8539 | 1060477535.3141 | 5662979440.5397 | 617279223.2438 | 196782189.9771 | 2.3723e+12 | 2392091.4449 | 952825.4678 | 1558637.5806 |  |  | 2.5341e+12
120 | 1166572232.1095 | 1072705513.6301 | 222426525.4029 | 176506119.3064 | 1086433443.2339 | 22315163.451 | 200689477.8916 | 306008325.1848 | 476486546.2902 | 126967704261.6469 | 2009219580.2287 | 1964347608.0621 | 1666073429.7127 | 200798809.959 | 606500067.049 | 716519752.7225 | 841291688.106 | 325215145.8689 | 527033854.9196 | 22232693.5014 | 120880039.2244 | 22919851.2205 | 24768996.3753 | 864233656.9327 | 20953930.8329 | 1201368135.1594 | 6476331411.3148 | 656709687.0939 | 193803847.9441 | 1.4455e+12 | 2558053.7744 | 915295.1783 | 1553751.711 |  |  | 1.5956e+12
121 | 1164986266.618 | 1203917544.7926 | 222751000.4337 | 170444711.4282 | 1052487207.7235 | 21149033.8132 | 206883001.5989 | 291035436.8928 | 436395302.0259 | 146355800458.0437 | 2090834028.1319 | 2036020593.0331 | 1826805818.1067 | 197223731.3435 | 662153869.0742 | 719625329.814 | 873323623.283 | 323674396.3113 | 585869480.6557 | 22845867.4672 | 111573666.8709 | 19037086.8647 | 24563038.7618 | 884906988.8512 | 28293548.7336 | 1227656168.8549 | 6257948034.556 | 709964728.3395 | 185919316.8188 | 1.915e+12 | 2440457.7935 | 988229.9021 | 1685167.7423 |  |  | 2.0849e+12
122 | 1253829074.2237 | 1138739763.6547 | 174923894.9296 | 164825859.9425 | 1044502594.3067 | 27343152.6588 | 203641381.8199 | 301186358.2623 | 438290901.122 | 145624683274.0174 | 2074613212.1697 | 1961551555.4258 | 2176115907.9885 | 188888785.162 | 571014653.4314 | 675556443.8637 | 854566943.2184 | 255885105.0419 | 539249593.5205 | 23434692.124 | 121164453.2003 | 21333144.076 | 26083347.5664 | 816535235.3534 | 26722494.7135 | 970769217.3861 | 4812585745.4476 | 695096225.6613 | 162746632.2806 | 2.5752e+12 | 2307889.9157 | 950070.6309 | 1737870.2927 |  |  | 2.7426e+12
123 | 1049126185.9077 | 1166430509.4435 | 220638834.1094 | 162260978.9966 | 1033649326.5218 | 24550592.6462 | 208104686.06 | 290921440.5546 | 498232294.9832 | 120516525030.1425 | 1957170247.5987 | 1556808064.1271 | 2070396007.0445 | 182511703.7908 | 409895894.9581 | 618052643.1024 | 786374114.3648 | 292957760.9702 | 557847306.534 | 26404477.1523 | 121888980.5249 | 22466665.06 | 24997285.8894 | 719569536.4723 | 28344442.0572 | 986294539.5168 | 6958545337.5901 | 629885187.8544 | 201025190.115 | 2.2226e+12 | 2394178.167 | 923866.0466 | 1677678.2826 |  |  | 2.3659e+12
124 | 1090796536.2165 | 1088650105.2513 | 203940921.545 | 173149504.1294 | 1002194480.2505 | 24449270.711 | 220852653.1202 | 278962854.5698 | 460641324.4612 | 150774671974.8774 | 1769297242.5285 | 1707505049.1169 | 2082214852.6348 | 202284358.4663 | 641291462.4614 | 718826082.2849 | 730451005.2277 | 353599599.9631 | 564415776.4428 | 19825992.2769 | 106069589.2598 | 24666641.7792 | 22509754.9211 | 934650366.5166 | 24793863.6005 | 1092488147.3279 | 6283770765.6813 | 589905042.242 | 195066204.152 | 1.7509e+12 | 2413544.3695 | 1021667.1356 | 1793470.7166 |  |  | 1.9243e+12
125 | 1194567880.8948 | 1167308376.5673 | 185430897.0108 | 179585057.0996 | 1021828372.1015 | 20953111.0241 | 214672758.3955 | 316571673.4837 | 472575239.2374 | 115885542972.6455 | 1867830502.2428 | 2116820002.7508 | 2174260045.1092 | 176650609.3353 | 561706806.7354 | 655429494.564 | 914244666.1439 | 340902086.1545 | 605579381.792 | 23688857.222 | 112514835.7144 | 18283863.9677 | 23678607.1661 | 791514612.7934 | 29991815.9444 | 1058079220.6837 | 6753298649.157 | 686781492.4305 | 196634361.9917 | 1.7407e+12 | 2663383.8836 | 902777.3542 | 1585199.6857 |  |  | 1.8804e+12
126 | 1200265263.2128 | 1214817893.1866 | 221640747.2577 | 171049574.8825 | 1068627679.3403 | 23332799.1695 | 193213970.2245 | 295706412.2927 | 500175357.8503 | 127331550091.5775 | 1597564969.8152 | 1933585655.4999 | 2134302772.0676 | 166098045.8469 | 476293156.459 | 625805079.0735 | 872245868.7203 | 316030299.4999 | 573261049.2534 | 24206703.1551 | 113934256.293 | 17455660.1572 | 25891292.6459 | 910436449.3107 | 28843975.944 | 1223270218.4302 | 5916847336.2955 | 623855786.4655 | 187203862.2938 | 1.997e+12 | 2577355.5508 | 929914.419 | 1826471.1057 |  |  | 2.147e+12
127 | 1112615592.117 | 1021616843.3013 | 200017055.4072 | 179121981.4601 | 990425803.0289 | 25628746.1305 | 202382864.2118 | 308556001.9267 | 467627291.1674 | 134248673847.8584 | 1903086670.2551 | 1686749109.1318 | 2074335511.5516 | 195243011.6512 | 499890624.683 | 585227129.9711 | 929499878.9692 | 337073089.1951 | 576018942.2134 | 25058646.3088 | 134998046.9248 | 24230531.5801 | 23850601.6788 | 936110524.99 | 23043782.2155 | 980172171.8845 | 6529900592.2549 | 668210960.0075 | 199644260.1693 | 2.1919e+12 | 2532473.5199 | 949574.2331 | 1661707.0342 |  |  | 2.349e+12
128 | 1125095967.2553 | 1165414955.2139 | 222286271.8825 | 163711051.474 | 1082464221.8775 | 23368714.9536 | 227020224.8625 | 291375978.1629 | 457644756.1498 | 138744089694.5773 | 1854755421.3899 | 2081439125.0136 | 1879485418.8842 | 189572778.4322 | 569135551.5625 | 704761093.617 | 754695571.6674 | 280700818.3704 | 578780191.7419 | 27298774.5021 | 110602268.5262 | 22571036.3677 | 20827806.3726 | 810740570.9551 | 26907102.9366 | 1052515597.4828 | 6162862305.3691 | 702441715.5977 | 151779449.6673 | 2.0208e+12 | 2560332.8803 | 898038.3894 | 1637473.322 |  |  | 2.1823e+12
129 | 1242108382.2162 | 1184396735.4334 | 196661219.762 | 172841120.0068 | 1063932069.0356 | 20525945.2511 | 220403500.3827 | 323880403.9921 | 480058209.8461 | 130741924680.7535 | 1782658360.4109 | 1934531931.2387 | 1958242972.7078 | 200268059.733 | 587295561.6412 | 645282027.6131 | 895539530.7316 | 308711617.4175 | 603917872.1468 | 22008689.0209 | 98196429.0205 | 18699331.0703 | 25401005.9454 | 786693510.1899 | 27038051.8444 | 1038569369.3238 | 7184128592.3284 | 628156387.4045 | 185139204.0502 | 1.8411e+12 | 2372581.2744 | 954020.9503 | 1642707.5442 |  |  | 1.9957e+12
130 | 1251446033.8704 | 1173695901.4146 | 212035190.6315 | 177119026.1883 | 1079677206.1571 | 23910183.0135 | 214058399.7995 | 323089444.1454 | 478913196.839 | 143171675482.5258 | 1960317646.0161 | 1743815519.1488 | 2117660663.3834 | 165388402.7535 | 527256300.3769 | 684876616.6189 | 867433211.2583 | 340891686.2571 | 569783296.651 | 23543992.9504 | 120760918.5174 | 23531902.5021 | 25958943.2549 | 796558412.3213 | 26615572.9204 | 1039127044.0181 | 4882311655.9358 | 584087222.8007 | 192193527.664 | 1.7472e+12 | 2373466.3155 | 973588.125 | 1540210.733 |  |  | 1.912e+12
131 | 1210632359.8405 | 1180088553.3815 | 200437087.37 | 177483014.5449 | 971290139.7518 | 25899320.3139 | 213607501.5179 | 311628923.9019 | 461809567.3743 | 146394306845.7309 | 1949814197.1506 | 1951859238.3657 | 1854518744.7389 | 170615250.6331 | 652387363.6018 | 700165427.0436 | 771437969.0486 | 345083479.3002 | 572051545.9644 | 26170691.069 | 128734465.5391 | 24466422.654 | 22713654.0051 | 890146722.1911 | 22543191.3586 | 847927030.8022 | 5930340781.6473 | 566983442.6028 | 190172473.4265 | 1.3486e+12 | 2571527.6255 | 933418.2357 | 1595241.5584 |  |  | 1.5173e+12
132 | 1044828068.4193 | 1115861493.6609 | 217137658.8119 | 180260387.0053 | 1069303507.016 | 24906744.9073 | 211831745.6 | 329464317.2557 | 491594080.3623 | 141947040533.8709 | 1819441737.7921 | 1938615643.4575 | 2196337051.5693 | 202937541.1775 | 622712435.2825 | 705161730.9467 | 744979662.249 | 351094675.2705 | 602181459.202 | 24727354.0688 | 119151688.218 | 21130778.5903 | 24654207.6969 | 713422206.438 | 28867498.3906 | 1097790081.9466 | 5600430057.6536 | 671637772.8834 | 176812947.9634 | 2.2268e+12 | 2386847.0077 | 933523.1832 | 1677894.7151 |  |  | 2.3911e+12
133 | 1067813020.5394 | 1201084380.814 | 203055421.637 | 181051210.5732 | 1068216083.6789 | 24428618.2725 | 223154779.898 | 288856841.3459 | 449962212.7865 | 131576804894.7261 | 1797162469.642 | 1674038657.3085 | 1993595254.8294 | 179494712.8534 | 645324165.3164 | 664480259.3593 | 631507144.1781 | 235866203.6184 | 575616071.336 | 20872235.3179 | 116191693.6733 | 21879134.4683 | 24303131.8734 | 814129064.7326 | 30617378.5413 | 1198517264.0763 | 6944317762.3486 | 674558929.2802 | 198105797.8526 | 1.7654e+12 | 2494702.2964 | 891158.6356 | 1560273.1175 |  |  | 1.9201e+12
134 | 1186423347.3257 | 1106692747.2023 | 206374892.5312 | 167819565.8053 | 971709180.6279 | 23039295.1827 | 222477910.1316 | 313734306.7515 | 496874471.1175 | 140923926210.846 | 1846585552.8392 | 2032600033.7832 | 2052467052.5254 | 197182403.0934 | 539892047.2092 | 668651503.3985 | 773012378.8537 | 334821853.3888 | 506929995.1576 | 23482599.813 | 100642681.3649 | 22785260.2675 | 23545970.5286 | 809099362.4847 | 27693827.2824 | 1152866033.075 | 5781576156.5429 | 689216933.4627 | 201519359.6975 | 2.525e+12 | 2651251.7741 | 907074.034 | 1747340.2837 |  |  | 2.6884e+12
135 | 1054789051.4474 | 1045060679.1254 | 211529075.9543 | 175470560.8879 | 1056783557.5064 | 28028371.596 | 181324325.8855 | 315919050.7601 | 490861359.3984 | 121427912143.1236 | 1941323656.9308 | 1834654846.0886 | 1827884651.0823 | 188215261.1932 | 660201807.7658 | 634841639.8662 | 700219722.7608 | 330954073.407 | 578689374.1079 | 20264650.5044 | 122889228.5336 | 20821607.6037 | 25109877.6018 | 895805702.5903 | 26913755.532 | 1171084782.6081 | 6288357263.6488 | 658267909.171 | 191915059.3107 | 1.6565e+12 | 2762516.1121 | 1000395.5277 | 1736692.7536 |  |  | 1.8006e+12
136 | 1213571369.3292 | 1135118520.9608 | 200691073.2309 | 181432677.3107 | 1087342515.3817 | 25498827.5433 | 208016609.4494 | 273333135.1534 | 440061002.4478 | 141154708959.2694 | 2011656650.2095 | 1816538314.8869 | 2211221472.8011 | 202931310.0676 | 453636792.5364 | 667658693.8975 | 877515398.829 | 237499777.0204 | 588453365.6712 | 24977362.3279 | 103885923.5538 | 23157734.3382 | 22616548.8693 | 841138837.2795 | 29664494.6628 | 1158866572.634 | 6710111075.5084 | 616491373.5719 | 200900953.1193 | 2.0065e+12 | 2346129.7177 | 940915.9166 | 1766102.8262 |  |  | 2.1712e+12
137 | 1151784562.8084 | 1139064789.8615 | 211854600.509 | 162542479.2362 | 1079926839.7104 | 24523228.4138 | 166335905.1382 | 322384559.5907 | 433718147.6481 | 132194896498.578 | 2076879693.6151 | 1949467686.6214 | 1685403898.1932 | 191188090.0025 | 590015828.9642 | 720678951.4126 | 663955156.1735 | 302644334.9832 | 558479720.5621 | 27214078.2515 | 124650521.2547 | 23202097.6418 | 24012754.1426 | 725755927.0124 | 31366717.392 | 1140794963.5828 | 6715786925.9151 | 688403677.0231 | 195546433.6523 | 2.3627e+12 | 2577481.3045 | 976675.1763 | 1500104.6966 |  |  | 2.518e+12
138 | 1244501162.8721 | 1194459400.7872 | 202710702.034 | 170396399.8426 | 989271747.6537 | 23940214.0942 | 214283720.537 | 306450550.3807 | 492854774.574 | 150897347038.6472 | 1728582199.143 | 2173421203.4433 | 2198639658.4741 | 200327705.183 | 549029200.7073 | 581867323.3533 | 868206453.4959 | 300934051.7662 | 603701973.3054 | 25307153.6327 | 115948264.8439 | 20897201.2561 | 23245153.2364 | 908495955.6682 | 22625654.0332 | 863168220.6147 | 6556168246.2032 | 591236960.5153 | 201435167.9137 | 2.4148e+12 | 2410292.0405 | 986624.1058 | 1642451.7485 |  |  | 2.5891e+12
139 | 1042287100.9852 | 1112006183.7236 | 198887432.4386 | 169809577.3031 | 1083039874.2107 | 21717396.1211 | 219472499.5407 | 323686613.8053 | 470529168.2371 | 150329105290.459 | 1869976685.1052 | 2119705278.7416 | 2106053355.2666 | 196546142.3593 | 673485599.9813 | 556131759.7827 | 786051263.8058 | 297519799.8349 | 527450914.8195 | 26322690.0745 | 114439016.9175 | 21447437.402 | 19550931.5718 | 889166316.7883 | 29559154.082 | 1058286284.8657 | 6850043618.9199 | 686630991.2356 | 200375392.6365 | 2.3312e+12 | 2319889.7831 | 903110.8595 | 1549954.4619 |  |  | 2.5052e+12
140 | 1097136299.8173 | 1223004044.8999 | 199111042.9859 | 169578905.2634 | 1057487797.322 | 22477424.022 | 206460780.191 | 300579252.269 | 463930129.8472 | 145119589245.94 | 2059698038.6538 | 1993393179.1367 | 1978591329.0557 | 198498346.7033 | 579785123.805 | 668257610.7362 | 840737623.9663 | 303107742.2801 | 567802716.2103 | 24788015.2823 | 108481623.7641 | 24712226.2814 | 21570558.9784 | 921495123.4796 | 28420487.5974 | 1079451462.7842 | 6887531871.8936 | 640830248.4023 | 186094197.9809 | 2.4888e+12 | 2370776.5735 | 935708.9825 | 1626036.358 |  |  | 2.6577e+12
141 | 1083800510.5513 | 1194642129.4503 | 207525034.9859 | 169979678.7385 | 1051764090.4454 | 27423571.9205 | 208115639.8324 | 323008936.7068 | 493468070.3143 | 146764915867.0868 | 1802378466.1725 | 1993681049.901 | 1900436782.7118 | 172955297.8961 | 534786054.1463 | 594287873.7937 | 911780410.7835 | 325286058.9684 | 473844713.6479 | 23429958.1132 | 120483898.8917 | 21678805.0128 | 24530425.6448 | 892221805.5284 | 27709252.2827 | 1205310035.8632 | 6695842900.709 | 689284767.663 | 190450565.6407 | 1.8859e+12 | 2335585.5171 | 926018.8623 | 1655610.4492 |  |  | 2.056e+12
142 | 1209182908.6275 | 1212027656.604 | 204483278.3167 | 172327134.229 | 948588022.4605 | 23908828.8654 | 200734715.7617 | 268126946.5142 | 496244884.8422 | 128963268450.9957 | 1918613004.5412 | 1931483956.8488 | 2195030050.3384 | 191640299.8216 | 623650087.514 | 506471295.3171 | 721174131.7558 | 340627762.1477 | 608243568.7617 | 25088845.4124 | 118861515.718 | 24635981.1143 | 25398622.5694 | 833526621.6563 | 30360189.7016 | 1032930023.9795 | 5445553234.3355 | 703742179.9067 | 189238265.0309 | 2.4639e+12 | 2276489.3754 | 957292.9701 | 1665528.6992 |  |  | 2.6151e+12
143 | 965387793.2171 | 1190317197.5786 | 197226479.3039 | 165218472.1932 | 947536869.4664 | 26927351.917 | 220199194.6573 | 314186791.5164 | 482941296.3141 | 152018471218.1299 | 1881709069.4523 | 1975244294.5117 | 2103475981.3545 | 198988445.3106 | 649790969.0522 | 720869456.4048 | 806462586.0714 | 274929508.0258 | 582439760.0206 | 20458621.337 | 126757520.9322 | 22289841.8333 | 20950978.6602 | 877792466.9905 | 26611683.95 | 1088093004.8003 | 6664685583.5876 | 644299723.7056 | 163772620.1164 | 2.151e+12 | 2602713.5234 | 931566.2443 | 1609714.6158 |  |  | 2.3264e+12
144 | 1179691494.8289 | 1205190285.5506 | 187488262.2397 | 145987019.2055 | 1062028031.3885 | 22670856.1931 | 182407952.1651 | 319356243.0031 | 452693898.9851 | 144521741111.8172 | 1907036681.6799 | 1940942100.9669 | 2187627568.1706 | 192183606.1162 | 468692481.4114 | 570178012.2736 | 885311895.0146 | 256307473.7454 | 559834897.6431 | 24935365.541 | 121160979.9095 | 21857067.1306 | 24429983.5274 | 912882465.9649 | 27157829.1122 | 1173953852.1701 | 6054247762.9686 | 676648197.0407 | 173910301.957 | 2.4648e+12 | 2296540.2806 | 926960.2997 | 1660365.9882 |  |  | 2.6323e+12
145 | 1156779352.2173 | 978052604.9065 | 210777679.7937 | 140438384.601 | 944674439.3665 | 22756987.4191 | 221655800.8745 | 293616365.3347 | 451782758.1289 | 154063397492.2765 | 1839363010.4061 | 2091131447.6145 | 2195885783.8618 | 181473963.9014 | 536481410.8381 | 648855997.8405 | 844758502.9761 | 357452755.5354 | 531073657.0636 | 23682821.5616 | 110318929.4538 | 23113071.8706 | 23323779.617 | 761624519.1259 | 26372951.1902 | 977238512.1992 | 4856075861.2376 | 690633345.2156 | 187615496.1737 | 1.539e+12 | 2719396.6324 | 916900.9741 | 1657852.6364 |  |  | 1.7144e+12
146 | 1185594837.3989 | 1076769663.0146 | 219410556.6842 | 172043062.8242 | 851202735.0124 | 21881804.278 | 214363478.9149 | 328435541.1438 | 494840872.501 | 114306374625.6989 | 1987634013.828 | 1895083170.7066 | 1754293827.5876 | 158161662.7599 | 524856116.2853 | 632038769.4798 | 891160223.0286 | 300417783.6153 | 510070678.8654 | 23998312.4564 | 125319074.562 | 22354945.6506 | 21459633.4388 | 896630853.2242 | 28407222.3149 | 1079703553.4571 | 6365006038.1605 | 668434051.23 | 179073584.9146 | 1.5839e+12 | 2760298.8668 | 937474.6555 | 1566990.3459 |  |  | 1.7208e+12
147 | 1010894488.899 | 1176613467.9984 | 204570431.8165 | 171823231.1313 | 908954983.2861 | 23650184.5021 | 218257850.1411 | 309112075.9006 | 473959055.7669 | 130297443617.0842 | 2088395932.7017 | 1893299087.7918 | 2067032497.4053 | 201208102.3693 | 627131304.3533 | 621122052.9314 | 836503825.984 | 292358567.8452 | 564379576.0784 | 24803171.0881 | 116274081.7304 | 22481197.2249 | 22793113.5735 | 877444852.1186 | 25570279.2847 | 1151219513.0309 | 6908967765.4961 | 682088490.6617 | 197548978.5807 | 1.6176e+12 | 2423038.0323 | 892830.0926 | 1672748.2459 |  |  | 1.7716e+12
148 | 1020474209.0428 | 1160012496.5585 | 211400651.4325 | 158663440.9852 | 1012252087.2359 | 26481526.1439 | 204225771.3719 | 300872554.408 | 449062451.0794 | 120734703213.7484 | 1954171709.2831 | 2122079941.8623 | 1951821752.6901 | 151087607.2727 | 654467465.0267 | 605285778.6152 | 820049021.4258 | 359787951.2862 | 600350324.3351 | 25963630.2886 | 117191950.6026 | 22434714.8207 | 24088146.1676 | 899036236.7778 | 28326284.6426 | 1160229429.6694 | 6931987373.8371 | 685461780.4477 | 184571362.199 | 1.5255e+12 | 2477590.2353 | 944242.1058 | 1607445.3271 |  |  | 1.6701e+12
149 | 1228753683.8923 | 1199643057.3622 | 201568532.6205 | 144598685.0615 | 1001620396.175 | 22550084.4328 | 219892968.4649 | 312245169.452 | 493652407.6278 | 143336943630.9825 | 2058281947.9489 | 1827865533.1067 | 2089958943.1114 | 198272911.4619 | 532665281.1433 | 683850914.7058 | 871467466.5849 | 315336590.2328 | 574395982.2415 | 27654305.2395 | 114307794.2124 | 22327303.3992 | 23310387.3181 | 922639058.8739 | 28544763.3911 | 1171205934.9856 | 6300611881.8749 | 705761008.1132 | 136538569.79 | 2.4209e+12 | 2651144.5743 | 1004367.5248 | 1569399.3438 |  |  | 2.5876e+12
150 | 1246064365.2165 | 1218160472.4945 | 216868939.1824 | 163577573.4946 | 1086637775.8857 | 24812896.7834 | 206983839.4412 | 329882976.7686 | 492565640.6636 | 136233301962.6807 | 2080888356.4833 | 1978479272.0474 | 2084422256.0471 | 197049540.4492 | 619907994.9953 | 660590242.4448 | 781559644.7232 | 318009966.418 | 549681550.9237 | 23703827.7459 | 124308293.6096 | 24378719.1423 | 25576814.7072 | 814994819.1614 | 22611446.4391 | 870277270.0821 | 6552593862.7348 | 608456118.3411 | 168181949.9021 | 1.5593e+12 | 2439058.489 | 1025532.7438 | 1827204.4949 |  |  | 1.7191e+12
151 | 1235100730.699 | 1180485052.6302 | 206116377.394 | 158787997.1868 | 1087354999.5457 | 23649279.7957 | 218196587.447 | 322949008.9322 | 483348125.1298 | 155058444949.332 | 1795768361.2394 | 1575929348.6958 | 2106648246.1926 | 184497093.5363 | 631067338.3219 | 659839309.7868 | 806670228.6261 | 268050588.78 | 553868890.1976 | 27313962.8401 | 135686137.0488 | 20564699.0164 | 19588719.2538 | 796658857.2706 | 28467530.8549 | 888998642.0438 | 6659844121.2837 | 660384371.3354 | 184122878.6637 | 1.8002e+12 | 2596040.7788 | 951320.231 | 1816714.3683 |  |  | 1.9782e+12
152 | 1230493293.2429 | 1133075611.3338 | 175327373.3772 | 178102066.9487 | 1038780088.4264 | 23877936.0348 | 204870179.8191 | 320559092.3669 | 488552449.2856 | 147681973394.4121 | 1944055022.5572 | 1643029239.1987 | 1944208270.0046 | 202764175.7559 | 554618954.2455 | 719836221.9079 | 622828939.7206 | 334474877.9715 | 585052056.3146 | 24558013.4062 | 116516145.3024 | 19786399.7772 | 20861810.9223 | 870314518.5648 | 30609702.8762 | 962490883.4275 | 5946184913.768 | 705290576.7333 | 195729110.8104 | 1.7768e+12 | 2489501.291 | 951990.0779 | 1563270.3465 |  |  | 1.9467e+12
153 | 1211467643.0649 | 1179522128.9372 | 222402408.6343 | 154865476.9406 | 895717013.0524 | 25905946.9117 | 223366288.8341 | 286708106.6553 | 446699592.7721 | 109564026510.6783 | 1685848972.7937 | 1906567265.4643 | 2185917044.2843 | 197219256.3517 | 539070640.1238 | 684483157.4385 | 874527007.5849 | 311949916.8347 | 506270499.7292 | 23753570.8882 | 113988931.5076 | 18544326.3721 | 25194500.7576 | 875780590.7924 | 28719156.1161 | 1065276937.1443 | 5579875922.6108 | 708513874.6708 | 176595394.987 | 1.7293e+12 | 2278673.1095 | 908207.4219 | 1581742.841 |  |  | 1.861e+12
154 | 1162772568.3392 | 1139394187.3186 | 194583767.8404 | 166334582.1087 | 1009912606.1258 | 24975002.8984 | 212194531.3411 | 297967261.6727 | 480940697.9779 | 153492737618.7258 | 1780378416.9403 | 1774310514.7223 | 1671106071.6212 | 169354192.8463 | 537648686.7208 | 711180194.9141 | 805168485.7484 | 339933846.9493 | 505141820.2889 | 19545395.1826 | 119476531.1724 | 18363740.923 | 22671064.9088 | 759900005.4445 | 30494669.9301 | 1052728341.3393 | 6023627550.4414 | 563745590.8477 | 152074107.3422 | 2.0705e+12 | 2797827.6411 | 931064.9368 | 1499924.9541 |  |  | 2.2458e+12
155 | 1104979728.1098 | 1225828776.7568 | 199664552.9589 | 168508516.9562 | 1081410216.0445 | 27087416.1074 | 204652805.9207 | 323467982.7484 | 484808289.248 | 116914638478.8506 | 2019632591.5038 | 2014465612.3491 | 1968942210.6641 | 187982569.9841 | 530691818.1096 | 689389753.4355 | 768027091.7946 | 304529106.4956 | 520717382.8117 | 25423061.7507 | 119568431.9989 | 24465906.2985 | 23775675.5503 | 887560657.4526 | 26726967.199 | 932595944.8882 | 7131345131.3302 | 617955953.0862 | 191070615.058 | 2.4318e+12 | 2491635.0911 | 889831.3629 | 1494760.783 |  |  | 2.5725e+12
156 | 1227477067.7385 | 1228658078.1262 | 219111349.0994 | 165601951.6152 | 1002099258.9462 | 25667662.7172 | 214910101.8943 | 324626380.9073 | 442795257.3413 | 146407448795.5685 | 1905075681.7486 | 1945861785.5798 | 1977179449.1276 | 199526541.2892 | 532751165.9394 | 699065895.3765 | 606505354.1338 | 341985412.0621 | 543254902.1991 | 25076631.5081 | 123919588.7999 | 24331140.3777 | 25396034.892 | 845998747.161 | 24673335.3098 | 1121650662.2992 | 6036139823.1541 | 594909440.5769 | 194038751.3204 | 2.03e+12 | 2427856.1733 | 969684.3456 | 1628579.8456 |  |  | 2.1991e+12
157 | 1023312155.5499 | 1174921076.1354 | 218496569.5864 | 162479589.0752 | 1024690308.1772 | 25327950.2161 | 207433658.2404 | 263555950.1004 | 497355384.8337 | 148484189486.6563 | 1956181940.8942 | 1841043544.7814 | 2102565451.2599 | 166989991.1851 | 430930654.5963 | 707983968.6527 | 730938594.0602 | 328600138.5775 | 507693705.3514 | 23810195.2017 | 103661588.4907 | 20398100.3445 | 23725100.9907 | 836752653.6898 | 29286460.1068 | 1061763564.883 | 6987982155.7138 | 706594061.122 | 188939061.4762 | 2.4678e+12 | 2539544.0684 | 945096.4509 | 1499618.9783 |  |  | 2.6396e+12
158 | 1074053363.1038 | 1218767298.5456 | 209819626.8829 | 173948230.1601 | 1047440016.7693 | 29122508.7976 | 194571742.8311 | 287844475.2259 | 405060581.2344 | 136393776610.5066 | 1888993294.9267 | 2014752301.9317 | 1726931853.0496 | 177307214.3476 | 542105406.7744 | 661253124.8221 | 818166077.557 | 345156401.2415 | 595456516.7142 | 25327508.1109 | 104112104.3396 | 22709794.2329 | 25580735.0371 | 844214050.5583 | 30343661.7792 | 987498604.0648 | 6387712553.2225 | 709784896.8451 | 161010075.8156 | 2.4226e+12 | 2509951.199 | 1017996.1576 | 1832695.9448 |  |  | 2.5817e+12
159 | 1194876831.3074 | 1163518420.6893 | 209790621.9792 | 170992924.6309 | 1075216597.5797 | 25260731.3515 | 200282721.6411 | 301449535.5046 | 477815669.8601 | 142032362604.4078 | 2067276926.7431 | 1961924303.1649 | 1968527942.1768 | 178144855.6398 | 588040252.1957 | 616319593.2164 | 718229245.5187 | 341983759.1471 | 566618889.2283 | 27729533.0927 | 126118715.8954 | 23109938.0862 | 25687639.9809 | 912294382.0984 | 22331037.7646 | 1161875310.8777 | 4370360298.8542 | 677555537.3597 | 187692142.5515 | 2.032e+12 | 2627577.6789 | 979164.2126 | 1591332.2339 |  |  | 2.1954e+12
160 | 1219395873.053 | 1214886952.3514 | 201883210.2718 | 182242825.3663 | 1044591286.4581 | 27102699.6392 | 205017653.6311 | 317348598.5757 | 493572838.363 | 162081724880.6763 | 2037197386.9024 | 1978658989.8725 | 2085838572.3686 | 186075834.0133 | 596656003.7848 | 708463070.0291 | 724094893.46 | 277444826.3628 | 589064575.0658 | 21468580.7537 | 107874498.2144 | 20410735.6708 | 21135743.1509 | 623482580.9634 | 24851583.6966 | 1103837171.5316 | 5341061635.4274 | 677751727.8804 | 160994931.7532 | 2.4028e+12 | 2278251.5031 | 988086.6325 | 1599288.1687 |  |  | 2.5871e+12
161 | 1101106509.5922 | 1157284494.2711 | 202428462.6673 | 168582369.6273 | 980268182.1551 | 23940505.413 | 204795402.3493 | 323417629.5601 | 466061640.5171 | 125353773615.9779 | 1838813875.166 | 2138633255.4953 | 2200140937.0882 | 192651646.6445 | 666160319.1034 | 712159212.0518 | 766937130.1372 | 346345522.855 | 601043788.4133 | 22002934.4425 | 128820616.354 | 24646074.8254 | 24006643.043 | 888374122.614 | 26163855.413 | 1077591210.5215 | 6671984835.5473 | 669170285.6969 | 152543930.1959 | 1.9877e+12 | 2518314.1603 | 937924.4109 | 1643291.114 |  |  | 2.1368e+12
162 | 1163237540.974 | 1043838255.8107 | 216937627.0693 | 170441455.0115 | 1039771116.9263 | 21205181.4276 | 216619045.148 | 314810850.3797 | 493558353.4295 | 144935152887.871 | 1906833667.8529 | 1833229609.1348 | 1987847113.6068 | 195482266.8209 | 682594204.1255 | 708280385.2568 | 757065371.597 | 300886168.958 | 598098244.5433 | 20362666.929 | 135115570.2293 | 20469707.0225 | 22250037.5389 | 856953493.0036 | 28150632.9106 | 1062513513.3823 | 6509667473.9673 | 705729255.347 | 190439615.894 | 1.5593e+12 | 2753057.3986 | 954222.2955 | 1689898.2828 |  |  | 1.7274e+12
163 | 1155887550.9467 | 1190496516.5354 | 222977957.7893 | 178488830.136 | 1021048953.8365 | 21349915.1679 | 203158858.1889 | 327499066.8502 | 454392323.7619 | 144692782215.236 | 1842236913.2396 | 1823997813.8096 | 2183522648.7172 | 171157146.5606 | 573165826.2242 | 693261687.9723 | 850663292.7193 | 280840892.0011 | 568347481.9249 | 25995326.0589 | 117156265.9332 | 21539195.2989 | 22780101.4179 | 674231785.4084 | 24444880.2119 | 1194148561.702 | 6266440860.1415 | 656374461.3466 | 192151585.193 | 2.1234e+12 | 2685585.8761 | 1012725.2289 | 1648799.3839 |  |  | 2.2911e+12
164 | 1246505640.9259 | 1196098524.4822 | 197499024.3119 | 157351938.7699 | 1051740818.3026 | 24858600.6185 | 215030144.936 | 285276809.951 | 472406476.122 | 149735074822.2045 | 1910463210.1869 | 2197930691.6831 | 1857171687.5715 | 178983524.2016 | 607508586.513 | 668773095.7042 | 856890558.4981 | 279200965.1764 | 525962384.073 | 24011050.5308 | 128022963.6191 | 23186440.6373 | 21662070.4197 | 786068173.2459 | 26913341.0217 | 1103991786.5654 | 5235088622.6345 | 619911626.9576 | 171128836.6459 | 2.414e+12 | 2623563.7748 | 979990.8218 | 1585822.2009 |  |  | 2.5858e+12
165 | 1252678314.2443 | 1139813215.1071 | 205135637.6438 | 165194783.2446 | 1075759472.7476 | 29330134.8868 | 201037764.173 | 276889039.7029 | 483071919.2819 | 142253954771.0895 | 1986783172.4839 | 1696593175.919 | 2165675719.1363 | 185527875.9014 | 602402414.0922 | 598857505.1121 | 867042698.5901 | 290214876.7922 | 563900108.9599 | 23727335.4558 | 122337011.3171 | 24003748.1745 | 21910642.8267 | 764294081.9 | 26753188.292 | 1187977873.3906 | 6376200510.6432 | 545391374.0644 | 199408136.2435 | 1.7139e+12 | 2326445.7582 | 929614.9647 | 1538978.4254 |  |  | 1.8792e+12
166 | 1131378511.1851 | 1171506095.5102 | 211374283.8573 | 170805176.0073 | 985222152.8932 | 20658110.1732 | 184161109.0713 | 312071162.8513 | 463460493.1493 | 149927904395.8927 | 1964447192.0217 | 2089564696.5999 | 2002903858.9064 | 200889797.8461 | 574315371.7932 | 564356757.5288 | 734916819.8645 | 254738995.3653 | 541214633.5317 | 23800524.3943 | 114663719.5334 | 21507879.8089 | 22896742.7265 | 906994387.7824 | 24314595.6212 | 1050750300.3835 | 6761033049.7062 | 662133791.1598 | 175311949.2759 | 1.7262e+12 | 2417840.5806 | 991553.4091 | 1842955.5162 |  |  | 1.8994e+12
167 | 1076376580.854 | 1086977735.0131 | 208191032.6946 | 176443512.1679 | 854627554.3169 | 25412980.1023 | 181726453.644 | 305311738.6203 | 477883271.7797 | 147399569474.671 | 1945000361.8491 | 1954436901.8337 | 2177071574.1024 | 169685576.128 | 533402003.5415 | 692246873.8676 | 807404645.2383 | 326856036.1731 | 547494842.4208 | 28027247.1475 | 127938061.5658 | 20611399.3324 | 25595294.1288 | 824568364.5846 | 29118847.688 | 1053756928.3207 | 6523982330.2222 | 711144913.6046 | 190706979.1072 | 1.7875e+12 | 2167372.5393 | 918223.4028 | 1516007.5433 |  |  | 1.958e+12
168 | 1057698144.3538 | 1190598561.1976 | 207647468.1648 | 173688071.2876 | 1008255938.8545 | 23964383.9734 | 213598066.3944 | 310404381.5736 | 461544706.6881 | 147106370731.8115 | 1882481745.9708 | 1715166530.3409 | 2141844323.5833 | 161980517.7207 | 690493472.4266 | 644781795.4851 | 727827443.0458 | 327391868.0868 | 579392240.1889 | 27091410.9792 | 111940001.0212 | 22389934.5559 | 24583233.6419 | 890435133.9845 | 25988749.7725 | 936241768.0594 | 6193687468.7578 | 607719372.4237 | 201718301.1908 | 1.633e+12 | 2408576.8832 | 963056.3254 | 1612162.1224 |  |  | 1.8026e+12
169 | 1237425077.028 | 1204342958.8803 | 195439955.7584 | 167936194.0777 | 912406726.3154 | 24255586.1504 | 220543755.3422 | 323800891.2638 | 427793857.7489 | 141940201711.8379 | 1816257159.5019 | 1956478747.6515 | 2117161052.4042 | 202512435.0498 | 587605554.2455 | 668476898.3628 | 719133365.6245 | 311700537.8993 | 550584377.8605 | 22238545.0794 | 106715512.36 | 24336558.6867 | 24188383.8353 | 884944747.41 | 26207216.1774 | 1121636891.6256 | 7091924608.1884 | 661746386.2525 | 184654528.1734 | 1.9184e+12 | 2580195.2623 | 947296.4581 | 1719632.1376 |  |  | 2.0842e+12
170 | 1205171588.7629 | 1221905442.79 | 200703358.7617 | 170127672.3856 | 1037236993.45 | 27874415.5519 | 211745818.4031 | 316204065.0232 | 464535780.9166 | 151677215315.2751 | 1869108044.8024 | 1884423941.2506 | 1757360024.5706 | 185562490.4698 | 627923649.5228 | 668638536.2281 | 811338298.1163 | 330048168.5689 | 608716694.0714 | 25341311.2125 | 103714656.008 | 22319261.3369 | 24251980.9469 | 813318184.5543 | 26846374.4365 | 1108185013.8892 | 6496869672.603 | 504073179.5599 | 190463256.6685 | 1.901e+12 | 2386839.3619 | 988074.2516 | 1817363.829 |  |  | 2.0756e+12
171 | 1214184856.0581 | 1194149680.6861 | 196311307.0438 | 167600457.9096 | 1073972257.2591 | 22190396.6669 | 216506938.995 | 327987686.8422 | 471159505.1595 | 154872808213.8921 | 1708967398.1696 | 1770723662.0301 | 2100895370.5568 | 187166672.9639 | 446837043.5707 | 689296826.2935 | 816420631.4497 | 303074831.9612 | 562208195.1326 | 25380996.8779 | 120888420.4565 | 17610716.9934 | 22341547.9968 | 911899588.887 | 25958064.4052 | 858311781.8002 | 6151617595.5553 | 659328794.9507 | 179846896.167 | 2.1008e+12 | 2483973.1252 | 983549.9275 | 1613522.8683 |  |  | 2.2781e+12
172 | 1211551421.7067 | 1219493371.4868 | 201664264.2031 | 181367703.2868 | 1025965276.3541 | 23582330.7864 | 208431045.8432 | 312004521.4717 | 459282320.3578 | 126883211736.2224 | 1861764368.0668 | 1961065217.0933 | 1860253997.7606 | 200117737.6954 | 586038936.033 | 672440572.3215 | 751964586.9764 | 335331158.7543 | 615373255.5414 | 24540226.1618 | 113882041.9247 | 23463842.1781 | 24714188.8923 | 775575960.9795 | 23182312.7975 | 998195237.0575 | 6810224475.9779 | 688071949.4262 | 169226793.1111 | 1.9397e+12 | 2386072.173 | 962750.0688 | 1708677.0372 |  |  | 2.0899e+12
173 | 1198596317.1476 | 1137617428.3331 | 220757644.4421 | 164022042.0913 | 900976141.4087 | 25291618.167 | 221335592.0058 | 330508843.943 | 498006846.8908 | 150399277515.3656 | 2038197649.7245 | 2000755117.1023 | 2030229043.7404 | 190658863.8968 | 648540109.663 | 692123745.5088 | 825351723.1293 | 311154444.0762 | 561755197.7362 | 23783394.9805 | 106226756.8356 | 21494843.4916 | 24094185.0849 | 917871659.6298 | 27934043.9621 | 1044490313.3369 | 6894583560.3072 | 697155911.9183 | 177101917.4106 | 1.7757e+12 | 2442292.8398 | 913557.7168 | 1678206.9416 |  |  | 1.95e+12
174 | 985367299.2784 | 1127549667.7735 | 196628801.118 | 171601196.9873 | 1040857383.2633 | 24591323.237 | 202393295.6793 | 303316384.7303 | 478000311.1184 | 148153100183.0771 | 1708166759.6901 | 1779325643.8825 | 2173322196.1047 | 183801379.9144 | 561341024.7519 | 646316007.4411 | 756519982.7332 | 315754907.3737 | 562031695.1188 | 28118153.2689 | 128441612.9936 | 23230301.8584 | 24582809.7385 | 834507835.66 | 24632673.4529 | 1054161201.4295 | 6753977264.8428 | 682694799.5185 | 132006853.1514 | 2.2614e+12 | 2204158.1545 | 942107.637 | 1680845.4275 |  |  | 2.4325e+12
175 | 1163115846.3173 | 1228841196.5955 | 216127442.0933 | 174733482.9534 | 1064972004.6774 | 27281892.9443 | 208392262.7442 | 308861893.2093 | 440248802.2241 | 150319346282.4332 | 1491149583.8517 | 1873200505.1477 | 2204699443.187 | 162190334.818 | 531573470.7599 | 724705328.9351 | 758939906.9891 | 322446151.3005 | 592724738.1727 | 27620232.5079 | 132734423.6752 | 18676327.1442 | 25550964.7782 | 865475308.8875 | 27734473.2251 | 1014280747.3038 | 5857510213.6931 | 610260042.8136 | 162274460.2281 | 2.2086e+12 | 2415572.6582 | 913799.1413 | 1869174.1936 |  |  | 2.3812e+12
176 | 1142941950.719 | 1228540408.2761 | 214475928.9717 | 165275347.5809 | 1062818377.2836 | 25227209.7674 | 192120660.4363 | 300359897.5157 | 474901361.8924 | 145999951316.9999 | 1940747760.7664 | 1971000909.9417 | 2116533824.8909 | 188688497.3289 | 516239690.1672 | 657343073.5 | 919118105.7313 | 321161077.5463 | 602246495.9131 | 23594902.6392 | 121323594.8024 | 20752293.1891 | 25075845.1679 | 749179206.1925 | 29051181.3654 | 1081172023.6405 | 5716312930.8913 | 622116516.5502 | 170982760.7687 | 1.4588e+12 | 2649844.0392 | 912922.7617 | 1686981.3651 |  |  | 1.6274e+12
177 | 1091287013.5449 | 1140523535.2109 | 188476334.0097 | 182328158.5936 | 947470006.2533 | 21103055.2919 | 171857869.8449 | 315143989.8803 | 411139185.9859 | 130900804938.9769 | 1739496852.6269 | 1908212317.417 | 1673240484.8653 | 197232907.9287 | 513057689.8576 | 649142757.8069 | 801028978.2499 | 298979722.2911 | 538629699.7427 | 25944203.376 | 130601395.7083 | 23119543.9756 | 21848138.6827 | 650315292.2955 | 26269724.62 | 966732995.8001 | 5646191412.2925 | 691908924.8169 | 191919346.1267 | 1.5658e+12 | 2560671.2535 | 909830.3921 | 1727350.5357 |  |  | 1.7179e+12
178 | 1038825136.0229 | 1062345298.6722 | 177887327.4164 | 170449155.9486 | 905910978.2616 | 26466566.5503 | 195920683.2256 | 321591019.239 | 492977382.3287 | 126808085933.0817 | 1640723180.9966 | 2016511821.3914 | 2023637615.4607 | 187116966.8942 | 629277788.1313 | 719392616.9269 | 822103093.6603 | 272494854.4929 | 558384881.8128 | 21867046.2596 | 125604087.5544 | 24410989.7525 | 22017982.4901 | 876222474.9432 | 23812189.5453 | 830151656.4786 | 5824749461.3961 | 688934926.8143 | 151178789.0195 | 1.3831e+12 | 2572405.5969 | 998540.1308 | 1628325.5881 |  |  | 1.5318e+12
179 | 1249585969.9797 | 1210259400.1111 | 191774072.4753 | 171799698.9976 | 1083027461.894 | 25808514.5013 | 197635414.6402 | 327983624.5692 | 480206596.1734 | 129841356213.9066 | 2095425080.0266 | 1682768485.1547 | 1956567777.8167 | 189568269.9031 | 614860307.3359 | 678881515.0568 | 833259109.0576 | 285102986.1812 | 552046709.9143 | 25769812.9323 | 102178468.2171 | 19665135.9012 | 23882829.7066 | 861790483.0846 | 27299829.9599 | 1010046121.1475 | 6279049229.1986 | 697677367.7993 | 201364560.5004 | 1.8126e+12 | 2569118.5814 | 1004912.7284 | 1639196.4089 |  |  | 1.9655e+12
180 | 1166357329.3014 | 1136712531.99 | 215979686.0872 | 176457002.7069 | 1080433859.3213 | 22524676.7106 | 198714049.261 | 293756642.7018 | 460207512.541 | 160024538533.4043 | 1906485981.3456 | 1710279368.999 | 2028338732.202 | 200317420.1091 | 645146047.1786 | 550737150.615 | 733575868.3001 | 309155517.7681 | 601765128.0681 | 24864192.685 | 123044420.3906 | 23359926.5748 | 24015769.1511 | 695611630.9626 | 22862062.4849 | 1021934398.9589 | 5143677486.7826 | 580414410.0886 | 188608047.8823 | 2.4929e+12 | 2332812.9569 | 927401.6581 | 1871230.6666 |  |  | 2.6742e+12
181 | 1241053102.4882 | 1177085032.6032 | 207914617.6596 | 168289416.0311 | 1065968952.0544 | 23511628.5617 | 222785368.7792 | 326299759.4242 | 496597819.131 | 157056574790.892 | 1626260653.5875 | 1896653150.8121 | 2067751809.8783 | 198873303.3509 | 643040847.3179 | 685212519.484 | 853127916.4973 | 304018231.4338 | 603614744.9803 | 27527962.2248 | 115278295.5061 | 23541798.7099 | 23961339.6575 | 816169363.1594 | 30442863.1156 | 1147740587.7549 | 6372647498.8137 | 664218238.6551 | 194983525.3522 | 1.6957e+12 | 2572312.5979 | 919506.9675 | 1571502.0748 |  |  | 1.876e+12
182 | 1210560970.9662 | 1194616350.9784 | 194822358.1481 | 160472842.7744 | 1035739304.7228 | 23682037.3827 | 213180725.5987 | 301021644.2502 | 487611047.425 | 139542339071.6501 | 1887176491.2901 | 1827668962.5181 | 2015447985.1592 | 184927697.6362 | 557262316.6594 | 684559406.0798 | 881031276.0602 | 289209583.0262 | 605081332.1039 | 22325669.2832 | 95718487.4806 | 24576138.9783 | 22494934.6514 | 829732246.0607 | 30397972.6 | 1056077444.2067 | 6988743379.7972 | 644929251.9342 | 170586220.2184 | 1.888e+12 | 2533263.7127 | 918821.5566 | 1599085.8255 |  |  | 2.0512e+12
183 | 1197203754.8794 | 1175382793.0561 | 207613862.2763 | 170285842.6128 | 1008398911.401 | 22154937.6014 | 207906127.8633 | 323603335.6282 | 470841603.3599 | 147703424699.0486 | 1827012285.9304 | 1902865131.0518 | 1982605800.2145 | 172552219.7145 | 650328907.9357 | 528027775.0389 | 840476210.1032 | 322889151.2529 | 561456067.5119 | 26662707.3988 | 101740141.1066 | 22856308.1995 | 21176623.0613 | 698348450.6182 | 24938795.4736 | 862554650.0716 | 6351973780.5536 | 688330507.0093 | 186813163.2351 | 2.313e+12 | 2369949.8051 | 1048649.5529 | 1796279.531 |  |  | 2.4833e+12
184 | 1109589144.4804 | 1062592194.3108 | 194338405.5538 | 164891147.5345 | 1086688341.3627 | 25358355.7657 | 218388948.0552 | 318245361.5702 | 497822887.8127 | 159931178731.0007 | 1936533497.3731 | 1807634851.5443 | 1990174719.7004 | 168827941.02 | 663027104.3283 | 705301799.6143 | 832899042.8353 | 256769722.9002 | 463579366.5093 | 25125160.3134 | 116045864.0765 | 23878893.8648 | 25933932.9455 | 837033598.417 | 29741886.3967 | 1001389191.164 | 6709253836.4477 | 712722426.9567 | 193630004.3346 | 2.4621e+12 | 2708949.8537 | 995211.742 | 1689086.4243 |  |  | 2.6452e+12
185 | 1129820382.8415 | 1209657621.0228 | 222047797.6509 | 163989731.8958 | 1070749018.4757 | 24586150.3956 | 185431705.8433 | 316206555.2042 | 472369849.3769 | 119507535474.0419 | 1946608369.7815 | 2021530155.5835 | 2142362612.7208 | 186370256.3009 | 590928199.5239 | 510535148.8215 | 833925792.0213 | 338538883.8869 | 550016800.0239 | 25594022.0425 | 125361758.7642 | 23389769.2122 | 25899281.7667 | 815584199.8972 | 25070862.1832 | 1045652163.0841 | 6449560023.3178 | 487331039.6106 | 195147020.2407 | 2.1759e+12 | 2207028.6085 | 952186.5952 | 1548763.2306 |  |  | 2.3185e+12
186 | 1094943152.719 | 1202817421.6335 | 181584291.7476 | 174709897.3245 | 1071284957.0708 | 20379583.735 | 224821602.8228 | 329545373.8118 | 462079450.341 | 157598206488.7982 | 2067452908.0779 | 1896483683.4487 | 2041625870.8562 | 194294995.1485 | 547397265.0547 | 718676041.2506 | 905701783.8171 | 271972213.7585 | 609504563.2254 | 26898067.3157 | 130561704.9181 | 19796183.1592 | 21930280.2566 | 776857234.4438 | 24089244.801 | 1138193828.7148 | 5944189862.0091 | 593756984.304 | 197772812.3472 | 2.3482e+12 | 2592468.354 | 958071.2439 | 1620833.8044 |  |  | 2.5287e+12
187 | 972022730.2857 | 1211804973.5899 | 225171234.2184 | 138559454.8334 | 1081371918.7802 | 25084189.6072 | 204204246.308 | 308444389.5681 | 483461078.6814 | 139875257641.3993 | 1755298331.4787 | 2093440650.3647 | 1738459636.8183 | 196037714.6536 | 629300055.2201 | 631576872.3098 | 914695179.7461 | 338913632.6139 | 592697831.492 | 20596669.4047 | 121328770.5686 | 23443492.2261 | 19814811.0695 | 724625122.8743 | 26722389.3599 | 1041729558.6629 | 7012289192.171 | 612846912.8531 | 171939231.3496 | 2.0927e+12 | 2284071.1066 | 977402.0304 | 1641024.4092 |  |  | 2.2559e+12
188 | 1091819293.1757 | 1182957018.8998 | 213247060.8004 | 175583712.4025 | 1013552026.1027 | 21758303.5738 | 214405966.0941 | 305730919.7764 | 481390456.1228 | 134471262334.8969 | 1774607941.9667 | 1754845841.6533 | 1906338414.2393 | 195737086.9681 | 633745832.9159 | 665752566.6879 | 881004107.0545 | 252103841.3484 | 611941469.8781 | 22375416.7015 | 121265349.0125 | 24757352.4887 | 25382471.3494 | 928293167.2569 | 23479758.9204 | 859072029.6706 | 6872536962.9988 | 606298092.7579 | 150470684.3722 | 2.17e+12 | 2748331.0468 | 915317.0762 | 1741936.6648 |  |  | 2.3275e+12
189 | 1217393822.4505 | 1155275877.0874 | 201784689.8015 | 175671514.7815 | 1059117571.3676 | 25392322.4228 | 226990387.9895 | 314032732.1037 | 498495974.9184 | 134716379394.4282 | 1837265111.2048 | 1654606608.1091 | 2097431927.9726 | 200246342.4434 | 534387784.0792 | 702806618.7867 | 829584967.9359 | 335949885.7868 | 581331064.4217 | 27619661.5339 | 116950634.0598 | 23025029.2096 | 24292962.7849 | 806637337.5699 | 23919322.0452 | 1129565140.0319 | 6549826091.6011 | 681293124.1527 | 200641244.0837 | 1.8281e+12 | 2507213.4058 | 924512.9904 | 1734591.7685 |  |  | 1.986e+12
190 | 1246301193.4138 | 1210305022.8911 | 216407179.0886 | 175301669.5044 | 987601308.5529 | 26273999.9524 | 212575601.1412 | 324070435.4639 | 403640692.0482 | 140741812004.6032 | 2047212142.8597 | 1984965911.8671 | 2151049717.575 | 178968918.6989 | 602698144.2153 | 674328907.4433 | 886652936.1117 | 342460761.6024 | 601772422.6896 | 24501454.1557 | 130718919.1306 | 24780671.0257 | 20971965.6465 | 844970061.1295 | 28460355.2108 | 1112198727.6409 | 6119199840.1918 | 520846670.2497 | 170304854.3175 | 1.7865e+12 | 2544086.9738 | 922323.8876 | 1552292.5495 |  |  | 1.9505e+12
191 | 1089644752.818 | 1166525902.9647 | 213505293.7771 | 171981207.8866 | 1036240628.7205 | 22954269.5313 | 223453496.3838 | 323139041.2631 | 475771100.1659 | 142201858308.6071 | 1897123256.6127 | 1846977355.464 | 1997854087.0095 | 199786415.9603 | 540835070.0052 | 679929284.4124 | 727434753.3989 | 288056959.5893 | 611272964.3291 | 18071690.12 | 130413655.679 | 22713393.2978 | 25832412.8431 | 920390486.7957 | 25557216.8829 | 1139920901.7657 | 6051131252.379 | 566079564.9235 | 200485550.7306 | 1.6192e+12 | 2586133.4027 | 933901.2549 | 1621632.7375 |  |  | 1.784e+12
192 | 1113509097.8481 | 1147177960.6192 | 205508786.2368 | 154033510.6273 | 1086193366.4453 | 29218288.5635 | 219264044.9931 | 327375254.4566 | 466095552.5311 | 158104424842.7816 | 1829419059.1132 | 2116380405.5669 | 2206789811.1663 | 188660237.0167 | 689227486.6 | 559234098.6747 | 873688734.3488 | 337002984.867 | 528061526.0482 | 26086408.3561 | 124894337.67 | 21821270.8029 | 25307346.728 | 679490211.0092 | 24024449.3255 | 821259565.1543 | 6786449568.4235 | 569238431.4796 | 198288735.3742 | 2.0971e+12 | 2676475.3293 | 969561.3886 | 1660976.5307 |  |  | 2.2786e+12
193 | 1201506464.639 | 1092206157.1074 | 207894701.0194 | 160939839.6209 | 1065308541.6938 | 23477812.1708 | 216862256.1154 | 297765330.2656 | 467599223.7535 | 141834951343.3087 | 2065403398.7348 | 2057955882.4409 | 1737639868.6132 | 192231379.6539 | 582311477.7671 | 621153151.7027 | 806054105.6059 | 257541377.9977 | 450952089.7942 | 26166375.9456 | 121866282.3671 | 18758957.6421 | 24694791.3265 | 863488848.163 | 23080429.0835 | 1114197893.2996 | 5837552224.7254 | 692758874.0257 | 165498850.4723 | 2.0369e+12 | 2532505.5314 | 940575.3568 | 1688739.2207 |  |  | 2.2011e+12
194 | 1173466708.8056 | 1208725697.2934 | 220121460.1442 | 173698299.9792 | 1003660423.2128 | 22637928.8501 | 203492002.628 | 324705901.9591 | 424178162.7058 | 130727501861.813 | 1742423246.5425 | 2033745795.5023 | 1909199656.9572 | 166852996.929 | 570041464.981 | 679766491.431 | 739435614.8023 | 344755455.5289 | 571119884.0591 | 26423903.5415 | 123735276.1693 | 22070848.9589 | 18950921.697 | 856683149.534 | 30483895.4152 | 966371341.7108 | 6793517369.9892 | 691835923.0556 | 199174134.5071 | 2.5146e+12 | 2376463.617 | 969304.1555 | 1590415.9468 |  |  | 2.6686e+12
195 | 991313954.2204 | 1222355397.138 | 216328801.5225 | 181757449.4096 | 1080936330.0774 | 24610056.943 | 224917968.0041 | 308334433.0687 | 473707959.0476 | 136113756466.8679 | 2041189366.6141 | 1908779393.6681 | 2104257561.6105 | 198378912.4833 | 649263097.594 | 715627711.4357 | 840025537.3072 | 332610263.4201 | 551809942.9777 | 27364095.9424 | 119212039.2459 | 23247525.6429 | 23499221.4116 | 700266020.607 | 22903781.9557 | 1119450864.1591 | 6012656290.325 | 614967740.4776 | 198084676.4969 | 2.1054e+12 | 2363376.291 | 936137.1211 | 1913143.7515 |  |  | 2.2645e+12
196 | 1191620465.0725 | 996788162.581 | 202519093.2726 | 155522939.9613 | 1033694186.2771 | 22635714.6086 | 194280252.1118 | 293918099.5655 | 439025890.5416 | 131197661674.3253 | 1995393014.3503 | 1997997720.7876 | 2140168150.3291 | 196698029.3187 | 635196855.664 | 711836844.0149 | 766051186.4279 | 278573777.6205 | 594931013.9188 | 23260311.1811 | 107752884.9048 | 21795811.5052 | 21970753.2386 | 803461723.5866 | 24094771.5386 | 1161890742.9591 | 6251732045.2074 | 661914478.758 | 159412922.8512 | 2.052e+12 | 2442356.8199 | 939141.0541 | 1683454.7098 |  |  | 2.2063e+12
197 | 1118385294.8915 | 1198768205.1948 | 225302997.3379 | 177119067.7221 | 1069961972.1898 | 26502262.7225 | 189301697.1716 | 330169242.6866 | 477791207.4938 | 133111620625.5846 | 1844373116.878 | 1833370986.9934 | 2191486690.7324 | 170948841.26 | 535486757.585 | 660263197.4838 | 718353223.4708 | 309646739.2184 | 519775057.3265 | 18640221.9669 | 121921640.4746 | 18480263.5689 | 24629263.4582 | 851485216.1781 | 29810405.797 | 1119665843.7188 | 7224951067.0826 | 668711545.3129 | 200019777.8878 | 1.9124e+12 | 2456068.5181 | 902364.9295 | 1586715.5625 |  |  | 2.0693e+12
198 | 1197980595.5544 | 1164058860.4454 | 210645386.5227 | 178239202.7445 | 898057204.3412 | 18508287.4361 | 211135250.8861 | 281003085.9247 | 469399564.1086 | 121596036071.4308 | 1799978254.2646 | 1918241356.1052 | 2085066736.5388 | 181733674.9931 | 519425453.679 | 618691239.1086 | 849068513.1566 | 332017234.9939 | 424247953.1951 | 26343744.3209 | 122751423.2296 | 20735722.9657 | 23035996.3249 | 930301576.1597 | 31306873.2755 | 863169119.8602 | 5845873417.0297 | 592771047.0364 | 197846784.622 | 2.4379e+12 | 2718742.0215 | 927776.8228 | 1644594.7676 |  |  | 2.5815e+12
199 | 1058533942.8546 | 1191970566.3569 | 187982872.5208 | 143596090.8904 | 1016640854.0482 | 21337031.2356 | 192218630.2182 | 305257398.3992 | 411006229.8213 | 140452174494.1219 | 1908050753.8748 | 2037925119.3827 | 2139380699.7266 | 202264903.2163 | 561065167.6287 | 659537917.0735 | 829234599.2254 | 301059375.6497 | 611126092.9633 | 21600163.8797 | 129149482.3193 | 19575570.9723 | 23760429.239 | 932453047.4278 | 30586774.3196 | 1036134129.8966 | 6381183579.2656 | 613729926.5918 | 198288948.0267 | 1.6223e+12 | 2303547.2697 | 895353.5075 | 1583499.7173 |  |  | 1.786e+12
200 | 1196220453.1317 | 1205653952.8989 | 210375599.9457 | 166254782.7219 | 1001816350.7551 | 24640336.0441 | 211791079.9191 | 326036765.848 | 438665752.1624 | 139754369689.0275 | 1906717806.2152 | 2107967577.7763 | 2151225763.4971 | 201123324.4682 | 606769547.3442 | 615040283.9625 | 859004787.1987 | 363497424.4196 | 613672297.402 | 22123675.9786 | 115417989.9778 | 18733155.2354 | 21998370.7729 | 911563159.6271 | 22753510.557 | 843952649.2547 | 5975490691.8954 | 607166310.0121 | 166668518.5992 | 2.264e+12 | 2385667.0593 | 979453.0781 | 1754599.7731 |  |  | 2.4267e+12
201 | 996739170.4666 | 1220770742.7675 | 208797734.8927 | 181370908.7401 | 1057867892.8742 | 23062632.331 | 203920143.4181 | 310479309.0766 | 452704853.643 | 137345817374.8891 | 1869683994.1553 | 2028671485.01 | 1915099777.4341 | 197222842.5158 | 627679828.3122 | 714758913.1447 | 833593201.3706 | 327214076.7528 | 548125039.417 | 21500882.8127 | 117126484.7275 | 22524278.6231 | 21944921.0022 | 858003120.5487 | 28211058.2076 | 1104797513.118 | 6355986982.8535 | 593525902.2144 | 200005948.3419 | 2.292e+12 | 2510238.6004 | 951117.5618 | 1612424.5489 |  |  | 2.4524e+12
202 | 1196043220.2083 | 1180188919.638 | 205375968.7128 | 165701968.9966 | 1020215249.3266 | 24854893.7945 | 226170482.737 | 316276008.6496 | 497782612.8537 | 144019692695.2331 | 1916797367.6576 | 2025201989.7318 | 1907798232.8123 | 201113983.2474 | 473715807.8428 | 670569008.9416 | 899608253.4123 | 336723397.8087 | 550857282.1308 | 27173432.5865 | 107684545.0329 | 21303279.4484 | 25636728.0516 | 930969961.6882 | 26510172.3019 | 1153834972.6292 | 6623654656.6457 | 607318765.3893 | 165855706.6059 | 1.616e+12 | 2606874.1353 | 966623.8435 | 1719686.2484 |  |  | 1.7836e+12
203 | 1193248549.7036 | 1144449842.9656 | 214736520.4382 | 162762765.8814 | 1033465630.7687 | 22152092.0571 | 203616270.6586 | 324775877.1609 | 492254561.4382 | 155480314723.6464 | 1781625019.8922 | 2144107188.2273 | 2136119326.634 | 200910571.8529 | 547072250.9076 | 670062856.2741 | 669078781.0449 | 336449415.2745 | 549347481.6355 | 26152957.2404 | 106748025.6803 | 22087826.5382 | 23064766.9295 | 794526398.1753 | 28122027.1812 | 1177130576.2733 | 6655330398.721 | 606197429.0233 | 198987385.6456 | 1.9976e+12 | 2507929.4987 | 996214.4012 | 1620201.2824 |  |  | 2.1766e+12
204 | 1115381290.9967 | 1221937427.4972 | 208454764.1876 | 178872921.9135 | 984601327.5817 | 24608606.0395 | 210865226.7592 | 272873459.0165 | 439275197.2697 | 155004213963.2253 | 1952851367.2027 | 1798426733.155 | 1947704618.054 | 201522825.1639 | 524498713.5676 | 587062642.1657 | 722411140.5054 | 279483506.4488 | 584666525.7022 | 25539999.6346 | 113170683.2925 | 21147290.7655 | 20580243.715 | 927817785.5722 | 27528219.6123 | 1007610734.0823 | 6938835965.368 | 705720787.2981 | 170231134.6513 | 1.6819e+12 | 2745392.5516 | 944268.4001 | 1622152.1253 |  |  | 1.8601e+12
205 | 1226162324.3672 | 1132174340.0177 | 209303067.1741 | 163595579.0127 | 1000899759.2559 | 18206351.2583 | 220542419.06 | 281479872.0859 | 492901347.274 | 128020717407.4601 | 1831601912.7667 | 1449743679.7343 | 1696340700.7348 | 182474633.9128 | 567969511.6464 | 676856303.5348 | 785498861.4948 | 291466164.58 | 525178294.7121 | 22341163.8113 | 102438919.9822 | 21491262.2844 | 24825171.3138 | 885093599.2633 | 25692634.8999 | 1136932934.8085 | 6617917856.1078 | 668608610.3082 | 179292462.1422 | 2.277e+12 | 2505709.1666 | 902728.0205 | 1583939.7686 |  |  | 2.4275e+12
206 | 1207837553.5438 | 1031652823.9293 | 213956825.7323 | 174258827.4727 | 1055747446.9042 | 20595662.6616 | 204674032.9315 | 312935129.5802 | 436526901.4752 | 150013739903.645 | 2034222927.8309 | 2221335766.2989 | 1616341551.3559 | 182053052.4999 | 596774999.325 | 651734179.2797 | 789304169.781 | 328699304.7618 | 602143269.1276 | 23834700.0742 | 116225418.8818 | 23637315.9805 | 24588997.1507 | 903312294.1588 | 23698669.5505 | 1039111547.0786 | 6530627530.8233 | 690034529.7081 | 189172824.9522 | 2.1951e+12 | 2261303.1024 | 957127.1278 | 1585625.4877 |  |  | 2.3684e+12
207 | 1120095664.5417 | 1203051306.5094 | 207165560.4447 | 169474614.1035 | 988794541.9604 | 26909002.0968 | 202839380.0377 | 315636638.2103 | 491871558.4929 | 130440140360.3249 | 1703350195.0645 | 1953824491.9081 | 2211504513.9284 | 198129242.4729 | 487821506.5761 | 521559895.6665 | 862115172.5248 | 326724875.3018 | 543884781.1047 | 24593308.4719 | 103042193.2474 | 23260275.1305 | 23537136.8394 | 721739175.6074 | 31237883.9894 | 1070567024.0584 | 6645965603.6457 | 687469494.1651 | 198659141.3919 | 2.18e+12 | 2579554.6376 | 893074.9474 | 1659703.9372 |  |  | 2.3335e+12
208 | 1227360550.9596 | 1156600579.239 | 203866920.6174 | 172273965.2226 | 1051561554.4885 | 27117753.7336 | 211243791.371 | 322043959.7654 | 449461575.8225 | 141955644114.1844 | 2022694488.667 | 1846279938.7111 | 2213083936.4019 | 169242131.7567 | 665703840.3113 | 506005606.5064 | 875199180.9578 | 305294935.5234 | 461228880.9096 | 23329099.4016 | 124271267.98 | 23089531.463 | 24713962.5124 | 805181409.9723 | 25812948.692 | 1173676220.1355 | 6696893682.136 | 609031005.2744 | 190825175.603 | 1.7606e+12 | 2606374.0962 | 900025.3885 | 1573409.4672 |  |  | 1.9262e+12
209 | 967366826.7242 | 1192859801.0978 | 205944577.9306 | 172369617.5587 | 1055883126.2382 | 24879079.0696 | 188183025.5587 | 309096267.7263 | 445467057.3763 | 151241387934.413 | 2032987438.2869 | 1941194437.6612 | 2057803102.4345 | 178196023.1688 | 595469690.2341 | 549524979.8385 | 814875910.2677 | 328323536.5312 | 437438872.6537 | 24478105.2073 | 102772503.1291 | 23618607.469 | 24784283.3254 | 766550499.1609 | 29226861.8631 | 990688490.508 | 5598632693.6484 | 526129535.353 | 199489822.2343 | 1.7317e+12 | 2179753.3394 | 959030.9912 | 1546488.6602 |  |  | 1.9048e+12
210 | 1136769762.4369 | 1179314148.7067 | 211685128.7896 | 180310765.8811 | 1084632580.2084 | 24826423.7819 | 195234435.1399 | 311775552.7579 | 461033028.2888 | 162178888518.8522 | 2016120962.7092 | 2081965424.0714 | 2198582302.7662 | 153787356.646 | 566025533.8083 | 665620394.7504 | 776850729.0954 | 329423365.1466 | 559156789.85 | 27360228.689 | 136132800.9934 | 23433444.3853 | 24743200.9254 | 906715660.7775 | 26175781.3395 | 1082008887.0223 | 6516492915.9973 | 590133267.5054 | 199805703.8079 | 1.7661e+12 | 2523116.6683 | 907664.6804 | 1668687.399 |  |  | 1.952e+12
211 | 1090819965.1729 | 1174344996.2658 | 212068031.8269 | 156623445.1234 | 1070956562.5551 | 21300054.9348 | 213767364.8443 | 310235672.9011 | 497262723.7772 | 143586362682.04 | 1675825666.4336 | 2008182145.0425 | 2052317536.559 | 191339653.4545 | 615608231.4517 | 623406779.1004 | 847582811.253 | 316108674.6268 | 550795340.125 | 24272686.2793 | 121607259.6065 | 16584454.856 | 21159305.9179 | 858601458.913 | 25488625.361 | 1067099528.8505 | 6673956664.2227 | 494534513.3745 | 196383119.7547 | 1.5865e+12 | 2715627.1564 | 933398.8595 | 1482204.1931 |  |  | 1.7532e+12
212 | 1181283588.6657 | 1052470298.2933 | 204700187.9187 | 171275300.248 | 998334265.5539 | 20209293.7255 | 205709358.6151 | 303956344.4411 | 471153947.7459 | 148495296626.2693 | 1739668184.0369 | 1867740201.6219 | 2052364082.1182 | 202772856.218 | 630038298.0747 | 690197150.6875 | 809547907.5427 | 284499524.8552 | 610362817.8227 | 23845624.568 | 128080799.6043 | 19387546.508 | 22926650.9417 | 868235300.7851 | 24789808.8425 | 990241471.8318 | 5743845001.3374 | 683598363.1438 | 173131994.7899 | 1.9573e+12 | 2577693.0798 | 904407.5518 | 1859558.7708 |  |  | 2.1279e+12
213 | 1245210888.3227 | 1134304313.0428 | 202134011.0602 | 165841316.7655 | 1024595812.2755 | 19953222.3782 | 189981440.3766 | 322041330.0148 | 472166919.8753 | 141742905647.1392 | 1991688153.1814 | 2066436042.819 | 1955729732.0368 | 172173336.2405 | 638480739.7304 | 685568503.6996 | 771178692.5656 | 309475279.9996 | 564202290.03 | 25776305.8334 | 85253503.0154 | 19786660.1816 | 24562940.6183 | 839426958.1985 | 29727678.1195 | 1100534740.874 | 6952400677.8059 | 659739467.3979 | 192062678.4714 | 2.341e+12 | 2553898.2789 | 912232.4297 | 1651656.0614 |  |  | 2.5066e+12
214 | 1088480524.2497 | 1191216463.5603 | 187798848.6159 | 176745870.4148 | 967988693.8185 | 26886067.0655 | 213219346.1252 | 311296509.0859 | 483400193.2506 | 145041083921.4071 | 1928613906.0926 | 2052982458.4883 | 1920143655.8111 | 194180890.1498 | 529046721.5708 | 706960492.7742 | 665095312.8984 | 313808051.7777 | 583045754.9288 | 24944568.1511 | 110667994.6691 | 18118508.4367 | 23001632.3367 | 798858467.1755 | 26748301.1196 | 1045405457.9733 | 5525892835.5743 | 605181618.317 | 174808857.4557 | 2.039e+12 | 2426861.5559 | 951464.5175 | 1502930.6526 |  |  | 2.206e+12
215 | 1185949979.0102 | 1140472541.1289 | 204056006.1592 | 172554998.5946 | 1083142359.2588 | 20976135.1169 | 201251829.4909 | 323899176.3416 | 419234304.2538 | 157099482077.8123 | 1780489605.4436 | 2152073765.2452 | 1783439756.7328 | 196178065.9573 | 541634231.5196 | 692457891.3031 | 687001098.047 | 256864092.4542 | 598572747.3406 | 24871095.4061 | 98781858.0917 | 20080646.8724 | 21807878.6753 | 693573495.5028 | 23605381.1868 | 945860480.1314 | 6568328428.2206 | 624705307.264 | 196103964.6038 | 2.044e+12 | 2600241.2702 | 908805.6923 | 1705015.2239 |  |  | 2.2238e+12
216 | 1122326902.6497 | 1174550724.3361 | 200339319.1169 | 151120713.4287 | 1019239828.5635 | 26297087.0885 | 215549082.9349 | 324641579.3004 | 489385522.1847 | 144366341644.3145 | 1989852922.5062 | 1937972794.313 | 2109769753.4337 | 190231216.2401 | 598949273.7231 | 655710377.257 | 826552982.065 | 245729924.8968 | 566589176.1531 | 28335424.5067 | 112045718.7538 | 23620802.4603 | 25462029.1145 | 746504774.5752 | 28005326.0922 | 1168708722.2187 | 5318711065.4268 | 670868720.3202 | 200210138.1569 | 1.5072e+12 | 2694150.136 | 903080.2937 | 1765037.4646 |  |  | 1.6737e+12
217 | 1245318943.7743 | 1176054284.5704 | 196837303.8565 | 168989493.0516 | 897888836.7016 | 26127067.1646 | 209946084.7782 | 321447695.8519 | 460099004.8971 | 126702179511.8032 | 2096040470.8485 | 2172262304.3675 | 2040077717.8174 | 199832228.2352 | 572394580.9029 | 683196499.7499 | 838805444.7004 | 264779079.3711 | 516065374.5033 | 21105007.2796 | 89707689.2312 | 22982699.0398 | 25083713.9004 | 695483354.9157 | 26735089.1581 | 775062821.8568 | 5752471453.4678 | 631934213.2424 | 148971484.331 | 1.8026e+12 | 2324210.7702 | 953572.3092 | 1681868.3441 |  |  | 1.9516e+12
218 | 1024205411.7318 | 1053505030.7742 | 180873525.3189 | 149868488.7262 | 1087483571.7073 | 23262026.4279 | 214419850.584 | 319298156.002 | 478513419.1619 | 143249241441.3178 | 2019976653.8708 | 1963875210.6961 | 2058145073.8499 | 158644520.7248 | 668483561.9377 | 698010553.3534 | 809800283.0827 | 339986696.0588 | 535836268.4959 | 24037781.7542 | 89911742.5532 | 22084504.7496 | 22917807.1794 | 905195741.8586 | 27341274.5693 | 1078353899.7873 | 7105613613.3646 | 613979044.6246 | 182765359.7885 | 2.2714e+12 | 2384608.1443 | 945733.7871 | 1500445.742 |  |  | 2.4386e+12
219 | 1134356597.0658 | 1224333908.2191 | 204018100.3009 | 165247161.5588 | 1058458794.8698 | 24166050.4456 | 227117451.6708 | 329931665.0332 | 489198657.9264 | 142458199090.9019 | 1602933612.9179 | 2000840661.3551 | 2089068948.3576 | 193524451.188 | 610078360.1288 | 700504274.8022 | 781458747.7409 | 331384509.9573 | 584734989.0954 | 23947043.9454 | 120737033.612 | 20269025.3232 | 24009799.0225 | 856947483.1247 | 25360873.5932 | 1135701450.4969 | 6582997360.9758 | 665382555.4619 | 181960099.9755 | 1.79e+12 | 2428342.1136 | 914555.6625 | 1647950.5985 |  |  | 1.9558e+12
220 | 1229450878.3906 | 1183039476.6086 | 212168591.3603 | 168148735.7631 | 1056028642.9899 | 22301487.1934 | 209713759.6746 | 282729739.6857 | 483902870.551 | 130626427857.8788 | 2022234928.7354 | 1839567512.1337 | 2064220827.7213 | 194916341.237 | 506455507.589 | 674135660.0756 | 818274238.1106 | 264908322.3694 | 570599858.1331 | 25582407.7748 | 111496813.312 | 23120035.3906 | 23160929.0699 | 907531970.7941 | 30372649.3697 | 1138306437.6099 | 6243185440.7199 | 598371460.504 | 198899393.8975 | 2.1001e+12 | 2625485.0576 | 1009920.4728 | 1672978.747 |  |  | 2.2538e+12
221 | 1257818913.5035 | 1229180369.7581 | 219174381.6077 | 140710457.0697 | 1076897296.4732 | 24774325.1707 | 218364685.5443 | 308685156.6884 | 490088163.8562 | 142958310887.1992 | 1940041625.1678 | 2105298188.4959 | 1709458222.1319 | 199989894.086 | 646970107.6532 | 669711200.8784 | 872685651.2888 | 298731533.5707 | 550143028.1089 | 23041479.4446 | 129247214.4931 | 22980581.5501 | 20382126.0956 | 784834843.7881 | 27924660.1472 | 993805805.8328 | 4782715159.1538 | 655269844.5099 | 200155290.6407 | 2.2748e+12 | 2592018.0563 | 956431.5344 | 1558505.3297 |  |  | 2.4394e+12
222 | 1130198544.019 | 1130820879.9337 | 184109955.9178 | 179685620.7469 | 1028617976.9713 | 23610485.5883 | 204275756.7791 | 319681271.9718 | 475159798.6726 | 140545899790.1489 | 1846059562.0342 | 1947473966.3716 | 2058528772.0534 | 183871518.7882 | 650927066.8373 | 691327686.7421 | 875537424.3257 | 289092091.0133 | 503742175.8861 | 27821205.3533 | 131365201.9104 | 23028167.3648 | 25136163.6975 | 865584804.0871 | 26627012.7902 | 1136625024.6547 | 5694812385.7188 | 677155158.7586 | 200188668.6035 | 2.0758e+12 | 2413718.4108 | 1003457.7752 | 1592341.4661 |  |  | 2.2389e+12
223 | 1163022545.1828 | 1127087414.9653 | 201920620.1892 | 165030380.7727 | 1086945448.393 | 25129807.9871 | 226065082.1247 | 310167481.8425 | 483382154.7779 | 146642946382.5219 | 1941250983.6844 | 2083262503.5403 | 2091343461.6492 | 170687847.7944 | 628263184.1091 | 616484976.708 | 762654819.1779 | 278875523.0395 | 520244374.1123 | 24128510.0994 | 114418201.0956 | 23235375.7014 | 21993899.9011 | 830422809.8976 | 27809654.4939 | 1189331218.8702 | 5810981818.5359 | 685130154.8151 | 174360139.3217 | 1.8843e+12 | 2442084.5175 | 931273.908 | 1692838.9788 |  |  | 2.0537e+12
224 | 1251300226.2237 | 1133439488.1979 | 185033446.444 | 155771708.9529 | 1027636834.7606 | 21440549.6489 | 215733553.4177 | 316714621.0458 | 497616039.4799 | 155825106111.9063 | 1781457957.7132 | 2167225527.575 | 2125775830.9183 | 191675841.872 | 619554000.8957 | 715983134.9171 | 790244336.3809 | 261746994.9961 | 460358546.0331 | 26631773.7945 | 115740686.0238 | 22582353.9048 | 23407079.8717 | 951582771.2134 | 28168470.454 | 1139131312.5483 | 5799879561.796 | 680279836.9319 | 200491071.8974 | 2.2786e+12 | 2568821.117 | 943395.6907 | 1909856.0543 |  |  | 2.4573e+12
225 | 1236870652.7444 | 1203874282.4364 | 208156798.742 | 164909712.3968 | 964267436.8123 | 21479441.1249 | 199788353.8347 | 290007017.3379 | 462205388.0129 | 141715780145.1655 | 2020698867.0616 | 1900535505.2143 | 2206172766.011 | 191272567.8443 | 592693679.9004 | 635291433.8213 | 855364671.32 | 333383399.9508 | 554580181.8745 | 27026156.8764 | 117247630.1854 | 23437010.8326 | 24728753.3244 | 687562633.2409 | 20122085.5941 | 1038464594.1862 | 6478234465.4727 | 671412322.6832 | 195691069.2239 | 2.4112e+12 | 2380220.4354 | 970695.3597 | 1615723.0271 |  |  | 2.5762e+12
226 | 1194444809.8619 | 1208208376.4173 | 212089788.96 | 171757455.6789 | 1044953726.8739 | 28274419.7228 | 180429399.3767 | 282109754.5713 | 460166097.433 | 156832807446.6231 | 1637920464.1166 | 1485438450.3902 | 2135548162.135 | 182606340.0934 | 608475993.9079 | 596914412.4395 | 920533473.0991 | 298109305.2592 | 587326309.9264 | 19276930.9228 | 115848998.9604 | 24165802.4535 | 21412968.5028 | 870347821.7644 | 28836633.6822 | 941709674.0483 | 5396287616.7379 | 601437227.7736 | 195832618.4051 | 1.8041e+12 | 2479445.8044 | 907784.044 | 1602851.2 |  |  | 1.9824e+12
227 | 1211628392.353 | 1180940995.5406 | 196430574.2485 | 156074036.0596 | 1049832737.9421 | 22452422.5268 | 218251828.6513 | 299343667.5079 | 458901788.5167 | 135791895618.291 | 1591279947.6174 | 1938287114.4002 | 2112881777.5603 | 178910538.5588 | 636489103.8009 | 719683172.6453 | 884024248.1552 | 355176230.196 | 580143682.9637 | 26268528.661 | 117795662.6744 | 22299333.57 | 23181067.5465 | 909896945.9063 | 31583809.5881 | 1144929461.7521 | 7129226819.7605 | 671704587.403 | 147627882.0586 | 2.078e+12 | 2468604.3575 | 960451.5226 | 1492779.4006 |  |  | 2.2378e+12
228 | 1230404257.1992 | 1223777917.4098 | 215844957.4418 | 173520696.2077 | 1080023100.8227 | 21382608.6762 | 204360499.762 | 294226863.8574 | 493005484.6588 | 158598205122.801 | 1847009499.7902 | 1796837494.5397 | 2058585988.4836 | 195922539.9551 | 640274386.3559 | 663598027.3193 | 778522216.4125 | 302737718.8393 | 593495891.2919 | 24596863.0822 | 94334382.2878 | 22170866.1097 | 23656442.0616 | 812821940.5081 | 29738555.4673 | 966193812.2859 | 4447393673.077 | 697077097.5719 | 196078276.9174 | 2.3488e+12 | 2447907.6871 | 925317.7469 | 1536433.9431 |  |  | 2.5286e+12
229 | 1152004355.3266 | 1176823821.7689 | 213586243.4058 | 168287848.9325 | 1069706531.9018 | 24798014.709 | 194883765.6482 | 326105216.2148 | 481373869.47 | 146599963202.9164 | 2054643255.0484 | 1857651574.3088 | 2001477392.2149 | 194384097.3284 | 639979651.7639 | 575309769.5909 | 861991349.3097 | 280342328.3272 | 578607397.318 | 23859265.6613 | 123844575.1168 | 23819162.2121 | 24433896.499 | 865375412.3017 | 27216222.4333 | 1128822171.2596 | 5002114083.7691 | 612532940.4047 | 187040348.7022 | 2.1604e+12 | 2493496.9272 | 903029.4196 | 1664448.2066 |  |  | 2.3289e+12
230 | 1198462618.8733 | 1169754089.4191 | 220126093.3547 | 179606275.2395 | 933253462.275 | 23951898.5529 | 221740850.7792 | 300964921.3594 | 491492313.3273 | 159612801461.139 | 2007119311.6515 | 1876588652.6012 | 1998778775.9037 | 187372081.5638 | 502573300.934 | 614800445.1422 | 800000073.67 | 316660799.629 | 515050352.1755 | 23721273.1228 | 114835170.778 | 22001420.8865 | 23939937.8796 | 888060909.9946 | 24412043.5529 | 1007046187.6452 | 7163961479.2393 | 625220453.6055 | 183486770.2876 | 2.427e+12 | 2479087.1377 | 934999.4211 | 1721942.8183 |  |  | 2.6103e+12
231 | 1117120010.0532 | 1026598075.4656 | 222864590.8309 | 172128108.0456 | 1035263533.2737 | 20587594.3352 | 192528219.3746 | 309370046.1749 | 436686218.4646 | 144186203805.9597 | 1870919891.5939 | 1784985110.9792 | 2012602926.9381 | 190006009.2956 | 647777005.9364 | 656312055.0946 | 831954361.2351 | 280373353.7231 | 603023609.1488 | 23420439.3936 | 119902888.278 | 24300718.1838 | 21890175.2831 | 894460652.1449 | 27174220.163 | 972738423.2729 | 6307093794.1016 | 592799871.6497 | 176204490.5584 | 1.6334e+12 | 2613687.9655 | 959999.384 | 1712198.0814 |  |  | 1.8002e+12
232 | 1251479888.1899 | 1206775162.8969 | 190371245.6555 | 167966924.6536 | 972492321.1021 | 23119346.7487 | 219588565.994 | 295138739.3073 | 478509560.4878 | 146960080228.3275 | 1883336068.9332 | 1980851587.4592 | 2200086615.0504 | 189532010.3374 | 536821008.7407 | 684552090.3982 | 821715564.2207 | 262689144.0165 | 588427833.0511 | 22148908.2794 | 137035899.308 | 24353848.2069 | 23782064.6413 | 934499842.2461 | 27116427.7369 | 1219587112.0068 | 5807356434.4299 | 620308626.244 | 150739228.798 | 2.5093e+12 | 2304769.7655 | 921077.2305 | 1589002.9324 |  |  | 2.6792e+12
233 | 1139019620.254 | 1188070652.1007 | 205446351.4911 | 168597923.5063 | 1087347563.8356 | 23854695.5841 | 216256885.9561 | 297266199.3746 | 482316607.7129 | 145028228572.3914 | 2010860422.4152 | 2099788170.9875 | 1617176498.6936 | 199388912.1682 | 662910408.9532 | 714728286.5066 | 660699252.6092 | 290586849.4528 | 544555465.2184 | 28604806.8335 | 120413682.2053 | 20106089.8838 | 20327962.6544 | 803702764.2894 | 25108511.698 | 1040116855.7032 | 6374207990.567 | 670254875.3131 | 171954742.8729 | 1.5589e+12 | 2222918.8996 | 952898.3093 | 1685637.5145 |  |  | 1.7269e+12
234 | 1045862490.8353 | 1217502104.2496 | 219094299.3466 | 170942935.1283 | 1009864552.3746 | 22003092.8009 | 224795362.6786 | 315677122.0796 | 478394447.9485 | 149580680322.9929 | 1868587230.5568 | 1817930571.2365 | 2126285583.7487 | 144393308.2208 | 614681021.9531 | 679616232.0921 | 903139697.932 | 251118103.9366 | 595213957.78 | 22356336.4163 | 102450248.5138 | 22165801.4621 | 23957422.5658 | 851650907.2394 | 29624648.5045 | 1014420400.4964 | 6700014204.6507 | 620525067.4232 | 201373107.1399 | 2.1587e+12 | 2674589.1338 | 889608.916 | 1731047.6359 |  |  | 2.3316e+12
235 | 1217566667.2983 | 1200715149.2748 | 179390788.0585 | 178526499.8701 | 994836678.1674 | 19620950.1274 | 214008656.9856 | 307203045.9773 | 444188592.6533 | 158152760291.1194 | 2055606547.3587 | 2047397152.4336 | 2113232387.6464 | 161770998.4684 | 588607409.169 | 711076654.4482 | 797634872.1234 | 345015691.7554 | 603117716.3169 | 26636960.0821 | 125277740.6034 | 24027136.2643 | 24860206.9056 | 864940299.9683 | 25383717.5374 | 996978736.1827 | 6522793561.3225 | 618176212.3243 | 198388967.932 | 1.9372e+12 | 2636668.4622 | 899955.5584 | 1612402.7648 |  |  | 2.119e+12
236 | 1244476341.5746 | 1220172616.9176 | 222093363.7245 | 175177202.7341 | 1039773089.7613 | 25426360.7933 | 215920299.0763 | 288016668.4849 | 460657107.7762 | 146384179742.9604 | 1901061802.7969 | 1986109880.8674 | 2135959113.9192 | 175909123.7719 | 660841428.3508 | 717230720.8057 | 827190932.4688 | 315064803.285 | 591606952.2528 | 26489332.1864 | 128824495.4696 | 23667457.1775 | 21237321.3017 | 905682945.8231 | 30135525.0446 | 1153502303.376 | 6809575491.464 | 612749080.4419 | 197707960.6325 | 2.1313e+12 | 2441939.9571 | 918302.8569 | 1718371.9122 |  |  | 2.3018e+12
237 | 1025692150.631 | 1216698422.022 | 196781749.6253 | 165809792.9679 | 1035805841.8342 | 22253386.0719 | 176455672.5249 | 317418180.078 | 440205044.7489 | 136350297129.0499 | 1763887538.513 | 1341012247.813 | 1842666418.7293 | 182447214.3637 | 450425921.3128 | 660994365.3367 | 845051956.4149 | 299260557.3439 | 562708303.8481 | 29025404.2121 | 100689690.3719 | 20991806.0707 | 24686386.9427 | 921667897.5582 | 21393292.5596 | 989827084.7016 | 6151860043.1256 | 624189931.4903 | 184862291.8163 | 1.8452e+12 | 2254435.8998 | 975983.8468 | 1616729.6042 |  |  | 2.0031e+12
238 | 1220635740.1999 | 1098910084.7781 | 222473146.2509 | 169531000.1036 | 1012526801.7883 | 23930014.9336 | 183120283.9172 | 258785961.477 | 496234772.1955 | 134233334465.1709 | 1761867055.3881 | 1966063235.1129 | 2154199375.1114 | 187581220.7248 | 609357008.0049 | 576712238.522 | 799884327.9353 | 294925186.229 | 607306317.1588 | 27630726.5965 | 101695978.6922 | 21265751.6057 | 24193955.9428 | 841691537.8586 | 28667951.1384 | 1073125436.662 | 6241692249.5198 | 680113153.2411 | 187469708.5109 | 2.011e+12 | 2542700.2892 | 966916.284 | 1640766.9038 |  |  | 2.1681e+12
239 | 1130261820.0151 | 1223583143.7109 | 185923594.7553 | 182339710.4367 | 960210287.69 | 24278963.6725 | 205898381.2374 | 330018667.3143 | 471689397.1658 | 118251280550.6672 | 1833587185.8387 | 1910619090.9206 | 2101660111.2069 | 178550918.4714 | 562474002.2006 | 456434139.0391 | 794603365.8611 | 271493630.3104 | 599838473.9438 | 24897347.8051 | 131924553.0304 | 24013410.3908 | 18813811.3724 | 934389124.4055 | 26888587.6758 | 956756453.4825 | 6098868012.0343 | 517317000.6887 | 179698690.6029 | 1.7643e+12 | 2521944.6025 | 939191.8761 | 1623149.5947 |  |  | 1.9048e+12
240 | 1242380649.0493 | 1151830221.5507 | 214997440.4118 | 171724457.4668 | 1075940664.224 | 25019094.0858 | 211849849.1512 | 330856904.5649 | 499761359.7448 | 129827110740.6274 | 1941487018.5408 | 1620899434.0475 | 2207239181.7388 | 168763924.322 | 557801073.1751 | 668288549.2326 | 799703294.0849 | 272203320.5642 | 614924236.6393 | 25408898.3784 | 111809386.6574 | 23500487.8215 | 23608021.6681 | 840258248.1271 | 27612626.2555 | 996462904.7255 | 6319898966.9298 | 663740212.138 | 174021018.1799 | 1.9298e+12 | 2222661.9779 | 908410.8005 | 1654637.3406 |  |  | 2.0826e+12
241 | 1197476132.2143 | 1198035221.8309 | 211425724.9123 | 168651993.3991 | 1074294589.3956 | 27008414.7511 | 224084541.6719 | 314894854.737 | 489413371.3676 | 148076064986.4069 | 1748618243.2603 | 1977138372.9666 | 2117029470.9997 | 192505359.6783 | 582175689.5629 | 570477878.0677 | 771197072.3374 | 361663078.107 | 547670326.7861 | 21987264.968 | 109528255.3394 | 22502622.3545 | 22716233.0414 | 828011568.5761 | 26634717.3919 | 1203772298.5004 | 6384107063.7908 | 672289389.8728 | 193170114.5119 | 1.7541e+12 | 2796226.9709 | 972752.6424 | 1509550.4954 |  |  | 1.9255e+12
242 | 1229091204.9223 | 1176503058.6728 | 203198287.9855 | 165393666.4543 | 1059644731.8642 | 20264744.5792 | 219832967.3689 | 315346834.8906 | 471790676.7599 | 148780202879.1508 | 1864558496.5359 | 2091324286.1678 | 2158633601.4544 | 193850533.0578 | 668097385.0783 | 713897881.9975 | 867090655.9326 | 321344926.9137 | 598111242.8479 | 25181619.7718 | 114184240.8284 | 23263231.1769 | 25855459.0314 | 791365003.1748 | 26801308.398 | 1034668803.5217 | 5728544772.6665 | 704224769.4336 | 183981472.3983 | 2.7843e+12 | 2470532.3958 | 913577.7255 | 1859697.2866 |  |  | 2.9561e+12
243 | 1133414403.8127 | 1209453366.6464 | 213909628.1861 | 177311505.7036 | 1080962291.2449 | 25998432.2891 | 193501251.1786 | 312395637.9197 | 462563278.5258 | 139499034685.557 | 1836017603.6231 | 2159478924.6097 | 1732115776.9955 | 184764271.5986 | 653599717.2752 | 553070889.9829 | 710811275.4247 | 248612085.8429 | 568027209.9912 | 27603064.0767 | 123360968.2477 | 22545831.2367 | 22261632.7679 | 854539820.541 | 26955067.6734 | 1008593259.8634 | 6222549477.1028 | 662305636.7656 | 187956782.3413 | 1.7125e+12 | 2649010.0738 | 924260.4067 | 1534563.0333 |  |  | 1.8746e+12
244 | 1253502576.4829 | 1157076455.9072 | 225557444.5028 | 180737027.4981 | 1083629767.438 | 25072235.0055 | 202118589.9826 | 329534263.6093 | 499287623.4487 | 134046827473.8712 | 1967475657.5959 | 1810653207.8573 | 2071141150.9881 | 196809497.9067 | 618515008.4168 | 711826279.3181 | 879445499.1644 | 296225811.9229 | 576024296.6608 | 23297439.776 | 130800434.9249 | 22234379.0101 | 20859842.6932 | 770294486.8726 | 26266554.3542 | 984441044.7368 | 5557586501.3785 | 676977515.0523 | 158943376.8401 | 2.1073e+12 | 2499406.3612 | 987252.2099 | 1732263.5743 |  |  | 2.2638e+12
245 | 1049025992.5941 | 1177190811.6118 | 202376293.5009 | 165194751.2958 | 1081533026.9475 | 24139278.6592 | 192950143.9781 | 296547642.551 | 492167571.7479 | 147925304096.9628 | 1806038288.5914 | 1758714390.2704 | 2137376942.3237 | 178403163.094 | 614383416.4301 | 713843531.6762 | 809548367.0478 | 348183131.0098 | 552810998.6736 | 23018120.3755 | 124718150.4762 | 20375210.5277 | 25281735.318 | 789204913.0856 | 28648360.4056 | 984009245.3504 | 5437146153.527 | 673434770.5278 | 174126105.3744 | 2.0728e+12 | 2342254.1159 | 916643.3288 | 1668476.2274 |  |  | 2.2426e+12
246 | 1151411621.202 | 1208955384.6864 | 191955838.742 | 172038723.0512 | 1014214776.3389 | 22034409.3176 | 223936803.0683 | 321546442.5138 | 490008571.3764 | 136940624194.7222 | 1508013146.8236 | 1715654534.7088 | 2090041990.8149 | 190067014.5945 | 627324036.3842 | 605946760.7869 | 900363092.3032 | 250395269.687 | 575730953.5306 | 22326778.8311 | 99590334.6219 | 22819779.0248 | 23536720.6525 | 939720112.2572 | 23743402.7923 | 1092775843.562 | 6322954437.3071 | 599670359.4813 | 196793097.5867 | 2.1178e+12 | 2236383.6592 | 989282.9454 | 1664474.9256 |  |  | 2.2773e+12
247 | 1126632552.6291 | 1147347667.6401 | 227510495.7743 | 181229027.456 | 1075884970.3283 | 28105775.7782 | 214963393.0569 | 295822089.9424 | 486075763.2555 | 153109445087.5894 | 1968529029.8188 | 2105391449.6082 | 1891047765.6309 | 189041893.6579 | 452728408.9172 | 631557639.4949 | 842125117.2655 | 322978655.9711 | 539765501.7395 | 25521392.5735 | 96548576.3288 | 23323381.9651 | 23968253.941 | 865899939.8625 | 29351214.681 | 1073462786.6839 | 5708815414.2066 | 706668570.8995 | 172595398.1787 | 2.4588e+12 | 2589077.5755 | 982367.9137 | 1818886.0981 |  |  | 2.6343e+12
248 | 1176236864.5823 | 1179873529.3708 | 213468600.9102 | 172049240.0909 | 1045017569.211 | 25735373.4529 | 181484279.202 | 307923730.1071 | 473346091.1001 | 151160331136.4397 | 1953832008.348 | 1656173209.4793 | 2191022805.2455 | 185420976.9727 | 573217562.9259 | 603219859.0992 | 814214312.1968 | 274143341.6389 | 520650514.2629 | 20871848.1455 | 116578552.43 | 19728388.462 | 23246728.7081 | 936577635.2736 | 27500803.5384 | 1142880996.1517 | 6600467727.7472 | 622360066.7429 | 189963828.6745 | 1.5538e+12 | 2721995.718 | 905302.6798 | 1613992.5504 |  |  | 1.7282e+12
249 | 1158779973.9313 | 1201096911.8448 | 202853464.2935 | 158901889.9395 | 1036631437.4505 | 20656134.1089 | 219984994.0201 | 297459320.6359 | 498306266.4597 | 128811568170.5928 | 1829561935.3397 | 1758171923.1233 | 2017679016.0641 | 171007213.747 | 550614473.7518 | 698191078.2709 | 884817004.7989 | 289400622.6513 | 529386187.7723 | 22498623.0678 | 126837662.9832 | 20860551.1244 | 24464335.7308 | 933370271.3529 | 24489018.2402 | 1038463239.7719 | 6660892755.3511 | 677604574.5267 | 176448961.0174 | 2.496e+12 | 2605242.1592 | 933782.0731 | 1617984.9934 |  |  | 2.648e+12
250 | 1203727227.3786 | 1126555856.3981 | 216757102.9414 | 180544604.5213 | 992180317.1169 | 25070120.7685 | 216898945.5502 | 305690880.2539 | 477460123.3203 | 142526473662.0447 | 2101111143.1958 | 1964104984.6484 | 2114465146.4561 | 189908988.8191 | 563765527.4218 | 518112024.4736 | 869154043.8259 | 352441455.6861 | 468860221.2023 | 24135824.2661 | 122224081.3635 | 20526371.8975 | 24463859.1575 | 757003664.8749 | 28671762.1606 | 1096700738.7741 | 6488648128.1669 | 667529415.9835 | 190150386.5607 | 2.1568e+12 | 2338428.8246 | 1045250.2275 | 1593616.0375 |  |  | 2.3227e+12
251 | 1169203357.0997 | 1225335271.3648 | 205954381.7372 | 178093023.3773 | 1060885609.4127 | 26342527.5779 | 204161172.6458 | 317588555.0599 | 413597979.9396 | 156020993430.5039 | 1873526850.0167 | 1677669998.6644 | 2180278255.3834 | 152802171.4691 | 507246609.6884 | 704720969.9811 | 821588713.5688 | 317215601.6065 | 493086698.4532 | 23541259.0909 | 126006252.4114 | 20440811.8102 | 25249001.6482 | 903689044.9852 | 30038292.5027 | 1081825197.6401 | 7259338790.802 | 585952824.8413 | 170429447.1966 | 2.5974e+12 | 2300561.2887 | 934542.5064 | 1546671.5053 |  |  | 2.7772e+12
252 | 1214880146.3317 | 1094261193.0032 | 215609001.696 | 167396737.6617 | 1033269173.1865 | 24547718.6242 | 219365725.5359 | 304788775.0608 | 447806195.0485 | 149123086532.6459 | 1810395894.2372 | 1645025348.5861 | 2056900218.5657 | 197633662.9527 | 460776608.4898 | 716268177.7923 | 732607991.8701 | 315813615.6838 | 535230370.7313 | 20962350.4885 | 114288866.9986 | 22506399.5301 | 19426259.2607 | 762364808.0708 | 31379234.6801 | 1115251691.4581 | 4610538698.3748 | 702827021.6468 | 177348698.1081 | 1.9972e+12 | 2351968.5244 | 984534.6444 | 1699114.0815 |  |  | 2.1671e+12
253 | 1166316528.9343 | 1089996180.0598 | 220425184.3878 | 180122140.3435 | 967231695.694 | 29777164.5018 | 201616129.7089 | 329089521.8258 | 494959492.7261 | 119638031852.9811 | 1611813327.4356 | 2032474117.5386 | 2131491895.6395 | 165705340.3196 | 596847498.4634 | 695097986.9369 | 791548629.7616 | 306719350.3221 | 459285251.8713 | 22549061.6923 | 120747579.1107 | 24423696.5523 | 24797302.178 | 842887527.6602 | 26144438.309 | 1092808149.7963 | 5996627384.7823 | 639541002.5921 | 174544997.2589 | 2.4033e+12 | 2469466.135 | 939763.7989 | 1578679.8647 |  |  | 2.5454e+12
254 | 1023445515.0741 | 1150389311.1202 | 221315282.5649 | 174137915.9052 | 992003380.2442 | 22695415.3332 | 212073347.762 | 301890338.5843 | 451415115.4326 | 158577038926.0297 | 1995899886.0978 | 1603769661.0092 | 2030268280.6033 | 191700644.5217 | 560038515.1314 | 640611124.9076 | 909030308.6278 | 298979650.2721 | 612637825.0091 | 24674946.6291 | 114995243.3429 | 22889436.9277 | 25999485.974 | 892791242.3209 | 30850660.576 | 998135285.8831 | 6350151705.7108 | 630537053.1553 | 190663042.3945 | 2.6467e+12 | 2761011.0774 | 974982.7595 | 1746316.6771 |  |  | 2.828e+12
255 | 1155286327.5137 | 1166506969.4534 | 219797120.2477 | 174944037.3893 | 1001116655.8102 | 27276080.9815 | 214154910.0746 | 322881450.9985 | 472111225.1467 | 153084287765.3069 | 2024084663.6233 | 2096019668.022 | 2173973135.1999 | 188192589.8177 | 616120584.5631 | 689767441.8184 | 783652127.402 | 347004087.8991 | 606192225.8045 | 21275345.4919 | 124928057.393 | 22217523.2062 | 24269617.566 | 800617893.4364 | 25499006.8879 | 1014969146.2129 | 6731048555.3629 | 683024838.0363 | 192687992.0928 | 2.2262e+12 | 2275729.2928 | 982617.4538 | 1585598.0844 |  |  | 2.4032e+12
256 | 1023766743.1117 | 1183691443.1451 | 187856841.1847 | 178806529.9444 | 978081860.3344 | 22339490.3073 | 184450527.3419 | 315564255.8207 | 499212500.5949 | 118045679051.5813 | 2088899443.1883 | 2146660417.0783 | 1952194584.1003 | 176451402.654 | 648860979.948 | 606198376.4669 | 848846734.9097 | 327171264.011 | 550836913.1698 | 25869765.0386 | 116678950.8026 | 18464159.9458 | 25007561.0222 | 801267009.504 | 22571659.8726 | 1088994098.6642 | 7170194586.7672 | 684580694.3186 | 143279185.5837 | 1.7249e+12 | 2312194.2834 | 935591.9902 | 1690145.1599 |  |  | 1.867e+12
257 | 1186448581.6973 | 1159547254.2108 | 222570369.0358 | 166093472.4584 | 1052858556.2316 | 22328826.6525 | 219382496.7131 | 326123538.9112 | 439607928.8999 | 150401333290.2621 | 1742650134.6614 | 1790317158.5626 | 1939433193.9754 | 202160555.1349 | 644587217.8969 | 710125053.6342 | 888208833.2179 | 275969264.3739 | 553736865.4002 | 22480865.3832 | 130625776.658 | 20900717.8791 | 23673176.5676 | 799776791.8615 | 24763914.2493 | 1120043607.6477 | 6753865480.1357 | 605195542.4245 | 196352465.2674 | 1.8559e+12 | 2589348.7813 | 953468.0891 | 1592326.0102 |  |  | 2.0295e+12
258 | 1246510833.9057 | 1003957973.6944 | 218286518.7402 | 172847834.1971 | 1039554615.8696 | 19319889.1776 | 215625141.9619 | 294630536.2062 | 453615125.7327 | 145654062422.7679 | 1810147286.6057 | 2110056365.9991 | 1896215473.2686 | 194762827.4594 | 662254769.7028 | 631754739.2358 | 777345456.5163 | 334153022.4053 | 476689648.5433 | 23363006.3557 | 118601433.0622 | 23530636.0792 | 23654166.6496 | 751447474.7391 | 26729302.3977 | 1194440089.6816 | 6499066190.3383 | 518598786.9214 | 187709504.6804 | 1.4834e+12 | 2312608.6695 | 1007273.4196 | 1723297.1969 |  |  | 1.652e+12
259 | 1129882580.132 | 1159734301.2049 | 192107842.0279 | 178719697.7115 | 1066199067.4679 | 26241461.3134 | 200734402.6124 | 313156239.8817 | 454942264.9616 | 140814607788.5527 | 1939319590.1337 | 1986188944.148 | 2206154371.1444 | 170341357.8809 | 512372123.168 | 724657985.7326 | 858034216.077 | 311065166.3292 | 584449757.7621 | 21559498.9146 | 128214219.0626 | 19033257.0121 | 23720925.9077 | 851382930.2486 | 28242491.5915 | 1042204600.3647 | 5582857785.5702 | 590222830.7192 | 201792802.2037 | 2.0561e+12 | 2671650.2231 | 896296.4315 | 1878615.2073 |  |  | 2.2194e+12
260 | 1192220742.5323 | 1181133197.8686 | 219601112.101 | 158795421.1315 | 1008003449.5586 | 25362575.5626 | 220947150.4584 | 285956295.6199 | 451790563.7142 | 140835446994.4229 | 1934019714.2837 | 2057799756.5986 | 1861346850.7356 | 150538742.5413 | 669302867.3072 | 652363956.4817 | 861957756.8856 | 283605254.3396 | 597301187.8818 | 24832290.9092 | 105962782.2181 | 20468293.3996 | 24603949.4757 | 775755163.5768 | 31268737.0321 | 1052501434.5649 | 6077249809.6834 | 683360120.5708 | 193497537.9318 | 1.5002e+12 | 2743672.7284 | 1008425.6903 | 1546136.763 |  |  | 1.6638e+12
261 | 1227762776.3111 | 1169699576.3538 | 217755532.2822 | 171414237.8548 | 945398444.8948 | 21764842.4682 | 222776336.4549 | 324891263.7279 | 467636704.9443 | 133324075093.8726 | 1598541162.9902 | 2054866831.2388 | 2142673107.3107 | 194668705.5445 | 629084866.1726 | 710605738.9169 | 816564536.6923 | 287248192.1428 | 491947367.3594 | 25830675.4147 | 129974426.962 | 23961680.9395 | 23306642.1622 | 741434846.6481 | 28463260.4084 | 1100564989.7649 | 5356990306.1481 | 661072615.6798 | 185344867.1053 | 2.1372e+12 | 2635443.4887 | 928850.0879 | 1620548.2826 |  |  | 2.2925e+12
262 | 1211576241.4173 | 1158818561.8612 | 207362929.0597 | 157293213.3488 | 1061884877.4687 | 25259069.5821 | 210045007.2863 | 302272031.4042 | 460622561.6662 | 158563711632.6758 | 2050924841.7215 | 1973815190.2011 | 1943265476.95 | 191055367.3539 | 589898624.6311 | 513481777.66 | 846105562.2449 | 294062937.3282 | 575124997.0835 | 24513753.9867 | 104168433.5934 | 23667423.4165 | 24060199.8711 | 775359590.0008 | 23502690.9503 | 1108235500.8827 | 5972490736.5568 | 657940363.7252 | 182997132.0797 | 2.748e+12 | 2336347.5356 | 1027011.2056 | 1592179.8615 |  |  | 2.9293e+12
263 | 1164164080.3054 | 1218643557.5073 | 205567884.5248 | 170001760.4714 | 1086254676.335 | 22432732.3885 | 216225805.3083 | 297308757.4799 | 475127909.1071 | 149223516768.6122 | 1605538523.2442 | 1931462724.7809 | 2164602955.6151 | 168292577.8933 | 604000877.5345 | 650267475.3467 | 738151097.4565 | 336778199.2509 | 588765149.4454 | 27608008.3875 | 119224946.5932 | 24350713.2043 | 25858904.5186 | 793063272.4038 | 26867651.7744 | 779999590.5468 | 6862619412.9948 | 672264811.4353 | 159698122.6931 | 2.1989e+12 | 2444945.9055 | 947003.0895 | 1689231.49 |  |  | 2.3713e+12
264 | 1189014855.4159 | 1176399121.1163 | 192020941.2402 | 164703435.2925 | 1045906469.9465 | 22535660.7695 | 207800444.6915 | 296823619.1245 | 460986634.0406 | 133100355338.7811 | 2069173635.1152 | 2030553326.2923 | 2062319370.4235 | 164543914.082 | 517330100.7493 | 724442725.8695 | 845413683.6473 | 278082187.8778 | 584961250.434 | 24119818.2813 | 105357078.5908 | 23928079.8549 | 24641308.9736 | 888293599.3576 | 30839707.7523 | 936384798.0123 | 5836586547.6866 | 543453776.1698 | 158057281.4658 | 1.9374e+12 | 2495432.95 | 990274.2169 | 1693795.2935 |  |  | 2.0931e+12
265 | 1140230821.347 | 1228060788.1414 | 209748927.6528 | 170347352.0963 | 1052190008.3088 | 22180689.9364 | 218721454.1818 | 314831414.5228 | 443430146.5211 | 145218686857.8284 | 1712130946.8692 | 1575799173.2321 | 2020573587.6133 | 169210133.4392 | 566023576.4893 | 703217230.3312 | 792568329.7694 | 336591766.7082 | 481241109.1964 | 27274110.0409 | 99613288.8057 | 22962519.4833 | 19001791.7149 | 842409161.4862 | 30091358.9414 | 1103120709.0016 | 6964111488.9885 | 647128749.4248 | 186534988.6829 | 1.9592e+12 | 2310167.6437 | 917260.0366 | 1681995.2485 |  |  | 2.1275e+12
266 | 1258052983.8184 | 1156748290.5578 | 209571176.4986 | 151391905.9625 | 977345621.3063 | 26713515.8654 | 187061219.697 | 294165586.5753 | 487652866.9824 | 145273308717.7373 | 2008830536.0228 | 1855345010.6279 | 2165435809.5431 | 185565181.4047 | 482569556.8314 | 526582419.163 | 913127157.6411 | 252900944.6261 | 609176301.3669 | 26104315.4737 | 124266320.0199 | 20711544.2286 | 25400872.368 | 685936528.2104 | 28428742.347 | 957654967.7999 | 4669046278.906 | 596205526.4436 | 189065192.6491 | 1.9855e+12 | 2619213.7847 | 985793.7968 | 1682285.6388 |  |  | 2.1518e+12
267 | 1248288764.4049 | 1170017528.8384 | 216476594.011 | 169327875.8535 | 1085011970.976 | 20179477.2632 | 219506178.1891 | 311223278.3783 | 495830285.5504 | 144263715936.8733 | 1912173136.3603 | 1722391382.3855 | 1996434810.8214 | 163932412.9597 | 559556172.3269 | 634763997.3337 | 888603327.5024 | 247069481.9326 | 525795841.024 | 24211680.2964 | 117767509.4603 | 19144185.4974 | 23619462.7581 | 857479353.7278 | 26740364.1475 | 1177857459.2582 | 6385478789.0822 | 621215927.6192 | 201414550.2896 | 2.1619e+12 | 2511959.9446 | 948801.2402 | 1591621.5563 |  |  | 2.3292e+12
268 | 1095250404.7047 | 1151238816.2286 | 206398311.3435 | 174715262.1941 | 980295685.2768 | 26943699.2297 | 177807124.7375 | 312078526.4793 | 460817122.1634 | 155406277416.3926 | 2055889798.1691 | 1945943351.1574 | 2173145185.9921 | 198381810.3833 | 603257850.3438 | 685080966.3674 | 749989433.5215 | 346942637.5829 | 542552155.7886 | 22954372.8172 | 132768797.8046 | 22506540.8494 | 24030290.2208 | 854848524.5661 | 28294481.984 | 1136319673.8624 | 6700681053.624 | 538235797.5669 | 169968764.6998 | 2.249e+12 | 2469612.2144 | 911793.5701 | 1705710.3316 |  |  | 2.4279e+12
269 | 1111274684.4039 | 1191183500.0677 | 205712110.9326 | 180844971.0848 | 939714964.4079 | 20743584.0361 | 215428594.0965 | 326764167.719 | 455270008.0343 | 141523017143.5327 | 1688583010.738 | 1944965958.6852 | 2119862063.335 | 176810633.6108 | 579844867.0883 | 571292844.2547 | 745034569.4479 | 312472272.6144 | 542016488.2574 | 26633674.2123 | 115878913.5976 | 21615134.7456 | 22498674.0588 | 867994715.6025 | 22058797.4866 | 1141805168.2425 | 6258307242.5956 | 614967876.2461 | 188186437.0046 | 2.4689e+12 | 2415819.1541 | 968679.838 | 1657727.2824 |  |  | 2.6331e+12
270 | 1216708885.6411 | 1126534191.5791 | 223467350.395 | 165089809.6221 | 909618951.0561 | 22121195.9766 | 212455950.4742 | 294552763.7721 | 473842144.1102 | 156356571866.8206 | 1796669347.2159 | 2067379251.356 | 1823008884.3991 | 176485763.9427 | 464325763.1249 | 694331358.1339 | 911408717.8621 | 299742958.7088 | 574403815.0625 | 25803157.3708 | 124863025.8339 | 21085600.7241 | 23512674.9078 | 836492713.1235 | 25283617.9264 | 1077695768.9849 | 5567555126.1123 | 643471303.1637 | 169212021.0288 | 2.2093e+12 | 2678733.007 | 956392.3358 | 1548993.1853 |  |  | 2.3877e+12
271 | 1169271100.6009 | 1216643473.4968 | 215147421.2019 | 170927815.9693 | 1080227342.958 | 21547099.3321 | 190096506.4468 | 297971659.054 | 482829266.3456 | 135026939605.8335 | 1587944252.3298 | 1947246234.3185 | 2073803920.0619 | 135473075.3093 | 542636721.5969 | 638709158.3638 | 829797864.7198 | 333355254.0145 | 591539266.4294 | 25527445.3956 | 112267962.9341 | 24055836.2418 | 22643344.2004 | 938206703.9037 | 22461294.0464 | 911975422.1377 | 6425400525.4309 | 508118899.8289 | 192445582.0081 | 1.7972e+12 | 2488898.323 | 944762.3051 | 1561382.6521 |  |  | 1.9549e+12
272 | 1120608514.1283 | 1201755062.1843 | 212521111.5107 | 174874346.7235 | 1028491357.9875 | 27690088.8064 | 216712453.4088 | 316747915.3766 | 497263041.8917 | 154460983512.6788 | 1765307351.7581 | 2059103723.3109 | 2212286075.7581 | 198937794.9214 | 584241868.6405 | 636655975.6233 | 783280466.1735 | 341325037.6696 | 600405660.4279 | 25368700.5309 | 131218021.4574 | 20761739.1246 | 21104202.5846 | 785418643.6184 | 29986177.8407 | 1135151699.6467 | 6999776609.4422 | 632285237.0711 | 178138855.7165 | 2.0589e+12 | 2296204.6703 | 978939.2975 | 1728719.0346 |  |  | 2.2373e+12
273 | 1143437443.0678 | 938946406.2089 | 215949717.2477 | 182424497.3647 | 1031162593.5234 | 19305799.143 | 204322167.3129 | 276099419.8613 | 483866832.1745 | 141580024759.304 | 1786678524.7175 | 1970911754.0309 | 1778682535.0774 | 185637637.1299 | 454462729.374 | 705338877.3456 | 883057374.7921 | 269940961.1473 | 601533778.3282 | 23322365.1152 | 127903104.1747 | 21340806.7455 | 25019648.3504 | 939590314.5409 | 28472575.0241 | 1041161659.1243 | 6186046721.1829 | 672825137.9627 | 189994483.0033 | 1.6174e+12 | 2327169.0454 | 945197.5707 | 1670829.253 |  |  | 1.7814e+12
274 | 1134674369.3437 | 1127352038.6477 | 216412111.4746 | 175920058.9167 | 1014209710.7052 | 21170543.3609 | 198080191.2197 | 266674919.98 | 495995630.3942 | 130887280126.2569 | 1912449986.7659 | 1733364525.7302 | 1777449469.8846 | 182247570.1261 | 626423265.2882 | 685107638.6565 | 844311228.2058 | 331093926.5148 | 583561217.7486 | 23971561.4223 | 124606740.4512 | 20350518.268 | 25136517.3016 | 880117081.8901 | 28690000.2522 | 1146375253.2688 | 5841231947.6643 | 686487807.8965 | 189763559.4182 | 2.044e+12 | 2381185.0078 | 990891.0342 | 1579614.0762 |  |  | 2.1972e+12
275 | 1157439003.5802 | 1229098986.4016 | 198096664.3623 | 165053509.6455 | 1034239226.0174 | 20373502.4891 | 193356730.3999 | 300455691.1455 | 482363930.5928 | 150520667178.9713 | 2045261258.9861 | 1789940403.3054 | 2062008042.235 | 195499428.4202 | 583192164.9557 | 614913612.8248 | 897948222.994 | 335733724.1888 | 615605299.2262 | 27235543.6099 | 118909665.8799 | 22025824.4447 | 24008085.4136 | 849120274.8098 | 24417020.188 | 1060194176.3389 | 6797568195.7502 | 603144535.3699 | 200452951.4732 | 2.4298e+12 | 2686014.2214 | 963031.9311 | 1695043.1986 |  |  | 2.604e+12
276 | 1069510055.8614 | 1193439680.5441 | 209658948.154 | 162979181.2399 | 1086823753.4495 | 22802635.9435 | 213159646.1975 | 314304965.8093 | 481158233.0444 | 132361199919.4572 | 2036160183.747 | 2049699838.2084 | 2075492911.1624 | 168401405.8484 | 671682045.8938 | 658722332.3633 | 859108306.0602 | 358510359.317 | 613420009.5825 | 20876889.9053 | 114944957.1765 | 24325082.3946 | 24598146.144 | 793696105.6824 | 23359755.3559 | 1064708293.806 | 6576383378.0148 | 704871276.4526 | 189791340.0802 | 2.3126e+12 | 2481908.0988 | 972472.7244 | 1528213.9356 |  |  | 2.4688e+12
277 | 1211691138.7821 | 1193823019.3334 | 186161839.887 | 159152922.729 | 1085733104.492 | 26443810.27 | 213642705.2097 | 304656009.4839 | 458020377.9463 | 162187479169.5487 | 1897790990.0734 | 2117036446.0656 | 1990429471.2913 | 188564177.2468 | 510845553.1332 | 685643109.5477 | 723908092.7172 | 285665773.8166 | 499787290.1127 | 26952287.9028 | 113179276.5424 | 24296971.4664 | 25889463.4645 | 795908897.4401 | 24725977.307 | 846057822.7861 | 6769602100.1852 | 689286528.5782 | 198794180.4081 | 2.311e+12 | 2744003.3669 | 944940.1911 | 1768950.3378 |  |  | 2.4964e+12
278 | 1060327346.5007 | 1211861046.1953 | 224210939.9936 | 144290280.1866 | 1077965603.1047 | 22410917.2889 | 207445139.7693 | 297378307.4574 | 490663442.1693 | 147710008879.1064 | 2070789243.0225 | 1865621645.0525 | 2170603218.1295 | 159341774.6672 | 631619019.5719 | 682861949.4093 | 922362916.6906 | 356423756.5986 | 556798776.646 | 20719180.1483 | 93853855.7737 | 20797041.512 | 23496874.1463 | 806469326.1092 | 27728282.2428 | 1108964894.8248 | 5592286930.4614 | 698632769.8261 | 181498659.1356 | 2.7422e+12 | 2460596.1233 | 936491.7616 | 1637139.2295 |  |  | 2.9127e+12
279 | 1158547335.3415 | 1180095790.7039 | 207530387.688 | 141039931.4316 | 1077987280.0935 | 26562991.8698 | 222227595.0045 | 309853072.6776 | 495818777.6069 | 153176299694.2122 | 1787696638.4268 | 1918771624.1086 | 2104560525.307 | 190927956.3967 | 644362346.0623 | 701422716.1853 | 801925677.2503 | 318544382.4349 | 576531307.8025 | 24013649.7947 | 135445493.6433 | 23698937.5206 | 25322858.8027 | 710836824.1131 | 27908288.6479 | 1167988973.5884 | 6836801165.6027 | 686968656.9928 | 190465850.8719 | 2.6246e+12 | 2382808.3315 | 973807.4929 | 1637268.0253 |  |  | 2.8015e+12
280 | 1134259348.4586 | 1174325826.6401 | 222355056.5518 | 179628395.1315 | 1065453298.1 | 21942651.4315 | 216456502.9556 | 322816003.3377 | 492034981.3689 | 162255027331.1171 | 1736347770.9188 | 1952273566.7267 | 2192771156.0163 | 196311899.5133 | 578350976.7537 | 586240181.4588 | 728353557.0324 | 288491682.9715 | 601127730.4 | 28410860.953 | 127895822.5809 | 22697732.4132 | 24645174.3554 | 789084793.4857 | 25923318.8023 | 1069512786.7486 | 6240632077.551 | 670046057.7089 | 171531174.187 | 1.7116e+12 | 2549705.1224 | 910433.7614 | 1638776.3182 |  |  | 1.8967e+12
281 | 1196241687.8663 | 1174774157.1704 | 221509024.4678 | 175876359.6235 | 1001451606.4802 | 22162244.7701 | 214075458.2472 | 328963680.2563 | 482127994.6033 | 136630600348.1264 | 2097811481.9454 | 1637232463.3473 | 2207458458.5489 | 174181880.2669 | 661207087.2648 | 710023798.7222 | 792766573.5521 | 270572699.8742 | 525389666.9073 | 24007230.6735 | 115185479.5333 | 21666825.049 | 24598350.1709 | 774597842.6886 | 26652118.1112 | 1145506224.4261 | 5314557861.6753 | 712111212.3382 | 189712424.5041 | 2.5675e+12 | 2249441.5665 | 893972.993 | 1518284.925 |  |  | 2.7264e+12
282 | 1204122532.4062 | 1138033281.0648 | 205085885.3691 | 161152854.4558 | 1048304101.6247 | 20109072.5293 | 217539157.4308 | 308153802.0152 | 481721705.3126 | 158180547027.7769 | 1727834360.29 | 1659401432.6047 | 1788735496.0114 | 199117697.9978 | 517789937.5118 | 690604778.5684 | 767645287.0769 | 298069619.5086 | 588949489.3982 | 24917423.2145 | 124021854.7563 | 20714426.6124 | 21949562.4407 | 773479811.6647 | 25546769.1848 | 1188724041.3611 | 6178352583.9301 | 678805850.3816 | 181210758.3366 | 1.8315e+12 | 2607640.92 | 962649.5428 | 1529646.1606 |  |  | 2.012e+12
283 | 1143960066.0053 | 1145791122.3375 | 208374272.3665 | 176543041.5171 | 1067642148.4658 | 25314948.6748 | 217199361.5106 | 326857729.6881 | 426787045.688 | 154552441768.2293 | 1951267663.6523 | 1643222069.5329 | 2152373713.0059 | 202505059.9248 | 577019658.9281 | 601190594.9765 | 901353919.2693 | 283267857.7197 | 553578822.845 | 21971925.9404 | 121329174.2225 | 21617856.1269 | 22239243.7205 | 898663021.24 | 27853604.5967 | 1113138537.7606 | 6668437025.8989 | 637794627.4236 | 169055300.9859 | 1.8334e+12 | 2364494.5729 | 975706.0924 | 1815778.6482 |  |  | 2.0113e+12
284 | 1176722390.7187 | 1223804060.2512 | 194547088.9359 | 174291573.7991 | 1018606116.5275 | 25246349.303 | 197877550.9663 | 303750452.0104 | 460869252.6968 | 154451002594.2027 | 2010439872.8634 | 1919028916.6725 | 2152738232.4819 | 196558439.8306 | 587718722.782 | 657525368.783 | 802642105.0882 | 312291419.679 | 536018545.7749 | 22242285.4515 | 128363833.1507 | 22553136.1465 | 25373065.3063 | 905654333.0782 | 23409477.8525 | 1055331973.0488 | 7158828314.5678 | 606150402.5847 | 196503299.814 | 1.7083e+12 | 2453871.8171 | 923498.8865 | 1754053.6295 |  |  | 1.8868e+12
285 | 1207019575.3152 | 1106164390.5624 | 208262176.7953 | 155285843.4665 | 983972474.7842 | 22883782.0605 | 202845871.7257 | 312406543.8198 | 493459595.167 | 132841521103.3476 | 1808340005.5771 | 1880113072.3011 | 2199318196.7001 | 171336921.4309 | 629344114.4169 | 717867594.1653 | 754769814.2879 | 274215377.4772 | 545554633.8303 | 25365456.8379 | 110055575.8261 | 23210301.6708 | 21434365.7001 | 681325075.3688 | 20013362.6125 | 1054513886.2925 | 6877146120.6126 | 612033265.1567 | 198287552.7204 | 2.4595e+12 | 2619559.3566 | 974262.3718 | 1705865.3095 |  |  | 2.6156e+12
286 | 1044718630.7842 | 1181705086.2177 | 191931113.3862 | 169346081.0098 | 917178696.1977 | 26039744.6699 | 187168047.4139 | 306694475.8205 | 467941793.3113 | 130735414462.9209 | 2066299078.4259 | 1825506064.1294 | 1996108167.5609 | 196553083.9096 | 486451496.5703 | 627843167.4664 | 829509635.7989 | 339384465.1391 | 447750102.6241 | 23943522.1444 | 112138914.3184 | 22016531.2376 | 24392675.4311 | 798082970.3901 | 25490299.7049 | 1049780925.7145 | 6337265453.5892 | 506196285.6767 | 180356208.0948 | 2.3598e+12 | 2499181.2709 | 1007653.5717 | 1669141.0324 |  |  | 2.5129e+12
287 | 1262185040.6191 | 1227952611.3026 | 223597255.7979 | 169188293.7666 | 1044475890.7219 | 22653938.0127 | 226420162.1408 | 308299046.3589 | 475767352.364 | 139824342469.9784 | 1932313555.6463 | 1875029582.867 | 1781305994.1833 | 183934425.5109 | 645145104.864 | 711317882.6804 | 836990938.1076 | 299843375.8407 | 539622941.4304 | 24053254.4904 | 92910932.8097 | 23139675.8026 | 18717414.399 | 728785187.5168 | 30815964.3466 | 1076772357.4762 | 5787102821.599 | 674555021.3711 | 199581058.9412 | 1.6259e+12 | 2532907.4042 | 1008242.2266 | 1502154.3479 |  |  | 1.7881e+12
288 | 1060432092.6008 | 1149148524.3803 | 208632735.8945 | 153299631.0886 | 1065264746.8195 | 22416341.3807 | 226083666.8168 | 324591743.94 | 449599070.5501 | 160653893683.4131 | 1860996180.8508 | 2027159443.529 | 2182828999.3455 | 177318403.3847 | 561616901.5716 | 633660675.5881 | 756763511.7361 | 287094512.177 | 556679701.72 | 26096383.6199 | 111120741.5853 | 19883278.5678 | 21353727.8771 | 873278198.3459 | 27545378.3898 | 1145335133.5162 | 6253586481.3307 | 670536108.2533 | 186332722.6602 | 1.6295e+12 | 2720330.032 | 893434.5614 | 1765988.2303 |  |  | 1.8132e+12
289 | 1237618316.3552 | 999474814.1416 | 203451092.248 | 160901754.705 | 1063643471.0303 | 25422531.7751 | 187175945.8712 | 327804809.7481 | 415641870.1667 | 128705202211.4131 | 2037191660.3053 | 1770526746.5931 | 1996839183.7891 | 200364878.3947 | 588879980.6836 | 718752518.6176 | 748162166.8326 | 326452797.1897 | 602495448.2998 | 26314847.2114 | 105844108.2984 | 21431185.9304 | 23260198.5336 | 875254236.3552 | 24427391.013 | 948835041.9143 | 5712451410.7962 | 633686356.022 | 187488266.9169 | 2.5196e+12 | 2427513.7165 | 945542.7465 | 1542697.8764 |  |  | 2.6704e+12
290 | 1193425805.0803 | 1213490144.7949 | 187367927.9297 | 167928307.0334 | 1085153149.4192 | 22986303.1351 | 224328728.7383 | 319679369.9283 | 402419013.5672 | 145193615096.4579 | 1742948579.8276 | 1888102223.4809 | 2048736143.6205 | 190057907.3015 | 665756174.463 | 715587788.9381 | 825048848.4997 | 310662888.8905 | 591279540.1766 | 24216604.6308 | 115415361.6799 | 24320845.229 | 25466790.625 | 915384647.2804 | 26868962.657 | 1112667098.0956 | 6716270319.3572 | 657373761.8122 | 200910349.4941 | 2.1081e+12 | 2778651.947 | 928819.2454 | 1695815.4331 |  |  | 2.2769e+12
291 | 1159026375.7669 | 1102935025.0647 | 206349240.3787 | 164767155.5324 | 1039241442.5728 | 23116577.8418 | 219350337.7466 | 320779512.6854 | 487431582.5671 | 143206586346.7347 | 1957711585.117 | 2034967764.3415 | 2158487322.938 | 199132846.2074 | 503623769.7734 | 707863460.3591 | 797037135.9638 | 325598340.0325 | 498524404.2358 | 21688560.3472 | 104554541.3523 | 23089941.5454 | 24378860.4437 | 754276739.5153 | 27939258.5609 | 1133829839.645 | 6485510673.6448 | 685329862.4077 | 191223894.1737 | 1.9784e+12 | 2593690.6722 | 963165.7805 | 1571129.2335 |  |  | 2.145e+12
292 | 1141918302.8365 | 1176105690.5444 | 209685951.1311 | 160132055.3941 | 1086058754.0518 | 21529262.3406 | 216348520.3743 | 328284014.6036 | 470101322.4821 | 143773824239.1395 | 1920871557.1225 | 1868095120.9842 | 2007716338.6932 | 183139875.6971 | 593584971.3161 | 639529735.7284 | 827084059.0323 | 298143716.0194 | 584671878.8416 | 21699555.9279 | 112759879.7465 | 20560297.7475 | 25171474.7262 | 794222601.833 | 28213353.3355 | 945071933.7418 | 5962712712.2821 | 604241759.7984 | 180573146.5043 | 1.6635e+12 | 2419510.4747 | 916257.0331 | 1880303.4852 |  |  | 1.8297e+12
293 | 1026906825.8287 | 1207365244.6234 | 219023474.0478 | 175737011.991 | 1065542510.6641 | 24592379.6425 | 179290661.6588 | 324119013.6849 | 482077037.6182 | 139663183230.539 | 1557769838.9966 | 1896973359.5108 | 2064835632.1331 | 194766833.4137 | 628005085.2512 | 659699611.2928 | 766095358.774 | 276589497.2258 | 531861774.5211 | 25727391.2306 | 127302031.6524 | 21167241.4136 | 21400119.9573 | 885164855.8577 | 27206736.26 | 1005610763.736 | 6418515744.9653 | 703379069.4478 | 194165682.5168 | 2.3982e+12 | 2405992.9191 | 931711.8234 | 1575914.0721 |  |  | 2.5606e+12
294 | 1246569108.1858 | 1211284027.234 | 196688578.8613 | 183033650.4394 | 1045305231.9763 | 24999771.8179 | 223395762.6161 | 306695905.8676 | 485201131.4563 | 150512943760.5797 | 1578794061.9098 | 2030021531.2613 | 2189367448.2272 | 164741521.1241 | 616996635.133 | 546850111.8409 | 733300384.9488 | 323623032.4792 | 610605124.5498 | 21459168.4163 | 102049393.6395 | 23940275.4395 | 23182938.5091 | 936022074.6197 | 24156178.9077 | 1164583729.7514 | 6024852696.8156 | 572017117.1197 | 179221643.4609 | 2.2989e+12 | 2822755.5482 | 940967.6108 | 1734838.7467 |  |  | 2.4723e+12
295 | 1181973417.5409 | 1073376557.0817 | 219089851.0961 | 171703866.9458 | 1066441188.1329 | 24644559.1697 | 219319737.0602 | 312471233.4355 | 494346879.9328 | 148608676457.6508 | 1966855572.3996 | 1939986761.0393 | 2202614897.6888 | 199527269.5996 | 612808133.9765 | 571488031.9334 | 832611718.9203 | 331062439.6465 | 572206991.6878 | 21822920.2773 | 117966874.8069 | 24729884.4085 | 22172723.6997 | 867673337.5778 | 25592866.3488 | 1150804643.3051 | 5801839361.1801 | 690159319.8485 | 199461021.0802 | 1.7772e+12 | 2347027.4693 | 1030753.3811 | 1874747.3657 |  |  | 1.9487e+12
296 | 1139203927.5 | 971818435.1611 | 211245353.5452 | 182259372.1264 | 1068681387.4638 | 22405724.2329 | 218605637.3845 | 306530551.0783 | 429307882.3617 | 127446985357.5976 | 1999217570.3034 | 1933928829.3314 | 2065718254.393 | 185645098.5679 | 615118060.4172 | 697468577.0851 | 716136844.5115 | 349035880.4942 | 598950019.5619 | 24150131.3258 | 109195065.7325 | 20633521.2362 | 24736321.2832 | 933929239.088 | 26704306.2282 | 1186358252.0652 | 6488763620.3824 | 627212851.5141 | 192973773.8921 | 2.5107e+12 | 2419019.9482 | 1027841.9676 | 1631109.584 |  |  | 2.6615e+12
297 | 1105998369.022 | 1132930766.3884 | 212402273.3164 | 153260029.2635 | 1040816041.3481 | 24051501.8567 | 215608500.3074 | 284347359.9133 | 456850581.3613 | 147206985176.6487 | 1917057817.9092 | 2115150146.9048 | 1940983282.806 | 179183510.5594 | 532971495.6801 | 527253064.4316 | 728019045.8227 | 313504343.0272 | 555960744.3884 | 22632093.6637 | 120751308.3688 | 23595434.7163 | 21833911.0275 | 871938966.8906 | 28929286.0426 | 1195956072.6352 | 6670561804.0032 | 612350611.2408 | 189687372.4768 | 1.9233e+12 | 2674688.7619 | 927430.0903 | 1644640.673 |  |  | 2.0937e+12
298 | 1156005403.5364 | 1003053679.7528 | 221225621.7077 | 170945026.0119 | 986794311.0205 | 18687043.5556 | 179220672.6587 | 310127579.0525 | 494645531.0274 | 150945519355.6007 | 1544152939.5485 | 1971089948.2127 | 2020984288.3807 | 181629447.7108 | 675535205.5945 | 587898736.9325 | 796886063.2506 | 236245767.679 | 589171058.3491 | 20562058.9585 | 104873735.1614 | 23974298.4587 | 24571781.221 | 773657138.2328 | 28139717.8607 | 1038693325.9999 | 5958590215.606 | 679540233.8363 | 170578569.6601 | 1.9947e+12 | 2647254.0949 | 905447.0088 | 1693671.9467 |  |  | 2.1676e+12
299 | 1111171390.6453 | 1074983936.6318 | 210555379.2887 | 181495021.4354 | 1066897318.6202 | 24108211.1868 | 219090018.5756 | 329694467.4787 | 458619035.388 | 151284233627.1047 | 1703925617.576 | 1938709269.4454 | 1707141260.0464 | 195394946.4216 | 493764567.0349 | 664048587.7516 | 779509507.7065 | 327512238.8111 | 520009953.8554 | 24821166.4165 | 105088611.6675 | 21450414.8524 | 25964864.1094 | 793917214.7833 | 25953178.0886 | 1012654710.7541 | 6804784507.0825 | 696596134.5783 | 157698144.4151 | 2.3782e+12 | 2612151.7639 | 962026.1889 | 1553045.1384 |  |  | 2.5522e+12
300 | 1241705583.8029 | 1069152597.4914 | 177112508.3015 | 165565559.9318 | 1077129184.0224 | 21882506.0463 | 185149506.714 | 319461076.9833 | 488261452.306 | 135216751702.4013 | 1932135695.3827 | 1830073671.5661 | 2107381395.4734 | 198428978.5429 | 611396817.9621 | 702843535.8235 | 801126184.5541 | 346579940.0995 | 562281731.7446 | 26074561.1617 | 99213182.1381 | 19809423.048 | 22374284.9464 | 826170074.4351 | 25768076.8256 | 1115301025.3429 | 6249884819.9173 | 658070854.7142 | 191596926.9616 | 2.1048e+12 | 2609666.8301 | 981718.4235 | 1526702.3741 |  |  | 2.2631e+12
301 | 1240796837.0086 | 1218987815.2068 | 225352432.036 | 155542473.6656 | 1078924336.0715 | 26008501.1145 | 219600400.9369 | 311272185.7558 | 448814802.7649 | 151802257676.0137 | 1781005768.0158 | 2122237072.7282 | 1937116681.2178 | 192502959.3971 | 618438761.3517 | 672468994.0016 | 763814100.3327 | 329083279.261 | 565384673.5449 | 19819918.3731 | 98717088.1996 | 20787801.7978 | 21785248.325 | 885823554.1775 | 27235469.8716 | 1057871150.7949 | 6434399758.1101 | 652382483.7533 | 176832223.6429 | 1.6223e+12 | 2551730.4798 | 952623 | 1533661.2292 |  |  | 1.7974e+12
302 | 1143667954.9532 | 1183656664.6561 | 207012142.7019 | 168146426.3969 | 1065364878.5491 | 24049895.8182 | 225704028.6836 | 294269644.6585 | 486761926.3173 | 139837165355.3549 | 2021045070.1149 | 1946768386.309 | 1865829191.6337 | 197501764.8466 | 615567665.3549 | 651273947.0701 | 796724383.3873 | 276789393.0333 | 575348673.2213 | 25165688.6265 | 104911698.6594 | 23020874.5661 | 25708275.8964 | 705938652.8277 | 30117124.9479 | 1028754637.0894 | 5443378489.3809 | 683579779.6538 | 199471777.9041 | 2.1569e+12 | 2489628.7168 | 1008921.3368 | 1824243.6724 |  |  | 2.3188e+12
303 | 1200864665.3134 | 1187894754.198 | 183993779.6885 | 154161867.8364 | 980148906.7366 | 18217770.5146 | 215548800.4647 | 313052997.5104 | 461002675.0662 | 129508413928.126 | 1999887788.3458 | 2151422837.0428 | 2130012874.4692 | 200170361.0107 | 498356011.6703 | 706580097.9795 | 823565949.1905 | 305660108.4614 | 432553023.3062 | 26661969.7595 | 112931891.9846 | 21298497.0235 | 25187678.7243 | 780647909.3071 | 28002934.3595 | 996504493.7034 | 6091881798.4363 | 676793951.3778 | 184248756.101 | 2.2016e+12 | 2571311.0184 | 1040357.359 | 1697811.6559 |  |  | 2.354e+12
304 | 1221879064.3328 | 1044715089.3626 | 219589399.6343 | 180180054.6901 | 897028868.0158 | 22928263.2394 | 199742333.1743 | 322960689.9662 | 413361428.1396 | 151547907259.935 | 1927871817.2347 | 1826404236.6988 | 1938673302.853 | 199452374.3634 | 660846491.1873 | 674933193.6353 | 704851233.8356 | 298525552.1567 | 608482363.8192 | 25134228.9691 | 127754090.3582 | 23219343.562 | 22656111.9036 | 755630995.4176 | 25348445.2922 | 1006595981.3239 | 6911518545.0244 | 628559130.8769 | 170815312.6947 | 1.7262e+12 | 2291505.3584 | 933342.2257 | 1650203.8253 |  |  | 1.9008e+12
305 | 1172534295.3353 | 1021452562.2178 | 195306653.6487 | 172071237.2956 | 1078100153.5036 | 24294768.9914 | 214912560.1805 | 315007814.1042 | 472709219.8582 | 128366276326.3384 | 2026661317.6419 | 1778519272.409 | 2148513869.8077 | 152035230.0998 | 636165628.1212 | 710405611.4042 | 837077859.1811 | 301354393.0331 | 606868102.3752 | 24611690.9357 | 110594025.1839 | 22373912.1309 | 25494751.4366 | 907840272.9547 | 27300327.3427 | 1167765491.391 | 7030057942.5828 | 695061950.456 | 181923394.9332 | 1.8838e+12 | 2394926.8985 | 947492.7402 | 1494590.7483 |  |  | 2.0362e+12
306 | 1178205374.9733 | 1202124837.7499 | 213736746.9698 | 172064938.9908 | 835360466.0078 | 23979143.9924 | 208057279.27 | 297703967.5827 | 416909307.3821 | 111827769682.9467 | 1963284674.3225 | 1895964243.3647 | 1964101919.9472 | 172635693.7536 | 508247547.7744 | 542297923.7909 | 885823247.5018 | 313037537.5849 | 593872025.872 | 24766595.0841 | 134191648.31 | 21315421.6591 | 25543295.4215 | 828345716.595 | 27276899.5287 | 1091507167.3268 | 6037692607.4489 | 591411436.0098 | 182190031.1507 | 1.659e+12 | 2593767.4609 | 971178.8729 | 1669321.6815 |  |  | 1.7932e+12
307 | 1123014384.6075 | 1068677650.1882 | 204285046.1766 | 180197407.0536 | 1034536743.3862 | 27219609.9643 | 204922358.6156 | 303116549.3004 | 413097770.8488 | 143209002574.7004 | 1624242651.6675 | 1909868188.1567 | 2166656867.2772 | 198055599.2338 | 516920815.6155 | 654126407.8576 | 744993486.6071 | 334723625.175 | 590475239.9322 | 25480142.4001 | 103511914.6858 | 22955755.0652 | 25064060.9288 | 884130474.4171 | 28476459.3217 | 1068816459.7234 | 4852193338.9313 | 594410277.1328 | 190198202.5503 | 1.8486e+12 | 2641308.7536 | 909150.5617 | 1645843.2075 |  |  | 2.0129e+12
308 | 1243906490.8317 | 1171324878.9983 | 199111863.0486 | 138158508.9142 | 950069105.3652 | 19991209.7397 | 221010136.3824 | 322953383.6516 | 496961210.0453 | 151688417722.6273 | 1759248474.176 | 2024709081.1857 | 1684978467.8286 | 173639248.2202 | 595250340.4637 | 654275665.2603 | 893287580.4574 | 302184829.8466 | 602808484.4239 | 27996685.667 | 129454801.5726 | 23435081.9309 | 25604133.2537 | 890762334.3959 | 24744292.1882 | 1084872362.4527 | 5666572155.6646 | 652889718.1221 | 191857650.6349 | 2.1355e+12 | 2523295.5983 | 956847.3192 | 1614838.5324 |  |  | 2.3094e+12
309 | 1176745173.1499 | 1172944831.7579 | 191643592.6238 | 167762326.9471 | 1030595856.0315 | 22679341.2578 | 223535847.3412 | 328490042.6783 | 445792692.423 | 152189518608.2593 | 1913339251.8153 | 1708926835.5946 | 2192387404.1689 | 190200636.4989 | 585492358.0447 | 720289302.2716 | 898360409.2426 | 345900384.1871 | 495767713.6122 | 25151641.5606 | 110685222.5226 | 17103321.0822 | 23297675.8375 | 950697607.1423 | 27126796.8945 | 1184827132.8829 | 6112563552.8336 | 538781124.4271 | 185461733.9699 | 2.2829e+12 | 2257391.6711 | 933665.7564 | 1702149.176 |  |  | 2.458e+12
310 | 1228351500.6556 | 1140021473.5277 | 188773190.1272 | 166474762.1789 | 1015960574.308 | 22590585.4025 | 222042690.1133 | 326342028.3857 | 493789699.3395 | 108353704895.1243 | 1873321842.6425 | 2217200786.7407 | 2159238012.2523 | 162393933.5994 | 680887083.2399 | 711307283.4662 | 921199818.3256 | 347469833.9788 | 608046357.567 | 24422842.2733 | 104060462.7935 | 24432749.3779 | 25746138.2428 | 934101836.4041 | 30971588.1962 | 1038636655.1359 | 6736494995.423 | 616790794.1351 | 196719329.2343 | 2.484e+12 | 2354198.1729 | 1007079.6048 | 1606375.6705 |  |  | 2.6166e+12
311 | 1231983414.9262 | 1202710342.4857 | 207897601.9257 | 141875429.562 | 1048685345.8069 | 24383768.7236 | 215189206.4121 | 315179630.7724 | 470506162.1069 | 151496635476.3239 | 1700888500.7687 | 1800216483.0776 | 2193186093.3178 | 160727552.9578 | 648290093.9648 | 690254668.2918 | 869329978.582 | 333813601.8595 | 607591595.9237 | 24211437.9278 | 127589025.6889 | 21495091.4575 | 21777918.2804 | 901317821.3105 | 25961657.1188 | 1076765162.6515 | 5421865954.4661 | 532735685.0624 | 200702657.0595 | 2.3169e+12 | 2272266.6059 | 899922.3895 | 1525507.3849 |  |  | 2.4906e+12
312 | 1131054627.083 | 1173185703.7267 | 194657009.7563 | 138814197.4656 | 936627194.8345 | 25178063.4774 | 213035791.6196 | 318579745.1915 | 477950301.2962 | 151130339447.6472 | 1962844391.3614 | 1560100701.8852 | 2171166282.0567 | 194491907.5024 | 589880695.7897 | 721821201.1231 | 850572446.0497 | 312679760.7584 | 603415316.0478 | 27952820.2102 | 122828919.6638 | 22662410.2681 | 22607654.4642 | 861920220.0109 | 23897501.3083 | 855227483.596 | 6945848707.0889 | 690240703.3844 | 173168674.6681 | 1.787e+12 | 2711993.3634 | 904625.6849 | 1755913.7667 |  |  | 1.9614e+12
313 | 1177381607.9556 | 1221368209.8388 | 216348330.7789 | 165115476.1145 | 952589117.4463 | 25122761.5044 | 208101099.8383 | 296057492.1377 | 474751019.6575 | 155094578882.2454 | 1968007608.9531 | 2156576802.5783 | 1821576585.8371 | 181526776.8584 | 588023901.1551 | 700952653.6043 | 763531465.2168 | 292979204.1364 | 472736781.6264 | 25464624.5558 | 99991718.6001 | 22257332.1138 | 25479292.1955 | 712210030.4658 | 23015394.0297 | 1113758859.2431 | 6807810633.472 | 598142572.7628 | 162135755.5404 | 2.1178e+12 | 2508541.245 | 935580.0226 | 1829121.6306 |  |  | 2.2962e+12
314 | 972916653.3173 | 1201794151.1533 | 222052952.433 | 153528640.9212 | 1007190922.3544 | 23401556.7154 | 201694030.6543 | 308887418.394 | 478148082.574 | 132620118088.6183 | 1497727710.1736 | 1921176188.8626 | 2176063790.4823 | 170961480.5732 | 594630815.7875 | 690772168.5328 | 874052977.0643 | 312186711.3796 | 575072427.5571 | 27198052.7079 | 119044121.6308 | 20367164.9164 | 19504570.6 | 867926810.4367 | 29625635.4711 | 987392333.1283 | 6520302908.1658 | 604946966.1594 | 195596188.025 | 2.5427e+12 | 2589648.9732 | 936099.2156 | 1718234.9874 |  |  | 2.6981e+12
315 | 1136687881.3419 | 1096318156.3204 | 209259659.5659 | 174979615.206 | 986391733.858 | 23502266.4823 | 211257216.4094 | 329043811.5881 | 441064598.7115 | 135715926649.8422 | 1972383773.7493 | 2206689343.7505 | 2141293494.3749 | 178838732.0544 | 689141989.6346 | 517053246.0746 | 858845376.7913 | 338285537.6349 | 544668242.0333 | 21156436.792 | 117671707.7345 | 23958705.8608 | 23417473.2679 | 768109285.039 | 28784288.6742 | 1064675197.1518 | 6264716388.5152 | 627625855.315 | 168839798.6292 | 1.8339e+12 | 2382693.9311 | 991464.3692 | 1794157.2284 |  |  | 1.9928e+12
316 | 1246056931.9665 | 1208104219.4753 | 176745406.6466 | 167153499.3883 | 1016455616.7419 | 23853570.1218 | 212342663.5694 | 322590617.9776 | 482325547.93 | 148773773585.0027 | 1947471387.2276 | 2077128068.8358 | 2200958318.1035 | 165036296.5722 | 594261218.5039 | 688387971.8015 | 833748539.409 | 302588358.0412 | 551954095.8102 | 23382707.369 | 119184629.3388 | 23632956.6818 | 22516981.692 | 794413591.4311 | 27868785.3632 | 940443275.2594 | 5749335217.207 | 687350361.0906 | 200513450.7407 | 1.4841e+12 | 2238748.4624 | 942081.8573 | 1673156.0797 |  |  | 1.6557e+12
317 | 1153968983.6874 | 1189200693.965 | 210442943.1974 | 180597399.6137 | 1022239871.1173 | 22401172.6125 | 211600766.1465 | 317292339.5337 | 462477513.1713 | 155009490613.5381 | 2079776032.8516 | 2014109904.3156 | 2066838333.9304 | 172009413.337 | 613737890.9915 | 675815702.4642 | 783406668.6674 | 289888726.0385 | 529360884.5259 | 19496254.5742 | 126039116.8901 | 20891719.5908 | 25711568.8677 | 813416258.6795 | 28190068.6272 | 1038232513.8857 | 6864078690.9793 | 702088381.8822 | 189052818.4594 | 1.9148e+12 | 2475285.9745 | 953945.9291 | 1601969.3609 |  |  | 2.0936e+12
318 | 1167996658.4057 | 1144234485.7847 | 217473956.5282 | 175334374.7497 | 1069328125.669 | 20586186.693 | 223462775.0247 | 265685922.0421 | 496494219.0665 | 136710669163.8622 | 2008249616.2753 | 1762939634.9467 | 2042965939.6599 | 182324225.1927 | 580451713.0867 | 722584875.187 | 661454232.9414 | 335885900.8058 | 601513800.953 | 26443807.9591 | 125945073.6435 | 18739361.7814 | 22567329.6455 | 696490400.2903 | 23036719.3948 | 1125771058.6764 | 6419641767.7309 | 579499580.3498 | 149644494.6613 | 2.3768e+12 | 2461244.9122 | 890620.3714 | 1609918.539 |  |  | 2.5363e+12
319 | 1129872169.5423 | 1158100963.0192 | 205234665.8589 | 173364282.083 | 1047369700.5159 | 24698339.9337 | 203304424.5851 | 277802792.1235 | 449786465.329 | 156111764485.1749 | 1585340579.6374 | 2151059486.4048 | 1831774392.5144 | 197591590.1662 | 611971941.7963 | 713426600.4749 | 858562219.3196 | 297896649.6651 | 463850331.2894 | 20669162.0152 | 131268704.6754 | 19689453.8872 | 23535994.7009 | 812810278.5831 | 20346271.8375 | 1103911090.6595 | 5487764456.8492 | 639320132.179 | 199921640.6991 | 2.1122e+12 | 2433697.5572 | 884639.3557 | 1674963.5148 |  |  | 2.2902e+12
320 | 1207268182.7561 | 1163544989.358 | 218779551.0883 | 177711818.3725 | 1055859195.943 | 23783628.6256 | 212663894.2515 | 318550853.0957 | 415841371.2955 | 152791984448.6461 | 1853802419.3287 | 1509259165.0405 | 2136727971.1363 | 170967775.345 | 599479811.7686 | 715730975.9969 | 880298571.2207 | 262556135.8039 | 611555251.8251 | 22118016.9851 | 87739866.7622 | 22002956.8222 | 25106903.083 | 796156161.0702 | 27528218.8767 | 1050858148.3307 | 6149822276.9584 | 668753669.0632 | 146077518.8727 | 2.201e+12 | 2389002.2844 | 984315.4293 | 1767489.4621 |  |  | 2.3763e+12
321 | 1181848514.3916 | 1143902930.5158 | 219418405.912 | 163278977.0823 | 957517014.9286 | 21833019.1203 | 214728602.5274 | 296086237.2095 | 466664625.7459 | 152036490676.4968 | 1565052507.6888 | 1820283038.5735 | 1636401069.0761 | 186281688.5088 | 598319766.2984 | 710788035.1175 | 744979064.1598 | 344525368.3799 | 602629220.807 | 24897194.3877 | 123972592.2765 | 23860001.4806 | 23295088.6791 | 708974026.7552 | 29181376.8464 | 1130681164.6635 | 5817169057.4258 | 622446032.5425 | 191025448.6953 | 2.2014e+12 | 2258966.2665 | 911230.181 | 1770513.3056 |  |  | 2.375e+12
322 | 1175059787.5621 | 1178831808.3729 | 224746474.2007 | 164216383.0068 | 1011135480.5655 | 21195767.9324 | 222866640.6327 | 328210359.8568 | 499402746.5402 | 142075378466.6311 | 1587695121.814 | 2183936576.9457 | 1986013218.9823 | 168863753.0822 | 634739243.7915 | 683574466.7447 | 861525323.0715 | 333974884.9264 | 577972135.6336 | 22465766.9229 | 121129327.8783 | 23707037.4991 | 25653167.6082 | 805114665.3055 | 31437887.6486 | 1214497613.2625 | 5348942453.0833 | 648462861.8309 | 186498562.9637 | 2.5949e+12 | 2371269.2493 | 913414.3937 | 1629951.282 |  |  | 2.7593e+12
323 | 1131987911.6517 | 1220303541.1692 | 217892598.41 | 154579636.3348 | 1028400994.7635 | 25155277.5867 | 195425638.2971 | 314349478.2561 | 494436986.1467 | 139049413214.3707 | 1552352228.4358 | 1968448221.5324 | 2044879908.0597 | 188095773.6524 | 547510765.1989 | 690308903.9418 | 752996903.0614 | 319986487.8567 | 596466555.3129 | 24649897.5397 | 98169992.5689 | 22210495.1835 | 22153627.7698 | 918832279.5517 | 30192323.416 | 1053409672.5002 | 6737417208.4636 | 641886256.6133 | 168253639.9778 | 2.0355e+12 | 2419536.8641 | 930619.5413 | 1552894.1321 |  |  | 2.1978e+12
324 | 1261120733.5314 | 1197004678.6813 | 204035949.0819 | 179049988.6884 | 1073483968.386 | 23166400.3187 | 216466898.138 | 297153715.4411 | 442848722.4224 | 152276683529.0161 | 1560026444.2734 | 2084716379.9337 | 1836202238.8728 | 171102087.3999 | 608922708.7389 | 621851644.8993 | 866479680.077 | 360422937.9898 | 535634751.0674 | 23246900.2336 | 120640436.4149 | 24119643.5637 | 23556957.15 | 870829142.3454 | 29422080.6394 | 1195607922.9476 | 6412687510.1589 | 711011015.0086 | 196965928.9053 | 1.6151e+12 | 2590461.3882 | 909553.2386 | 1806875.4677 |  |  | 1.7905e+12
325 | 1165970377.7658 | 1111442274.5146 | 216749135.4684 | 155654784.5369 | 951376412.799 | 25865226.6593 | 199191337.1757 | 314672393.5857 | 485642809.9476 | 146841796338.0223 | 1688122530.1941 | 1801315913.835 | 2189448078.6777 | 194585521.238 | 588465945.3443 | 587267833.286 | 668043958.9411 | 318424467.2166 | 594696002.8 | 24525859.3598 | 112835784.9887 | 23863925.6862 | 24141337.8889 | 802248502.3145 | 24087880.6882 | 1095002688.4485 | 7019390283.3995 | 662729553.6384 | 175594924.6131 | 1.7474e+12 | 2585079.9804 | 992899.5907 | 1665163.2781 |  |  | 1.9175e+12
326 | 1157446234.1735 | 1182313794.1464 | 198258546.9247 | 161958376.1435 | 1040229018.2099 | 22478527.5909 | 209189253.6972 | 303505498.8307 | 467577391.9385 | 142322262045.0344 | 1951425059.3363 | 1710915016.6638 | 2148085367.5266 | 194251892.5586 | 501749645.4617 | 717797516.0064 | 875124349.1449 | 308122405.659 | 611892014.5039 | 22247013.0658 | 100222012.784 | 22965389.9643 | 25460188.1329 | 708142509.9398 | 31130475.4901 | 1149821178.772 | 5830967268.5516 | 665111576.6228 | 199707771.7871 | 2.5547e+12 | 2784759.1239 | 894698.0403 | 1628596.321 |  |  | 2.7196e+12
327 | 1254508819.6911 | 1226713780.3647 | 180474456.8884 | 152742382.0748 | 1059822340.8296 | 23604213.6423 | 207108274.0545 | 324019205.3717 | 479999511.9503 | 151607295692.0331 | 1930679478.5733 | 1890584808.4479 | 1984443322.3134 | 195667881.7722 | 617359575.3188 | 709781949.883 | 767494285.1803 | 336460398.8086 | 552951199.7259 | 25467519.1415 | 129785317.2953 | 23096174.3707 | 25865160.5772 | 809777616.4627 | 29472790.0919 | 950230338.2254 | 5968335815.3068 | 587206036.4805 | 199043061.0848 | 1.545e+12 | 2592302.3661 | 1014516.7783 | 1519853.8709 |  |  | 1.7193e+12
328 | 1233883935.5155 | 1168430584.3723 | 202191029.7711 | 182006962.8273 | 1066974986.8488 | 24259729.1004 | 203812493.9464 | 294475756.3312 | 474670380.865 | 139931471082.1435 | 1799799445.8161 | 1715678573.243 | 1596894398.7381 | 149050229.1789 | 561187300.083 | 653989157.1358 | 794507357.3775 | 291035621.5014 | 603131335.3831 | 27667033.8099 | 115758554.6706 | 23196268.0859 | 20327864.8916 | 819414933.0778 | 22992431.9817 | 1075927497.1571 | 6963840394.4127 | 640284386.3018 | 198232133.6444 | 2.5854e+12 | 2295153.6978 | 891219.4255 | 1629902.4838 |  |  | 2.7483e+12
329 | 1001000215.8871 | 1223174539.4669 | 215894431.0245 | 152334103.7939 | 1054511540.6879 | 22563462.6778 | 202280338.1016 | 307690793.1442 | 464388772.0829 | 109877862825.9308 | 1897046811.6733 | 1921805004.542 | 2081780317.5484 | 179575116.21 | 553842446.5221 | 554398176.8178 | 658578921.6765 | 329050810.5972 | 582740844.3789 | 25268138.9752 | 134936666.8924 | 19500839.7598 | 24776210.0948 | 823667245.5109 | 26272391.0809 | 1099978138.9612 | 6374775642.9107 | 675120883.6176 | 178435012.7835 | 2.1075e+12 | 2345780.6679 | 957896.6033 | 1589693.015 |  |  | 2.2402e+12
330 | 1114945189.0925 | 1199457683.7916 | 213447613.9591 | 152736195.9266 | 940906697.1109 | 22606796.6208 | 216103064.9316 | 316796328.9097 | 458256086.3948 | 138225692042.9552 | 2092383294.1239 | 2024306183.2757 | 2155776958.5376 | 185465611.5399 | 633079121.6413 | 699312323.1872 | 736094907.3686 | 307763317.4657 | 576240161.871 | 24894734.5136 | 108814955.7876 | 18494940.5464 | 21913658.6777 | 855780720.8205 | 24086618.1208 | 852156416.9301 | 6460354788.4771 | 629212963.9937 | 189700152.9869 | 2.1704e+12 | 2312864.6458 | 1003231.9794 | 1577221.077 |  |  | 2.3319e+12
331 | 1048319875.7482 | 1177254391.5493 | 193077108.0176 | 139735770.8159 | 1055245664.1491 | 23964175.6768 | 214193042.0849 | 266994296.13 | 470234018.0077 | 126274599615.4502 | 1647467252.7448 | 1891782122.8347 | 2071894649.4957 | 179134807.9231 | 584748453.2976 | 674918971.2275 | 754974677.2789 | 335279584.7099 | 572311006.9051 | 28446927.2762 | 123073913.7615 | 19360364.0191 | 24072625.6113 | 789521837.7821 | 23902036.8876 | 1067592172.9145 | 7124128988.2586 | 651527342.7373 | 166345990.5046 | 2.3407e+12 | 2336228.3525 | 990321.4046 | 1721442.215 |  |  | 2.4903e+12
332 | 1243081004.9028 | 1164155557.1616 | 211109376.0469 | 167710249.6566 | 1027650192.7934 | 23532625.0715 | 213566741.7347 | 296451822.9438 | 472302982.2087 | 149699216725.2401 | 1990483124.6612 | 1914291303.5113 | 1848775578.8338 | 190361108.6483 | 501513105.1981 | 658861194.7225 | 770092549.5152 | 343684057.1055 | 583471432.5755 | 20029557.154 | 110594157.8022 | 20934551.9339 | 23880670.3772 | 806772720.4558 | 29307166.9438 | 1188768371.0172 | 7064081385.2837 | 636322748.4989 | 183836001.4885 | 2.3919e+12 | 2410406.6826 | 961093.2681 | 1781011.7297 |  |  | 2.5653e+12
333 | 1093672698.9934 | 1123251567.4903 | 195460647.0886 | 168446865.183 | 1031942920.4873 | 22383241.3955 | 199498349.5455 | 330975440.0394 | 480989197.163 | 141169298958.485 | 2033948810.5375 | 1856676302.1437 | 1811377975.9713 | 177970710.5975 | 633486442.9153 | 717792013.5186 | 714092008.6015 | 250487216.882 | 556504574.6117 | 20669449.2863 | 120317783.5428 | 20476935.4959 | 24842123.2185 | 801441979.2578 | 27458979.9942 | 1069894670.2882 | 7181245770.3864 | 663662804.4054 | 198159081.6088 | 2.3275e+12 | 2552434.9091 | 997781.5681 | 1585238.7713 |  |  | 2.4922e+12
334 | 1231589368.354 | 1101758161.824 | 191948174.3284 | 152266625.1521 | 1085874523.9454 | 21005164.9747 | 190166890.4173 | 299797098.7038 | 478277524.9188 | 147015157548.0374 | 2028439134.3812 | 1868874457.5508 | 2183386323.3276 | 202671776.1827 | 578640789.1378 | 710181248.7741 | 925533982.405 | 332937882.437 | 551375615.4034 | 27467550.3893 | 116172263.6883 | 23776633.3811 | 22204235.5309 | 716120057.6921 | 28339060.7562 | 1183766391.5576 | 6936160075.9978 | 691536652.6289 | 198893897.606 | 1.4801e+12 | 2285246.1198 | 987634.567 | 1565239.5521 |  |  | 1.6512e+12
335 | 1075192920.8782 | 1085784844.5163 | 203587541.1736 | 178318045.7537 | 980164234.0392 | 22065563.3688 | 181727959.8611 | 303937802.2526 | 499492510.949 | 126598179359.0679 | 1505774429.2613 | 1652031827.6959 | 2140242725.7361 | 190344897.8784 | 611400804.893 | 645741750.2923 | 831004985.6487 | 331397233.0232 | 596167504.0929 | 24973892.7992 | 116366028.3326 | 21400404.1562 | 24361303.3413 | 718974378.8044 | 23552078.4054 | 1140671945.8824 | 6729322615.2194 | 693704728.5559 | 183203724.2273 | 1.8642e+12 | 2462913.9228 | 982646.481 | 1548718.5502 |  |  | 2.0135e+12
336 | 1227035167.1244 | 1142738272.7359 | 205627307.9418 | 181777254.5975 | 1082106377.6396 | 21679649.7878 | 211034348.1407 | 276102552.6681 | 401956570.0726 | 129066611203.0647 | 1830858839.8635 | 2044854902.2254 | 1703894751.7604 | 196393965.4599 | 441316876.6688 | 578535522.2072 | 786988980.0164 | 294589011.9775 | 604252527.5892 | 22009698.6402 | 101234379.509 | 22492583.7379 | 25811643.1523 | 700729660.3688 | 30879817.9076 | 1146290847.2059 | 5654093422.523 | 686854739.4863 | 201133712.7362 | 2.5505e+12 | 2405694.5687 | 938670.1566 | 1611180.7616 |  |  | 2.7014e+12
337 | 1239807894.7572 | 1128314860.6704 | 180872452.3978 | 158667807.8576 | 1070120105.4553 | 24139149.9656 | 221766089.137 | 318141537.6455 | 485928803.8498 | 154140293300.7229 | 1963755057.83 | 2069098968.5443 | 2028064965.5602 | 196879865.4395 | 635215134.148 | 567917016.7738 | 773500229.153 | 359308178.435 | 565031267.9519 | 24434328.3575 | 103981176.023 | 22638674.1087 | 24340369.9433 | 766887092.7342 | 22706923.2291 | 841309170.1328 | 6352321983.3393 | 627216162.9397 | 136157894.0534 | 1.5161e+12 | 2560503.1693 | 934814.1589 | 1726007.4248 |  |  | 1.6932e+12
338 | 1042766200.8015 | 1175463508.4635 | 211679048.5002 | 169041399.6648 | 1020744804.0655 | 21077715.1053 | 190633910.9682 | 324586728.4862 | 465900981.2653 | 139008235600.7199 | 2034391761.2577 | 2136190829.036 | 2172535937.2393 | 202000595.7145 | 608407537.3232 | 599212913.481 | 811935784.5721 | 315686418.5011 | 612763825.06 | 22848851.5333 | 124452303.4806 | 20216607.0312 | 25255812.9277 | 824476530.6902 | 27035549.993 | 1080885089.0189 | 5976807093.322 | 662550166.0182 | 196725637.366 | 2.7338e+12 | 2393176.0655 | 947836.8573 | 1786972.7806 |  |  | 2.8959e+12
339 | 1210636430.7019 | 1177474279.6982 | 222445903.0156 | 176789162.0409 | 898394296.4444 | 26498289.0797 | 206782651.0282 | 323790332.1477 | 459563871.8206 | 155847677004.4459 | 1811830208.1349 | 1949403517.5392 | 1884337209.1896 | 161357145.6267 | 608207312.9442 | 713108636.0175 | 846271451.7563 | 358231901.8302 | 544112767.4102 | 25791633.8907 | 121931867.1599 | 23162660.2233 | 22940664.7587 | 850514925.0106 | 29353806.6347 | 1187418137.7987 | 6326589378.6216 | 634196575.746 | 185246194.3891 | 1.7326e+12 | 2309351.1094 | 952330.5288 | 1690914.9743 |  |  | 1.9114e+12
340 | 1204049848.9636 | 1124779521.1031 | 202210760.3072 | 171526117.7296 | 1031400887.7724 | 24491383.3498 | 206457535.5062 | 314641458.8222 | 417702760.1008 | 135129100608.9356 | 1877357071.1176 | 2016386472.0331 | 2039937743.8285 | 152761245.8549 | 639282664.0967 | 651824322.5712 | 720514958.3444 | 357331876.7755 | 579255250.1262 | 23000900.4357 | 131994010.6446 | 21564942.2227 | 24777394.7507 | 777447249.0897 | 28675921.9944 | 1149930548.221 | 6109202441.72 | 672060993.9571 | 166412301.1535 | 1.9731e+12 | 2343835.755 | 924117.2034 | 1650033.9506 |  |  | 2.1311e+12
341 | 1191104935.8978 | 1229152866.2116 | 186812233.9827 | 139868950.5528 | 1056577511.8792 | 24138062.9859 | 204316610.2057 | 297817667.6947 | 485260128.6038 | 138608743849.9893 | 2079962896.7999 | 1745569280.2486 | 1940835546.0669 | 165387485.3295 | 644351431.5702 | 696919218.1968 | 856171496.3072 | 315535381.264 | 558045812.084 | 23094900.1491 | 129062018.6283 | 21739385.3301 | 24178223.1118 | 838964824.5656 | 30443289.7035 | 1210339531.6281 | 5399727823.7578 | 685026287.3722 | 198097911.6773 | 1.5529e+12 | 2489138.1107 | 907008.7121 | 1658261.1843 |  |  | 1.7139e+12
342 | 1022085347.1899 | 1213386979.5721 | 195332753.8992 | 168507507.1248 | 1083191929.5533 | 20306528.8299 | 201792864.1373 | 323531724.6571 | 454345147.2276 | 144680535841.6141 | 2001631813.4134 | 1940521512.181 | 1895586445.0373 | 177917620.9122 | 629319249.468 | 680377412.0308 | 887038699.9368 | 316258840.5908 | 598367766.3977 | 24580020.8386 | 109920724.6923 | 21946809.0132 | 17719676.0892 | 899967576.5445 | 23191981.1461 | 1043600466.9191 | 7153106077.219 | 551994786.9575 | 196358761.429 | 2.3975e+12 | 2637685.1944 | 954732.6247 | 1778742.7155 |  |  | 2.566e+12
343 | 1202959583.1505 | 1219640473.1963 | 201077730.9093 | 179133782.8371 | 981435535.4089 | 21463225.7456 | 198923732.5248 | 316562727.1289 | 431305705.6652 | 154670739687.9143 | 2089449728.9111 | 1968903688.7662 | 2094893321.1516 | 199353407.003 | 569107831.6335 | 688484964.0803 | 685575789.0134 | 334672382.4652 | 564490183.2579 | 24019668.2732 | 112654689.9229 | 20411777.068 | 24266175.104 | 741729697.1114 | 26193207.0937 | 1036775739.1438 | 7179539672.348 | 562982523.2887 | 187286249.589 | 2.4258e+12 | 2550963.4766 | 887308.3393 | 1640534.7615 |  |  | 2.6044e+12
344 | 1228447200.4514 | 1085716565.3233 | 217633634.3278 | 167918133.5197 | 1042503177.0823 | 26165979.8813 | 186183629.6011 | 299591525.9271 | 418073054.4358 | 144905196132.0264 | 2042833539.3327 | 1887439143.8941 | 1999057494.8345 | 188311873.3753 | 541891682.6123 | 723249399.1164 | 880373319.0673 | 320987350.7401 | 539268233.4971 | 25616966.7336 | 121986592.5779 | 21309497.3028 | 25099192.6527 | 868534042.7426 | 26205776.0234 | 999190561.6467 | 6688505949.9712 | 654125312.4293 | 133808141.3211 | 1.4886e+12 | 2518527.721 | 940530.1535 | 1641920.1461 |  |  | 1.6569e+12
345 | 1246018091.7933 | 1223042951.3246 | 205386253.2126 | 175426853.3021 | 1056758647.5309 | 24266785.9424 | 225178123.5965 | 307750661.3236 | 449897692.2742 | 144029849984.2753 | 1763160205.0065 | 1970411188.8361 | 1767702093.1525 | 196082235.8082 | 500363063.3259 | 603991523.4784 | 822459632.6331 | 309463109.4702 | 614841663.2539 | 25964709.8973 | 113060585.747 | 20370109.7303 | 25493359.0841 | 915010884.4319 | 24681166.5318 | 1020155508.7158 | 6250342463.0452 | 647605466.876 | 200194969.1581 | 2.6624e+12 | 2519009.3256 | 976622.964 | 1749638.4761 |  |  | 2.8291e+12
346 | 1185522041.6089 | 1222227516.2662 | 199055416.3256 | 163409573.871 | 1068016735.6981 | 26347538.2757 | 215608985.7055 | 285847774.1597 | 469867449.2537 | 144689485522.1853 | 1845604732.8203 | 1560548720.0366 | 2000845255.6945 | 180066919.1743 | 666983051.4293 | 550057625.8104 | 860171997.1813 | 322729085.4382 | 586599449.9674 | 21849076.3618 | 126167609.3471 | 22713419.088 | 24764351.9299 | 722752961.6772 | 28492619.7279 | 1145569462.9708 | 5847963258.5204 | 632933625.7781 | 180135983.6349 | 2.2056e+12 | 2507464.1078 | 935705.5771 | 1680097.9279 |  |  | 2.3724e+12
347 | 1198208161.1349 | 1017950425.5161 | 202836988.5088 | 163622098.9607 | 1069391267.5263 | 24265541.948 | 220220861.2441 | 320388971.9421 | 466091344.0474 | 150511558818.2938 | 1863950985.6219 | 1744962117.9959 | 2120740568.7399 | 159588468.0727 | 649103972.2542 | 695719628.9604 | 890561703.3175 | 247802513.1504 | 572999295.2017 | 25094040.2124 | 131130057.5932 | 21415252.2528 | 23250338.6294 | 930689918.7051 | 23649118.3006 | 1205115065.0589 | 6470917596.0635 | 692668202.3508 | 197108950.7051 | 2.1459e+12 | 2383672.4456 | 976882.2718 | 1610947.0969 |  |  | 2.3198e+12
348 | 1227861531.6404 | 1091028818.6821 | 205474802.8943 | 153189441.479 | 1039971463.9682 | 24523194.6981 | 221219742.1442 | 328311962.8435 | 471802792.6576 | 132922377379.3108 | 1873852861.7458 | 1985910509.1472 | 2023042970.4097 | 200071863.3775 | 522302904.3663 | 627265842.2123 | 829652804.3277 | 320588519.1652 | 556860383.3539 | 22723670.676 | 129622981.4099 | 17939510.1307 | 24680476.5934 | 948220303.1939 | 28300487.2528 | 1062164099.9949 | 7187386752.9289 | 685626339.5589 | 192825838.8524 | 1.9643e+12 | 2550350.7523 | 936205.4209 | 1563212.0909 |  |  | 2.1212e+12
349 | 1197460645.8654 | 1145751660.4659 | 205853609.1587 | 176526443.0031 | 833543588.5085 | 25849170.9089 | 217171762.7456 | 322602447.226 | 469596301.8847 | 142339786630.5975 | 1974784762.1549 | 1934075367.2417 | 2060741561.7745 | 158834652.2766 | 648911048.3156 | 657803353.4854 | 827506852.8385 | 345023248.8111 | 611647796.6128 | 23070381.1822 | 105129253.2433 | 21097759.5231 | 24063092.4243 | 861176192.2798 | 28983861.7204 | 1103562708.3372 | 6926964308.6358 | 660664386.6462 | 195015069.4747 | 1.8549e+12 | 2362280.5051 | 910836.2278 | 1721182.2443 |  |  | 2.0211e+12
350 | 1181994785.3499 | 1170163325.6295 | 202365048.3011 | 152655558.2105 | 989429954.3015 | 20692537.2135 | 220281616.7146 | 314551529.4491 | 496510450.798 | 128275877475.9096 | 2007572680.636 | 2094049235.1223 | 1944530394.7339 | 191526279.6706 | 664061550.9694 | 693035689.7928 | 712130029.7448 | 321300525.8662 | 601890187.9655 | 26371862.5967 | 106593757.0998 | 19901992.8163 | 20403739.6039 | 911897949.7963 | 25908336.4052 | 1179793664.5768 | 6178570728.7556 | 674809643.4752 | 192672346.4713 | 2.5858e+12 | 2247137.918 | 922133.9461 | 1617299.9411 |  |  | 2.7374e+12
351 | 1155193530.4591 | 1186260538.2157 | 216596201.5155 | 164795047.7227 | 1053741226.2332 | 24857123.6813 | 196855060.3328 | 297495953.9942 | 493654557.6171 | 129614440702.066 | 1701968721.9468 | 1645479144.8574 | 1439619531.0436 | 177064616.8314 | 628385844.9415 | 615209105.0137 | 779845981.2244 | 356191021.474 | 583465939.0999 | 27341903.8 | 110415146.4052 | 23689390.5162 | 19429945.9829 | 942630818.6055 | 27731372.0992 | 878952618.6487 | 6588342382.9822 | 642393400.2043 | 193797511.3454 | 1.9928e+12 | 2372409.5086 | 964290.4296 | 1577463.1595 |  |  | 2.1446e+12
352 | 1229118551.576 | 1222210550.7433 | 188566605.5659 | 172039357.5186 | 1070077695.5365 | 22155408.3419 | 215983012.5082 | 326321857.1646 | 452986819.1914 | 140929717288.7144 | 1988944014.3255 | 2071179976.708 | 2130069674.1299 | 166016135.3917 | 639018063.3051 | 659922690.9211 | 824668108.6351 | 282180378.5828 | 613753273.9996 | 19463999.292 | 97824942.6161 | 20773504.9552 | 23284223.3409 | 870116624.739 | 31404092.2304 | 1027067426.609 | 6529901118.6431 | 690307163.6171 | 199539425.2932 | 2.2624e+12 | 2326106.9865 | 967886.659 | 1628234.7692 |  |  | 2.4271e+12
353 | 1179805173.9747 | 1224814531.2454 | 190537649.5741 | 175607674.4092 | 1048744204.4464 | 25819906.1425 | 205524453.0438 | 305946003.3374 | 433264031.6873 | 132765311516.7243 | 2010961253.3072 | 1992487565.9436 | 2174665195.888 | 201475242.3003 | 579883676.0345 | 578982294.4625 | 844414043.493 | 325056979.0365 | 519688311.836 | 26860071.1672 | 108693693.9072 | 23068367.1438 | 25302614.9232 | 916436283.7235 | 26759900.8941 | 1113097453.5958 | 5503427826.1066 | 583620984.2571 | 200562803.7689 | 1.52e+12 | 2775788.6913 | 963935.2008 | 1592623.8129 |  |  | 1.6753e+12
354 | 1148158393.735 | 1228643411.56 | 222252715.1767 | 181646766.8775 | 961559862.1486 | 20179805.0459 | 223931081.1062 | 290686446.675 | 472952305.5529 | 123415366471.7708 | 1850497358.6964 | 2000814447.1564 | 2029393397.0262 | 191114695.1498 | 640818293.9733 | 639203007.7732 | 801949474.6741 | 319198224.4411 | 422225941.4976 | 23064438.5561 | 112718793.2434 | 23233975.1725 | 17473765.5658 | 868115758.7422 | 29901149.5184 | 1086601546.0454 | 5863082906.5565 | 592905577.4497 | 185657794.2125 | 1.7139e+12 | 2401667.8162 | 980133.7196 | 1707556.0091 |  |  | 1.8598e+12
355 | 1080592524.1956 | 1138011746.6919 | 217794363.4805 | 154335344.9227 | 1048981130.4598 | 18631562.6298 | 223109962.6262 | 294203393.1575 | 484045322.7213 | 128745765511.5653 | 1832967248.2444 | 2017969857.582 | 2193073963.6157 | 190721623.1958 | 625640735.7616 | 572027513.5072 | 699910480.5782 | 332920962.9589 | 615036592.3242 | 26500434.8739 | 111929135.6395 | 24427497.415 | 20661347.3517 | 952733450.687 | 20531069.3486 | 1148771783.2998 | 6477337643.2918 | 642704826.2746 | 200634468.9142 | 1.8679e+12 | 2450446.544 | 1012754.424 | 1618624.118 |  |  | 2.02e+12
356 | 1166869567.3797 | 1226793209.9117 | 212420640.2434 | 153240055.2124 | 844265683.7487 | 21212977.6074 | 224216467.2076 | 273557194.649 | 473519446.7872 | 151836924420.8744 | 1807612048.402 | 1633452614.2985 | 2062564298.1131 | 185355568.304 | 650419944.6673 | 594769909.3807 | 770009909.4324 | 347843325.1481 | 593923134.5815 | 27186023.6301 | 129836851.7768 | 19436381.0166 | 23238783.2542 | 822556141.3348 | 25041528.6829 | 1117715287.5135 | 6587123218.6418 | 700293433.2442 | 174921871.8881 | 1.686e+12 | 2524558.3419 | 982359.5625 | 1703338.0656 |  |  | 1.8607e+12
357 | 1210468131.462 | 1113263791.8486 | 220158817.6985 | 176959075.6603 | 1071642817.4123 | 26175883.2177 | 190586873.1113 | 300629758.7579 | 487730303.4431 | 151602063147.5716 | 1557178134.1435 | 1961648331.3669 | 1882362407.5215 | 192426580.5419 | 663586743.8494 | 623035103.1609 | 816048574.1189 | 303483106.8884 | 607755226.9484 | 20900465.5233 | 134623780.6751 | 21600134.6269 | 25443502.699 | 925780147.043 | 31177765.6905 | 999914859.7831 | 6026025780.9759 | 684683794.7141 | 198984931.0903 | 2.3457e+12 | 2523843.162 | 1003414.5141 | 1769533.4521 |  |  | 2.5198e+12
358 | 1157235664.6745 | 1073735561.9887 | 215758884.4865 | 178025433.8917 | 1074013555.2468 | 21145115.095 | 202778412.3226 | 320953334.5592 | 496891652.7527 | 123719551489.4111 | 1942890275.009 | 1953500009.3711 | 2053364965.8416 | 186001552.5535 | 568127670.5032 | 637064287.6522 | 740485212.5638 | 354282657.6385 | 606450098.6655 | 27636708.3517 | 108053518.2349 | 24497657.9616 | 22101080.247 | 853177931.9443 | 24996477.4507 | 1015218854.928 | 6244181767.8078 | 674762529.8869 | 157877159.753 | 1.6648e+12 | 2506444.5894 | 970433.0277 | 1698846.0995 |  |  | 1.8115e+12
359 | 1108016560.7076 | 1167304620.0016 | 208223622.0172 | 161911375.8928 | 1018887178.1859 | 24810389.5317 | 215858169.5779 | 318982657.009 | 469538184.9026 | 142106191202.2531 | 2042904898.1271 | 1682214668.3327 | 2172925883.9867 | 200855411.2399 | 626117621.4067 | 615410193.6214 | 811419535.4663 | 327946460.0161 | 550359622.2687 | 23533565.8678 | 102946796.1219 | 21930420.2979 | 23225762.9482 | 760790700.0282 | 26577692.0322 | 1197718484.5691 | 6260727727.3251 | 564847546.908 | 200651450.3887 | 1.891e+12 | 2250698.7769 | 948603.5254 | 1621732.4899 |  |  | 2.056e+12
360 | 1181211292.1306 | 1146082913.9863 | 222544792.8594 | 161843728.5217 | 1082522464.1693 | 21409688.926 | 200904522.6769 | 305811635.0454 | 450768833.1613 | 117078862974.9009 | 2059865717.6876 | 2197856922.1528 | 2009162086.9684 | 193343399.368 | 624113298.6638 | 722651560.9209 | 871337459.8953 | 251103925.1687 | 566893672.9558 | 22276867.4848 | 107972554.4099 | 23370192.8563 | 21751639.7875 | 831636639.3377 | 24030861.2723 | 1137808040.1337 | 5955021183.4244 | 673888334.1113 | 194740159.1113 | 2.2327e+12 | 2711310.7434 | 959146.0963 | 1655861.9801 |  |  | 2.373e+12
361 | 1225515972.5374 | 1168092223.3514 | 191996180.1045 | 169402424.5998 | 1079570507.381 | 21217436.8276 | 217648811.4603 | 323275208.2395 | 464200500.51 | 150266885670.0136 | 2063734040.9748 | 2108925751.6532 | 2105140219.4781 | 201630727.961 | 604203592.6797 | 701703673.6135 | 825071719.1096 | 302568606.466 | 580304579.4498 | 25150934.0906 | 127474439.0348 | 23694847.2418 | 23521951.8788 | 869074687.2999 | 29426284.0031 | 1167168388.3047 | 6793088950.0728 | 654878704.361 | 200988349.6653 | 2.1871e+12 | 2373095.6357 | 987034.6944 | 1455028.3629 |  |  | 2.3617e+12
362 | 1164256966.9642 | 1223601958.3451 | 213350343.103 | 166144594.9444 | 1028228147.5999 | 25677718.9469 | 219126165.2914 | 271911831.1798 | 472228044.4253 | 132151931603.7163 | 1873525972.6535 | 2101499599.9264 | 2020554473.2237 | 192105492.6643 | 556109732.0152 | 606955406.9384 | 895265922.6329 | 302261519.5366 | 600841008.2022 | 20246403.3979 | 131130532.6707 | 24492280.0184 | 22232781.6959 | 887396554.0426 | 29985174.0793 | 1099774858.4265 | 7097418864.859 | 625745845.2925 | 186505868.1554 | 1.9533e+12 | 2418082.6796 | 928282.8411 | 1663298.8602 |  |  | 2.1095e+12
363 | 1209926137.4183 | 1194701979.1811 | 217865132.7898 | 180933675.2041 | 983081680.8851 | 26297905.886 | 213296609.2891 | 317702724.3344 | 469082787.9538 | 140503574879.6122 | 1713963736.0895 | 2075538879.3526 | 1953655291.8163 | 172391429.9928 | 585116275.9544 | 711989515.4164 | 903541893.2453 | 277687492.1979 | 518814502.4844 | 21091342.2745 | 109565398.2828 | 21628379.7544 | 24002467.4786 | 754644293.7215 | 20751379.6099 | 1126403295.6064 | 6352383671.0761 | 668947967.4389 | 194143179.2743 | 2.1433e+12 | 2690463.8613 | 964309.4671 | 1656933.8458 |  |  | 2.3068e+12
364 | 1019551999.2 | 1212237822.3964 | 220540286.1553 | 173676167.2041 | 939604408.9795 | 26868957.4549 | 219427003.6043 | 322137028.8434 | 409739354.0888 | 134993139822.5119 | 2005220691.4339 | 1520282817.5099 | 2195570467.4118 | 159740044.3392 | 586244060.1487 | 524124472.5098 | 741838534.1758 | 324524722.5092 | 540183067.6349 | 26525814.6319 | 105952329.4455 | 24248301.3116 | 24986245.2786 | 873801654.0898 | 30357199.4734 | 968874903.3493 | 6441585077.2755 | 699419318.1235 | 192929925.8481 | 1.6319e+12 | 2474702.2524 | 1000435.1721 | 1584665.5191 |  |  | 1.7894e+12
365 | 1188478450.7337 | 1225654835.1004 | 199497978.566 | 179829958.2285 | 1050174089.0374 | 19314589.7033 | 211225931.4014 | 321357954.9703 | 455493583.0756 | 116228792745.7934 | 1776028033.5097 | 2152283162.9726 | 1927453542.7994 | 194523842.5808 | 434689680.723 | 719714247.1464 | 850653100.8974 | 286976069.0901 | 562723045.3133 | 26689947.9848 | 107202545.434 | 23206598.3213 | 23335172.218 | 864668759.9947 | 28548283.9217 | 949339686.7376 | 6931960096.6726 | 564348641.0072 | 179440834.1105 | 2.6241e+12 | 2394320.2481 | 982383.4067 | 1586519.6877 |  |  | 2.7638e+12
366 | 1081745621.8147 | 1203724975.025 | 208360721.2984 | 177566488.1073 | 1037073335.2029 | 22995332.4524 | 222598393.053 | 327000654.3921 | 459400859.1898 | 129158352603.0557 | 1877338153.0377 | 2019011189.986 | 2166960985.0138 | 197665159.9973 | 639387049.3578 | 699277363.1839 | 806098617.8075 | 281347396.2745 | 568083587.7988 | 23944774.5949 | 119479590.2706 | 23478774.3093 | 25651413.6843 | 830303201.7423 | 26472606.28 | 1123734692.7247 | 6035664213.0196 | 700634384.6116 | 193332326.1561 | 2.0435e+12 | 2626232.4378 | 942160.1557 | 1675643.3482 |  |  | 2.1958e+12
367 | 1259497926.3975 | 1165743631.4119 | 189832602.008 | 173711923.2778 | 1068280325.6509 | 24261513.8218 | 216164517.369 | 328183237.6377 | 498787709.7425 | 130274111844.1779 | 2080071796.1042 | 1642087143.7782 | 1888205968.0464 | 187535236.6727 | 564505684.745 | 672640431.0869 | 598793027.4539 | 330817303.5301 | 572477099.1424 | 19045366.0088 | 107598097.9129 | 22680139.3328 | 25003225.1258 | 934727601.6725 | 25537177.0422 | 1177439311.8191 | 6603532388.1598 | 466284984.4284 | 169276215.4795 | 1.7791e+12 | 2697234.3248 | 904610.0859 | 1711321.9719 |  |  | 1.9324e+12
368 | 1098551684.3782 | 1184254270.5898 | 219678939.7155 | 168784575.0531 | 1085098662.0222 | 23247409.6254 | 210839039.9325 | 323968878.7653 | 489700443.2233 | 151155420134.4428 | 1906713633.9124 | 1965650895.1752 | 2133408075.9148 | 183464931.5508 | 463310583.6001 | 512266960.2025 | 780686835.6303 | 273473584.7042 | 607171444.3144 | 21208930.119 | 108712749.1404 | 24599320.141 | 22398058.4843 | 747922758.041 | 30859247.0999 | 1144933622.7455 | 7158867502.7705 | 646287027.6335 | 164611670.8172 | 2.5317e+12 | 2461367.6437 | 990897.8193 | 1545490.9143 |  |  | 2.7065e+12
369 | 1078858922.3483 | 1196254291.8803 | 209122984.923 | 181132387.1718 | 1085316280.4061 | 25270793.5714 | 185618944.7592 | 317078379.0124 | 454296866.3744 | 152553141736.1956 | 1972362117.2977 | 2106453352.1091 | 2164881167.4962 | 192531811.9791 | 677374102.2733 | 619380473.5432 | 741543912.2717 | 318878777.8816 | 587009690.3914 | 24530142.1031 | 115325178.1132 | 21926071.6657 | 17666464.3384 | 887006892.7116 | 27274712.7828 | 1190516084.9665 | 6287448393.0957 | 706856418.6518 | 184124797.6794 | 2.2839e+12 | 2544063.6887 | 934069.2134 | 1505484.7078 |  |  | 2.46e+12
370 | 1240978744.5216 | 1213424226.5209 | 213731412.3413 | 173349025.4617 | 1084314221.0909 | 28677290.1973 | 222587063.3606 | 301935973.7459 | 439107664.6268 | 130412121618.9924 | 1714710220.3599 | 1844988530.6725 | 1971309256.5857 | 193286416.3787 | 580390063.912 | 628955638.2378 | 855399157.2092 | 321053211.7176 | 548293130.4039 | 24178140.9873 | 117766614.4099 | 19223539.4035 | 21874116.4003 | 805805436.3297 | 27375106.9507 | 1044337534.172 | 5781085019.798 | 640294702.5201 | 144627128.1657 | 1.7735e+12 | 2798395.2074 | 915530.0345 | 1646860.6826 |  |  | 1.9261e+12
371 | 1077925367.2249 | 1123623028.9645 | 216252817.6459 | 163285275.4595 | 1013732088.217 | 22733800.0503 | 197286452.8848 | 302680470.9377 | 489178241.9688 | 135954115444.8391 | 1904270928.1442 | 1980947825.145 | 1662688957.1555 | 167658907.9317 | 595598207.1334 | 630115763.7421 | 768436531.307 | 329194896.8715 | 534087394.146 | 26810843.3139 | 110007140.0771 | 22198670.1787 | 23720663.7586 | 808810418.8124 | 24579031.6834 | 1185540846.3333 | 5651130428.3771 | 553087095.0169 | 192578110.3869 | 1.668e+12 | 2812365.6603 | 932291.556 | 1734111.8604 |  |  | 1.8257e+12
372 | 1133399731.066 | 1150360113.9143 | 203369905.2108 | 162701146.2097 | 1027881776.2223 | 19374510.731 | 221780673.8349 | 291731421.8666 | 440097102.1174 | 154478698027.599 | 1986987890.9164 | 1913915664.5043 | 2145076263.6421 | 177635028.1229 | 579502433.8866 | 624144485.0741 | 764543826.9036 | 326165959.1937 | 605420544.4475 | 26485068.2453 | 121219945.2891 | 19948696.9664 | 25365906.0214 | 836250634.0919 | 31350672.4263 | 1052056956.3995 | 5657360629.8338 | 536274390.7418 | 191868725.5748 | 2.0981e+12 | 2694115.6689 | 945369.9687 | 1758934.6931 |  |  | 2.2748e+12
373 | 1063631235.4652 | 1193334765.2453 | 222517288.6091 | 161406730.5497 | 946160610.0669 | 21620729.8222 | 226221826.0669 | 319813667.6751 | 497905176.8296 | 140333138677.4575 | 1675800065.1957 | 1985877448.3032 | 1973506329.03 | 186459992.5149 | 590801037.3178 | 701858113.4397 | 822245230.797 | 298539857.7811 | 577532014.6219 | 19486804.9632 | 116788347.4174 | 19510525.5832 | 25158776.5581 | 829112874.1761 | 22049256.1202 | 936594352.2866 | 6868804096.2097 | 555194615.4647 | 187551108.1717 | 1.5462e+12 | 2515136.0338 | 1010585.7841 | 1532179.6612 |  |  | 1.7096e+12
374 | 1121886823.6046 | 1148016979.7366 | 197337605.3384 | 156325436.6551 | 1067327728.3662 | 23814891.9936 | 215557829.9462 | 330041154.8644 | 485613770.6821 | 129555530043.0181 | 2035729773.994 | 2048760516.8585 | 1907324627.272 | 202133614.3452 | 499619786.1847 | 693395057.7881 | 804018743.6089 | 331584912.8466 | 576898901.6495 | 24872625.7915 | 131491255.3445 | 23328571.0025 | 25821749.1816 | 838431367.4572 | 29312354.5614 | 1031241707.0646 | 6354761181.9172 | 598700818.9648 | 190286294.3056 | 1.8747e+12 | 2291057.2617 | 946010.506 | 1625616.2504 |  |  | 2.0273e+12
375 | 1178949596.4795 | 1201895784.4969 | 210022700.0975 | 176440526.3432 | 1062631962.5821 | 26133733.5015 | 212633605.587 | 328628579.6487 | 487276617.5587 | 137596922063.2659 | 1929873396.5266 | 2028336624.0509 | 1970982332.8494 | 192604826.3984 | 613835936.9806 | 658858175.6871 | 733841706.1544 | 341014857.061 | 515198920.948 | 25231826.346 | 93129920.9955 | 20196759.8001 | 21790912.7158 | 725545319.8736 | 26567129.6917 | 1166303586.0282 | 7133557669.594 | 662528400.6105 | 155145370.7492 | 2.2603e+12 | 2686982.5795 | 915722.5605 | 1645410.7601 |  |  | 2.4218e+12
376 | 1252406181.0786 | 1216591720.9202 | 176171972.4464 | 176112644.7422 | 1041996067.7527 | 24703206.1496 | 221345728.5034 | 318115284.9405 | 472131754.3559 | 149844857793.6471 | 1790317127.547 | 1837955079.9303 | 1837956432.056 | 194061705.1733 | 585446287.9502 | 612176758.559 | 762105929.1553 | 326288984.8265 | 577019250.9289 | 23443950.5871 | 127258666.5355 | 24831800.0404 | 24454981.5778 | 760532238.7358 | 24727377.0639 | 825550492.2993 | 7076961431.6216 | 651034653.9182 | 180196491.5853 | 2.1717e+12 | 2561949.7096 | 913764.3168 | 1892737.1607 |  |  | 2.3447e+12
377 | 1024950780.8616 | 1093910033.6021 | 204732222.474 | 165217084.5831 | 986072521.7323 | 23717938.6066 | 219102607.7695 | 292454487.6655 | 485506676.3524 | 156046829484.173 | 1601932218.8432 | 2091029246.0741 | 1950691790.0257 | 190808972.1639 | 680954248.5021 | 603285620.8427 | 845236816.2814 | 289686506.7741 | 570757364.8893 | 25892425.5599 | 110192184.5955 | 22869376.1635 | 22348934.113 | 808641009.741 | 25909757.4426 | 1085197992.056 | 5569429144.2188 | 596957072.3001 | 187999420.8371 | 2.3726e+12 | 2664928.094 | 949635.0267 | 1723384.9934 |  |  | 2.5504e+12
378 | 1231224273.6087 | 1089397618.6483 | 211592942.2322 | 161294375.0205 | 1083461315.5995 | 22977975.4237 | 201486978.8187 | 281975333.5435 | 499460901.0296 | 145169062050.9724 | 1997152237.0167 | 1760330596.8468 | 1982688709.4787 | 196021406.0823 | 543685919.0007 | 635442455.679 | 812236037.8911 | 299389614.7575 | 606505657.7106 | 21459594.7011 | 119632977.1619 | 18856508.88 | 25211673.1856 | 897331399.4086 | 27175662.6093 | 947888144.6606 | 5037183055.7881 | 495946765.9057 | 194688332.6044 | 2.168e+12 | 2348346.3838 | 967867.2719 | 1517863.9899 |  |  | 2.3346e+12
379 | 1131805490.0601 | 1226974448.6769 | 194819228.262 | 167315693.7449 | 1051623310.3004 | 21626622.6333 | 209836166.0441 | 314066084.3833 | 478756805.0436 | 137563226779.3085 | 1726480198.1458 | 2047856687.1259 | 2132579754.8389 | 142104346.7905 | 593965504.3049 | 705933332.8848 | 889590917.314 | 360398416.1679 | 532069345.1768 | 23666334.8293 | 113852656.7693 | 20109412.8615 | 23987649.9119 | 907311621.0002 | 29441472.7996 | 1221791649.3642 | 6627187268.2036 | 611752066.7453 | 194911547.1044 | 2.1028e+12 | 2166168.731 | 1010756.1727 | 1639011.617 |  |  | 2.2641e+12
380 | 1225688712.3901 | 1228858132.0683 | 212385074.962 | 147342835.8219 | 988518290.9056 | 19978541.1396 | 210755128.6414 | 277157761.8723 | 462255725.9027 | 139164399876.325 | 1968323167.5828 | 2063001874.1104 | 1838363931.9875 | 179441782.8027 | 550747477.1124 | 672120572.0309 | 770063523.784 | 329003172.064 | 552034106.4243 | 25142953.9195 | 114381188.7955 | 24321427.6696 | 23188923.5009 | 787381731.0811 | 28584262.348 | 1062911369.3897 | 6486837755.3157 | 590241661.5558 | 184652177.3229 | 2.0177e+12 | 2876909.1499 | 954432.1986 | 1574345.9183 |  |  | 2.1799e+12
381 | 1205309703.8425 | 1131320023.5853 | 187696740.6421 | 168053889.9605 | 1025542563.7946 | 22002896.8544 | 211480426.6329 | 311738590.1386 | 457116897.6849 | 157273465393.1122 | 1877818364.4733 | 1876684461.0508 | 2178983798.4142 | 201260589.1253 | 637764001.5454 | 507477513.4736 | 671341814.4727 | 335970715.6682 | 488525706.7078 | 27585197.1108 | 111367280.257 | 24224359.7971 | 25042539.9358 | 884384812.587 | 23349214.8947 | 1052125763.8271 | 5862967705.9628 | 567960740.4904 | 199232326.8747 | 2.5765e+12 | 2550137.8242 | 881816.5678 | 1701458.0379 |  |  | 2.7561e+12
382 | 1157694011.4287 | 1217180037.8327 | 224826209.9867 | 162251303.3614 | 1030442278.4369 | 19948799.9647 | 205494490.0357 | 301912023.3674 | 467225265.818 | 161094340276.428 | 2036913321.4221 | 2135261364.9047 | 1710909245.8585 | 181515797.7677 | 618817054.7122 | 702426504.8367 | 824623372.4157 | 351976208.4512 | 581867749.7298 | 24040500.4179 | 124265580.5633 | 23098598.7901 | 25994768.2477 | 844625478.8485 | 27367919.1434 | 1129639640.8939 | 4649371267.0012 | 639429239.0138 | 159613106.1516 | 1.6655e+12 | 2392411.0964 | 944244.7697 | 1602782.751 |  |  | 1.8482e+12
383 | 1077465773.8498 | 1219488123.3737 | 223800871.295 | 174191511.1504 | 1075140893.5318 | 23635887.5652 | 223668183.8859 | 291751240.9855 | 497434385.2994 | 147526693518.5844 | 2059981566.1691 | 2024743986.4523 | 2079054004.4768 | 127970959.4455 | 620633540.9022 | 634281907.8829 | 774014014.6854 | 274691375.9343 | 583261983.9927 | 27501242.8003 | 95984848.5359 | 23340178.3148 | 20496678.035 | 851815525.2208 | 25679736.4822 | 920094221.7063 | 5195115672.6502 | 459892057.529 | 184980520.7578 | 1.6678e+12 | 2497825.5218 | 936449.3369 | 1518929.0823 |  |  | 1.8371e+12
384 | 1202646729.5791 | 1168444907.7891 | 195938456.6705 | 170015763.7729 | 1058433230.4329 | 23467828.9204 | 204094040.3201 | 322221855.1334 | 459668137.3326 | 135845472207.5928 | 2074119052.1282 | 1897820678.4044 | 2143736995.5455 | 189635569.8368 | 621662358.4219 | 676271249.3615 | 762551446.6578 | 261420275.4725 | 574400830.6305 | 24957789.9808 | 106222033.5964 | 22365073.354 | 22321407.0585 | 846721550.5594 | 28878141.3953 | 1122821257.1441 | 6376802899.3682 | 665828041.0284 | 185220151.6794 | 1.5464e+12 | 2491282.6656 | 924813.1147 | 1673016.1141 |  |  | 1.7056e+12
385 | 1052142118.4435 | 1195951628.5201 | 177255698.2496 | 179093494.7333 | 1006660626.1671 | 25027209.4333 | 223414922.8452 | 303405095.3336 | 484400037.2796 | 146376625140.1494 | 1962814190.9802 | 2083046316.6735 | 2162330578.4868 | 198504523.7168 | 567524393.4761 | 656106287.8107 | 912229299.0389 | 345565281.4047 | 479171278.3387 | 25262228.2203 | 109569149.8201 | 19280508.8794 | 25657329.0193 | 895236936.8572 | 26457943.1328 | 996346065.5102 | 5702150279.4419 | 695133171.679 | 195305217.3414 | 2.3566e+12 | 2383619.3181 | 932406.5803 | 1768091.6108 |  |  | 2.5257e+12
386 | 1022911849.7323 | 1063138417.0111 | 223886948.4 | 152040214.1319 | 991262520.7697 | 21848033.5983 | 208095339.6343 | 321698885.6768 | 467662141.2717 | 135893179471.2053 | 1913780069.7709 | 1935232132.6555 | 2130629180.3974 | 202056521.0227 | 558296015.4151 | 681117551.9597 | 765142081.6009 | 299101509.7594 | 539325948.3011 | 21267539.2992 | 120333195.1853 | 21001060.7199 | 22518327.4914 | 853232134.4929 | 27404712.172 | 1123617814.127 | 5938197029.351 | 557545769.3294 | 192609571.3023 | 2.4897e+12 | 2379778.3084 | 992741.9291 | 1618781.0775 |  |  | 2.6479e+12
387 | 1205574126.4118 | 1155661092.7501 | 186449300.3075 | 164237978.9174 | 1000903610.5534 | 24279252.6076 | 201601755.0112 | 312796050.0405 | 448555967.1958 | 160046195508.572 | 1871228453.0474 | 1982495644.0451 | 1843709671.8473 | 196081803.2305 | 516505604.0999 | 678608580.8499 | 735496720.4041 | 301987388.1113 | 577972814.8961 | 22772033.2866 | 106746033.2129 | 20634234.3219 | 22743426.8133 | 893103217.4791 | 27245090.2508 | 1156366612.479 | 5970789868.242 | 622714567.407 | 185429421.2428 | 1.849e+12 | 2583758.1057 | 910246.76 | 1747460.2972 |  |  | 2.0315e+12
388 | 1206975338.2125 | 1223143065.372 | 219485553.1008 | 176002142.1175 | 1053449813.8637 | 24634905.9111 | 204998260.2665 | 268942266.0988 | 485558576.2162 | 128421988913.9099 | 1964819041.6778 | 1828825479.8452 | 2112798887.0322 | 174544540.017 | 568325223.0937 | 639757716.6169 | 864650228.2356 | 332003592.7656 | 545317826.2684 | 23784161.0726 | 128456556.3548 | 23029035.3399 | 24187329.3363 | 930066103.1132 | 26978795.1829 | 1226028445.1224 | 6403462291.6378 | 695993041.168 | 187618033.092 | 2.4055e+12 | 2537358.945 | 953702.535 | 1729169.3897 |  |  | 2.5575e+12
389 | 1250351063.4906 | 1196767554.9575 | 227425876.7593 | 170116757.7394 | 943208454.3183 | 23896308.6726 | 212359684.2985 | 309521016.2816 | 431570278.6757 | 127474339310.5268 | 1990443919.3796 | 2032428820.5414 | 2129799293.9599 | 182972884.9614 | 656228164.3962 | 683614335.1378 | 704583354.2447 | 302691743.4779 | 533857448.8007 | 26890852.8424 | 104944956.9477 | 24793626.3102 | 22889104.7638 | 950398557.8168 | 27247273.2076 | 1052929250.9845 | 5933285044.5323 | 703307659.3306 | 176920128.5542 | 1.7884e+12 | 2511360.5269 | 947978.4181 | 1670161.3197 |  |  | 1.9389e+12
390 | 1194687096.5665 | 1198915687.9011 | 220441748.3652 | 155089819.7034 | 1087160981.7729 | 22837718.0249 | 220597850.085 | 317622578.463 | 493138853.9034 | 135548101719.3463 | 1969106068.2215 | 2024069983.2124 | 2015353094.59 | 202740815.3979 | 645506722.0014 | 699632796.3608 | 835743107.0431 | 319061676.4896 | 555694707.4382 | 22303572.2499 | 108300232.7471 | 21693029.4606 | 21850866.8697 | 761369446.6557 | 27518654.0029 | 1124689405.7374 | 6294636273.0367 | 649599608.1536 | 175960400.9511 | 2.5174e+12 | 2449757.4981 | 951244.0427 | 1503205.4514 |  |  | 2.6763e+12
391 | 1194747106.3508 | 1125546004.1368 | 217585563.2112 | 158603395.4278 | 1066813085.2314 | 23942643.004 | 212678947.5353 | 303263980.8183 | 475170497.0853 | 137906446123.0804 | 2043463060.4036 | 2119834246.5194 | 2095104732.2504 | 202929211.2449 | 624390113.3685 | 689296423.1533 | 817972257.2189 | 250370404.0843 | 549520943.543 | 21416911.3179 | 127882744.994 | 17213105.706 | 24312410.4786 | 881373095.0092 | 28180969.4944 | 892654373.6789 | 5649580640.2884 | 699791080.5932 | 195310798.506 | 1.6413e+12 | 2390023.4425 | 888363.0636 | 1763899.2661 |  |  | 1.802e+12
392 | 1178694404.4474 | 1175408215.8736 | 197769444.5847 | 147285046.1067 | 1080129914.7413 | 23753794.1864 | 206617920.2632 | 327722858.6391 | 498615925.4232 | 153385744106.3903 | 1770411150.6264 | 1920948548.0561 | 1695049023.1288 | 192994902.1823 | 512705827.1628 | 635216910.4981 | 766845420.5786 | 319755259.0211 | 605979064.1878 | 21675507.8464 | 122720161.1674 | 24352901.4823 | 23899062.1266 | 897447062.245 | 23719964.5687 | 945071141.9828 | 5230481834.3872 | 671769544.051 | 193167253.2394 | 2.0733e+12 | 2492024.2486 | 965914.8145 | 1702817.793 |  |  | 2.2481e+12
393 | 1222494685.2567 | 1226252456.402 | 212169494.4656 | 173329006.4357 | 1038124772.1205 | 22534730.351 | 194793713.8282 | 307828171.6948 | 483457564.9851 | 134304619447.5604 | 2035382542.5521 | 2033739343.0348 | 1360242047.1712 | 173208334.0664 | 495686168.7985 | 716042165.2502 | 890251825.1237 | 265793182.4672 | 451594239.4288 | 22458015.0384 | 125544269.3555 | 24658618.61 | 24313670.146 | 910778692.9031 | 29033937.1639 | 987974079.0656 | 7145757019.213 | 523655211.7296 | 178633796.2876 | 2.8746e+12 | 2536984.18 | 922219.6824 | 1652162.8857 |  |  | 3.0321e+12
394 | 1138887490.3435 | 1083396161.3254 | 201664587.1041 | 178501109.2767 | 1079836373.0296 | 25107312.6031 | 206605533.822 | 316239193.6832 | 474727870.5322 | 155247040425.5509 | 1776321124.6633 | 2197721088.0202 | 2158261564.2776 | 161651390.6755 | 570414409.4814 | 707246759.8368 | 706997020.3288 | 317907945.7662 | 583871988.234 | 25276660.648 | 130004720.2389 | 22826043.4989 | 22125685.6189 | 786288967.4513 | 30231534.6991 | 914342851.5981 | 6287415611.0168 | 615487783.303 | 178838084.7314 | 2.462e+12 | 2299479.1715 | 1008464.3432 | 1551098.4564 |  |  | 2.6401e+12
395 | 1183608259.6476 | 1195418195.9553 | 198122328.6731 | 175115704.8359 | 950280687.8322 | 24595133.0572 | 193757691.2062 | 291881395.014 | 468202547.9018 | 132339402539.9427 | 2091263266.8197 | 2119240473.3026 | 1911170045.6946 | 157694373.2688 | 445654680.604 | 692047631.5286 | 803867384.9514 | 276255225.9724 | 559615858.0808 | 24978037.4322 | 127806792.6929 | 23104210.2795 | 19555290.7533 | 721068983.5165 | 23583460.8831 | 960910190.4691 | 5927747955.4856 | 700324723.91 | 172017319.4678 | 1.8192e+12 | 2583313.1934 | 938285.9737 | 1823464.1357 |  |  | 1.974e+12
396 | 1134366338.1767 | 1023966402.2716 | 201472963.553 | 172881300.0202 | 1083350700.0379 | 22915664.3741 | 205606847.8553 | 271282780.8857 | 461768925.5468 | 157330624322.5245 | 1825571139.8704 | 1949834161.8476 | 1760724188.715 | 172883827.0568 | 460213788.9369 | 666038485.3741 | 799580410.1203 | 317290937.1685 | 593967648.3155 | 22747827.1777 | 118718058.1574 | 24546931.2682 | 23346716.9911 | 868643833.4018 | 25417102.6153 | 906158969.1668 | 6942558863.3364 | 656755829.746 | 155719846.2711 | 2.2666e+12 | 2328285.639 | 972300.9944 | 1579734.9098 |  |  | 2.4469e+12
397 | 1223350478.9649 | 1181324276.7025 | 185210291.3917 | 182293678.6328 | 1078663468.0459 | 25919846.0914 | 216413798.4033 | 314385269.2633 | 464057499.3468 | 134017338919.8929 | 2022302236.637 | 2026505925.3172 | 2094666655.7413 | 200057352.6335 | 547646179.1223 | 710974254.5554 | 861856616.8699 | 306134092.0928 | 519677400.7438 | 26503286.1119 | 119721106.7577 | 18130999.1938 | 22536689.5352 | 877823246.1667 | 29328057.4722 | 1080004987.1515 | 7084669288.7318 | 661303858.0388 | 166377146.8225 | 1.606e+12 | 2575606.1159 | 976624.7492 | 1532835.277 |  |  | 1.7643e+12
398 | 1193878518.9815 | 1224669016.9982 | 216758990.3262 | 169373189.9915 | 1082098177.8881 | 20825292.3861 | 215653633.1388 | 327964776.784 | 467706890.5891 | 146692719190.5617 | 1888891254.9093 | 2206492007.6432 | 1959278067.6858 | 169152048.5706 | 541458091.0069 | 562083153.6166 | 870172835.8213 | 323231760.3031 | 560506818.3714 | 20630746.7313 | 121977461.4202 | 24673068.9416 | 22244677.8756 | 755795986.9296 | 30200319.7691 | 958177432.5848 | 6838473442.0259 | 625895131.8333 | 130261001.7382 | 2.3023e+12 | 2276496.2093 | 950539.905 | 1688150.6889 |  |  | 2.4725e+12
399 | 1185570115.8826 | 1217847427.4285 | 210233891.8649 | 174891250.1615 | 1074320598.423 | 24794052.8112 | 204586856.4598 | 320259821.5884 | 499884329.1886 | 147537229006.3508 | 1580753112.434 | 2069055567.2408 | 2143361022.8987 | 163463937.8055 | 631421987.7736 | 641806846.65 | 711061877.1141 | 256535719.0566 | 577883203.7889 | 22896395.128 | 132927992.2089 | 23525170.0594 | 21515525.1383 | 834296550.5966 | 27623067.5366 | 1157303871.1866 | 6777783610.287 | 687639365.5423 | 162539167.1151 | 2.2682e+12 | 2447976.2705 | 903290.3142 | 1695378.8113 |  |  | 2.4393e+12
400 | 1263127990.6773 | 1141969821.7765 | 207578542.5464 | 182413217.6228 | 922781319.2346 | 19167072.4327 | 219200793.5705 | 312757074.033 | 489107938.3317 | 119573494984.5555 | 1974086313.6426 | 1823157394.1436 | 2130338743.018 | 172273238.0012 | 627539000.2462 | 719498784.2814 | 778905622.4971 | 330965632.9214 | 594051984.459 | 22696709.4666 | 116447866.022 | 21684583.4948 | 24341324.6169 | 691205252.9822 | 27198935.9244 | 1083271060.7559 | 5101227621.1902 | 652740093.8348 | 191678509.9243 | 1.8501e+12 | 2857790.8004 | 906710.7172 | 1653571.2484 |  |  | 1.9915e+12
401 | 1222941004.14 | 1027360458.9394 | 216886548.2075 | 153373782.0893 | 1085623422.8726 | 22477623.2474 | 219380372.544 | 309671773.8836 | 434256441.2079 | 155376469740.3194 | 1837742773.8108 | 1816568632.6905 | 1735198213.1624 | 192373339.0016 | 631912730.7347 | 708945136.5811 | 872668183.9912 | 296950571.0296 | 478738435.1241 | 27374990.6027 | 102955950.3496 | 22295381.4286 | 25619387.1318 | 700015747.0449 | 19612714.1111 | 1011917037.0477 | 6198395872.1334 | 635633514.1037 | 187203641.4763 | 2.424e+12 | 2656996.6833 | 952846.015 | 1791705.8358 |  |  | 2.6016e+12
402 | 1230817589.0874 | 1229065012.1978 | 218783670.1376 | 173784250.2171 | 1046788174.2963 | 23078112.9124 | 216436050.252 | 271109250.8523 | 451228948.4933 | 160544489308.1269 | 1900274736.5946 | 2077879994.8439 | 2135105384.2144 | 186373696.3087 | 542822577.7035 | 573818721.4411 | 780608728.9085 | 298785996.4442 | 519544628.6658 | 23822490.3407 | 126349212.8381 | 23400063.5898 | 21504252.9667 | 916285668.5088 | 24752058.2016 | 1087676323.9646 | 6470897763.1044 | 560299551.7398 | 200359987.2255 | 1.3417e+12 | 2568239.4263 | 934854.7214 | 1605001.0868 |  |  | 1.5256e+12
403 | 1121916095.1353 | 1095496432.6246 | 210208313.0764 | 175525437.9837 | 1077507851.8838 | 25420734.6826 | 200514452.9682 | 314108824.513 | 492522508.4028 | 115115184513.2242 | 1779521649.9131 | 1989045565.4813 | 1993856905.0551 | 198568614.6043 | 511550756.702 | 719475140.3451 | 783651674.1672 | 321321331.9461 | 542998888.4297 | 25303254.1411 | 91052657.7539 | 22604640.5635 | 22362508.5983 | 886811978.5102 | 25808361.4871 | 1150703951.5932 | 6889982003.8577 | 705871154.4592 | 174986069.6309 | 1.7038e+12 | 2327632.046 | 891573.3481 | 1539279.2141 |  |  | 1.8425e+12
404 | 1170977272.0181 | 1106915451.6361 | 224470411.4849 | 167717465.9056 | 1069282036.5438 | 20907738.0617 | 204265522.3045 | 295700074.0283 | 421227026.174 | 125175673506.0819 | 1838838307.7537 | 2051606467.3597 | 2028483520.2589 | 194431225.3055 | 651439511.5942 | 622796967.5129 | 800002554.8055 | 326663987.3605 | 518121072.3572 | 23005690.1825 | 125573074.3654 | 22972618.0986 | 24175710.9056 | 847236070.2077 | 28860807.736 | 1057031294.9972 | 5958482257.3504 | 690158089.6778 | 200568062.5314 | 1.7696e+12 | 2334689.5152 | 1032015.1351 | 1619878.1409 |  |  | 1.9175e+12
405 | 1131024510.5288 | 1067183553.1595 | 187068569.4133 | 168649132.0512 | 1039861660.2779 | 24517444.5034 | 221059772.6654 | 289002831.0865 | 484049396.5271 | 158192255778.1066 | 1982713201.9064 | 1420778261.0936 | 2203644164.2832 | 194544090.7462 | 656227968.7657 | 681715186.5694 | 854528300.1048 | 331434256.9869 | 594408673.9416 | 23967403.5108 | 103746386.3225 | 23305050.5872 | 23028726.2748 | 709096934.4717 | 27669324.9075 | 1052841715.5804 | 5788329886.3157 | 695808831.2207 | 156715208.1798 | 1.6826e+12 | 2377664.0429 | 891799.6366 | 1578952.6941 |  |  | 1.8629e+12
406 | 1129085382.7981 | 1198617597.9144 | 194042209.8119 | 146352484.5 | 1029620305.8206 | 27395571.7671 | 186825073.424 | 314175799.2533 | 388987037.903 | 145409807328.3835 | 1880576129.4382 | 2045113450.0408 | 1935940071.6149 | 179773629.7526 | 645801109.753 | 648434407.1938 | 762050723.3535 | 337038109.8582 | 595946630.3689 | 23592677.9502 | 130228503.8881 | 24676220.5081 | 23864537.078 | 843787223.4025 | 25819950.7936 | 1139523791.5287 | 6660563872.1584 | 673528068.8935 | 188193705.4397 | 1.6802e+12 | 2534761.1661 | 886705.76 | 1702029.4754 |  |  | 1.849e+12
407 | 1209494951.8135 | 1154280524.9898 | 221996134.7649 | 171500276.7446 | 1026011608.5643 | 24896504.9045 | 222145119.2849 | 292964594.5495 | 454468086.1293 | 139857173893.2422 | 1691694556.1551 | 1900729573.7796 | 2210404456.9551 | 168515674.735 | 640473285.5299 | 706756457.5319 | 784039717.9836 | 294012184.2427 | 543738278.4159 | 25642762.9369 | 90695576.4221 | 18826497.7408 | 23905157.5439 | 725720905.9694 | 27618897.5203 | 970472823.8305 | 5269626126.2935 | 606233231.6117 | 194034608.2829 | 1.8059e+12 | 2565947.2083 | 1052891.3859 | 1715001.258 |  |  | 1.9674e+12
408 | 1218599262.2393 | 1064962560.5648 | 206239514.7284 | 181044209.7507 | 947220308.9296 | 23551154.6659 | 220068358.6629 | 293949512.238 | 496246757.1538 | 119633739030.1149 | 1848072181.7602 | 2038102425.7462 | 2098101241.126 | 188337362.042 | 640306257.5655 | 670830418.5066 | 819800380.2017 | 313937399.6756 | 577702479.4736 | 25196892.1794 | 119401768.0897 | 23202418.2286 | 24271463.4357 | 875614668.8987 | 27260385.9128 | 926616784.3824 | 6191618155.38 | 613388513.0754 | 193862554.701 | 1.75e+12 | 2527959.4231 | 983496.6172 | 1513577.4721 |  |  | 1.8925e+12
409 | 1229986465.019 | 1200793822.2661 | 207448401.4961 | 170835251.8599 | 1064949672.5099 | 25274953.563 | 211213235.6148 | 318180037.4674 | 490783420.8946 | 146188811492.9508 | 1964549340.357 | 1542441099.3635 | 2117367000.4008 | 199137184.316 | 596978945.7212 | 538669998.9922 | 933770627.28 | 338513220.8648 | 536916542.7485 | 25476624.1874 | 137268789.2011 | 20767211.8333 | 23818766.8918 | 872139079.4879 | 26785232.5441 | 1029877069.3776 | 4935755794.6656 | 538434375.9037 | 194476962.8755 | 2.1118e+12 | 2557013.699 | 1018135.4937 | 1594506.2059 |  |  | 2.2795e+12
410 | 1221033792.4545 | 1192962643.2133 | 199249513.8719 | 177070323.5283 | 1033575051.3989 | 21965946.0539 | 201772170.9998 | 314540837.3417 | 471504539.0308 | 141856642993.5264 | 2067324838.9465 | 1852704911.9758 | 2116720738.3923 | 190612449.7386 | 652771661.1836 | 701473879.4586 | 748851777.3864 | 292891034.2093 | 518681736.39 | 21620816.5474 | 111192984.0371 | 21318772.8094 | 21681923.8015 | 898090539.9633 | 23324736.254 | 840108860.9316 | 6598865877.9273 | 656803970.6786 | 193446178.4592 | 2.1334e+12 | 2323157.2611 | 907102.8539 | 1597876.8513 |  |  | 2.2986e+12
411 | 1156291123.5146 | 1074890956.3006 | 212215698.0018 | 165207221.6654 | 1068697460.2035 | 26609853.5719 | 222505155.5362 | 311264196.1894 | 462620369.0369 | 159325159450.4772 | 1931200094.9707 | 1902142143.3949 | 1917896887.8396 | 180806552.786 | 532020118.8928 | 655339869.9149 | 821336947.6262 | 339013058.5154 | 608760573.8296 | 26240707.5004 | 123453287.7248 | 22583579.4542 | 22020042.6531 | 799172530.586 | 28670450.2501 | 944357423.2637 | 5303865946.087 | 668156569.3092 | 171068433.1851 | 1.7704e+12 | 2560697.1015 | 928293.8957 | 1709469.1621 |  |  | 1.9514e+12
412 | 1207162293.2976 | 1149421527.2234 | 208120196.1842 | 166929113.7813 | 1075449077.4944 | 21872509.8969 | 213453523.0943 | 297775370.8764 | 482878127.6246 | 142498491392.4001 | 2017592593.1535 | 1829556970.4099 | 2110646278.186 | 195948568.3138 | 644323613.1739 | 617406270.8909 | 753500959.8619 | 321894462.5894 | 614546143.1293 | 21796299.3049 | 115405040.5025 | 23737006.0126 | 23823087.1923 | 922628802.1688 | 21274894.9974 | 1044317246.3732 | 6470624075.1335 | 618658832.8321 | 153841170.3892 | 2.0285e+12 | 2643562.5593 | 914341.7745 | 1607916.6516 |  |  | 2.1944e+12
413 | 1221527656.2052 | 1103739435.9659 | 221162099.3123 | 169770748.7681 | 987944052.0999 | 26909865.3042 | 224925403.6604 | 315734870.5546 | 467399860.6329 | 130867118291.568 | 1989376905.8492 | 1857483479.7418 | 1998563499.6152 | 189776367.3512 | 572424456.6146 | 645495110.5359 | 715753272.3982 | 295640154.1517 | 580445726.0628 | 26087626.1124 | 119093475.6493 | 24198693.8742 | 23877773.2591 | 899598525.9961 | 29388413.9359 | 1109467453.1072 | 6802638092.8167 | 624543945.7387 | 182710567.7719 | 1.7742e+12 | 2537272.7019 | 880049.7476 | 1611113.8268 |  |  | 1.9285e+12
414 | 1173581426.9099 | 1203316077.039 | 225839873.0938 | 148692291.7649 | 950572460.8464 | 23884036.239 | 189512657.7117 | 327251917.9359 | 463570247.9451 | 141675911970.3747 | 1847899759.5965 | 1441337646.0872 | 2197972702.9609 | 191255868.2478 | 639765562.6403 | 705819728.6915 | 700418960.6499 | 354584785.725 | 552874902.0327 | 25502377.1336 | 116684126.5535 | 20711334.2487 | 22624004.0905 | 826346929.7256 | 28119124.8929 | 1075295139.8394 | 6128460785.5957 | 653913214.5869 | 201394240.0347 | 2.2445e+12 | 2371382.3267 | 906778.4412 | 1595615.5528 |  |  | 2.4087e+12
415 | 1060849243.7197 | 1049386414.7398 | 220509831.6569 | 171718950.7908 | 1087257363.5973 | 22059459.6377 | 219920482.3484 | 321613199.8572 | 457830272.4395 | 112178863166.7663 | 1982970091.2118 | 1562832794.7254 | 2201595332.0416 | 189621197.9813 | 599537526.1105 | 676799759.0856 | 754338964.5909 | 350370926.9558 | 571876366.0368 | 24987749.7352 | 105052677.6746 | 21889831.7713 | 23695547.4935 | 808062374.1778 | 20004757.3923 | 1117809119.1505 | 6472982166.8534 | 582042698.0043 | 193647475.8025 | 2.1279e+12 | 2434063.87 | 964610.0616 | 1654598.8087 |  |  | 2.2629e+12
416 | 1108766340.0795 | 1151511496.3941 | 206656071.1731 | 168255782.8101 | 993720237.0528 | 24955767.851 | 209023367.005 | 313813390.9804 | 482181599.7701 | 112294354665.1415 | 1615811635.8626 | 1510566984.2247 | 2203011816.6578 | 192023676.9773 | 642136480.6804 | 723719666.0277 | 883476255.5516 | 315788653.7024 | 609931128.5047 | 27243560.9553 | 137229078.9209 | 21960989.0463 | 24498951.7573 | 871765948.4835 | 20481399.412 | 1130406404.9364 | 6211455399.314 | 624048137.3746 | 186557207.9812 | 2.6535e+12 | 2573153.465 | 972893.241 | 1674492.3354 |  |  | 2.7885e+12
417 | 1169809134.5618 | 1099211742.6497 | 219656446.6506 | 153255715.662 | 1046811922.4007 | 24935247.1468 | 211309795.8404 | 324349114.6048 | 489419601.0992 | 139821010173.7948 | 2023734510.872 | 1692166515.2394 | 2191879483.9982 | 201890213.0579 | 522618960.1586 | 622328661.8398 | 851149574.5086 | 266405627.2089 | 604464067.7301 | 27287467.5624 | 123255701.7857 | 18533571.6866 | 25493615.512 | 832458845.5043 | 28139997.7977 | 1076587632.0578 | 6754036104.1805 | 679410338.6218 | 191288034.2863 | 1.8706e+12 | 2258930.1907 | 1019634.2172 | 1672500.6331 |  |  | 2.0339e+12
418 | 1146298608.0411 | 1194483700.8459 | 217713668.0581 | 175783569.4055 | 1050366744.4801 | 25438194.7175 | 221025127.8795 | 329034319.7141 | 487282442.2587 | 153873709210.9995 | 2062208852.2458 | 1868135538.4798 | 2193822715.4247 | 194051846.7112 | 668508763.0956 | 631629251.3253 | 777957857.0701 | 350790506.5838 | 604516132.8843 | 24543906.1789 | 119431894.584 | 19525829.3901 | 19742179.5046 | 927487686.204 | 27428122.8024 | 1138544687.5406 | 5208056385.886 | 533005393.2475 | 175449246.5646 | 1.9175e+12 | 2263503.7546 | 913380.512 | 1664473.3872 |  |  | 2.0938e+12
419 | 1024293113.0888 | 1141719288.8663 | 222358960.6324 | 162716694.2217 | 1019814055.6626 | 22930234.3049 | 190567200.6898 | 322456626.1228 | 473726700.8083 | 135915038292.2861 | 1640447181.8879 | 1648754647.8299 | 2200554619.2577 | 186382828.2358 | 608158994.6909 | 706322820.9824 | 798420829.7798 | 302834070.0641 | 471606652.439 | 19842075.2922 | 101189031.8914 | 20785931.6236 | 25366544.4228 | 913041384.7799 | 23788770.5875 | 1066817804.7996 | 5972397628.3628 | 656105477.6117 | 191869641.6857 | 1.8665e+12 | 2212918.3813 | 881856.7657 | 1699256.0055 |  |  | 2.0245e+12
420 | 1212525203.5537 | 1228050007.207 | 204419647.0831 | 179427065.8768 | 1046375727.2188 | 20329202.3489 | 221477768.0364 | 319491626.5069 | 468772125.6926 | 148489949207.1186 | 1718155483.7733 | 1978887804.2862 | 2182670560.6042 | 196426336.377 | 548278287.7898 | 721149302.1078 | 834496777.2186 | 308184095.3963 | 608781840.918 | 23189713.7548 | 100318360.8291 | 23420717.3363 | 25615747.2493 | 848018283.4196 | 29032714.8109 | 1014180157.6493 | 5312105330.8975 | 672929176.2325 | 147115233.5118 | 1.8748e+12 | 2736193.0115 | 934565.0659 | 1550210.9758 |  |  | 2.0454e+12
421 | 1085633085.5113 | 1211058450.2243 | 221078643.5198 | 164479485.508 | 1080546846.4119 | 25963859.4242 | 200208169.9141 | 303138002.4235 | 494964340.138 | 153900392630.42 | 1912645052.0196 | 2205996932.0815 | 1956981077.4797 | 198461556.7973 | 638750866.0727 | 668367510.0526 | 842498679.0039 | 337603591.3952 | 532142676.5016 | 26318423.9476 | 108313757.6686 | 22949442.7453 | 22491612.8585 | 797492260.5518 | 27479267.6681 | 1115195037.9075 | 6130406564.0627 | 665251829.3418 | 172350923.4254 | 1.7954e+12 | 2304872.5576 | 903066.4428 | 1594375.6725 |  |  | 1.9724e+12
422 | 1112890935.2254 | 1051735324.7999 | 190897921.9651 | 170317694.1016 | 1034073867.4836 | 23365781.9357 | 218161083.615 | 288343796.9222 | 494995417.9966 | 130821444659.657 | 1948495959.9632 | 1834650926.5962 | 2155211379.8048 | 168860357.2037 | 616106412.3292 | 707775971.811 | 897328647.6742 | 340841434.3588 | 589688750.8355 | 24482659.8619 | 109479901.9582 | 23241269.7358 | 25274624.0263 | 800318995.5547 | 26447996.4809 | 966182622.1116 | 6910236176.2003 | 681858279.9157 | 188960100.2168 | 1.3244e+12 | 2388998.4143 | 971781.9836 | 1494981.8842 |  |  | 1.4788e+12
423 | 981819756.0222 | 1201343331.1032 | 217926691.8727 | 176314078.5651 | 1079670347.8607 | 20042292.047 | 227189214.0464 | 317489494.0993 | 492676414.1329 | 126793324736.5622 | 2089992978.7798 | 1952052842.23 | 1922016088.3381 | 181286385.0102 | 592463407.5995 | 660008085.3862 | 863052697.7777 | 347159475.262 | 613405295.7922 | 24577470.754 | 126272447.339 | 22728174.2706 | 24699804.883 | 852622547.2819 | 28039304.9937 | 983372368.5909 | 6045364935.4424 | 641993814.7526 | 155393413.3989 | 1.7373e+12 | 2668060.6483 | 962369.9392 | 1505769.1578 |  |  | 1.887e+12
424 | 1237039766.3857 | 1219185355.4518 | 199772709.2685 | 172602948.5227 | 1057795082.8455 | 23648163.2674 | 206585820.5057 | 304027143.315 | 478220557.6461 | 111146735943.7371 | 1512618611.7037 | 2065377915.7252 | 2090994358.7569 | 161440855.3967 | 555020273.8718 | 710792586.1359 | 871593356.8657 | 272199798.0943 | 563950198.4533 | 18839946.6606 | 125347421.1456 | 24596679.0351 | 25405506.4072 | 711004350.6425 | 25185361.7464 | 953954211.0748 | 6959260462.3961 | 615567121.4309 | 194408902.094 | 1.826e+12 | 2375229.4463 | 986459.5869 | 1600214.3591 |  |  | 1.9606e+12
425 | 1118967359.497 | 1226364843.9879 | 218898750.4592 | 169661390.0175 | 1061593689.2107 | 22116599.3406 | 206925581.5927 | 298022274.5265 | 473233167.0201 | 143669880101.7126 | 1671807904.5325 | 1677643307.0968 | 2038081421.8145 | 195302311.0616 | 473695322.7855 | 684371677.7575 | 849064936.7 | 277355114.9427 | 527918144.0516 | 26222451.08 | 96349033.5588 | 19463814.9486 | 23245824.8225 | 934352830.2244 | 25141014.0511 | 1062136799.2736 | 7085947301.6232 | 694081109.0748 | 198184385.2266 | 1.7481e+12 | 2467314.8172 | 1009795.1516 | 1699940.0796 |  |  | 1.9152e+12
426 | 1144508699.187 | 1198099229.9537 | 213162689.6631 | 182874635.2341 | 1026552595.1785 | 26288848.9868 | 224888544.3445 | 315957376.1639 | 463153295.1469 | 143219992745.8776 | 1947639442.017 | 2078769842.8312 | 2124599196.1642 | 199770264.351 | 472125779.0532 | 669542938.1942 | 860693430.9598 | 325782160.6389 | 591560500.4057 | 22620900.9285 | 102510705.7342 | 24125435.3902 | 20951340.4223 | 885324165.1454 | 29224642.2449 | 1103052642.9644 | 6597972901.1123 | 659880578.1237 | 200537001.9463 | 2.4638e+12 | 2423273.3263 | 955668.9813 | 1582831.2712 |  |  | 2.6308e+12
427 | 981816509.3084 | 1156427405.4706 | 202045909.4577 | 153192677.7188 | 1085658349.8727 | 25220738.5008 | 204830216.4563 | 323873063.0107 | 467951465.4955 | 150525795488.4876 | 1819269612.0038 | 1880672191.6018 | 1850281331.2064 | 182147130.1419 | 596688827.1704 | 694105876.4539 | 778120807.9462 | 299340736.562 | 569540503.7211 | 23314501.8327 | 101306831.5591 | 23556303.0811 | 25391433.1654 | 857104837.8231 | 27727751.043 | 1006345383.4694 | 6277411068.294 | 553240607.5492 | 194193757.1007 | 1.77e+12 | 2318702.8283 | 941365.0469 | 1615666.5199 |  |  | 1.9429e+12
428 | 1082915400.3307 | 1219759395.3036 | 201724696.494 | 167690813.3907 | 1087234684.2435 | 23988128.483 | 226576245.1503 | 308782229.8113 | 445637101.0978 | 162400584116.9532 | 2005418032.8726 | 1954669581.599 | 1396783006.5915 | 188338711.186 | 452467696.4871 | 578157899.5573 | 764651088.8044 | 332665951.4126 | 606015066.857 | 23187161.2666 | 112999525.5665 | 20610162.2251 | 24709345.4347 | 772968986.9066 | 23684028.9345 | 983179199.4677 | 6984618636.0628 | 642963036.5581 | 194767548.41 | 2.3729e+12 | 2418287.8644 | 906699.5843 | 1629132.2187 |  |  | 2.5582e+12
429 | 1179133711.1924 | 1228103980.7946 | 198213936.8962 | 164151182.3886 | 1063785711.399 | 21129480.4414 | 214015813.0264 | 319933488.5326 | 476249008.5457 | 156267787112.0915 | 2038213243.5318 | 2021201846.4816 | 2157892805.2374 | 177104358.4591 | 603220482.3231 | 614094287.4845 | 813509417.8253 | 244460334.2492 | 545570609.2411 | 26131078.4802 | 134006081.8039 | 23835200.2708 | 24266494.0694 | 885975468.3985 | 29251442.6061 | 1062878060.7104 | 6266712053.3051 | 694303671.9954 | 191607674.0694 | 1.7266e+12 | 2444718.8572 | 908017.9677 | 1678198.3054 |  |  | 1.9063e+12
430 | 1244587682.4887 | 1098838784.2294 | 200646770.7963 | 172592969.6954 | 1074005477.3971 | 21688058.6463 | 220235764.6877 | 317680624.4587 | 465124009.2125 | 146934736677.2521 | 1626567071.3675 | 1986691118.9792 | 1871603887.2289 | 185007427.9858 | 555404671.4497 | 688882333.4607 | 699102269.4672 | 354432601.587 | 533013900.9345 | 23828532.0595 | 120754917.4037 | 23041831.5754 | 21521280.382 | 821481971.9845 | 28407470.1128 | 986665939.4458 | 6553223051.7011 | 655068738.4098 | 191633151.621 | 2.846e+12 | 2435849.349 | 1017994.9943 | 1504726.5661 |  |  | 3.0157e+12
431 | 1221633400.9236 | 1206805097.2621 | 217013304.4454 | 178053511.2754 | 1043967415.7086 | 20867624.2171 | 206170298.4122 | 275570829.9233 | 469090324.8374 | 143697632685.2319 | 2023983814.3307 | 1875837584.5949 | 1832488865.5738 | 162419555.3417 | 525126194.4732 | 673367067.0025 | 903525293.285 | 291956091.6674 | 598583722.8138 | 24915164.3024 | 121259861.0418 | 18986645.5901 | 23597700.4184 | 890804775.1774 | 27070777.1545 | 1025728713.5928 | 7223337450.8965 | 640176031.5936 | 171715827.4825 | 2.511e+12 | 2364695.3108 | 1001290.1019 | 1676017.4214 |  |  | 2.6786e+12
432 | 1141191245.9533 | 1044388237.8965 | 226146232.3519 | 169475377.3209 | 1016992981.2743 | 20542512.8759 | 204751751.2709 | 318177325.5004 | 456909842.5852 | 145956855279.9923 | 1956843219.1522 | 1503996307.0424 | 1967564944.7 | 193408541.0499 | 661460783.4553 | 721761585.9899 | 839278382.9469 | 277658176.6008 | 513682617.8305 | 23808531.4243 | 108400473.8927 | 22722504.2188 | 25951471.2281 | 759968629.7356 | 27297326.6426 | 1193160408.7437 | 6286603847.1514 | 692328818.0752 | 189381962.0559 | 1.899e+12 | 2521931.6342 | 1008738.414 | 1617351.1677 |  |  | 2.0676e+12
433 | 1231788141.7839 | 1207605763.6677 | 223710191.7504 | 174740731.5068 | 1054312342.0009 | 23686619.8989 | 216919552.7594 | 311312410.632 | 441379887.2753 | 131196797821.1212 | 1703301224.8291 | 2199779436.0439 | 1908603438.6069 | 187322220.3257 | 512748508.4478 | 517177753.1531 | 882850246.938 | 322697598.9351 | 558403383.9842 | 24918320.1206 | 115493496.8922 | 20919564.2499 | 24263893.5405 | 774687936.258 | 30467858.2698 | 1094602825.1359 | 6431563802.9201 | 629516146.677 | 180643734.0463 | 1.6428e+12 | 2595975.4817 | 985451.437 | 1791410.5713 |  |  | 1.797e+12
434 | 1222010722.2974 | 1051124523.908 | 216030531.1889 | 163864965.2749 | 1077349209.6433 | 21539830.2993 | 221022616.2073 | 314379611.0023 | 478471817.2025 | 155120706387.8108 | 1856090644.9697 | 2199544048.7064 | 1779560254.4754 | 179217191.5102 | 478422837.8543 | 694850785.7372 | 789610397.7815 | 296989781.8897 | 563710021.2962 | 24847718.3526 | 115352878.2326 | 20221644.4724 | 22994430.5301 | 823272702.3414 | 25446903.5106 | 1142771634.4101 | 6884340205.5668 | 695787668.9676 | 192698257.6423 | 2.7781e+12 | 2674315.5484 | 1006179.3547 | 1650427.5944 |  |  | 2.9567e+12
435 | 1167065832.0342 | 1206254350.637 | 193512829.4107 | 174995057.6808 | 1059039836.5643 | 24533863.6502 | 192200797.9416 | 297640292.4305 | 473809585.6359 | 144314583579.1715 | 1968665236.8062 | 1953702514.4945 | 1753069791.8308 | 147467586.14 | 584856317.2233 | 697101334.0108 | 861468098.2556 | 314941450.6469 | 557203333.7699 | 19482143.4633 | 127533280.8401 | 23040231.8869 | 24269719.7481 | 943509439.3379 | 22734390.4898 | 1041242466.6944 | 7014770845.914 | 580893196.2762 | 158113612.1202 | 1.7922e+12 | 2520362.268 | 927564.7523 | 1823878.0561 |  |  | 1.9601e+12
436 | 1200643722.1302 | 1221218432.1751 | 220633920.4538 | 160775713.8601 | 999833110.437 | 26230580.6506 | 200647273.9703 | 304488427.1439 | 486782382.3463 | 140367390462.0293 | 1668289209.9186 | 1959986255.0992 | 1942329444.1027 | 178011195.0759 | 525803672.3431 | 687384854.0832 | 730095201.5129 | 301829248.3876 | 595494374.5439 | 24248470.2178 | 98538360.6969 | 21351514.817 | 25559302.7601 | 790250716.8621 | 30015429.2936 | 1093659064.9907 | 6591249772.8272 | 661573525.8751 | 197764042.4826 | 2.0436e+12 | 2424937.0038 | 958566.3124 | 1611464.8938 |  |  | 2.2069e+12
437 | 1178340842.8463 | 1215409535.571 | 193570858.9149 | 162478585.2925 | 1087472470.7585 | 22428163.4742 | 205731714.1781 | 288872795.1546 | 474215052.1876 | 149295118952.267 | 1807367121.6891 | 2101372255.7235 | 2193039353.3113 | 193499559.412 | 546961706.7359 | 690564405.3891 | 754902120.3459 | 296390991.8821 | 596144864.7832 | 25018166.9164 | 91764929.607 | 24511403.6581 | 25730152.7573 | 699691707.8981 | 28805556.1425 | 1130833695.0618 | 6615035576.955 | 612134047.9548 | 188139306.2599 | 2.0705e+12 | 2499097.2526 | 937134.3479 | 1540759.7482 |  |  | 2.2433e+12
438 | 1246628661.9074 | 1029904555.8773 | 183028731.9556 | 160534050.6225 | 1079143529.6892 | 22177930.5951 | 218183207.0431 | 323453564.588 | 377530680.4807 | 134786135455.4652 | 1997086993.1033 | 1935084594.189 | 1708689323.5073 | 174094240.4962 | 557863791.5825 | 723165783.548 | 868293061.9967 | 268918227.485 | 582301885.1656 | 22025486.6638 | 124350656.9646 | 21236888.9159 | 25775236.1159 | 855795440.5326 | 26391118.5924 | 1173527943.7957 | 5902303219.5188 | 614234705.393 | 190272650.8915 | 1.6673e+12 | 2477312.3193 | 1010742.7642 | 1633003.9735 |  |  | 1.8245e+12
439 | 1085282716.3126 | 1106721014.8419 | 222123519.7906 | 166980691.7889 | 977018213.8837 | 21401673.2988 | 202383531.3922 | 304444704.2379 | 492774017.0518 | 141461722851.832 | 1940354121.0188 | 1823774085.5068 | 1957655614.5907 | 198339728.0091 | 599387497.1096 | 660542220.814 | 834767500.0482 | 343703080.4942 | 570591833.8661 | 24647639.7601 | 118247422.3586 | 22602878.6496 | 22993186.0788 | 899167298.5938 | 26345924.0622 | 1130092136.5409 | 6491193015.2507 | 646226694.5646 | 183395668.3659 | 2.2069e+12 | 2290070.1962 | 961195.0307 | 1857934.9591 |  |  | 2.3715e+12
440 | 1202652844.115 | 1226378235.4293 | 217967858.1604 | 176077984.4628 | 940090304.0431 | 26763246.7357 | 226401561.7743 | 322054992.2177 | 496270762.9553 | 154636655811.236 | 1983795283.3772 | 1746975786.9832 | 1928854074.4642 | 200084215.694 | 654671756.4004 | 526313062.629 | 837682032.369 | 338878340.7376 | 554874651.1758 | 22327183.2943 | 95413387.782 | 22906027.8529 | 25279541.4641 | 795134943.7191 | 31102581.6083 | 1069345660.6573 | 5977645779.913 | 681918996.4562 | 172921962.5017 | 1.9912e+12 | 2499767.6255 | 914646.5673 | 1635027.936 |  |  | 2.1683e+12
441 | 1265770233.9587 | 1142771009.8059 | 191452042.9858 | 167492945.3784 | 1067335680.5291 | 23245416.6353 | 193937003.0491 | 323755253.9387 | 493935611.1015 | 135377911077.7392 | 1864084263.8328 | 2012717674.7949 | 2121106804.6866 | 186717758.7037 | 615748583.1608 | 576229835.5523 | 841001163.3745 | 258579083.8096 | 497956867.8547 | 27687689.6146 | 127002935.2457 | 21988435.3601 | 24011736.4978 | 829782888.3004 | 25411942.852 | 944206446.0514 | 6048155521.7095 | 588254646.4179 | 199074737.3192 | 1.407e+12 | 2454517.399 | 948983.2515 | 1664325.6943 |  |  | 1.565e+12
442 | 1105062463.7223 | 1187469327.0495 | 223167224.1251 | 155381804.1909 | 974267416.3395 | 24125438.1038 | 199513165.2828 | 329949223.8307 | 480673628.0814 | 117591313632.2069 | 1972780663.8847 | 1988177169.1795 | 2101538776.5496 | 198541678.8682 | 470637805.818 | 712566540.1888 | 768482357.1043 | 335587312.8778 | 521687615.2201 | 22637530.0668 | 129459147.7297 | 21429490.4165 | 22044484.4593 | 893026608.3212 | 26626221.7293 | 1081239824.9954 | 6927036569.2254 | 645283491.1182 | 195606747.8445 | 2.0433e+12 | 2434146.1204 | 947396.6754 | 1838190.6311 |  |  | 2.1846e+12
443 | 1222732019.5581 | 1225118213.9266 | 194955578.4116 | 156997618.0458 | 1084158964.0469 | 17657853.2581 | 213197390.271 | 312997703.0729 | 491983523.8877 | 139977862166.9944 | 2056721209.7778 | 1681876683.0347 | 2002018606.984 | 198022692.232 | 619674391.7311 | 724622682.4169 | 777432629.648 | 309488156.2227 | 549149725.6036 | 21968561.6764 | 127374359.8511 | 23610205.3246 | 25619830.6519 | 802242528.3917 | 27708738.3816 | 920351984.6581 | 6676920614.2537 | 538047301.8044 | 178070878.6394 | 1.6933e+12 | 2483459.3521 | 924122.4803 | 1765739.6856 |  |  | 1.8564e+12
444 | 1070919198.7761 | 1110967906.2253 | 186632084.2971 | 180011688.0576 | 1040545008.2829 | 22656222.3302 | 183470950.4669 | 285945736.5685 | 430558257.195 | 148096079625.1481 | 1797066178.5804 | 1882774306.9025 | 2138079783.5363 | 199513179.6921 | 636286413.5204 | 694554449.4118 | 783287847.8445 | 300731309.5572 | 559449227.1175 | 25429142.1944 | 122272466.5327 | 23330035.6661 | 20855451.0671 | 774265900.4728 | 22705886.0291 | 1057891963.2795 | 5952268603.4511 | 711851071.3177 | 188481855.4347 | 2.6283e+12 | 2282646.361 | 912312.4167 | 1539425.7997 |  |  | 2.7988e+12
445 | 1125553998.3748 | 1131299439.8974 | 222134239.78 | 168571585.9878 | 926886470.1988 | 18966954.4629 | 217727949.1784 | 293500451.6124 | 473710726.7951 | 139530272259.6606 | 1895327497.7989 | 1833699655.6948 | 2159046677.3124 | 189049148.9561 | 542062035.8072 | 719353504.6433 | 908029469.5833 | 250591484.5225 | 610935191.4098 | 24010488.9631 | 128959615.4784 | 18659690.964 | 24655692.8161 | 723794781.5839 | 26916233.4434 | 1076733041.5101 | 5106020151.6455 | 618878498.7687 | 185218650.1725 | 2.2912e+12 | 2845500.5825 | 898535.8312 | 1731312.8745 |  |  | 2.4524e+12
446 | 1176843724.3237 | 1094643398.435 | 210074164.1052 | 172162937.1341 | 1002737038.4314 | 23998632.0536 | 184836822.6071 | 309007651.3969 | 483287189.0563 | 154308763674.7449 | 1881915495.7795 | 1963662070.8591 | 2174837914.4914 | 199176921.7425 | 541401065.0801 | 700031178.4114 | 791826077.3516 | 307815981.2406 | 604823664.5442 | 26875932.807 | 119282522.2242 | 21672960.2307 | 19225003.1135 | 890327423.1523 | 18454853.0309 | 1185703414.7407 | 6079475291.0005 | 666111903.4241 | 192835510.9625 | 2.353e+12 | 2570327.2166 | 955302.6152 | 1693769.1587 |  |  | 2.5303e+12
447 | 1167309638.0298 | 1219736914.0165 | 196740439.2319 | 171967595.1899 | 1075571647.9547 | 20302781.9188 | 218694534.88 | 315148151.4737 | 462011447.9589 | 156881887721.8458 | 1840839790.2664 | 2115710064.8291 | 2159176919.6279 | 194472506.5668 | 576575587.9305 | 682917424.0922 | 823546726.5847 | 321952035.7211 | 551175121.4125 | 20700347.0692 | 116084786.8053 | 22424003.1848 | 24287534.5745 | 797185244.0678 | 24491652.6868 | 1048687072.7517 | 5661688628.6844 | 643538043.2099 | 188267756.848 | 2.3222e+12 | 2569743.688 | 1017305.4756 | 1545022.3925 |  |  | 2.5017e+12
448 | 1210008129.4836 | 1084595000.244 | 176134767.5942 | 146399299.3781 | 1078963560.5712 | 21302430.7081 | 206377106.613 | 294049429.5017 | 461646491.267 | 154561635552.3126 | 1952312436.6346 | 1811812366.9426 | 2164109610.7616 | 202728744.6847 | 596385962.8777 | 690334432.2755 | 716154013.0526 | 351671745.104 | 562953867.6633 | 23251074.3784 | 125361906.5512 | 19307216.9592 | 24177060.3062 | 848480160.5579 | 24784126.3489 | 1028010629.8072 | 6144734677.2132 | 573061615.2375 | 169977580.6083 | 1.8813e+12 | 2561012.0622 | 881656.4889 | 1903789.9959 |  |  | 2.0586e+12
449 | 1178076665.6381 | 1201416700.3199 | 206403558.1823 | 163012230.7339 | 1051625670.6532 | 21993631.6353 | 206211185.6813 | 317629071.0388 | 470413789.491 | 143315666267.5175 | 1627283322.6388 | 1775414162.4328 | 2188262085.8136 | 192803778.6507 | 544053340.2997 | 663384270.2715 | 713424659.933 | 345495728.8964 | 605299496.839 | 20784080.0447 | 107129311.4569 | 24525757.481 | 23772945.3432 | 821429360.5591 | 26301154.9879 | 1139020303.5934 | 5043325469.8474 | 524745736.2418 | 177307056.962 | 1.501e+12 | 2505907.1765 | 915160.7067 | 1622711.5648 |  |  | 1.6657e+12
450 | 1104058183.7178 | 1136368516.2785 | 221085983.8139 | 178342791.2178 | 1043367883.9149 | 26771324.5889 | 222872221.7253 | 313532814.6762 | 481614294.9894 | 161012331662.6467 | 1999719611.8597 | 1783087498.5948 | 2010516040.4373 | 184044629.2587 | 598330514.2003 | 560052158.9362 | 706592215.9371 | 242980872.4626 | 614270224.0418 | 28568100.3624 | 130570453.0932 | 22119307.0574 | 25076517.5119 | 781482494.4979 | 26863378.0789 | 1072656280.72 | 5665950212.0615 | 674146318.0608 | 200125945.9381 | 2.4768e+12 | 2572705.5395 | 960371.0899 | 1684464.166 |  |  | 2.6598e+12
451 | 1122218550.6404 | 1136530512.0772 | 187197314.341 | 164885935.2581 | 959385790.7543 | 23228798.3566 | 201035336.1205 | 308160752.1187 | 494082235.1168 | 144544083982.9301 | 1929185229.8677 | 1354175122.4446 | 1815392186.055 | 180078037.5829 | 532333130.1794 | 625778768.5193 | 770214726.9153 | 320902514.3314 | 506693610.4381 | 23858477.5611 | 126783566.1399 | 24076960.3845 | 24614877.3901 | 916356422.353 | 23279207.7565 | 1135196085.8792 | 5755807831.6668 | 693829902.0457 | 187753031.0872 | 2.0734e+12 | 2779509.9876 | 962599.8055 | 1698019.2527 |  |  | 2.2395e+12
452 | 1135048504.6892 | 1144815627.9275 | 196968658.1025 | 171890441.5676 | 968387158.8764 | 20634356.778 | 222261512.2328 | 310860952.3701 | 440893786.508 | 146762903532.9742 | 1980803909.5586 | 1777901246.4174 | 2047135548.2604 | 147028056.215 | 623209103.715 | 691470410.9866 | 865262529.9004 | 336104969.8415 | 603093085.2177 | 23506819.4735 | 119821140.9491 | 24245518.4445 | 23877308.4925 | 943067552.2037 | 27860189.0755 | 1146923799.257 | 5991777839.5631 | 636360756.1382 | 189691982.5619 | 1.6666e+12 | 2345382.2336 | 913554.1116 | 1568038.0941 |  |  | 1.8362e+12
453 | 1126142229.4778 | 1196007324.8812 | 226236089.6315 | 167680129.7657 | 1062013577.0821 | 23215570.4675 | 193541571.1097 | 314066559.2949 | 480364744.0144 | 131127867868.4436 | 2000906153.4921 | 1829218011.546 | 2056753232.7001 | 159954001.5127 | 478741510.3575 | 703631044.1028 | 805092462.9721 | 334032966.1256 | 512286027.3076 | 24054921.7973 | 129340589.5713 | 23721783.9727 | 22220748.3896 | 926282577.0434 | 29956073.9024 | 1018587331.2745 | 6610495547.7838 | 638662287.8825 | 191195483.6789 | 1.9409e+12 | 2442991.8113 | 981794.636 | 1674540.4238 |  |  | 2.0953e+12
454 | 1087675881.4147 | 1218413522.8565 | 215740401.5744 | 166941633.4496 | 1036650641.4211 | 22192895.0202 | 215946999.5891 | 274617713.7424 | 450110959.8929 | 160656090687.4967 | 1801677788.5848 | 1864332069.0818 | 2100230780.4119 | 192873450.8931 | 649670256.4384 | 599877548.3251 | 882105857.2941 | 332884058.6111 | 482045118.3997 | 26393957.2572 | 121310046.9521 | 21960333.0434 | 24144178.6253 | 875730337.0496 | 24214292.2824 | 1160368152.5708 | 5489954194.3417 | 641826662.1112 | 195255973.5686 | 2.4934e+12 | 2607549.7856 | 962334.9728 | 1569575.012 |  |  | 2.6762e+12
455 | 1179674388.0958 | 1229187301.112 | 195810507.6169 | 166348275.5365 | 1017014629.1907 | 26775802.5389 | 209259696.8294 | 327593607.8654 | 462511986.9211 | 138821630651.2869 | 1908698375.2309 | 2033089968.3441 | 2002396900.2072 | 190848124.5751 | 513064611.4766 | 641795913.5 | 724142551.1669 | 301541566.631 | 460209294.7284 | 23946075.515 | 103661483.1758 | 20756406.3886 | 23839415.8315 | 763883595.0832 | 18463515.7305 | 1074175575.9969 | 6507159365.0341 | 651888062.232 | 197145140.7759 | 2.5534e+12 | 2546171.4667 | 925756.585 | 1757499.9312 |  |  | 2.7152e+12
456 | 1241183921.1056 | 1213212200.295 | 210369382.2929 | 177701637.2512 | 1065462667.8806 | 22210741.194 | 205277629.9506 | 278788427.7374 | 491994908.5613 | 138694185899.7911 | 1998615442.2927 | 2020942963.0435 | 2169188073.3245 | 190805599.4698 | 652825527.8828 | 699221348.569 | 834301960.8616 | 293762324.1857 | 543802135.6361 | 24497143.0638 | 112948530.8774 | 23869018.4844 | 25350319.543 | 877001316.798 | 25234280.422 | 1128177251.7409 | 6620473334.2201 | 700390363.2596 | 169859785.345 | 2.9078e+12 | 2698254.3675 | 959942.0183 | 1631830.3957 |  |  | 3.0705e+12
457 | 968939643.7886 | 1194539685.1601 | 212441451.7134 | 180701172.4049 | 994783059.6696 | 24053910.4296 | 198700114.8588 | 300012903.8956 | 469632362.8554 | 149880722546.3362 | 1595110861.2699 | 2040334111.5319 | 2181457424.9865 | 193584417.732 | 525899528.6532 | 717006078.7819 | 769769473.3477 | 344254090.1679 | 579851869.338 | 21176897.9638 | 131712282.2723 | 22282419.5782 | 25989035.1375 | 830331236.1227 | 25134948.9657 | 1132310324.4745 | 6494981110.0477 | 598451427.9039 | 194013164.2697 | 1.622e+12 | 2446363.3222 | 882797.7885 | 1713150.2427 |  |  | 1.7948e+12
458 | 1190407717.3166 | 1227770016.3649 | 199108938.337 | 176073492.9829 | 1040180291.1866 | 21457330.4283 | 192645653.8949 | 330462367.5581 | 470891371.9948 | 127066451619.8065 | 1732558633.642 | 1686696656.7778 | 1810141305.952 | 176655581.792 | 674937332.8434 | 694038932.0232 | 721701130.7668 | 234184838.2257 | 568227115.1162 | 26100770.359 | 123652315.8995 | 22085229.0777 | 22458136.1177 | 779366987.4042 | 29683492.2531 | 1171114132.8866 | 4594658476.6521 | 634173261.6996 | 147970305.2335 | 1.9932e+12 | 2463924.7993 | 937025.876 | 1784528.4333 |  |  | 2.1409e+12
459 | 1189715561.9878 | 1227581746.8152 | 213531196.0144 | 161470426.1188 | 1081214130.7271 | 23559467.4113 | 214079516.0403 | 279596449.8931 | 499484199.9994 | 142761354256.9065 | 1972308194.6762 | 2200731031.5612 | 2198428518.9131 | 180817751.6769 | 532904031.2622 | 687564503.3232 | 850142093.8596 | 271170976.8618 | 545378999.2135 | 23110048.0903 | 117128949.2884 | 24939226.7829 | 24561461.4173 | 819170083.4717 | 26337217.5142 | 1187019295.3337 | 6305955837.8202 | 606743366.497 | 197890438.4916 | 1.6593e+12 | 2625915.0729 | 967382.5219 | 1614629.9642 |  |  | 1.8258e+12
460 | 1126388618.291 | 1026638574.1476 | 206590679.739 | 163072887.0699 | 1052081895.9814 | 27790437.0988 | 219179721.7129 | 315600521.5978 | 487225119.1728 | 157749450287.0588 | 1940205592.702 | 1999134426.8161 | 1947388735.3518 | 177500170.5022 | 609714256.7428 | 700280021.8128 | 934019751.745 | 277766162.8547 | 512134209.4919 | 24479549.0407 | 120769648.8268 | 22220545.7515 | 24311549.5306 | 942726790.9089 | 25375401.2247 | 1150240278.2862 | 5056326741.5155 | 579795158.7465 | 176987829.1165 | 2.0121e+12 | 2394159.9969 | 999141.4122 | 1512744.777 |  |  | 2.1917e+12
461 | 1093528545.9131 | 1113292006.1615 | 189394374.6226 | 150188562.9256 | 1081509366.3473 | 25801562.3893 | 208212209.809 | 302394335.2796 | 466316762.7252 | 145137256190.8688 | 1916060047.3602 | 2208371980.7972 | 2201439126.4731 | 183260448.5351 | 609215200.6286 | 643474049.9095 | 571727569.609 | 298773652.8501 | 599531234.8083 | 27211881.9167 | 102918206.2973 | 19051549.0746 | 25669564.8959 | 738578722.5652 | 25510227.8664 | 1132236315.2376 | 5596406310.2796 | 606665939.7933 | 191135953.9021 | 2.3149e+12 | 2588172.8791 | 926274.5783 | 1602165.8321 |  |  | 2.4824e+12
462 | 1232681450.5898 | 1157158968.0646 | 184725889.6664 | 170013591.7567 | 1058917817.0752 | 23996442.7177 | 205062339.9803 | 288903824.6063 | 491053334.5971 | 144357749863.1396 | 1999302801.508 | 1727593131.125 | 1908321853.949 | 193680804.3723 | 657540587.271 | 687162042.2885 | 878065070.5971 | 253818421.2692 | 481273538.9636 | 21964694.5179 | 102685244.7587 | 24972288.3076 | 25077357.2761 | 812219307.645 | 23589961.3342 | 1006627191.2994 | 6395514847.4736 | 548637885.3448 | 169812081.753 | 2.2437e+12 | 2287853.6569 | 913428.7178 | 1629786.2428 |  |  | 2.4107e+12
463 | 1170413759.0486 | 1213422084.8011 | 223168585.3504 | 181919264.5854 | 1086675904.8516 | 21800327.9927 | 178437639.5774 | 282155982.8337 | 455162739.6371 | 134876619463.5512 | 1855311826.3235 | 2123908843.3874 | 2179717815.6972 | 159027770.792 | 525412134.6096 | 676197241.9036 | 906768827.2817 | 315627952.6455 | 600938139.8494 | 27272759.4155 | 120321398.7172 | 23301656.3185 | 21458114.4438 | 893987412.9678 | 30734368.9272 | 926425446.8096 | 6188407712.4761 | 695969860.176 | 193386777.8041 | 2.4795e+12 | 2234985.0418 | 945386.299 | 1578488.5301 |  |  | 2.6377e+12
464 | 1232545359.0436 | 1179879295.412 | 205551913.2897 | 150975644.2122 | 939111879.961 | 25829096.4038 | 180388819.3348 | 293797744.9814 | 459182796.9012 | 146139211039.1741 | 1885010666.3863 | 1817021231.403 | 1746758086.5069 | 201743186.0147 | 437735307.2485 | 622224403.3963 | 843852350.2251 | 315215226.8436 | 575488996.33 | 22362162.5271 | 125364589.3276 | 23645070.611 | 22223439.6824 | 908862225.3273 | 28215964.4195 | 1149448936.5538 | 6898656021.8584 | 694916700.1524 | 188766441.4677 | 2.4998e+12 | 2433167.2304 | 988352.9983 | 1710508.5221 |  |  | 2.6692e+12
465 | 1206510446.4361 | 1176615673.943 | 209766255.0901 | 175951932.7102 | 1057067565.33 | 21439641.0916 | 179353508.4795 | 269502909.9915 | 448012199.752 | 129506648152.5145 | 1720310712.1708 | 1551335194.2393 | 2124621124.5435 | 175884935.2552 | 621918050.7171 | 696531390.1012 | 848915411.3131 | 265797898.3896 | 569377178.9178 | 27795168.1123 | 112487468.7044 | 18704596.0993 | 25350061.6273 | 921615520.1508 | 22749140.5109 | 989600325.4339 | 6066446921.9025 | 712757097.6425 | 192300472.4462 | 1.9945e+12 | 2558395.1056 | 918084.6779 | 1666226.3139 |  |  | 2.1465e+12
466 | 990335148.7947 | 985144889.6582 | 186334191.8599 | 178239969.9238 | 995093224.5751 | 25488892.8964 | 204592607.4326 | 324410458.7373 | 431516402.1775 | 150238636198.0951 | 1744401903.806 | 1833297394.5308 | 1887125678.1544 | 200803993.5152 | 687811959.679 | 650169005.7659 | 795633467.9057 | 341435675.8071 | 588937961.6227 | 25996350.6329 | 135225615.0766 | 23791813.1948 | 21484335.1336 | 860646780.8097 | 30040561.3751 | 1141391595.3727 | 5333511870.6768 | 693724807.917 | 176537898.3559 | 1.7103e+12 | 2353228.4898 | 910082.5381 | 1669934.3739 |  |  | 1.882e+12
467 | 1073748019.5292 | 1192821169.0647 | 216450791.9247 | 174680313.8115 | 1030802515.8215 | 22031734.3079 | 219896966.3861 | 326089898.2827 | 468766921.7421 | 161798642035.0641 | 1992651513.5584 | 1920271711.4329 | 1700456632.8832 | 202057532.6543 | 513298623.0037 | 719817920.5634 | 828100433.031 | 218895487.6414 | 615677117.0086 | 26410799.4749 | 113962531.6818 | 24401713.6145 | 22152262.4887 | 900871011.8558 | 23901733.6559 | 1202271766.6557 | 5756864065.1463 | 698597776.7808 | 183332108.6078 | 2.8037e+12 | 2561943.2795 | 886321.0827 | 1582304.5968 |  |  | 2.9879e+12
468 | 1082836288.5999 | 1063279454.6514 | 212324577.8481 | 177421640.2888 | 1064987908.674 | 24728118.0795 | 224050560.0683 | 313644249.8436 | 482822815.7498 | 125622858083.0026 | 1964079890.8068 | 1808230445.7624 | 2094808400.9647 | 187537244.5364 | 533972666.7718 | 661061211.9746 | 867967422.6218 | 294316951.4419 | 472196526.3722 | 25736802.8418 | 127985669.1971 | 22600839.4756 | 20300955.6327 | 890243736.876 | 27089350.5066 | 1209791269.701 | 7274430202.2468 | 651643405.5594 | 189791594.4796 | 2.3773e+12 | 2552825.4536 | 956208.0875 | 1614519.1617 |  |  | 2.5269e+12
469 | 1106532922.7884 | 1208361266.7126 | 220964202.2837 | 175076748.0097 | 1077042764.8587 | 28797893.1661 | 197539976.5079 | 284133225.147 | 493258137.5303 | 145106733388.2122 | 1904455864.6747 | 2056502136.4329 | 1889898988.4773 | 199276235.2169 | 581774415.5379 | 673234873.1681 | 697020883.2539 | 262594368.3976 | 611380202.5809 | 24441936.1182 | 126215144.95 | 22738994.7146 | 21637568.1831 | 783748503.5718 | 24992048.9816 | 1160949699.8181 | 6037274394.5007 | 653984136.2829 | 188085920.1691 | 1.8271e+12 | 2573629.6395 | 955748.675 | 1648124.3731 |  |  | 1.995e+12
470 | 1213913702.6994 | 1131763652.3949 | 199785954.1967 | 158586499.0514 | 935231883.1929 | 26086167.013 | 214565835.6926 | 306885696.9572 | 498557681.5049 | 150977074952.6853 | 1860093428.7303 | 1924224392.0632 | 2065488785.7865 | 186510081.7263 | 610199101.2441 | 670015751.6995 | 762343684.9514 | 297978674.0822 | 601585595.6652 | 23574695.9023 | 125218056.8962 | 20633397.0934 | 22799608.1461 | 728188227.9222 | 21678401.9297 | 1139144169.1778 | 7150362746.9821 | 678890486.2446 | 193874371.6436 | 1.9976e+12 | 2379567.8296 | 1005280.8892 | 1532760.2332 |  |  | 2.1724e+12
471 | 1109801052.9487 | 1214897442.4502 | 210854764.8164 | 175455881.4081 | 1004930189.7853 | 20163068.325 | 221177066.3658 | 322248398.5454 | 495924239.6513 | 156855141862.6672 | 2036943986.5933 | 2046871866.7554 | 2096262559.7529 | 174136861.6045 | 598065934.6161 | 624908739.6937 | 826207776.1167 | 288844351.5746 | 564377712.74 | 27981817.5794 | 132490387.5364 | 19543377.7112 | 25427290.714 | 851187706.7611 | 27018440.2675 | 1108189056.0918 | 6256066029.5733 | 630889915.3415 | 196119581.7004 | 2.0489e+12 | 2656313.8257 | 1017082.6131 | 1543694.1082 |  |  | 2.229e+12
472 | 1251072228.8213 | 1178713671.4167 | 200460514.0968 | 158028083.5711 | 969738723.0059 | 21703380.8336 | 202928620.6521 | 279486030.2851 | 481510912.7324 | 149226521830.7648 | 1772683234.6163 | 2205702785.4603 | 1788419072.5242 | 194103632.2596 | 546324851.1398 | 636482185.2285 | 672568080.0012 | 291263355.5069 | 595569313.8975 | 25425702.0335 | 118545337.9104 | 23471931.9315 | 24613388.9029 | 798873032.7361 | 28911738.0808 | 1109610525.6485 | 6616175756.2085 | 671896264.4581 | 185037548.6572 | 1.7229e+12 | 2562845.0329 | 959418.5454 | 1490810.0172 |  |  | 1.8952e+12
473 | 1047271417.7227 | 1188512565.5126 | 211631688.2076 | 169751525.982 | 976800901.0631 | 22124456.4979 | 203780436.5603 | 320511138.814 | 461075947.2228 | 141604391042.1334 | 1954509931.1239 | 1809986960.0316 | 2154478506.823 | 189631134.4456 | 514158089.9016 | 612052760.8531 | 764451956.358 | 345926755.3955 | 523999758.2915 | 28777074.7547 | 130762662.0346 | 22555486.7059 | 24453316.1453 | 794401476.5559 | 26223399.6103 | 1150091345.7804 | 6226361332.5727 | 683691234.5294 | 179880084.1135 | 1.688e+12 | 2621747.3387 | 957332.9113 | 1736501.9046 |  |  | 1.8524e+12
474 | 1072688806.2179 | 1160977704.5901 | 224049379.5792 | 163488265.0281 | 1041998597.7482 | 27697295.4377 | 201080108.1917 | 318285283.1385 | 455218834.081 | 142177826307.82 | 2024209542.6228 | 1896194861.9564 | 2175040734.5795 | 156976696.8489 | 557585176.194 | 701565044.2966 | 700317329.839 | 319831969.1163 | 611941824.7296 | 21854202.7202 | 116151299.2459 | 24276310.4984 | 24157705.8798 | 920180680.0995 | 24998395.0075 | 1025970759.1417 | 5662497413.0098 | 663408355.3053 | 199365468.2881 | 2.5015e+12 | 2324377.2937 | 1015380.6485 | 1654030.7388 |  |  | 2.6662e+12
475 | 1203529581.6712 | 1051840348.227 | 195942674.9118 | 171453923.2471 | 1083058110.7796 | 23294872.4228 | 222941980.4111 | 320947282.5381 | 482706088.8219 | 139220551388.8431 | 2064434348.2175 | 1920214973.4658 | 2009411235.8246 | 188445824.3588 | 580599008.8945 | 642476021.1135 | 918859465.3201 | 345646510.3967 | 560023006.3122 | 22111402.7656 | 106372503.7831 | 21300808.8503 | 22432172.6388 | 918250795.2616 | 26221059.6482 | 1035001807.1098 | 5574571377.5137 | 612108680.1704 | 196880919.8826 | 2.3729e+12 | 2806533.8335 | 939359.0993 | 1720015.2889 |  |  | 2.5346e+12
476 | 1214425324.5526 | 1158264347.6311 | 213797574.2976 | 158174666.3292 | 1007118784.5601 | 21745001.6703 | 198460337.1448 | 330980915.6199 | 472827117.6943 | 154171469768.3981 | 2037493086.6719 | 1628622394.8209 | 2177756106.2879 | 184472326.5134 | 537450215.9796 | 703487934.1619 | 815275356.8076 | 313061038.5856 | 497175282.5068 | 24193679.0023 | 114042036.7332 | 24447437.1088 | 24420341.9713 | 840987613.3571 | 22006173.2003 | 1088617658.8038 | 6419931737.2195 | 634077160.1989 | 191875440.5114 | 2.5222e+12 | 2298343.5685 | 932107.6022 | 1743012.8442 |  |  | 2.6995e+12
477 | 1129563556.1655 | 1207315599.3213 | 199169622.7615 | 167452141.4894 | 961068145.0695 | 26421827.1531 | 188348472.5107 | 310045036.7435 | 468545269.0718 | 151413509345.6279 | 1942946024.99 | 2040061839.1831 | 2142722446.719 | 197475470.5449 | 627203099.0932 | 689794635.6746 | 737397918.2482 | 319162427.1249 | 557020991.0546 | 27575950.7679 | 120700015.1034 | 20784076.25 | 25661917.8196 | 874852486.2444 | 26627471.5786 | 1065186081.1974 | 6803161769.5417 | 660217455.5387 | 148558300.8718 | 1.3988e+12 | 2501362.9804 | 990532.4134 | 1669463.6977 |  |  | 1.5739e+12
478 | 1157973877.3449 | 1178389589.1845 | 220089985.9322 | 179202569.3647 | 1087486991.9048 | 23281107.8363 | 227111069.8675 | 309397869.1764 | 499856081.7703 | 117609318931.019 | 2077130550.723 | 2095478303.1066 | 1983552854.7976 | 202260453.5797 | 600884515.8538 | 588021959.247 | 813209967.8221 | 307278451.3813 | 565053488.9686 | 24702124.533 | 129050633.4992 | 24421452.4526 | 21833622.6061 | 777191448.2957 | 27027457.1687 | 884397868.5365 | 6144331805.0767 | 696893923.1237 | 188873199.1916 | 1.8357e+12 | 2496622.6088 | 933832.6519 | 1680912.6987 |  |  | 1.9763e+12
479 | 1230641593.6372 | 1084247758.4218 | 184798063.9887 | 173611521.0878 | 1068325540.828 | 27361383.5433 | 204474765.1837 | 306122720.9285 | 465998036.055 | 136293767441.8144 | 1546929241.9374 | 1881242014.5339 | 2109977323.2316 | 192829726.7771 | 465169414.3471 | 685797886.0112 | 717017044.425 | 345797629.1995 | 492908888.951 | 25398208.2387 | 115700722.338 | 20986200.5856 | 24421337.8472 | 726589128.1462 | 25759861.9809 | 1125320146.6496 | 6463445240.821 | 666343751.9285 | 195451573.3878 | 1.6894e+12 | 2368653.5615 | 953731.7926 | 1492545.2723 |  |  | 1.8483e+12
480 | 1193376443.3825 | 1224315684.0002 | 222255131.5362 | 162420904.7634 | 1061735620.0944 | 20656482.9614 | 195968498.4634 | 308086666.2835 | 452811333.6653 | 147742400288.8112 | 1905950700.3944 | 1949426696.1831 | 1849752655.3639 | 186859407.9354 | 592425461.9957 | 722868734.4967 | 720684763.6595 | 277448788.3371 | 543408370.8537 | 20616455.8703 | 131499588.2261 | 18237304.543 | 25388536.979 | 932282195.5789 | 24334957.9808 | 939376578.9818 | 6981460131.2461 | 536842046.4587 | 166997432.8292 | 2.0109e+12 | 2303590.4846 | 901495.4571 | 1619819.3625 |  |  | 2.182e+12
481 | 1190975732.6708 | 1204265010.1442 | 224066347.9422 | 165343868.5855 | 868505749.7867 | 21753761.7731 | 213074622.7966 | 305307118.5132 | 499568753.7972 | 156574048906.5073 | 1989729215.6388 | 1809583820.633 | 1917829622.5763 | 166486837.1058 | 554782449.9189 | 550875428.268 | 803102695.3128 | 297068146.0642 | 554013210.7201 | 24279411.0782 | 122967595.3638 | 24520137.8161 | 18329947.1609 | 882085353.601 | 27057731.5378 | 883018463.2707 | 5558036627.3727 | 623852027.7981 | 181056471.3293 | 1.7582e+12 | 2405200.6709 | 997828.6451 | 1611433.8259 |  |  | 1.9364e+12
482 | 1166124607.4485 | 1195255992.5465 | 214488001.722 | 171304975.3025 | 1032036710.61 | 23569273.9692 | 215825066.5582 | 325529993.3242 | 484811352.0076 | 149073451053.3054 | 2046055352.7974 | 1691898864.4656 | 2156899268.3553 | 193417952.0779 | 622788755.5782 | 713787988.6982 | 810181562.7329 | 345529635.5883 | 608085208.1261 | 20743537.9461 | 118137687.9256 | 23074645.7334 | 19553571.0396 | 895824832.4837 | 21759999.7398 | 1019241888.7668 | 5832704520.8002 | 680927590.9822 | 166044892.1241 | 2.6174e+12 | 2524467.5338 | 920376.2702 | 1701420.4976 |  |  | 2.7893e+12
483 | 1187254461.1644 | 1221885417.9161 | 214386136.7561 | 146415387.141 | 1057409403.3595 | 26061487.0184 | 204937799.362 | 300762418.9654 | 464954372.9089 | 140366133969.3555 | 2037852993.9365 | 1639989358.9286 | 1951599344.7028 | 183757433.047 | 583852581.7299 | 696862537.9941 | 845774071.0404 | 345610798.3014 | 582348845.2486 | 25832298.6481 | 91492399.2801 | 23553317.4088 | 24327443.9157 | 904011423.5325 | 26750392.5432 | 1057087981.552 | 5012895777.7323 | 683361304.3553 | 172796580.3262 | 2.4451e+12 | 2589484.871 | 890809.9371 | 1815920.3309 |  |  | 2.6072e+12
484 | 1205630510.3542 | 1132326206.8962 | 208388813.2777 | 171159411.5933 | 1020621992.2397 | 24861303.0756 | 208469264.8581 | 301183443.5521 | 481257965.7759 | 141658533153.5772 | 1998244625.9444 | 2065951151.8363 | 2147383502.564 | 188029222.0276 | 578283665.3599 | 623895452.9899 | 927948415.8817 | 311753194.2323 | 560652623.6259 | 24832198.6965 | 136309521.2428 | 23490778.0923 | 24278945.9481 | 761290693.3229 | 29419645.3015 | 1210932418.7741 | 7045329826.6232 | 678890965.0193 | 126747127.9432 | 1.952e+12 | 2777935.8312 | 987728.7506 | 1505790.8409 |  |  | 2.1178e+12
485 | 1234687822.0312 | 1145121350.8345 | 208005140.886 | 172811264.4404 | 1062952587.4594 | 22882264.8339 | 212978422.9975 | 312893587.9488 | 478213356.1308 | 152186101670.736 | 1326324425.175 | 1729980121.667 | 2071080220.4298 | 194736214.6342 | 560950149.953 | 689149042.325 | 650677561.1807 | 286291686.8257 | 553274252.3969 | 20575588.3213 | 115640457.8759 | 24948714.4387 | 25610729.926 | 905590399.6533 | 26604879.0772 | 1186768660.0821 | 7042286195.7586 | 670482333.7634 | 196693169.2812 | 1.7971e+12 | 2341770.9167 | 918569.705 | 1478772.5703 |  |  | 1.9724e+12
486 | 1137286683.9815 | 1131756187.2366 | 206478223.4339 | 170943826.9984 | 961475293.0189 | 22076283.0869 | 211698335.2546 | 296600871.238 | 488288945.2283 | 159814582833.4781 | 2001580106.8891 | 1974538477.7651 | 2088939373.0359 | 196968582.459 | 572623314.031 | 544469430.605 | 866799054.5921 | 315952781.131 | 614883592.0954 | 23227931.2081 | 116811278.9032 | 23554520.0232 | 22132838.1177 | 812082770.8575 | 29566520.0904 | 1066250192.715 | 6167228252.3761 | 639035282.8479 | 190763805.8431 | 2.5448e+12 | 2476906.7798 | 980442.0195 | 1628189.6134 |  |  | 2.7276e+12
487 | 1253119290.7563 | 1216188849.9564 | 215168708.0351 | 161743192.3711 | 1058185783.1915 | 19276259.128 | 220022032.8052 | 303237127.8092 | 486919334.5693 | 100181495404.2552 | 2010038959.3296 | 1935354670.8987 | 2133597183.3864 | 153909930.59 | 627896566.6391 | 631664273.3216 | 924440966.8575 | 265563452.9388 | 580846379.7854 | 27672250.9576 | 119082198.8339 | 23699665.7814 | 25759780.6918 | 886870936.9986 | 28351888.7472 | 929225484.0056 | 7170817812.0252 | 627233118.2448 | 187757607.5374 | 1.7798e+12 | 2578234.0018 | 996436.1162 | 1658135.8418 |  |  | 1.9042e+12
488 | 1218229654.0318 | 1106152534.7583 | 212112658.2715 | 169200716.5182 | 1070013534.7127 | 22568940.6 | 215462811.0539 | 316285684.3719 | 475427434.4774 | 144891374066.42 | 1976263231.3114 | 1688060200.3663 | 1622151106.6507 | 199790770.7806 | 632218138.6463 | 719547934.9906 | 885014735.3144 | 323595864.8591 | 586272869.4115 | 24340774.8781 | 108858230.5169 | 16449763.4502 | 21932214.8391 | 903179359.1899 | 24044763.364 | 1019746037.0642 | 6024949884.4722 | 660321824.9366 | 195088313.4676 | 1.7172e+12 | 2505607.5322 | 962090.8092 | 1659496.2409 |  |  | 1.8845e+12
489 | 1201664475.6086 | 1167688207.3088 | 220433031.5407 | 168361484.5636 | 1061473985.1513 | 23483485.3524 | 203236277.3849 | 316633725.6541 | 481658685.5073 | 141420508564.5723 | 1872660189.7594 | 1891213273.392 | 2016963290.9819 | 198700258.6627 | 568956557.9062 | 703559772.2548 | 844449292.5825 | 332923994.8569 | 540156565.5165 | 24775560.9213 | 125227154.4904 | 24467345.0793 | 21661703.4242 | 926915430.0888 | 23471864.6535 | 1098943398.7425 | 4814928556.9897 | 696647152.7225 | 200929816.4259 | 2.0963e+12 | 2425109.9469 | 907226.5067 | 1650270.2529 |  |  | 2.2595e+12
490 | 1244739614.5929 | 1158196038.7637 | 222352026.5504 | 154104187.6098 | 1012504779.7039 | 22663784.6406 | 186320719.1396 | 314245800.0975 | 434557343.6464 | 145934716337.7852 | 1796736501.1243 | 1779520577.3669 | 2061266827.1324 | 196032960.8322 | 563752123.3356 | 658840938.5082 | 918442582.2869 | 318681483.6235 | 562310083.7106 | 22253457.3683 | 126165662.7097 | 18607398.6404 | 21962402.823 | 863995686.9164 | 28140870.4035 | 885959282.5621 | 6382024738.5724 | 581528924.0378 | 171725137.0419 | 1.7378e+12 | 2596576.215 | 927147.1386 | 1685189.1097 |  |  | 1.9065e+12
491 | 1248904798.7506 | 1117991775.0953 | 183356251.2196 | 175624626.5605 | 1055552544.3012 | 24709121.1931 | 209780183.951 | 300152179.0963 | 495374028.943 | 148512526998.9162 | 1843934971.545 | 1759636367.1892 | 2004589926.098 | 176661326.1551 | 611359647.0408 | 634565685.9558 | 613648975.9178 | 329998396.522 | 601428507.4611 | 28168595.9773 | 121872572.7188 | 21057889.1229 | 25917054.8546 | 920982643.3752 | 23027690.9681 | 1128167244.3509 | 7056696693.1373 | 688581166.2093 | 182110544.4378 | 1.4732e+12 | 2432799.8518 | 945929.4509 | 1599390.6331 |  |  | 1.6453e+12
492 | 1155087620.4758 | 1157510834.705 | 218516362.7223 | 142425480.774 | 937735404.1655 | 21332621.8803 | 193774543.8466 | 278205431.6306 | 484427828.9897 | 134347522642.1836 | 2080257503.9478 | 2162678375.2409 | 2008816431.9837 | 193767593.8317 | 627938808.0203 | 583217645.0035 | 836919519.1342 | 290812939.3186 | 553237520.046 | 27999414.0939 | 110275048.7481 | 23645999.4342 | 24139559.8168 | 926633829.0705 | 26040195.1528 | 1104151015.6514 | 5705478032.8838 | 668056083.6499 | 184421184.6466 | 2.511e+12 | 2532108.5519 | 1052896.0245 | 1505360.6602 |  |  | 2.6681e+12
493 | 1220833152.5281 | 1066156253.8742 | 203011908.8186 | 164199868.1366 | 893280250.9501 | 21608198.7581 | 202987326.1559 | 301693883.5572 | 491130078.2098 | 145642857741.5371 | 2030769657.4804 | 1894402929.4087 | 1826716416.0869 | 203002779.0425 | 517027594.6547 | 699816844.6511 | 723716513.8252 | 295988525.8793 | 578231635.439 | 24255598.4735 | 132275691.6047 | 20624733.9682 | 25694913.1714 | 853761192.0737 | 23899930.1509 | 934457175.9936 | 6737767874.417 | 614589857.261 | 146876236.6287 | 1.6477e+12 | 2651950.922 | 979597.7195 | 1692386.9572 |  |  | 1.8162e+12
494 | 1231438807.2128 | 1183507873.6482 | 224722301.8347 | 144991385.3213 | 1081140991.0373 | 21392069.6673 | 206532137.9191 | 314195359.6908 | 494174781.5466 | 116152083207.5291 | 1995963116.5009 | 2033658404.491 | 1952591029.9767 | 178189472.0353 | 677426800.1835 | 699276352.9977 | 893256482.8138 | 319357040.8944 | 558827220.6209 | 24831850.1047 | 120075922.1654 | 23317220.9149 | 23659229.8487 | 778745717.5135 | 27360231.4047 | 1142308823.447 | 6509967438.3634 | 666801695.1106 | 165821223.439 | 1.7697e+12 | 2666351.7633 | 940481.7808 | 1850893.7369 |  |  | 1.9095e+12
495 | 1193754435.828 | 1147414122.7091 | 204898153.2044 | 173028781.0809 | 1004636594.9853 | 20977604.4348 | 220891297.33 | 321717981.875 | 482587151.6024 | 128288823511.7296 | 2069253182.606 | 1583194301.4217 | 2182629579.7776 | 156555051.5005 | 611101182.0041 | 697828983.1106 | 858987421.9835 | 305898295.3348 | 567922198.843 | 23139186.1089 | 101394295.759 | 23223050.0282 | 25524323.004 | 812806150.1152 | 30607131.8844 | 1043207898.2677 | 6603546283.2732 | 699633337.8876 | 192838753.0876 | 2.4089e+12 | 2446669.7603 | 935767.9395 | 1490370.411 |  |  | 2.5606e+12
496 | 1209669818.7011 | 1190346892.6279 | 218390828.6477 | 164348242.9843 | 1002998035.9674 | 20561126.208 | 207990396.6633 | 313980289.8845 | 476553046.5197 | 119891202919.3818 | 1740771634.275 | 1834381055.5914 | 1941515339.111 | 188738453.6401 | 625618951.8953 | 548616251.9996 | 687880999.012 | 340922657.6439 | 594496509.3901 | 24390084.8863 | 130772456.8981 | 21792322.1244 | 24949828.439 | 863452629.9976 | 21602014.5741 | 1185604752.079 | 6731149120.8307 | 560131806.7822 | 179735374.7463 | 2.0542e+12 | 2772586.2155 | 936996.0229 | 1570897.2754 |  |  | 2.1972e+12
497 | 1192753228.375 | 1070179917.9535 | 208697855.9449 | 163258615.4611 | 1023593612.0894 | 20755471.2886 | 213481044.985 | 326460231.7782 | 488973586.5468 | 147163589047.6221 | 2029603184.2625 | 1858312335.3111 | 1881383550.0428 | 184536892.3813 | 622673359.9514 | 595114910.933 | 837922655.6497 | 275584674.3881 | 598011092.8248 | 26295255.9937 | 94358568.7653 | 23557929.9802 | 25385812.2063 | 804633269.0714 | 31088359.387 | 1034422728.3272 | 7109076229.2074 | 630590394.3671 | 165843035.3088 | 1.3869e+12 | 2571013.062 | 962317.4813 | 1533715.4036 |  |  | 1.5576e+12
498 | 1056761104.8872 | 1134612354.2735 | 208698665.1049 | 173157663.7415 | 1042572005.6073 | 21411824.4554 | 211809882.3375 | 316652460.6484 | 455606742.0241 | 124477343990.2456 | 2074249085.2843 | 1997220106.6329 | 1876232316.2965 | 199576820.4253 | 543834562.5032 | 695151159.6133 | 926869838.9713 | 274095964.3057 | 555674202.0701 | 27771721.9423 | 125137264.297 | 23741103.1481 | 21386929.767 | 776941323.9415 | 23925221.1282 | 958322197.2256 | 6430842909.2753 | 590945313.3641 | 191488819.7008 | 1.93e+12 | 2505743.6391 | 922229.5425 | 1726822.9065 |  |  | 2.0774e+12
499 | 1201704486.3663 | 1174951748.3732 | 204091107.8611 | 155044507.5777 | 1071114231.8103 | 22544811.2481 | 200746946.9684 | 316859480.5074 | 496674700.7351 | 144869532743.7476 | 2049053904.7434 | 1729864333.389 | 2019539179.6198 | 195517334.5384 | 624006840.369 | 704478890.7301 | 879206269.6125 | 327091475.8526 | 558294746.1814 | 25496958.3925 | 133498759.4409 | 19462409.5134 | 24002432.0394 | 915224705.9118 | 27940003.1212 | 1075546450.9824 | 6252695184.0672 | 679677828.2514 | 167661911.0795 | 2.2734e+12 | 2490698.0916 | 1001201.7173 | 1645400.4016 |  |  | 2.4416e+12
500 | 1159554953.8298 | 1225620474.5996 | 212888703.3817 | 161453674.7244 | 1066720423.5703 | 20277913.8191 | 200453719.9651 | 328474389.0034 | 383674191.8781 | 150532432441.7401 | 2041549721.6857 | 1841319796.7797 | 1879862121.9252 | 190560422.3728 | 673487431.4888 | 686257389.9678 | 856902061.7255 | 339668320.4814 | 593904444.8399 | 27176906.533 | 117262711.3414 | 24796681.2082 | 20989390.9539 | 809242789.6045 | 29915709.4807 | 789686646.6029 | 5453828665.5807 | 609943322.8868 | 160993694.3317 | 1.9011e+12 | 2457418.2467 | 952649.1086 | 1489108.9206 |  |  | 2.0735e+12
501 | 1170485568.0791 | 1194921608.5881 | 201367515.1493 | 159792055.0965 | 934610113.6749 | 21401997.342 | 205393361.167 | 312811438.4499 | 482935184.2872 | 141122995700.9545 | 1947215040.2196 | 1847382381.0951 | 2201358695.8571 | 157638159.7134 | 561815379.6697 | 622978554.7343 | 784517539.4734 | 243987080.2224 | 492283275.8482 | 25160546.5172 | 117894540.2394 | 24101740.4001 | 25735313.5059 | 923828998.8389 | 29835274.9839 | 1133368321.9423 | 7098368025.3006 | 512001398.6235 | 197027544.6247 | 2.0227e+12 | 2334191.0724 | 950250.7006 | 1708313.861 |  |  | 2.1875e+12
502 | 1162041344.1596 | 1196427010.0558 | 200344626.9192 | 180669301.7268 | 990863127.9671 | 24747918.003 | 214155534.3881 | 275113256.4619 | 466701073.6818 | 151240135894.5613 | 2062656304.0397 | 2182295097.7186 | 2016669366.0172 | 168849792.1055 | 662149732.3821 | 630673414.4733 | 807851314.2107 | 322995187.3208 | 568231547.9223 | 27033843.0929 | 112636797.0069 | 24376509.7853 | 23334507.8058 | 850174949.126 | 25487800.0099 | 1170192759.0735 | 5052917015.5921 | 707228206.4835 | 154069166.1031 | 2.6197e+12 | 2828076.6128 | 921851.4476 | 1837256.2086 |  |  | 2.7932e+12
503 | 1233844623.4487 | 1065962842.7484 | 223294472.1095 | 177019116.4814 | 1029660643.0315 | 24316639.4053 | 216377304.4274 | 329378987.7245 | 427864431.2501 | 117924248382.7604 | 1450412701.8157 | 1960725357.8339 | 2179753729.4357 | 199441838.8129 | 627486845.862 | 620813969.9896 | 875631515.7222 | 320348175.121 | 614313564.0278 | 22166655.3977 | 119688494.5281 | 24789902.2136 | 24420563.3147 | 829316021.8558 | 27750806.878 | 905735276.5036 | 5664900116.6023 | 654505972.0307 | 195664783.5454 | 1.6143e+12 | 2460777.9455 | 905031.8504 | 1577183.9023 |  |  | 1.7542e+12
504 | 1034613207.6925 | 1171661061.7802 | 179975689.4277 | 159924445.5105 | 1052145060.4887 | 22583821.6993 | 219477271.329 | 324679986.7396 | 480946574.1002 | 131426496571.8062 | 2044584377.9203 | 2090322864.3868 | 2023628416.4329 | 185873232.4035 | 473475865.7808 | 671763637.0293 | 772690522.0728 | 334011364.0389 | 522376918.9647 | 22263137.7681 | 120178493.2899 | 21872501.2932 | 23739560.4174 | 928826846.5907 | 28846126.6162 | 1003071929.7141 | 5035707323.8166 | 654191777.0735 | 185744965.017 | 2.1093e+12 | 2585821.387 | 932753.8142 | 1646654.756 |  |  | 2.2626e+12
505 | 1163366716.2654 | 1134638788.253 | 210906143.8925 | 176485382.7527 | 1079755586.7396 | 22752886.4832 | 221939009.8531 | 299659554.8351 | 455424413.7047 | 140771490739.5059 | 2015944514.3742 | 2024235647.6236 | 2059676644.9432 | 182565575.6599 | 506109260.3146 | 689661775.5362 | 900870037.7038 | 330653090.2696 | 536245150.3908 | 24687563.1775 | 133577592.7701 | 17375609.6952 | 23383136.4814 | 809785618.0345 | 30546560.742 | 927164887.6415 | 6720227373.9439 | 667587782.1588 | 193855351.4848 | 2.4179e+12 | 2517607.9598 | 935862.1034 | 1664727.1049 |  |  | 2.5822e+12
506 | 1233887837.104 | 1194937088.6353 | 181146656.6216 | 163578759.9953 | 1028012024.737 | 20360670.0652 | 212138459.0223 | 316612862.0209 | 447746353.0424 | 142327722015.117 | 1938676347.8038 | 1936111538.2612 | 2133173713.7282 | 202594800.6718 | 552823846.1972 | 706904937.6958 | 874215877.4492 | 305533398.2535 | 583597119.1857 | 28053272.174 | 104146318.9916 | 21610734.2806 | 21282317.5503 | 685983189.4418 | 23601587.0058 | 1145259342.1662 | 6343818058.59 | 573163272.4948 | 196082674.2573 | 2.2613e+12 | 2473978.977 | 986469.3287 | 1600739.472 |  |  | 2.4269e+12
507 | 1171727244.5727 | 1113098236.302 | 222351218.6014 | 156093240.5544 | 1047884236.9458 | 25056649.131 | 218348144.7264 | 314792825.329 | 479355783.9904 | 150330665136.634 | 1935606408.7944 | 1739288253.8472 | 1875686988.223 | 191302249.2354 | 616869758.1879 | 675536073.5479 | 736870518.3655 | 319373646.162 | 497562693.886 | 23339438.3889 | 120919309.122 | 22732444.1404 | 22548868.3527 | 804115575.738 | 28675885.6344 | 931978411.3517 | 6569671796.4723 | 680472630.1281 | 163817661.4808 | 1.7033e+12 | 2544407.9743 | 923321.0473 | 1558764.2177 |  |  | 1.8764e+12
508 | 1241638166.6526 | 1165379605.7496 | 207091343.9766 | 175153757.4614 | 1007815902.1639 | 24435851.4553 | 220871476.5999 | 299668576.7711 | 450930180.2311 | 145913652897.2615 | 2019276867.1715 | 1908829281.2891 | 2142604728.8158 | 200629211.0191 | 540603431.2701 | 683530643.1283 | 821076512.7565 | 341407935.8404 | 612590392.3955 | 25378464.6114 | 116215017.2702 | 22664848.3916 | 25397857.2149 | 948793955.1207 | 27390468.6607 | 1061610629.4141 | 6134971590.6452 | 696366598.4335 | 192789523.7227 | 1.9283e+12 | 2529802.1323 | 925161.6671 | 1557612.8894 |  |  | 2.0975e+12
509 | 1149938046.9681 | 1198417078.9778 | 176198890.6721 | 160621829.2943 | 966262927.7151 | 25571382.6169 | 208946515.9693 | 314767136.4058 | 442191141.3796 | 125714932797.8278 | 1844948648.9637 | 2058612116.403 | 2180364798.6138 | 183025156.2553 | 547799392.2559 | 641874099.8652 | 848749748.6575 | 330062170.0881 | 543012529.6994 | 22250817.5228 | 107776839.2649 | 23112853.1432 | 26011327.6622 | 707076696.4319 | 25039520.511 | 1088009696.8587 | 6426232956.2077 | 576255611.0118 | 201160260.5744 | 1.6905e+12 | 2660708.3062 | 946917.9587 | 1538552.6239 |  |  | 1.8393e+12
510 | 1242428120.2323 | 1162442809.0763 | 212356463.0635 | 173499878.6514 | 1063143275.581 | 20927097.9888 | 186898678.9776 | 328339486.895 | 473727688.424 | 155275610451.8279 | 1972473791.7515 | 1729930149.0832 | 2135476013.1669 | 201617545.9496 | 630991996.4436 | 653969699.9339 | 811501862.0276 | 320823809.0086 | 578418684.483 | 25855464.6195 | 112244677.1553 | 24536987.4937 | 24027363.5781 | 813181457.3538 | 29893822.6342 | 1075769283.376 | 6739567246.6003 | 675733312.8895 | 146288980.8737 | 2.4857e+12 | 2536168.1189 | 1003969.1612 | 1763679.7833 |  |  | 2.6646e+12
511 | 1225624267.1399 | 1049866401.7986 | 186794091.944 | 168144609.0298 | 1079131969.9427 | 23644395.5811 | 204297751.1369 | 318669462.9901 | 464965283.8876 | 134173998618.3127 | 1772778864.4637 | 1993006600.0053 | 2090494943.6336 | 197526109.8051 | 607439294.7448 | 672772465.5663 | 821622465.2125 | 290568540.1839 | 471609447.7656 | 20563005.6458 | 113079408.571 | 22948846.459 | 25937648.18 | 880689700.6356 | 25528887.4766 | 1162317676.5852 | 5315200746.0591 | 612647599.3782 | 185350685.5533 | 2.312e+12 | 2434047.9063 | 918522.6534 | 1520702.0118 |  |  | 2.4682e+12
512 | 1178693815.8364 | 1201315818.5139 | 198100101.7051 | 180787550.1556 | 1085307564.9264 | 23767129.5668 | 189362835.4092 | 292839199.3548 | 460511550.5961 | 128077064921.7 | 1741312530.9325 | 1892916391.1989 | 1685832291.6093 | 184499322.157 | 572038654.8685 | 670740649.6405 | 865632573.9169 | 357282995.4413 | 485097335.7784 | 24888685.8532 | 122504885.4797 | 23526236.7284 | 23891712.9083 | 762479594.8991 | 27498803.5114 | 1110409341.967 | 5437548042.7806 | 547413917.2639 | 194166668.3256 | 2.1163e+12 | 2544923.3808 | 919092.9273 | 1696379.5894 |  |  | 2.2659e+12
513 | 1173775458.672 | 1188288152.7106 | 217918927.0458 | 152776916.0415 | 955834959.7198 | 20063157.6293 | 201012915.5724 | 310241272.9808 | 486360604.6145 | 155419505585.3468 | 2030120278.001 | 1910029880.4849 | 2093162282.0093 | 177234217.3371 | 605091842.6886 | 640219212.9184 | 746915049.5464 | 306755084.0502 | 592185553.8123 | 26678273.9938 | 115756771.3128 | 24206147.1783 | 25165556.6583 | 768797539.3612 | 27253095.8595 | 1159048458.691 | 6482519573.8625 | 459545886.387 | 185946129.0991 | 2.2001e+12 | 2270302.3358 | 925923.4212 | 1487977.8309 |  |  | 2.3786e+12
514 | 1021174562.1334 | 1120052859.9393 | 221198905.2531 | 156522392.5284 | 1036731874.0134 | 19488818.6071 | 204112828.171 | 288670197.0431 | 494910901.6078 | 149894678221.1482 | 2023096775.3438 | 1857238247.8429 | 1925364279.692 | 192299456.9983 | 655355654.029 | 642238890.2257 | 907020084.2906 | 304148421.4418 | 598700606.4336 | 19285847.6708 | 126367095.1695 | 23402406.1858 | 21035283.6439 | 874963320.0942 | 28590077.2559 | 1210276741.1713 | 5791381032.4864 | 545002610.8199 | 158275887.7982 | 2.1751e+12 | 2379285.9319 | 1007044.738 | 1537918.3519 |  |  | 2.3475e+12
515 | 1232542975.7444 | 1214385445.4431 | 208790261.6781 | 169201991.5732 | 1086512816.8582 | 25188016.0517 | 220354463.4043 | 293899400.0584 | 466941086.3744 | 127248765862.9416 | 2012419945.662 | 1992486262.158 | 2198346029.861 | 174778342.4017 | 506490775.7265 | 698638939.745 | 862495321.5835 | 321534579.3374 | 600038697.4842 | 24437236.6997 | 103306320.2322 | 23007691.4309 | 25925699.442 | 786141132.4962 | 28306837.4376 | 1034102174.6526 | 6449952224.9314 | 638206972.248 | 190511310.8465 | 1.8046e+12 | 2546225.9928 | 990810.9381 | 1628287.1989 |  |  | 1.9554e+12
516 | 1185022718.5255 | 1169923287.7042 | 209833839.5805 | 164833337.7427 | 1071225597.1615 | 24090677.4998 | 217415635.2997 | 290357646.6123 | 455089303.9469 | 151386116151.3762 | 1588399396.8429 | 1817361874.8401 | 1656655653.2677 | 199454892.7982 | 652014231.8192 | 657409525.8641 | 868458907.0189 | 329568957.7952 | 522433713.2502 | 28214956.202 | 111133884.4991 | 23443070.934 | 25965237.3663 | 871545530.7309 | 29068896.5184 | 1169589751.1616 | 5889020166.2062 | 669658177.2087 | 159809327.0393 | 1.9739e+12 | 2582952.7793 | 916694.8608 | 1691586.5283 |  |  | 2.1473e+12
517 | 1229961920.1344 | 1086840068.2431 | 185384768.4677 | 174260283.4636 | 1008408319.782 | 22417508.8652 | 167559914.6936 | 324247232.0255 | 473125136.1592 | 135792833877.2141 | 1791905433.1874 | 1533696939.4817 | 2120303457.1959 | 180384041.463 | 686365366.8671 | 712653773.4697 | 672757597.2703 | 280464842.0319 | 592065260.3899 | 22925623.6617 | 79983143.4353 | 21575147.311 | 23531001.6651 | 826621109.5889 | 26890862.3254 | 1065522251.8015 | 6547677269.169 | 683650784.5758 | 169578826.32 | 1.5445e+12 | 2331237.6038 | 920834.5732 | 1528481.2173 |  |  | 1.703e+12
518 | 1194833632.6972 | 1216598545.7848 | 208314699.6935 | 172627627.6708 | 1075780411.1045 | 26527512.5494 | 216616437.5358 | 315773951.7999 | 492079545.3282 | 144151180730.6717 | 2013209761.7658 | 1812743560.7105 | 2062774000.502 | 199481264.9152 | 637707725.1006 | 715602019.7162 | 811880090.6526 | 353602608.5534 | 591106942.2458 | 26621778.6335 | 131567644.1997 | 21653208.6461 | 23948447.9099 | 750886865.8186 | 28416755.0023 | 975619040.4853 | 4960246613.8554 | 682246308.3678 | 199320801.0236 | 2.6601e+12 | 2666852.8858 | 978740.8106 | 1640809.0129 |  |  | 2.8262e+12
519 | 1168919771.7456 | 1204806106.6288 | 213687139.5516 | 177498693.8278 | 1010800542.0861 | 22272601.9038 | 214261382.1795 | 307703193.2849 | 438963803.8319 | 122213622330.7375 | 1841992175.0813 | 2150852824.6053 | 2092620269.672 | 149647341.3839 | 621850447.3433 | 630086789.052 | 772270123.6862 | 292354622.4167 | 576175218.2288 | 25082498.3087 | 111950477.3292 | 23531620.8725 | 25129871.7383 | 664515007.1234 | 23208406.4036 | 1084673949.1469 | 5553964048.827 | 658735046.0755 | 189754642.7774 | 1.8724e+12 | 2475776.4236 | 891131.4563 | 1543598.0798 |  |  | 2.0169e+12
520 | 1108832964.0315 | 1198122984.1963 | 214402031.187 | 157498654.538 | 1048565643.4111 | 27203224.82 | 204987646.6694 | 327178669.4362 | 445274368.7257 | 127037128001.337 | 1805750467.0146 | 1861850346.124 | 2071978171.1858 | 187633126.3898 | 623138529.0928 | 714996840.7524 | 872283226.0429 | 306664822.8521 | 536834357.6153 | 22629896.473 | 129326936.4188 | 23257191.3622 | 25813212.1447 | 844186443.5234 | 27136885.34 | 1176187400.9744 | 6529819163.211 | 471683030.7371 | 187500441.2837 | 2.0631e+12 | 2435973.6948 | 936718.225 | 1609298.4252 |  |  | 2.2133e+12
521 | 1262930034.3114 | 1178486895.21 | 204346571.246 | 159130533.6179 | 1079854485.488 | 27113103.4454 | 200642910.8752 | 277281203.8137 | 475627487.4467 | 161621207875.0104 | 1878990451.2952 | 2092938392.1232 | 1852821789.1285 | 201266979.9625 | 641088369.4627 | 490796823.0087 | 847860365.7002 | 348613767.6465 | 596252903.7538 | 22074407.0188 | 104891504.2333 | 16580217.9944 | 23858548.3664 | 936558412.6869 | 22859074.3589 | 1212090533.6093 | 5183174547.9574 | 600642338.1042 | 185204242.0862 | 1.9666e+12 | 2569554.4222 | 948308.804 | 1609778.797 |  |  | 2.1503e+12
522 | 1179450321.3335 | 1147541804.487 | 216306360.7388 | 168515574.5228 | 1000550561.6374 | 21903713.1203 | 213100657.0765 | 304623260.3758 | 411311998.5021 | 150240689972.2832 | 1999151134.7956 | 1903154376.5556 | 1735823176.6568 | 185468719.878 | 629236180.5887 | 720117039.1638 | 905135369.6241 | 274396997.2584 | 575238016.7452 | 23737091.7523 | 120212242.915 | 21357200.0234 | 25711664.0813 | 885955361.7385 | 30108976.929 | 1038210108.5212 | 6078312258.8238 | 614475410.9479 | 162183558.9208 | 2.0914e+12 | 2226717.2432 | 1012525.8622 | 1614446.346 |  |  | 2.2642e+12
523 | 1255476336.0243 | 1179818439.3579 | 218649880.3686 | 175049789.5619 | 1044659231.5122 | 25283312.9848 | 207418821.7617 | 320246227.8259 | 496659338.102 | 138197425241.0169 | 1650186383.0059 | 1997843843.4189 | 2011024842.8099 | 137968674.585 | 456525789.3337 | 672643631.6681 | 808587940.9784 | 321788391.8557 | 608947230.1492 | 24062000.6371 | 118124504.5347 | 20827417.5892 | 20772405.6185 | 913221086.4399 | 29116572.2206 | 1193871455.0831 | 6180181714.3518 | 685693885.1849 | 176936707.5715 | 1.7794e+12 | 2615260.0397 | 881917.8478 | 1530434.106 |  |  | 1.9405e+12
524 | 1206720136.2729 | 1164918315.8542 | 205859780.6275 | 177343836.3792 | 1070655497.9213 | 23928432.0618 | 220780168.2724 | 327331068.2117 | 475178583.0581 | 155529840791.0127 | 2009670789.8389 | 1875642109.6049 | 2061981573.8425 | 196295139.9858 | 593539811.9356 | 601038435.2042 | 796288133.1432 | 322851176.9231 | 597338010.7519 | 24122854.9303 | 102677119.3191 | 24739880.5068 | 25174143.413 | 941196232.8815 | 28226698.3966 | 927098080.7292 | 6625972137.9933 | 674857407.3426 | 191642278.3889 | 2.2936e+12 | 2503611.4663 | 943155.285 | 1727680.4402 |  |  | 2.4727e+12
525 | 1203550169.5561 | 1225287998.7726 | 215618887.6997 | 166086357.2588 | 1071403344.2166 | 27457645.1038 | 209830824.6169 | 310510535.1274 | 495985924.2692 | 131530172244.2973 | 1753762571.9861 | 2093780112.3871 | 1884009793.2865 | 180646939.4094 | 486176714.2268 | 724654085.2166 | 837979849.4647 | 242753006.4327 | 593966760.661 | 22017007.0191 | 106186821.6942 | 24777325.8106 | 24507535.9038 | 877759182.3503 | 29649371.9121 | 1094127135.8362 | 6317807378.3002 | 666709598.203 | 179523810.2021 | 2.0392e+12 | 2501869.4208 | 918753.6671 | 1640081.9103 |  |  | 2.1938e+12
526 | 1165031556.7563 | 1224200976.8688 | 219620625.9374 | 165060504.5542 | 1003564881.1754 | 21892543.2888 | 195384334.5708 | 301458678.8104 | 462167467.6551 | 157018029979.9974 | 1942007655.9405 | 1766365803.2733 | 2028721759.54 | 188007392.6379 | 503438767.2568 | 682138916.3681 | 739562290.9288 | 345590011.0845 | 506603206.7004 | 27854257.327 | 116398534.8951 | 19317201.3427 | 24892073.1891 | 815420341.1059 | 28468845.337 | 1006449057.496 | 6589331903.3839 | 660117554.1165 | 199227804.1083 | 1.739e+12 | 2649013.5802 | 884600.3216 | 1621736.1688 |  |  | 1.919e+12
527 | 1179860150.69 | 1219168279.678 | 200747698.3897 | 180363144.0381 | 1051506422.9279 | 20753191.8209 | 193955252.0149 | 327169059.2587 | 457393419.9913 | 151921837044.4386 | 1977822389.7334 | 1864331213.9666 | 1980887018.4689 | 200758118.71 | 661826899.1759 | 635510903.9881 | 704498811.3901 | 343415005.7093 | 561219010.1761 | 25756164.3132 | 121854892.3477 | 20549663.4429 | 24858055.623 | 890711367.9978 | 28493029.2417 | 973489976.0245 | 6528121396.9071 | 650509488.5815 | 175049048.3359 | 1.3642e+12 | 2371613.8919 | 977051.2266 | 1640123.4783 |  |  | 1.5393e+12
528 | 1232740259.5786 | 1104860651.0521 | 216172225.0576 | 157096133.6727 | 962768390.7429 | 28648270.746 | 217033783.2774 | 328839325.803 | 500239714.4421 | 128416226198.5837 | 1868400386.4015 | 1833216627.3508 | 2037091183.8592 | 196770651.1415 | 481088884.213 | 627146913.0239 | 843258358.817 | 302800134.9985 | 604849794.9218 | 23330039.383 | 127186109.8149 | 18914546.0302 | 24578087.039 | 873692627.3407 | 25874870.2007 | 929116389.5983 | 6858748137.8723 | 545260428.8469 | 177309945.9495 | 1.3774e+12 | 2443540.2552 | 995472.4244 | 1605402.9978 |  |  | 1.5289e+12
529 | 1240925683.7245 | 1197576506.3614 | 202309765.8374 | 172791644.2506 | 1086241337.1376 | 23227050.4251 | 198283074.2345 | 327059195.5257 | 472560579.6402 | 142913313597.0725 | 2023522581.365 | 1824719043.5044 | 1842727974.233 | 199702170.8785 | 616508022.446 | 709504827.6111 | 770337794.8625 | 301947708.3925 | 606731085.4249 | 22315112.3841 | 125604577.1996 | 21403253.3735 | 21973828.4597 | 937111925.1601 | 22447480.5249 | 889934908.929 | 6672457848.9222 | 580416155.6721 | 196701719.9856 | 2.7085e+12 | 2732954.6902 | 945290.1763 | 1616561.6707 |  |  | 2.8747e+12
530 | 1240693671.3002 | 1207237667.3349 | 205996090.2422 | 175910076.0262 | 1035629039.409 | 25526504.2657 | 194358665.965 | 316094604.4076 | 440725364.159 | 140401400610.8317 | 1731163134.529 | 2134203807.2353 | 2037829911.9415 | 199950603.6359 | 596541743.4301 | 678365585.3751 | 747764660.5242 | 277478188.8947 | 570132364.8815 | 25287775.8001 | 116658234.2524 | 22791795.4415 | 23276406.272 | 793307911.0693 | 28876546.3694 | 1084580814.7862 | 6028680008.968 | 648988898.1633 | 197549771.8308 | 1.8348e+12 | 2464341.5313 | 963502.7973 | 1739839.1302 |  |  | 1.998e+12
531 | 1238765503.5139 | 1177071275.716 | 224087592.2358 | 163664029.9137 | 1030084567.4584 | 27438373.0229 | 213689578.9807 | 307162916.3137 | 422356920.814 | 130508984058.6942 | 1803183253.342 | 1857200572.7393 | 2114822350.453 | 201578251.4119 | 607836546.9176 | 700930642.5752 | 735885425.1255 | 285475650.3744 | 471848849.3994 | 25647564.0907 | 120200438.4104 | 24380023.8771 | 25070555.49 | 835779421.7981 | 27922938.8199 | 1094527177.8012 | 6379281256.0137 | 545386671.9878 | 177810994.5547 | 1.9948e+12 | 2305967.5126 | 976788.1585 | 1707029.7182 |  |  | 2.1482e+12
532 | 1100939774.3275 | 1108914980.1079 | 216994338.8923 | 149466624.7297 | 1005876594.4778 | 22133731.942 | 196342438.8658 | 320969534.6219 | 484260061.5189 | 126419497743.956 | 2097507910.5136 | 2095827863.5565 | 1924745969.2774 | 183238754.0058 | 562972596.4861 | 669645869.027 | 632798270.3157 | 312416596.1128 | 538906344.7411 | 25630019.8109 | 115152658.6303 | 19474749.133 | 22127616.5627 | 818678804.326 | 27334035.8466 | 1185162238.0659 | 6398741460.0065 | 667351689.2796 | 201918032.2372 | 2.4498e+12 | 2487475.3862 | 911777.7771 | 1707484.9851 |  |  | 2.5993e+12
533 | 1260731498.4929 | 1125445646.9343 | 207061836.7543 | 150338910.8718 | 975270521.1686 | 26905380.025 | 206224178.6051 | 314377337.8126 | 489406303.5975 | 123068142322.8671 | 2052642359.0323 | 1687747648.4357 | 1827848906.0003 | 189799216.5765 | 655028283.9296 | 642378391.6467 | 808795450.8781 | 279366044.5465 | 580230562.9018 | 27814738.6039 | 109175258.0059 | 23531425.2235 | 20214793.4102 | 811161804.9748 | 25853148.4673 | 1187317458.1922 | 4771023342.0453 | 695136879.5905 | 195698022.9576 | 2.1096e+12 | 2342119.4902 | 909764.4604 | 1537669.4879 |  |  | 2.254e+12
534 | 1236095354.9154 | 1199749678.1752 | 212350032.1794 | 170429682.1904 | 1077988694.8686 | 25385501.2167 | 214263324.8937 | 293474203.3294 | 457247048.0138 | 151224361954.4054 | 1919263247.3257 | 1990958699.2494 | 2179710751.1312 | 186773550.8362 | 596619140.0859 | 710079482.6024 | 813523215.7085 | 336649727.5416 | 614552671.7597 | 20251907.603 | 105621053.4658 | 24507615.0704 | 23411847.2762 | 817383760.2003 | 27815455.5836 | 1012496751.2027 | 5897728865.4413 | 684199595.7634 | 193977745.7255 | 1.7816e+12 | 2649622.8029 | 989875.6363 | 1733825.3523 |  |  | 1.9559e+12
535 | 1118256456.5191 | 1193866341.929 | 225660501.8042 | 181215177.8426 | 1068124247.6359 | 23694982.7747 | 215281526.0007 | 283528433.2442 | 464016514.8497 | 149014295690.904 | 2025567407.0292 | 1998520428.4392 | 2021396490.514 | 196731665.647 | 513036425.6946 | 703558412.5817 | 824596115.1086 | 319626404.4361 | 510704780.247 | 22650772.9824 | 117697194.4611 | 24585483.1143 | 24421683.0876 | 786386392.7824 | 29386026.1952 | 1184750155.8263 | 6674792267.2154 | 566107585.2817 | 139540014.6275 | 2.2608e+12 | 2747431.5574 | 958273.6622 | 1780683.0633 |  |  | 2.4333e+12
536 | 1130629120.5952 | 1195537498.828 | 190064229.6922 | 160610814.6998 | 972697864.0255 | 26445001.9791 | 194900307.7162 | 330301945.52 | 497608120.6376 | 146313262389.2525 | 1947240339.5325 | 1996985841.0662 | 2158337302.8986 | 194945414.6209 | 620210863.103 | 623814040.1149 | 811604647.8819 | 349165582.4614 | 601397708.919 | 23819470.7909 | 109650568.0249 | 19507457.3734 | 20046898.4614 | 779010915.8295 | 26018631.3537 | 1069796192.1704 | 5432263592.1377 | 564769906.8255 | 187517674.4767 | 2.1322e+12 | 2501936.1312 | 895848.8946 | 1730735.2594 |  |  | 2.3008e+12
537 | 1231525790.9641 | 1104272956.3609 | 196012174.6957 | 154809067.3992 | 852712386.9576 | 24274903.1787 | 222143530.8889 | 326858251.1833 | 479893275.0341 | 133402222717.7296 | 1874561741.6705 | 1712763471.4643 | 2196687803.8176 | 199186288.3037 | 503609737.4854 | 654355811.7902 | 765580921.4673 | 324650396.81 | 554353714.2066 | 23211785.2021 | 115075005.7079 | 24056059.3606 | 25188381.3397 | 876121002.3403 | 28835244.2769 | 1122913672.7728 | 6162962312.4393 | 635460691.5037 | 161497639.1001 | 1.8964e+12 | 2405584.0131 | 967633.5462 | 1811161.3046 |  |  | 2.0524e+12
538 | 1173795090.2914 | 1165351368.1849 | 194947199.9034 | 170749026.2983 | 1071384033.0946 | 22784609.2412 | 194973556.9674 | 317943931.6894 | 444282534.6394 | 117993586235.2865 | 1973991604.8891 | 1768526951.0083 | 1810014974.4309 | 201159914.7074 | 650383156.083 | 632914880.7555 | 790726468.5054 | 286316192.3007 | 577514749.4029 | 24915014.0886 | 123043277.4617 | 21789038.8811 | 24125131.6172 | 752641991.1728 | 24341142.3419 | 1212691632.7517 | 6023344070.393 | 688876328.8055 | 192644434.1505 | 2.4782e+12 | 2432766.573 | 925583.8434 | 1645442.0217 |  |  | 2.6187e+12
539 | 1240282194.2544 | 1180631760.2466 | 208546015.7566 | 168541632.8544 | 1056100397.1924 | 28435888.0537 | 221863829.2363 | 293552602.7857 | 461039053.4186 | 153554242245.1818 | 1755161824.9077 | 1860650124.3542 | 1950625358.4284 | 199879217.198 | 598076040.6858 | 678844354.3461 | 877871521.9917 | 328890197.8843 | 522308829.7161 | 26767512.0565 | 121849482.8899 | 20213396.5998 | 25174454.412 | 924426784.2429 | 26931940.571 | 1060601302.8816 | 6302425709.1488 | 601419517.4496 | 165066407.2433 | 1.9394e+12 | 2600384.0316 | 944265.4956 | 1497800.4296 |  |  | 2.1159e+12
540 | 1112133534.4723 | 1216443332.7166 | 186874128.9762 | 141289220.6829 | 1040743467.6565 | 22275984.3696 | 223251473.7809 | 304209055.9037 | 424751425.1164 | 155404954743.3084 | 2065353872.6906 | 1841750375.239 | 2093366580.8467 | 199383738.9879 | 527560428.0176 | 694169526.1965 | 806613002.8473 | 342500141.7254 | 571155414.4204 | 21722584.443 | 121142348.2248 | 24402668.6132 | 24947209.6328 | 876887254.9066 | 28241011.2955 | 951519644.5417 | 5161613656.9189 | 597929068.2534 | 166207537.1556 | 2.0424e+12 | 2489491.0729 | 969251.0656 | 1759906.2342 |  |  | 2.2196e+12
541 | 1257142887.1783 | 1021118988.8488 | 216301917.5754 | 149931154.8626 | 948561598.7374 | 23054726.1974 | 211410642.5829 | 316309872.948 | 497412246.6482 | 157419854598.8604 | 1825257334.1885 | 1820706852.7386 | 1999267994.3229 | 202976591.2729 | 598860472.6346 | 652233405.2647 | 883674856.4048 | 288762153.2678 | 537101788.8744 | 25468643.5674 | 89750945.3571 | 24077840.6687 | 23541551.36 | 820159993.9203 | 29107227.9509 | 1087304153.2455 | 6170352353.2088 | 621070514.1223 | 172916859.1057 | 2.0436e+12 | 2618018.454 | 994498.1298 | 1553626.3092 |  |  | 2.2235e+12
542 | 1172387389.5363 | 1179739145.0198 | 221034116.8245 | 161461566.2687 | 1071454742.3973 | 24463200.8873 | 206173371.5499 | 283105028.244 | 465788513.3326 | 128582281258.0197 | 2093461289.5781 | 1711847796.8482 | 2088354390.189 | 182216438.7881 | 517621846.5763 | 620825542.1208 | 775817148.9323 | 332664887.1189 | 585659456.6713 | 26475935.7304 | 111195169.7915 | 24802128.4089 | 20206200.4712 | 794434892.1352 | 31014769.073 | 1081566061.5515 | 5534141494.5068 | 577622863.4886 | 195535681.5338 | 2.3102e+12 | 2420142.5795 | 953888.4197 | 1558649.0003 |  |  | 2.4609e+12
543 | 1182132726.3636 | 1180760794.1499 | 206677172.2738 | 175492552.581 | 1046824857.2364 | 22037018.543 | 220118585.1576 | 311588666.807 | 472283089.5865 | 147613324249.6045 | 1831021138.8526 | 1770510297.4967 | 2201787268.8924 | 188817990.9789 | 562363732.7613 | 669792329.1643 | 684587310.7444 | 249722237.1883 | 553640649.6525 | 28341175.8683 | 125724272.8519 | 20326113.5426 | 24261062.6354 | 779958026.6394 | 23080276.0609 | 1054850422.9785 | 5062719049.6054 | 710178634.7315 | 175897481.8645 | 2.1899e+12 | 2573970.3432 | 922149.0236 | 1555627.9115 |  |  | 2.3591e+12
544 | 1196740723.4078 | 1203466733.4042 | 195124521.7671 | 173682102.7316 | 1023696196.8213 | 22391619.1923 | 208237261.8921 | 315872683.2743 | 485875848.2824 | 142515981767.6207 | 2033032581.7837 | 2042597267.6755 | 2075865808.164 | 196036497.9937 | 573614412.3836 | 641881171.5556 | 802212083.3349 | 346712103.715 | 603211639.5097 | 24126528.2949 | 122401358.5225 | 22748506.8406 | 22732634.8578 | 911396845.6981 | 27406067.046 | 1100005490.8824 | 6939008742.7738 | 707543269.41 | 197324412.6262 | 1.9375e+12 | 2361766.0453 | 900793.3046 | 1779806.9792 |  |  | 2.1043e+12
545 | 979662963.4424 | 1058828574.0273 | 190525445.4001 | 160959172.4717 | 1055395710.7089 | 25279338.039 | 185363532.874 | 280798832.0688 | 499387077.6772 | 137685103610.7165 | 1872307185.9588 | 2008771206.6566 | 2158737403.3047 | 197057126.2188 | 618922750.2269 | 697215024.2992 | 839862749.8577 | 286103144.5849 | 513973871.7849 | 27133103.2473 | 115800377.3773 | 20443407.4546 | 24121659.1007 | 881400316.9237 | 30708071.9405 | 1223379901.5815 | 6345563341.328 | 708277638.2477 | 197189717.8728 | 1.92e+12 | 2502512.7086 | 900592.3498 | 1609253.0867 |  |  | 2.0809e+12
546 | 1080737443.7389 | 1226324644.7197 | 220427574.2238 | 162957910.621 | 1038201864.339 | 21194787.4724 | 189384406.8509 | 321814465.0741 | 469457999.6151 | 119149992892.4498 | 1795985829.1462 | 1536706645.248 | 2209486207.912 | 176387830.6408 | 656175107.8678 | 711649484.0801 | 846997097.8427 | 264775072.6309 | 595227080.7658 | 27438060.9042 | 124501827.6745 | 24359690.4101 | 24479710.0728 | 913794475.9394 | 25892849.4713 | 1072079046.7426 | 5976843793.3391 | 653527357.2617 | 158111995.5182 | 2.1447e+12 | 2358902.7133 | 950028.7419 | 1718770.3432 |  |  | 2.2864e+12
547 | 1069095889.4646 | 1216700975.5568 | 209851812.0838 | 162793060.9361 | 1058773452.1356 | 24283975.2582 | 202307953.914 | 295247251.956 | 430895689.9901 | 141656446805.0574 | 1661962424.6552 | 2096217172.3954 | 2178381036.7421 | 180617971.0396 | 491293159.2725 | 710239286.4545 | 704394782.7707 | 328038602.864 | 597011451.844 | 26627533.6405 | 132931178.1703 | 21064987.8488 | 25974338.5396 | 727315520.1443 | 23988013.7699 | 941636372.8589 | 5463517287.5166 | 627209298.1607 | 155509992.3045 | 1.6414e+12 | 2682029.271 | 931390.6198 | 1649409.9852 |  |  | 1.8048e+12
548 | 1132669277.1956 | 1169598166.1582 | 203432899.6503 | 150599547.7732 | 952351904.535 | 21250574.8374 | 206533327.1736 | 297335851.9228 | 477355607.2819 | 145893805625.0574 | 1953633697.2458 | 1529060866.8295 | 2013613188.4186 | 196728928.0373 | 633803694.0663 | 709105802.2517 | 774045729.0721 | 313934163.0198 | 566177408.614 | 25729065.4913 | 113543568.2253 | 24125161.8778 | 24746525.1624 | 831220146.8945 | 25327170.5493 | 985397355.884 | 6881895318.8289 | 542382281.966 | 143941677.8915 | 1.6527e+12 | 2270565.3533 | 981112.0639 | 1773017.1157 |  |  | 1.8215e+12
549 | 1125435225.9564 | 1202703300.1013 | 184660354.3438 | 162135176.9338 | 820513897.4538 | 20220794.6186 | 192094680.5025 | 318019054.8631 | 437599562.3905 | 145649680322.4318 | 1946417028.6509 | 1994484469.2743 | 2128536699.2598 | 165904916.8062 | 478901025.7755 | 634758208.1864 | 902265992.314 | 307031970.9606 | 589416290.9846 | 23866497.6949 | 103131186.5761 | 17868440.6356 | 22361668.3151 | 867709489.3328 | 27920313.7885 | 1132249795.209 | 5402963944.4981 | 697285467.9198 | 181933566.4405 | 2.1233e+12 | 2437647.7724 | 984429.9573 | 1652149.7631 |  |  | 2.291e+12
550 | 1118987778.8429 | 1150801956.5472 | 198152160.8809 | 163145542.6478 | 1055500780.1561 | 18857656.4555 | 209785962.9625 | 286611555.7667 | 460278059.8369 | 161073108217.9572 | 2055004438.8194 | 2064956797.1639 | 1971688027.746 | 160362481.539 | 620343691.1911 | 692519290.9828 | 805902389.2695 | 310489591.3754 | 566451660.1004 | 26008547.0194 | 114732730.4628 | 23315101.3182 | 23508729.7903 | 764846195.2389 | 28543264.2447 | 1099091628.9229 | 6903419889.9837 | 592901382.8493 | 187196898.3438 | 1.9322e+12 | 2276975.644 | 925516.8356 | 1650036.0854 |  |  | 2.1169e+12
551 | 1197362184.0839 | 1055582142.2037 | 193728850.579 | 150399987.0704 | 1085884462.4094 | 27188815.6207 | 190139674.3504 | 327963265.6218 | 471241139.6241 | 156719145774.6063 | 1939253773.2239 | 2154283985.7457 | 2001304989.9492 | 182133261.0831 | 637661438.3789 | 614696336.3992 | 691572356.634 | 292105159.9236 | 486079274.9788 | 22270356.239 | 88679826.1442 | 23826495.2873 | 21889000.8054 | 860007414.0823 | 29874238.7254 | 1137503919.6646 | 6892551197.5136 | 664758081.4586 | 201969097.5823 | 1.5475e+12 | 2361762.0432 | 943388.9956 | 1771227.3479 |  |  | 1.7279e+12
552 | 1206511681.2203 | 1228738080.2252 | 217678439.1247 | 169305537.8536 | 1075095001.8846 | 20682337.1061 | 216083375.5384 | 299965246.2674 | 443958411.8379 | 131828643723.7064 | 1427698022.419 | 2045599712.1473 | 2151810747.6432 | 178654429.0533 | 596924558.6122 | 661033338.851 | 902307840.1269 | 263282432.919 | 501422380.8251 | 22989948.5195 | 112827827.4884 | 21417754.4213 | 24409014.7325 | 899540366.4443 | 29429800.7233 | 1054386384.7498 | 5890408882.0918 | 687224746.768 | 199903509.6538 | 2.1995e+12 | 2463981.4037 | 919544.5081 | 1671611.1196 |  |  | 2.3539e+12
553 | 1168183465.089 | 1122615356.0303 | 191934069.8645 | 157450209.4348 | 1020825594.0201 | 23481761.0557 | 219942254.784 | 313793648.3375 | 496545370.8121 | 144369717645.2699 | 1971934456.2567 | 1498881213.1673 | 2014457432.2019 | 195468555.5839 | 632424603.2813 | 573521029.2622 | 760248770.6145 | 325483245.7946 | 553987446.0961 | 24118270.4872 | 121956735.2822 | 21540787.9179 | 25080243.2906 | 828428190.0529 | 24300198.391 | 980382427.9224 | 5978028434.5824 | 607660035.8868 | 179231088.714 | 1.8207e+12 | 2467722.0155 | 951017.296 | 1611173.0463 |  |  | 1.9871e+12
554 | 1200645315.5085 | 1221392025.3853 | 194783626.6288 | 161291308.1809 | 1067826291.0461 | 23033815.5423 | 217802276.4153 | 326241668.5519 | 490452899.144 | 138074367052.785 | 1876543852.9935 | 1704222087.2177 | 2038423161.5756 | 202893397.5408 | 596112654.6069 | 698925040.1742 | 916605775.6942 | 326847223.8447 | 412669013.9701 | 24818096.5652 | 120574879.221 | 19526502.2692 | 23578071.6351 | 668693217.7919 | 30039151.9646 | 1208552968.2114 | 5756307380.0152 | 706056368.5156 | 159181721.3561 | 2.5086e+12 | 2561743.059 | 993783.9341 | 1680721.6022 |  |  | 2.6691e+12
555 | 1204791983.8201 | 1091257345.9956 | 207820872.6316 | 163279192.8116 | 1078539873.0119 | 25372832.3106 | 207888912.8848 | 267974000.1546 | 493377521.6264 | 136199757649.9928 | 2025454097.0403 | 2066027189.9363 | 2043821855.7165 | 201634776.7019 | 443958860.5617 | 722851519.8177 | 791532423.7093 | 274686141.7758 | 556230435.0731 | 23696503.1824 | 114422514.1535 | 23745307.612 | 23908123.4359 | 843316386.7898 | 30505353.8146 | 1083077328.5787 | 6718435693.7115 | 623854049.7213 | 200294914.3224 | 2.6808e+12 | 2326686.6842 | 988906.613 | 1674797.7722 |  |  | 2.8405e+12
556 | 1237272386.559 | 1170635469.8279 | 206668963.0426 | 164943365.7563 | 991164009.8464 | 18604696.9799 | 214278424.1667 | 290950900.2883 | 497264916.5337 | 137279197338.5589 | 2086630662.4535 | 1987332419.6265 | 1772101316.3463 | 198910018.7862 | 484365102.6721 | 679054684.6058 | 776644595.536 | 290630491.1813 | 596732160.3957 | 25831703.6253 | 119640034.1852 | 24648915.3093 | 25567993.7792 | 832560054.6048 | 25685067.8548 | 1181074071.3677 | 6303048162.0272 | 654384932.2337 | 187336875.8065 | 2.0671e+12 | 2767581.1768 | 947323.4164 | 1533263.8473 |  |  | 2.2274e+12
557 | 1072893274.9324 | 1118194681.9658 | 208204823.6587 | 172859620.0182 | 1087244872.4279 | 23848643.1871 | 204022598.0857 | 307401592.8269 | 454061658.6362 | 130832545635.7279 | 2047217908.8249 | 1545824032.6606 | 1861372282.1943 | 192436383.9877 | 518718123.6172 | 690293177.171 | 689921479.7357 | 329332239.5798 | 539039635.8592 | 26342155.8588 | 134116959.75 | 17625058.4173 | 24435414.6055 | 923679346.9519 | 27809560.2432 | 1040939059.6469 | 6898999656.0549 | 698023032.3117 | 195884033.1809 | 2.5532e+12 | 2309460.9569 | 935160.8794 | 1630842.6494 |  |  | 2.7071e+12
558 | 1110135092.2111 | 1161007657.1329 | 199091587.5504 | 178683100.9919 | 1065483777.366 | 23293789.4295 | 212848574.9062 | 281741413.4921 | 460601767.6734 | 150250608136.7944 | 1806951783.7385 | 2032361881.6052 | 2106733939.5614 | 192090095.2967 | 579199027.4753 | 645346621.8571 | 881908885.488 | 329752953.4001 | 495093835.7821 | 23536507.9585 | 122381448.6827 | 23453006.6512 | 24477218.0892 | 738919461.2831 | 25673478.7851 | 1233909574.1965 | 6723741710.2814 | 654061410.4571 | 201561408.1892 | 2.1715e+12 | 2868066.8278 | 909755.6543 | 1605250.7959 |  |  | 2.3453e+12
559 | 1084729054.5191 | 1206444602.1007 | 214542288.7533 | 169073543.3828 | 1085990721.0524 | 27256719.1127 | 217381798.8929 | 316847559.4444 | 436585763.3874 | 150878311865.9733 | 1713165062.1567 | 1744248019.4429 | 2170004267.6376 | 195338879.665 | 588417401.1224 | 599179829.4523 | 861560347.5048 | 265287158.7056 | 467026852.4813 | 22606629.6741 | 113900881.3673 | 24101643.7086 | 24232098.5458 | 902910013.7123 | 29168891.1888 | 1126239864.3518 | 7015986527.5886 | 562012454.9442 | 170333955.7163 | 2.2507e+12 | 2507638.1071 | 942799.1838 | 1622289.715 |  |  | 2.425e+12
560 | 1217667426.403 | 1134201066.4625 | 211598655.5864 | 172054287.8573 | 1037463751.3218 | 24067971.9075 | 207093487.3809 | 328545621.1034 | 491233344.3541 | 152000374451.161 | 1429324789.1948 | 1772462790.5889 | 1985649788.6456 | 179036966.8869 | 609263306.4995 | 695056668.6944 | 715910763.353 | 326820094.3564 | 589768877.2859 | 22996058.7828 | 106819786.5547 | 22872955.6517 | 23100515.1389 | 880533096.6713 | 31077634.5843 | 1008040585.7553 | 5736243567.5227 | 662188111.0055 | 195751040.5904 | 1.8115e+12 | 2222965.4648 | 981236.1442 | 1688417.2918 |  |  | 1.9853e+12
561 | 1125714142.3931 | 1219973032.3103 | 176036932.7893 | 171427262.8364 | 1039465371.8547 | 26379574.2872 | 204142836.2141 | 325134840.5598 | 481195268.7918 | 136169493475.9991 | 1913776231.5848 | 1641979296.0697 | 2164461863.7346 | 172778677.8749 | 650225521.7684 | 683467594.3669 | 821883438.467 | 326275188.2507 | 585749981.0743 | 26330237.3454 | 130212045.5025 | 23093052.3148 | 21277214.9314 | 811239235.8393 | 27730880.6884 | 1169638598.9652 | 5362145599.1171 | 652493249.7292 | 168230978.9563 | 2.1136e+12 | 2363339.3369 | 944133.5666 | 1513941.229 |  |  | 2.2719e+12
562 | 1078290952.7992 | 1195369084.6358 | 216089537.2249 | 166529938.3379 | 1074080969.3331 | 22259770.2838 | 216735471.2585 | 317055209.0531 | 440889933.2912 | 150359486888.2617 | 1984456407.4666 | 1945822183.4569 | 2161249432.5039 | 168088586.6694 | 638188873.8169 | 654591684.3202 | 778658355.376 | 285650192.8709 | 610606914.5854 | 26503323.3284 | 134973338.6122 | 23085430.3351 | 21233319.6018 | 764072879.7953 | 25133465.1659 | 1103041288.1471 | 6788257070.3709 | 707319659.7567 | 190065222.2113 | 1.8812e+12 | 2451564.5926 | 945082.304 | 1647093.2121 |  |  | 2.0553e+12
563 | 1261112176.0347 | 1031558840.0186 | 214220136.8272 | 176910271.9927 | 1032937902.9858 | 24721162.3686 | 207376653.8369 | 324306813.2415 | 496530718.1562 | 129808537387.3953 | 1914407964.7233 | 2051026173.2625 | 1960247420.2999 | 167292440.7172 | 645187612.9998 | 647343185.5814 | 872606472.8132 | 307107293.5256 | 535351908.3014 | 27673449.513 | 127156160.4269 | 20323001.901 | 22900874.7675 | 880622029.4972 | 25329134.1102 | 1091941942.7448 | 5959256000.1994 | 686007687.8407 | 193581093.9754 | 1.8963e+12 | 2676152.5278 | 943481.5614 | 1628189.6545 |  |  | 2.049e+12
564 | 1146122932.218 | 1172437273.3772 | 206513310.541 | 177298124.0855 | 1067678044.8303 | 25053643.0849 | 191233598.7002 | 309344135.4418 | 471388948.1283 | 125148792925.6839 | 1927993064.0425 | 1906222176.349 | 2008640102.4058 | 191613389.9845 | 545225120.2961 | 716677278.9647 | 776951667.1678 | 331498772.1673 | 583399352.6524 | 25515830.6157 | 129452084.4177 | 23749339.1978 | 24305970.7219 | 908690275.3482 | 26089671.6421 | 907447814.3476 | 5888088513.2728 | 689799605.016 | 189609620.2545 | 2.4303e+12 | 2280541.4955 | 973691.4921 | 1853967.9277 |  |  | 2.5781e+12
565 | 1072729379.5293 | 1115534510.1523 | 206575710.3615 | 171096443.4363 | 1066567992.7522 | 21647826.6191 | 202006989.0927 | 306909785.3155 | 461517306.9419 | 122312668525.7971 | 2043688282.1143 | 1860497599.7326 | 2149343782.1652 | 163955453.2749 | 547117820.6404 | 690355551.6741 | 845151971.1892 | 238401186.4861 | 606132994.1865 | 22308694.0652 | 117034569.9556 | 24339059.1437 | 21973019.8199 | 859687414.479 | 30086190.7032 | 1138570963.7631 | 6579305960.8475 | 697069579.0503 | 160627005.373 | 1.9056e+12 | 2537042.8535 | 985005.601 | 1572618.5836 |  |  | 2.0513e+12
566 | 1251861112.6454 | 1130991049.4206 | 192504118.2139 | 182749047.9218 | 1074815579.3417 | 26407862.4087 | 207236774.3014 | 294611236.8241 | 488867430.8637 | 136421145678.242 | 1896350403.5425 | 2024699771.9438 | 1928456348.6509 | 178651845.9081 | 570778376.921 | 697638986.5569 | 784102174.8629 | 352982308.7839 | 570216574.4169 | 19786274.3991 | 106125324.6842 | 20369354.8064 | 25450484.8724 | 872840310.5821 | 26065099.8344 | 1121502272.6461 | 6195758313.4822 | 543966493.413 | 193017491.5207 | 1.8343e+12 | 2557258.8438 | 1001435.2759 | 1611596.1673 |  |  | 1.9937e+12
567 | 1181394693.2978 | 1155646615.8565 | 201448129.4113 | 161479608.3332 | 1016648043.6777 | 28176032.2946 | 226769916.3149 | 322111011.9684 | 493005755.1417 | 149075780663.5795 | 2043091131.4094 | 1646573055.9925 | 2091338443.5849 | 183080188.0182 | 644486592.7024 | 658473431.1257 | 830661397.3787 | 342190872.5077 | 548893634.2998 | 24047618.6115 | 104240165.5107 | 21569059.4565 | 22918396.0255 | 889828830.5873 | 24599981.1233 | 979503465.9127 | 6430216698.1741 | 689744244.3938 | 181751267.7386 | 1.8278e+12 | 2233676.6111 | 909716.8725 | 1619770.0402 |  |  | 2.0001e+12
568 | 1228603437.8417 | 1145912644.2382 | 220364049.9662 | 163333680.6235 | 1057081916.0627 | 24720182.1337 | 207263909.2045 | 306670129.1344 | 431523031.5362 | 151154649158.0994 | 1850853725.7012 | 1790546049.3672 | 2135250396.5558 | 181000018.6517 | 675097233.2675 | 712531287.9323 | 832826472.4656 | 308597172.1544 | 561645410.6567 | 25097912.8246 | 121053775.8326 | 22801597.3925 | 24523082.8215 | 895276165.5935 | 25201320.1981 | 1160456847.7451 | 6472957404.714 | 597745136.6266 | 195056331.6141 | 2.6759e+12 | 2291896.216 | 988106.6619 | 1688699.5404 |  |  | 2.8504e+12
569 | 1087993478.0559 | 1218612908.7233 | 217623073.2523 | 174895907.3217 | 1072119510.8409 | 22065662.4053 | 191674390.8579 | 321745511.4435 | 481473997.7433 | 154327113402.136 | 1850558658.9787 | 1844513381.8379 | 2204275875.895 | 179521957.3305 | 583420629.099 | 596304786.6202 | 914188449.6152 | 321220965.9107 | 600307578.9488 | 24879038.7579 | 133593850.5111 | 23880760.413 | 20175042.2955 | 753390043.8316 | 24237487.7059 | 1100145772.3957 | 4846470824.0525 | 547407552.0635 | 196433190.036 | 2.5732e+12 | 2599925.9516 | 977508.1092 | 1531559.009 |  |  | 2.7491e+12
570 | 1220428785.0905 | 1209582855.1608 | 222874268.3434 | 168800589.3568 | 997323688.0098 | 21620635.5739 | 213492950.2019 | 250202369.0897 | 466829274.1819 | 137015746710.3317 | 1965365422.3834 | 1939825351.7728 | 2067584794.7743 | 157543610.6772 | 640215586.745 | 648324581.3856 | 799733582.3419 | 306776946.4726 | 598399636.6327 | 25301733.5643 | 121639237.733 | 21384383.2247 | 22977498.5308 | 854999289.4235 | 27314728.4852 | 1171472507.8033 | 5737056463.8064 | 678907501.3298 | 176492597.0415 | 1.8582e+12 | 2538621.2634 | 910436.14 | 1560456.581 |  |  | 2.0179e+12
571 | 1188913057.2384 | 1171318153.4052 | 191751186.5663 | 153155946.9104 | 1073496974.3038 | 22828157.8668 | 213024839.9765 | 293092278.1938 | 460318187.4979 | 152010510409.7031 | 1982144013.5238 | 2068844203.9338 | 2131947438.432 | 196588617.4989 | 657057496.4217 | 708626668.4654 | 722213885.8946 | 280260654.6269 | 594386106.2357 | 27762986.4787 | 123672139.3528 | 21093246.7707 | 21257546.0751 | 870656821.4977 | 24920738.2407 | 883325140.5962 | 5303605303.5882 | 661341536.62 | 175211372.6397 | 2.9379e+12 | 2613168.4448 | 990035.7883 | 1653188.2033 |  |  | 3.1122e+12
572 | 1223443699.9407 | 1056370338.4413 | 202149010.3072 | 163796447.4118 | 1064870031.7455 | 25854767.1506 | 196642688.7829 | 314227938.1156 | 465638614.2913 | 131822356730.9887 | 1969461000.866 | 1826643081.1849 | 1880190003.4077 | 171010490.8519 | 555236266.5173 | 684077078.4257 | 818501461.0717 | 292575816.6431 | 528328417.6687 | 22949958.427 | 119692541.6738 | 20038558.8118 | 25459169.5066 | 849781514.2356 | 29588323.4509 | 1200856729.1187 | 4939795841.0937 | 667820185.243 | 198091329.0042 | 1.7561e+12 | 2572541.9268 | 885322.1227 | 1561928.4287 |  |  | 1.9095e+12
573 | 1187641469.995 | 1194257503.1335 | 183767975.7171 | 171281367.5473 | 1085110457.4095 | 22901578.0368 | 219776383.5596 | 286894832.3801 | 483707257.5169 | 127327088199.4445 | 1973537633.6499 | 1948855047.0288 | 2123374562.4602 | 190150325.5252 | 648939197.508 | 712896949.6913 | 868099900.1558 | 322603724.5814 | 565933067.7551 | 26378759.7198 | 129812810.6277 | 21277900.2115 | 22646409.193 | 833417745.1267 | 28076932.6278 | 1007831500.2455 | 5803921679.9687 | 695535126.5198 | 198755040.5181 | 1.9152e+12 | 2256183.5297 | 929656.438 | 1833553.2749 |  |  | 2.0655e+12
574 | 1258937568.8729 | 1214286685.2859 | 193225782.1615 | 181791150.6324 | 1061130401.1999 | 23255624.9077 | 217406594.4754 | 298223363.8803 | 469362394.4904 | 122766513968.7832 | 1708255608.3072 | 1932705897.5693 | 2196794031.8261 | 187049230.7357 | 648229157.8598 | 646601576.2848 | 767051094.4147 | 311455987.6876 | 481710389.0694 | 25823785.5633 | 118346765.9649 | 23509424.3457 | 23212657.3752 | 722934767.1747 | 28159906.1377 | 1167105459.5487 | 6130883032.7228 | 647413665.5885 | 170460159.3451 | 2.6225e+12 | 2230147.3759 | 1037047.5952 | 1639301.0391 |  |  | 2.7681e+12
575 | 1050988523.5244 | 1109118642.9505 | 224345899.1419 | 165421970.3228 | 1067488040.5231 | 25550832.5042 | 176663382.4846 | 323561449.0588 | 461658485.8954 | 141397345089.6209 | 2076278176.9536 | 2195883458.2135 | 1998561508.285 | 193109521.1173 | 599142703.8209 | 675432859.4738 | 870239217.3382 | 347130189.2629 | 581921371.2229 | 24579459.6599 | 122287933.8302 | 21792743.5224 | 25415562.1172 | 932674346.0408 | 28117137.4615 | 1146025604.4908 | 6703826843.2295 | 614886188.5229 | 165493062.7378 | 2.4586e+12 | 2580786.6187 | 918836.4291 | 1608679.5814 |  |  | 2.6239e+12
576 | 1256144426.4484 | 1084894584.3123 | 178421223.7772 | 179771194.4805 | 1060330244.1524 | 23452003.1059 | 226979148.9764 | 321835184.6216 | 472596701.1686 | 159183706083.7993 | 2085931711.5555 | 2119787297.0769 | 1711132475.8956 | 184079367.0932 | 547345486.0082 | 719604270.6938 | 819849690.7757 | 286932085.805 | 448526758.4572 | 22542575.7327 | 131234907.7522 | 24152996.9995 | 25463404.3558 | 652514000.6536 | 26281130.2842 | 1086860512.5414 | 5888110938.6931 | 701000237.6369 | 192714523.7404 | 1.5508e+12 | 2250122.0693 | 950844.5845 | 1619335.4154 |  |  | 1.7325e+12
577 | 1248877119.9804 | 1177183877.0225 | 213300919.0408 | 179134121.6613 | 1087116134.6661 | 25651414.7028 | 188848128.6837 | 296112164.6567 | 493263585.8872 | 153740434149.1117 | 1603888500.9682 | 2106127670.9752 | 1738058291.2397 | 197878927.6756 | 442663727.0743 | 678802094.4716 | 895536564.6516 | 321493228.4116 | 486620987.1803 | 24291167.3344 | 104391103.8308 | 24589626.3675 | 24151570.1713 | 881283635.147 | 27560535.6516 | 1193885802.2336 | 6037779985.1908 | 582111730.0338 | 149276960.7914 | 1.6786e+12 | 2402281.8441 | 922517.7348 | 1667273.5709 |  |  | 1.8547e+12
578 | 1254302392.6643 | 1223493029.2698 | 220504738.2426 | 166019001.2445 | 1073912320.3141 | 26843056.9547 | 178156220.61 | 302265430.2921 | 439097172.96 | 150083412658.8757 | 1998351285.9034 | 1916827174.556 | 1657289029.4819 | 201898120.1815 | 514455650.9656 | 602798963.8247 | 841151224.4438 | 328127609.2194 | 582832908.019 | 21244156.9267 | 130298625.0543 | 18963577.7312 | 22571785.1627 | 939882295.0812 | 31471149.5535 | 1182128934.6495 | 6302520974.1594 | 677616543.1645 | 179730277.0057 | 2.4349e+12 | 2648486.7046 | 943392.4238 | 1626410.6512 |  |  | 2.608e+12
579 | 1157441983.1265 | 1172484612.0528 | 212969566.2898 | 170778609.4491 | 935568797.9516 | 21084597.6519 | 226523309.1474 | 292633073.3332 | 496004083.6174 | 129856002859.6739 | 1842185094.4823 | 1971193012.7127 | 1896369615.2065 | 173837946.5381 | 488185556.3339 | 675357852.4402 | 620162031.6438 | 342373618.8855 | 507197871.9422 | 27504459.7808 | 111335967.9908 | 22895971.3189 | 24934067.133 | 844232492.8408 | 24173982.3426 | 1055686882.561 | 6619104662.8134 | 597422693.8497 | 180986483.9403 | 2.1444e+12 | 2699962.3142 | 905286.3766 | 1578974.1298 |  |  | 2.297e+12
580 | 1142195505.314 | 1108324017.7704 | 222872037.9975 | 152949776.1178 | 1082582729.897 | 24567676.1507 | 200977329.528 | 307563214.9244 | 444407854.2554 | 125865217762.1125 | 2100417806.4802 | 1700799550.0498 | 2109206449.5564 | 180295563.5491 | 547109721.3788 | 646292691.1206 | 912902580.8072 | 291069985.2498 | 613690088.3991 | 27794527.2714 | 129081391.5195 | 24322753.2726 | 24124873.3099 | 722069637.8872 | 27319629.3112 | 1162348162.8121 | 5272534467.4738 | 618204141.0255 | 196227798.5084 | 2.6418e+12 | 2572928.2776 | 1003579.2762 | 1673312.2557 |  |  | 2.7896e+12
581 | 1153128158.4782 | 1213854509.228 | 200581517.8041 | 178503097.6309 | 955331964.1298 | 22932052.4505 | 216806614.2147 | 296055320.9187 | 440608691.1986 | 162054514277.7317 | 1907293245.505 | 1957008335.9543 | 1831301723.0988 | 162821187.2635 | 560754434.7818 | 687351573.438 | 734948807.4724 | 318065608.7628 | 567251383.109 | 26013869.4198 | 111112330.1194 | 23748270.3535 | 22993985.7378 | 925848406.8868 | 27251181.3592 | 1056036016.1245 | 6465499396.3588 | 653422345.9146 | 194605717.5257 | 1.5948e+12 | 2516854.5856 | 1016735.1033 | 1637772.8895 |  |  | 1.7798e+12
582 | 1156127902.4776 | 1220980042.2165 | 206286428.703 | 177491876.8063 | 1061025268.0097 | 21392092.3612 | 222731156.6201 | 324440039.9177 | 490731909.5152 | 148325971811.1025 | 1991243890.3256 | 1948879312.6984 | 2086822073.2477 | 200341907.0212 | 665365979.075 | 723253641.7067 | 717274401.9666 | 318675536.3645 | 490690032.1467 | 22117025.794 | 136218810.008 | 20328285.2328 | 25507873.2254 | 865688587.8784 | 21160238.0199 | 865427453.5721 | 6672676696.5208 | 696018403.3109 | 161763763.3128 | 1.8526e+12 | 2364243.2435 | 882313.1323 | 1674788.3035 |  |  | 2.0244e+12
583 | 1266192907.0407 | 1202598193.9144 | 195537506.5336 | 180438385.6503 | 1085168022.8054 | 21113738.3886 | 224414063.2632 | 284866651.555 | 497428443.7039 | 158190969259.8732 | 2066530204.7575 | 1717595166.765 | 1697208715.4266 | 198118350.2552 | 508161724.0275 | 685636635.0699 | 811923509.1605 | 314073665.1453 | 592702169.1687 | 24490309.3866 | 118850548.1286 | 24603031.2149 | 21856482.6751 | 939548689.5959 | 27262389.2474 | 1040854644.0651 | 5608667417.4107 | 686136835.4324 | 174039156.5284 | 2.2717e+12 | 2563287.7341 | 1009098.185 | 1580613.1283 |  |  | 2.4521e+12
584 | 1193399322.3429 | 1195121861.9093 | 201367866.1129 | 168512418.7601 | 1070955585.5113 | 23889924.4885 | 211932534.5004 | 315469662.1868 | 440055606.3419 | 128142228050.8136 | 1643438756.9626 | 1997026857.8569 | 1761876385.5489 | 188925579.2113 | 634703068.9739 | 665859261.1246 | 824645481.3623 | 334298639.4418 | 570124225.2163 | 21080406.0378 | 110546280.5995 | 19151220.2236 | 22432725.7345 | 808915763.0581 | 27827413.947 | 1073311421.2889 | 6932754957.3755 | 706461769.9024 | 165119177.2065 | 2.5274e+12 | 2587920.4422 | 910222.6676 | 1633096.6163 |  |  | 2.6789e+12
585 | 1121512896.0377 | 1169710756.7333 | 209445285.0067 | 173235407.7289 | 1060754265.2715 | 25769202.149 | 198424175.7922 | 324308183.9998 | 486131336.2665 | 152741442219.7857 | 2078044944.9729 | 1905730579.6432 | 1813732855.1232 | 188197893.275 | 555885980.0845 | 688323322.0611 | 881273364.8384 | 333435165.969 | 511370247.1362 | 25685571.9727 | 132594760.6833 | 19614612.0261 | 25042403.0927 | 928938102.9472 | 23477923.624 | 1134110019.7827 | 5659969636.3465 | 685362037.9163 | 169850015.3144 | 2.125e+12 | 2454929.9409 | 922031.2605 | 1519811.0283 |  |  | 2.3003e+12
586 | 1140518158.7949 | 1106047663.4304 | 188975182.3166 | 173939045.1649 | 1030017120.8833 | 21480633.4649 | 219103821.6325 | 287815936.8031 | 478799440.6599 | 147073597024.9773 | 1889824930.9041 | 1890543217.9069 | 2135548009.0207 | 188882064.7435 | 623026192.6103 | 604098690.8298 | 878793315.9664 | 333395359.2089 | 543780292.6483 | 27111133.0502 | 110253672.9649 | 22210426.2554 | 25346455.3837 | 782830974.6628 | 29782888.6126 | 1095843209.828 | 6873344552.4035 | 702566379.1387 | 177922570.584 | 2.0941e+12 | 2601821.1385 | 925380.1775 | 1622812.0395 |  |  | 2.2648e+12
587 | 1162636832.1567 | 1094200894.9181 | 192993726.7332 | 176779077.214 | 1032836783.5428 | 17811660.433 | 207073906.5906 | 305071460.1145 | 495136181.8468 | 144867679643.1177 | 1995001539.8983 | 1636991678.3768 | 2075860492.3295 | 195178754.8503 | 522609676.4367 | 705485798.8102 | 618840292.5731 | 295640872.3437 | 581247613.657 | 27859786.3544 | 113724263.2218 | 21910457.9676 | 23856134.7153 | 873863312.2339 | 27475904.5666 | 1175815508.3041 | 5732441919.4529 | 658593864.112 | 173758494.1785 | 1.9908e+12 | 2662564.2347 | 998671.7188 | 1727704.1739 |  |  | 2.1578e+12
588 | 1058169044.3516 | 1217639006.4668 | 209264138.9482 | 147211918.5125 | 1021694066.9971 | 24152424.7159 | 194341638.7392 | 307928825.0373 | 426352086.9855 | 147640181286.6158 | 1791075762.5826 | 1917833729.6769 | 2041632109.6895 | 179995285.6794 | 614138400.4196 | 712653045.5963 | 819398089.3011 | 265404742.0513 | 521458676.1879 | 22616062.1702 | 116945352.0569 | 20695612.2785 | 24624535.0108 | 832991145.513 | 25433119.4863 | 1118674316.383 | 6618810360.7527 | 636498652.5601 | 188132358.1806 | 1.5902e+12 | 2496137.0102 | 912028.7466 | 1862242.0937 |  |  | 1.761e+12
589 | 1172401554.9194 | 1083825966.1652 | 200279941.0329 | 177649655.6406 | 996108840.3123 | 20956535.8208 | 189723838.0721 | 316852133.7731 | 438083280.5154 | 147248479544.3837 | 2000782528.0655 | 1902521295.2933 | 2175977348.4769 | 198231048.8817 | 628001343.9621 | 631644606.0008 | 829799705.1774 | 288965520.3424 | 601942609.7765 | 21670440.4109 | 124871328.2128 | 17545481.5087 | 24320732.8849 | 913515111.2284 | 21925486.3098 | 1181404290.7066 | 5507229403.2574 | 638663229.9281 | 172870033.4077 | 2.1912e+12 | 2475361.3013 | 939512.6683 | 1519403.6281 |  |  | 2.361e+12
590 | 1191364560.1046 | 1083648911.2156 | 181452697.6511 | 176062028.176 | 998891673.8639 | 22950073.6708 | 221694754.9009 | 310351072.3475 | 381215239.3869 | 155096037209.9665 | 1732913394.476 | 1916821259.9035 | 2186843372.1892 | 200895857.7284 | 517547396.5829 | 642502487.7286 | 915511324.9038 | 302900158.6843 | 563796848.4443 | 22694338.6739 | 104460688.8424 | 20893298.3563 | 25657404.1101 | 781245610.727 | 25713415.2513 | 1019352621.9896 | 6954746405.8639 | 685872091.2736 | 178178210.2353 | 1.8308e+12 | 2486530.1259 | 948591.6164 | 1579446.5535 |  |  | 2.0093e+12
591 | 1055315891.4861 | 1190963177.3161 | 215819451.091 | 169058236.5812 | 1055369414.1744 | 22155952.2304 | 194853752.5299 | 315131211.2384 | 423053663.9844 | 136959773897.448 | 2038590485.912 | 2126165021.8777 | 2194845599.0973 | 146205340.945 | 524484768.3285 | 675869343.0245 | 768000980.6285 | 334932923.6098 | 615845485.4785 | 26180737.3457 | 133656238.6958 | 23896326.6141 | 19633288.7193 | 801461883.5129 | 24828019.4129 | 1090446364.6939 | 5998261185.371 | 685563482.1187 | 166531117.6301 | 2.3706e+12 | 2468163.9006 | 949425.1609 | 1736699.7337 |  |  | 2.5306e+12
592 | 1079681335.1074 | 1225453432.5676 | 218064965.1653 | 154867840.623 | 1059656689.0056 | 18683409.4503 | 206337202.1543 | 319764533.8039 | 494206774.8989 | 146245352570.0794 | 2044320347.8035 | 1814377570.3329 | 2187419548.6629 | 195442411.8912 | 642755484.9004 | 640568885.1711 | 820952154.8151 | 300623642.3847 | 611891054.0933 | 22306810.3806 | 114529424.3785 | 24293473.2462 | 24953866.3969 | 923440588.7898 | 27125668.8673 | 996582533.9836 | 6747433375.4718 | 581084036.9513 | 193356050.9895 | 1.471e+12 | 2348895.2936 | 966467.5937 | 1711612.7175 |  |  | 1.641e+12
593 | 1054877980.4208 | 1176524879.5915 | 204732473.231 | 172215006.4312 | 959081436.4088 | 25369924.4788 | 209350831.9593 | 311144104.1709 | 479273181.8793 | 146075966899.1733 | 1920526865.322 | 1681059714.4766 | 1939804410.7897 | 182354727.4135 | 644745191.0497 | 718504298.2365 | 785089651.9097 | 321117202.7193 | 494494306.9425 | 24775828.7015 | 131906643.0596 | 24096453.5339 | 24964597.516 | 856547622.4864 | 26276911.9258 | 1104545270.1751 | 5752079648.6543 | 585022114.568 | 197054776.2569 | 2.4259e+12 | 2376897.3119 | 999341.3943 | 1566540.8685 |  |  | 2.594e+12
594 | 1098494925.3886 | 1121201436.3295 | 194931917.8569 | 163474949.0036 | 1023381176.1693 | 19594638.3288 | 216790733.2387 | 308588448.5546 | 440717787.5498 | 144830599878.545 | 1817922048.5222 | 1736963252.7857 | 1859563234.0595 | 176149506.9232 | 583717933.0559 | 718894584.2693 | 847449749.0085 | 359107120.4287 | 560131505.996 | 27351477.8671 | 127537915.7574 | 20815728.8556 | 20219369.6006 | 845869954.3944 | 29475705.8631 | 1116263068.09 | 6716222380.2914 | 706924367.4917 | 173499665.4083 | 2.1436e+12 | 2576214.43 | 939777.8127 | 1931540.2238 |  |  | 2.3114e+12
595 | 1174733068.1558 | 1191621934.6253 | 208331129.8361 | 171234034.7288 | 1032332157.2921 | 25422725.2405 | 216469015.8811 | 322365251.7759 | 440191107.5383 | 132596095363.3137 | 1869272017.6709 | 1969352267.1692 | 2039575673.0467 | 201714763.5859 | 643933385.377 | 637968831.481 | 907946369.7907 | 321016058.6551 | 561649359.9687 | 26042427.1053 | 124705588.9967 | 21743458.9203 | 23782640.9523 | 867424810.5061 | 27534415.9367 | 1120484153.3421 | 6759629225.9233 | 629975622.5746 | 187976334.6436 | 1.4788e+12 | 2543611.3473 | 930945.8682 | 1560496.9282 |  |  | 1.6351e+12
596 | 1058119179.0045 | 1093123325.1465 | 206522191.1012 | 179119471.954 | 1086669868.6846 | 23607152.2402 | 215002322.6661 | 307882821.2956 | 478625509.6452 | 112431266318.7202 | 1708211274.8747 | 1804244577.4127 | 2207567535.0207 | 202925936.0684 | 571428648.2714 | 641675676.3697 | 915314087.5829 | 306982981.0675 | 612082997.0101 | 25945151.7224 | 106468440.1167 | 20960227.0603 | 25323440.9376 | 943401938.0132 | 27527064.583 | 1045895673.161 | 5925030840.5889 | 667203328.066 | 186250636.5798 | 2.0712e+12 | 2355503.4785 | 913936.0331 | 1623196.8938 |  |  | 2.2062e+12
597 | 1237397414.4762 | 1156142085.549 | 188048775.0629 | 167261231.6673 | 1078278305.3088 | 21801580.7667 | 191004568.4875 | 328398487.397 | 495119255.1592 | 144653324112.6442 | 1748698575.0416 | 1777706807.2181 | 1800476951.5182 | 190657572.3678 | 534571055.4643 | 622781032.2275 | 728708687.7792 | 335394548.716 | 605463296.884 | 25833606.2673 | 120193135.8446 | 24184897.9604 | 25615664.6685 | 763308777.0912 | 24893475.5649 | 960003347.1379 | 6934757956.8714 | 679364712.4324 | 191075366.1108 | 2.2117e+12 | 2399834.7562 | 947497.6575 | 1648812.1087 |  |  | 2.3794e+12
598 | 1168323259.2678 | 1081648997.8496 | 215752045.8445 | 174368354.0632 | 896661307.0489 | 25729703.1222 | 192282313.7275 | 293204150.083 | 496299348.2631 | 146488446714.2946 | 2079420526.014 | 2057585163.4218 | 2182689653.8263 | 174611925.6601 | 575033274.7983 | 690734200.3301 | 809939296.568 | 362928256.6857 | 525210471.6135 | 25454594.8991 | 110220887.6009 | 24747758.4776 | 24582415.1674 | 895072647.927 | 30354413.85 | 1052866320.1647 | 4506566345.8636 | 664222356.744 | 177526949.9139 | 1.5884e+12 | 2613718.408 | 914997.4662 | 1722230.8836 |  |  | 1.7564e+12
599 | 1111220353.1064 | 1186624709.4133 | 216673408.6214 | 165588047.6721 | 1037346358.6737 | 25252949.4707 | 224888367.6419 | 308537132.3551 | 469083503.1134 | 143668049072.6091 | 1824515704.3023 | 1818157182.8596 | 1819628625.1761 | 191726290.954 | 624023055.319 | 711480179.8494 | 772574073.9071 | 300722112.0198 | 581310432.9171 | 27014233.1466 | 99814663.4066 | 18868869.5929 | 24219388.979 | 855963244.3748 | 24646590.158 | 1111264139.7453 | 6313074448.201 | 686586935.7861 | 176346649.6228 | 1.5399e+12 | 2433680.9792 | 936811.9461 | 1708510.8069 |  |  | 1.7063e+12
600 | 1132165054.4652 | 1195985898.6937 | 213725785.7794 | 168016509.0976 | 1069337719.0116 | 20298422.0827 | 191322851.2047 | 286498896.3357 | 462106578.7515 | 155275253998.7514 | 1848107220.9795 | 2042392254.1469 | 2186598708.2581 | 199226240.9561 | 519295496.9851 | 637966398.3277 | 811235263.9656 | 245701669.8281 | 458279065.6199 | 26056749.5996 | 96911211.9449 | 19976940.5524 | 20194940.038 | 921995966.1709 | 30108415.101 | 940993456.2459 | 7067565465.8078 | 686224899.7935 | 194035452.5373 | 1.869e+12 | 2525937.3732 | 1008817.2103 | 1674656.7969 |  |  | 2.048e+12
601 | 1129703393.2821 | 1164483887.0351 | 222299272.9108 | 173575791.7694 | 1086914569.8376 | 19756464.8795 | 190254769.9106 | 280800739.6787 | 415386718.6439 | 158033025578.3396 | 2080271849.8082 | 1656432225.8865 | 1845926453.8385 | 196861005.238 | 561513291.6679 | 693781999.0809 | 874298759.6246 | 306720453.8058 | 449760590.0984 | 22762123.1859 | 131209633.1467 | 22604551.8252 | 25594328.8006 | 705722742.853 | 28282245.31 | 1167960906.2786 | 6381683921.4936 | 625912200.665 | 184266391.4353 | 1.973e+12 | 2548306.7311 | 983863.2681 | 1746565.0161 |  |  | 2.1537e+12
602 | 1143599841.4077 | 1010034142.286 | 207132362.9165 | 169044144.8375 | 1064958960.9337 | 21418868.0815 | 218168014.3079 | 292670358.853 | 492265219.5479 | 156820653767.9508 | 1965563167.2091 | 1917817580.263 | 2206506592.3267 | 168312228.6211 | 597395615.9033 | 659783499.0154 | 793849588.7745 | 298724381.8764 | 583683666.0027 | 26860871.9691 | 129845004.8145 | 20151556.5429 | 25369224.3958 | 925319842.4225 | 26141907.9215 | 973669029.3623 | 7220710112.3818 | 663150701.1756 | 198263749.3727 | 2.1331e+12 | 2432567.9578 | 914974.7413 | 1571389.6886 |  |  | 2.3139e+12
603 | 975747312.2375 | 1220082356.9724 | 222981985.7815 | 177851853.0963 | 1050983224.7531 | 25393405.8425 | 204047542.1944 | 287209909.316 | 488938323.8226 | 128061253268.9652 | 1906827929.9582 | 1539035742.9896 | 2055995577.0211 | 182152623.7339 | 628115563.4225 | 685090605.6086 | 846661175.3987 | 354558970.7365 | 485481755.7874 | 25068733.7902 | 124465338.5049 | 23321643.2578 | 24962434.0239 | 835954426.1082 | 30566175.9531 | 914011191.2061 | 7165597800.4354 | 635661052.0948 | 186969421.5181 | 2.3775e+12 | 2441734.1942 | 1013496.6995 | 1546804.2264 |  |  | 2.5289e+12
604 | 1225077724.7859 | 1174568023.0098 | 190862294.039 | 164558150.9549 | 1011922473.101 | 24856527.6682 | 212259839.4855 | 325356895.8819 | 491786383.3471 | 148137441708.5755 | 2081836266.2485 | 1969968521.9593 | 2138373204.9284 | 198957715.5033 | 627626112.1601 | 628278771.6485 | 868410855.7958 | 259547821.0129 | 601032680.0641 | 26520962.456 | 112611783.2925 | 17030627.7124 | 22673020.5476 | 747122770.7324 | 24899412.6359 | 1169425787.1446 | 7161497123.1946 | 582455111.7708 | 182167155.7163 | 1.965e+12 | 2387185.2049 | 1017069.992 | 1644628.3627 |  |  | 2.1374e+12
605 | 1206174123.6266 | 1007875366.6867 | 205753613.1252 | 166666457.4859 | 1031032480.3876 | 25449026.8635 | 219255671.8223 | 330307751.8397 | 471317513.997 | 152542712171.0548 | 1833735322.6526 | 1559761555.5957 | 2115165525.7049 | 194279673.9107 | 523168607.5576 | 688691492.8282 | 706976739.5797 | 291306602.0531 | 571696061.6975 | 26125129.4446 | 114653759.812 | 24195814.87 | 25171821.1401 | 906439498.4072 | 27228771.0614 | 1076338171.3312 | 6558943683.9407 | 703515112.3831 | 162016411.6955 | 2.3626e+12 | 2717398.4688 | 971085.6639 | 1656904.4868 |  |  | 2.5379e+12
606 | 1200950088.9128 | 1202251030.1901 | 220921280.9361 | 176985809.8434 | 1061077025.7971 | 23051729.4623 | 205258679.4102 | 303392064.6061 | 486206752.8942 | 119488689667.5898 | 2068590707.2445 | 1586997703.4891 | 2160434777.3452 | 179830876.0583 | 599019430.464 | 645666693.7736 | 782698929.4708 | 344831140.9114 | 437059406.0042 | 19083449.1162 | 110531773.1103 | 24649363.5455 | 25733581.5425 | 905248677.3272 | 29966391.5536 | 1118721034.1795 | 6842863283.1661 | 703592815.1432 | 193477037.0914 | 2.2983e+12 | 2562505.181 | 986351.2542 | 1646965.1772 |  |  | 2.4415e+12
607 | 1159539864.4726 | 1085661528.6995 | 197997019.0959 | 164987113.7741 | 982383707.7212 | 22785720.9598 | 217513671.4977 | 325398654.8573 | 477076785.3994 | 128012317864.1635 | 1493176478.22 | 1854238141.6191 | 2100478415.5226 | 183639337.3296 | 636434892.5639 | 610176420.8321 | 773957041.3734 | 289496672.9216 | 563739879.6539 | 26653776.6341 | 121964247.3674 | 23608772.609 | 25910835.6534 | 884972611.4923 | 24686383.7465 | 1110987028.3462 | 5862945782.2037 | 704753689.0122 | 173010184.6431 | 1.8574e+12 | 2665020.4316 | 882225.1412 | 1677041.1504 |  |  | 2.0076e+12
608 | 1234430416.1865 | 1137756216.5161 | 196253213.999 | 149273415.1892 | 870339633.459 | 21475409.3752 | 206419611.9544 | 313034586.0471 | 470924260.1249 | 135648590001.9819 | 1906347850.3984 | 1753583294.1512 | 1810574428.9152 | 188223059.5833 | 477852887.1054 | 704556277.087 | 907194738.6573 | 315554446.0275 | 579484930.3318 | 21861974.0665 | 129996564.2765 | 20763916.0836 | 24977464.9742 | 877626201.7996 | 21738773.5298 | 994093138.3325 | 5559562623.1329 | 693033221.1177 | 190001794.9367 | 2.2513e+12 | 2802862.6495 | 995714.8578 | 1560022.749 |  |  | 2.4087e+12
609 | 1207525035.2939 | 1219831369.8096 | 205783747.5584 | 153905254.4955 | 1077787777.0376 | 24231568.9052 | 210537570.2033 | 322186519.445 | 434812156.4493 | 160340348982.4069 | 2085900976.8423 | 2076837462.5459 | 1842670857.4839 | 172266970.6902 | 520603494.8684 | 711173844.1799 | 728279146.0789 | 322615477.2581 | 608462557.8077 | 25768214.3024 | 117692880.7317 | 19893111.5828 | 18872227.3998 | 813959268.5454 | 28277322.0153 | 1137379618.7643 | 6804157857.2629 | 624804566.7884 | 184443514.0038 | 1.7488e+12 | 2395759.2105 | 1056391.8323 | 1734423.7185 |  |  | 1.9328e+12
610 | 1247700936.5671 | 1136825031.1881 | 216873248.7941 | 168690162.213 | 1019114701.4821 | 26368735.4725 | 224035997.6964 | 331049924.03 | 420018611.6799 | 154391946779.0532 | 1769948513.8464 | 1864417296.1253 | 2003422278.1182 | 201868485.9173 | 657102519.1932 | 690795062.1037 | 830895431.0464 | 315749134.4066 | 605977493.926 | 28275574.5393 | 118638264.9852 | 21388225.9611 | 25672288.159 | 870339265.6533 | 27750263.4428 | 1108041672.7996 | 5449193071.2827 | 654707849.2282 | 171760172.2323 | 1.8602e+12 | 2356298.9576 | 877711.9244 | 1683313.9134 |  |  | 2.0368e+12
611 | 1218377533.049 | 1107102475.0511 | 202510164.3523 | 175273852.0661 | 1083441265.8988 | 21482539.7316 | 196604381.3868 | 326368524.5623 | 494391560.7854 | 135872148488.4722 | 1680958849.0005 | 2057950586.2773 | 2158235763.4789 | 200933374.0922 | 583353220.0436 | 707670278.6227 | 765594528.7464 | 315622794.9987 | 574339620.6643 | 23757165.3855 | 122189491.4584 | 22484920.4327 | 23744256.6928 | 937360115.4287 | 27765093.6805 | 1017055819.0936 | 7055634228.3816 | 604715183.856 | 186804416.4733 | 1.9495e+12 | 2520292.4802 | 1017951.1754 | 1655662.3173 |  |  | 2.1092e+12
612 | 1186554298.755 | 1136344740.319 | 187036667.5806 | 159215552.0953 | 1086535776.4728 | 19338347.3526 | 217518466.1401 | 329832776.0994 | 492749156.3618 | 142815745351.1727 | 2029501912.6602 | 2116434964.1105 | 1864541919.8325 | 195579183.4349 | 550393262.3637 | 685317099.8693 | 741229780.7906 | 318161034.1519 | 585684442.3059 | 26419251.2275 | 100174178.1959 | 22039983.6252 | 24776204.8967 | 798028340.5285 | 30111475.3009 | 1166053597.3993 | 5981433858.2653 | 702781002.6189 | 196924935.1909 | 1.9044e+12 | 2526250.7151 | 932308.6969 | 1683469.6694 |  |  | 2.0702e+12
613 | 1209006212.3262 | 1182374727.2894 | 215197810.9742 | 174351886.471 | 1020947178.4152 | 20966254.0841 | 214109811.9262 | 300857647.8971 | 488047846.1842 | 110695383611.2057 | 1905765687.2136 | 1782714792.6377 | 1979235090.2817 | 185331540.4272 | 497406864.8043 | 616139275.8354 | 759669923.9511 | 292410247.8193 | 515685948.7632 | 25774341.1448 | 119581979.5242 | 22247569.5623 | 21748403.4373 | 867806984.2675 | 28191627.7653 | 1170165944.6419 | 6998070954.6107 | 706530541.9707 | 199762393.5208 | 2.681e+12 | 2440563.6198 | 933163.5148 | 1737520.9695 |  |  | 2.8152e+12
614 | 1197294428.9213 | 1188320335.1389 | 217486612.6113 | 173563491.3615 | 1060787117.8549 | 23907182.4511 | 213160758.1806 | 323742619.6715 | 440038182.29 | 114879101941.4158 | 1809482363.0514 | 1806787244.9685 | 1941195807.5288 | 197405403.0635 | 639340797.1553 | 678375601.6041 | 857163068.1709 | 318730862.0305 | 584628051.2535 | 23949536.7738 | 104665422.4785 | 20870336.0299 | 22534466.0817 | 889838807.8945 | 26287790.6691 | 1094483592.1691 | 5962094538.4736 | 645158225.8523 | 186241132.2225 | 2.1007e+12 | 2424357.1111 | 897938.6039 | 1620401.7074 |  |  | 2.2382e+12
615 | 1198223152.1434 | 1208691381.8651 | 207423244.4687 | 174995536.7576 | 994324881.7583 | 23935833.3569 | 220052862.207 | 314850841.4756 | 490753219.2406 | 144583969733.4285 | 2014202595.8731 | 1975852597.5406 | 2196371659.6057 | 199263447.3415 | 600076124.3346 | 607945026.8445 | 770139206.5499 | 288202905.9525 | 542347161.5351 | 25417385.4962 | 114652519.7533 | 24310375.8386 | 23268643.2892 | 877467997.8743 | 26836686.1717 | 1116160851.0287 | 5744513992.7057 | 706935545.438 | 199837556.3102 | 1.7555e+12 | 2588749.6573 | 1016873.2978 | 1717563.7407 |  |  | 1.923e+12
616 | 1073502666.3477 | 1040385298.259 | 220344749.2382 | 168305538.2032 | 971147442.5667 | 19736534.0898 | 221427895.0969 | 299453735.3717 | 474733934.3944 | 133560580603.8113 | 1857416577.0345 | 1742395835.8643 | 2131327638.0513 | 187412799.7748 | 641094096.3295 | 708582754.1154 | 721908257.264 | 346225473.0883 | 511834635.8971 | 27442409.1145 | 104811227.9424 | 23276912.6873 | 24838803.6129 | 930131726.105 | 26997811.0356 | 1199831916.0624 | 6048680249.0731 | 691908823.9078 | 188791338.7452 | 2.2351e+12 | 2522200.163 | 893529.0726 | 1699177.1151 |  |  | 2.3913e+12
617 | 1137956299.0183 | 1162060502.84 | 191107019.2049 | 174870117.2859 | 1046839316.6205 | 25469853.532 | 216150505.6361 | 287234756.2171 | 489313541.2731 | 143898669899.2627 | 2045306357.9719 | 2031876506.4538 | 2040074212.421 | 198505472.3172 | 518485100.0893 | 672426564.7842 | 766356702.86 | 342062894.4135 | 559980448.0504 | 19854584.044 | 111406543.6089 | 21637067.6051 | 24590700.33 | 905817829.9809 | 25655080.0458 | 1082244367.0503 | 6578050591.2035 | 669021352.5925 | 180508881.1303 | 2.1402e+12 | 2524206.9399 | 911996.4625 | 1589723.5185 |  |  | 2.3076e+12
618 | 1191282617.8357 | 1113590410.1868 | 201469759.1368 | 179528302.7672 | 1044941262.2466 | 28328957.8244 | 214315196.909 | 290624938.2632 | 433932593.1638 | 115863280883.0482 | 1936709727.4383 | 2068006779.8661 | 2188643466.0166 | 149850485.0606 | 590032046.0748 | 701144725.1893 | 903955903.1671 | 302242315.5918 | 570256803.1331 | 23081895.6583 | 124317478.2214 | 24523482.9986 | 24643630.1796 | 773681146.6429 | 26603221.9237 | 1117320421.9145 | 5771629077.5431 | 578557009.6061 | 193088192.6671 | 1.4776e+12 | 2429276.7957 | 959060.9347 | 1618590.8842 |  |  | 1.6162e+12
619 | 1110341214.5735 | 1173418039.3303 | 221895474.464 | 170650534.4277 | 1065611805.1323 | 21771059.574 | 217991238.095 | 313810101.0092 | 479098986.4269 | 153386122740.935 | 1960161994.4539 | 1546203951.5423 | 1766862742.9819 | 200934067.0167 | 686477600.0967 | 670201462.2537 | 685049751.6505 | 341413729.7767 | 572579311.735 | 26501920.677 | 119490897.6558 | 22579121.5453 | 24749490.7896 | 901740598.1061 | 26722938.587 | 1017144265.1279 | 6451425655.7551 | 685779273.0587 | 190485795.2644 | 2.2242e+12 | 2546604.944 | 942117.7638 | 1670999.9699 |  |  | 2.4003e+12
620 | 1209153337.8292 | 1069988696.8564 | 212752523.7351 | 166369549.7299 | 1013287810.3981 | 19703180.2133 | 217350950.9244 | 294422567.2095 | 469542771.546 | 140196436436.9477 | 1831070874.6704 | 1972837070.5267 | 2088733736.3156 | 181950153.5662 | 632816932.4287 | 555005588.9588 | 780449681.9001 | 310194051.2554 | 540396805.5034 | 24393458.1068 | 128260662.1389 | 22107497.665 | 25883452.3022 | 894671788.7187 | 25066907.1857 | 1190553791.5621 | 6891849117.3592 | 657380544.6858 | 201594414.2364 | 1.6045e+12 | 2398592.7439 | 924146.1854 | 1545234.7577 |  |  | 1.7683e+12
621 | 1155944177.4911 | 1088849348.0659 | 212081323.4919 | 169925386.5627 | 1008843611.0832 | 25829678.5224 | 195887313.3898 | 300509653.233 | 491832343.5493 | 136460294639.3649 | 1803039271.0059 | 1938013595.7495 | 1761346174.7985 | 196039234.6368 | 602664861.5613 | 676753294.3959 | 843218047.9582 | 296564007.8844 | 494270569.4724 | 23232818.8656 | 123979032.7157 | 21046565.802 | 25005685.9836 | 912725421.7665 | 26404108.4987 | 1047192247.1142 | 5859904588.7184 | 656333525.1655 | 201400160.6944 | 2.1576e+12 | 2333600.4256 | 950284.0127 | 1708693.8355 |  |  | 2.3162e+12
622 | 1151145825.9775 | 1201402616.7307 | 203234917.3082 | 142259906.1085 | 973974021.5033 | 24235901.253 | 184956258.0334 | 307412850.4129 | 476817757.2037 | 135790877621.6241 | 1568411924.1897 | 1658818877.6853 | 1909529703.398 | 200648245.7867 | 635734112.7201 | 709023022.0967 | 674370191.9419 | 285591501.8603 | 593225073.3754 | 26568090.9628 | 117715936.095 | 23014489.0232 | 22146059.9402 | 893657954.3281 | 31557589.8123 | 1154934607.6046 | 5873006576.5775 | 586873519.8708 | 178290367.2242 | 2.0232e+12 | 2403960.5425 | 938346.1415 | 1557071.3275 |  |  | 2.1809e+12
623 | 1229747693.5576 | 1213156996.6209 | 210875072.8315 | 156978647.2563 | 1036494477.0727 | 24248910.994 | 198831155.5988 | 271917218.6253 | 479237085.3169 | 134394802599.6673 | 1998851524.9296 | 1796985832.5221 | 2026346510.4114 | 187735999.368 | 562339393.4877 | 706511432.6295 | 842506707.2803 | 324190310.967 | 456277170.089 | 23511036.5736 | 108983467.7724 | 20407896.5945 | 23154255.7661 | 905500505.3776 | 28701842.6887 | 1029990303.7495 | 5757962792.7421 | 567250771.6355 | 157343757.7617 | 1.8083e+12 | 2495216.5378 | 983614.7041 | 1505780.1074 |  |  | 1.965e+12
624 | 1193936281.3805 | 1222658209.2362 | 186307378.3056 | 178225551.5312 | 1025482444.0327 | 28747905.1372 | 181931190.0697 | 326451874.6651 | 499675032.3592 | 142144627454.4833 | 1616997336.6513 | 1706233929.7181 | 1878399328.4715 | 198572914.7479 | 624928583.3369 | 646561443.241 | 843547897.8435 | 360433648.0192 | 563297772.1113 | 24753406.2287 | 131531978.333 | 20849924.0833 | 24773865.9468 | 848542526.7557 | 24006512.6581 | 1167447208.2563 | 6937483376.9818 | 630193609.4122 | 185903133.2593 | 2.2685e+12 | 2311106.1944 | 918206.3706 | 1794926.3278 |  |  | 2.4339e+12
625 | 1230029882.0887 | 1092091954.924 | 205357003.2633 | 165652028.7843 | 991487957.5011 | 27362346.5532 | 211158771.9151 | 311360051.9225 | 401785857.1752 | 150997356439.5862 | 2029283124.3902 | 1884333564.2841 | 1975020139.0225 | 186251799.0437 | 676813055.0214 | 672238640.181 | 835044737.627 | 274563194.4614 | 584954769.8747 | 26568061.0006 | 131349248.5388 | 24362747.7949 | 20410139.3209 | 901993353.094 | 29159074.9187 | 1078685951.282 | 6517235376.8348 | 698750092.3976 | 198555374.8329 | 1.9865e+12 | 2309090.6486 | 917043.8109 | 1898716.1911 |  |  | 2.1609e+12
626 | 1157394954.604 | 1213967236.4827 | 214737400.5748 | 175332874.4287 | 1043392460.5145 | 19472070.3561 | 180372967.5735 | 322797088.7504 | 483234125.9949 | 145933655166.6229 | 1478799863.0364 | 2101709789.7337 | 2189307892.2247 | 168008910.2175 | 572096887.0056 | 670898905.4682 | 773315072.3818 | 351265647.4835 | 567181442.2892 | 26269952.0345 | 111483961.6079 | 21467298.2268 | 21068813.696 | 839350562.3555 | 25972978.3083 | 1198139958.5963 | 6999000413.0915 | 678623649.1107 | 197373521.9337 | 2.0975e+12 | 2641616.1389 | 925177.6173 | 1540745.7719 |  |  | 2.2672e+12
627 | 1122288750.6613 | 1212082316.5455 | 170221943.4311 | 170222672.6977 | 1078922553.4911 | 21820030.8631 | 225538134.028 | 306639601.5862 | 483039006.0004 | 127139616185.5976 | 1952668132.8153 | 1659716681.8689 | 2110667749.6879 | 183274050.0352 | 637314559.0367 | 657142381.0857 | 743602455.6124 | 260308967.0403 | 529734437.6472 | 20727387.6509 | 130471927.3057 | 19364793.8841 | 23316467.8321 | 741930755.5248 | 24165082.5484 | 1110929816.424 | 7043799984.0757 | 688043458.5442 | 191554568.4271 | 2.1799e+12 | 2483725.1743 | 1014905.0225 | 1840493.5086 |  |  | 2.3306e+12
628 | 1119569614.01 | 1188755779.353 | 217344868.153 | 176436622.6629 | 1080815729.3734 | 20076263.1163 | 188814129.5521 | 323159684.8782 | 485728384.7557 | 112327506039.0382 | 1939731606.0472 | 1950491646.9969 | 2110086664.4688 | 192500323.4159 | 620185760.6831 | 723897580.9455 | 823915471.8139 | 314830329.0884 | 597519122.6382 | 26566392.0858 | 109438736.1547 | 18469979.1392 | 25308278.7607 | 836305698.4351 | 29097708.6531 | 1059371210.3266 | 6568447035.8513 | 663023969.4793 | 145290538.605 | 1.9556e+12 | 2731337.3457 | 1029126.3376 | 1498913.7346 |  |  | 2.0915e+12
629 | 1120114285.0752 | 1018791553.4834 | 203320472.0136 | 175586841.9533 | 1026322917.5804 | 23042640.6678 | 194619887.5254 | 324231495.7363 | 468735002.6138 | 115819587101.3909 | 1521669699.1367 | 1751341179.7094 | 2084291485.5183 | 201676178.2895 | 609767345.8882 | 661655569.4472 | 902151501.8707 | 321322051.536 | 577552799.5324 | 26324211.5836 | 122348754.4263 | 22946978.4954 | 22357912.3103 | 831888372.407 | 24983971.505 | 1132968886.2023 | 6721322607.2863 | 636444038.4942 | 201163400.0243 | 1.8409e+12 | 2412668.0843 | 938471.9701 | 1605672.2303 |  |  | 1.9796e+12
630 | 1167373381.1648 | 1043962561.2524 | 208438795.7696 | 155026936.3318 | 1050809566.6733 | 28446703.0509 | 217327787.4269 | 317887690.6886 | 454499286.1306 | 134319243329.8517 | 1772866758.2247 | 1863088630.3311 | 2000262449.9019 | 177850821.5069 | 577608060.4009 | 721562200.1268 | 729647779.7722 | 242174595.9894 | 597555942.3118 | 25187369.764 | 133225687.3013 | 19947542.5398 | 25045889.2209 | 831765107.6033 | 26625441.6592 | 1102837889.0063 | 5734851748.392 | 682111172.3427 | 182823343.7927 | 2.6225e+12 | 2490316.8172 | 968788.6292 | 1522217.0339 |  |  | 2.7789e+12
631 | 1228600519.9545 | 1226063333.7751 | 208075505.9538 | 173025201.3827 | 953390601.5696 | 19028579.35 | 224655147.3427 | 327577913.5524 | 470200256.3726 | 153455439478.9712 | 2017275093.4057 | 1871906342.2547 | 2206493908.72 | 194945180.1926 | 591900809.5018 | 682715982.1166 | 763567891.4224 | 295902800.0403 | 540697296.1713 | 24553909.5889 | 103395796.5858 | 24823621.4907 | 25083965.6208 | 761709201.5546 | 28027053.3255 | 1083259395.179 | 5449439683.0097 | 571000610.2501 | 163261501.9257 | 1.7127e+12 | 2540017.981 | 925571.3566 | 1605570.1971 |  |  | 1.8884e+12
632 | 1058877992.8131 | 1116220869.2771 | 211964836.5624 | 175068333.9773 | 1067290842.3976 | 26339874.8767 | 196688409.3467 | 307736904.8049 | 477047386.0614 | 123617442715.6518 | 1767537778.0771 | 2072954241.7306 | 2120389688.9058 | 197787661.1204 | 582768507.5065 | 700949722.9208 | 898315647.05 | 272477567.3477 | 572225364.3348 | 20816493.1582 | 112754899.7824 | 20059467.5228 | 23692094.4535 | 761100192.9246 | 25672064.0587 | 1176477371.2305 | 6149885448.9015 | 630851283.9038 | 189928601.3612 | 2.0581e+12 | 2217659.7036 | 962959.1611 | 1472938.6769 |  |  | 2.2047e+12
633 | 1240368737.2823 | 1223374201.747 | 212879881.7624 | 174771935.6725 | 1012217751.635 | 24761089.4505 | 200736782.2721 | 331103383.1638 | 498005652.1264 | 134751278030.6944 | 1942741845.413 | 1978856925.45 | 2210996094.4522 | 165653332.2435 | 663647135.284 | 641484842.4836 | 898386659.9334 | 296586064.5052 | 603074273.5491 | 23177213.0751 | 98075143.7477 | 21582999.799 | 26010568.4695 | 798508677.6644 | 24998087.239 | 1136900186.9306 | 6471038996.3582 | 668185164.2743 | 199495765.9434 | 1.8458e+12 | 2656280.8183 | 949113.1967 | 1669686.1287 |  |  | 2.0044e+12
634 | 1221855355.4795 | 1188485548.5588 | 184991521.1419 | 172131730.5153 | 1076646518.2595 | 20479518.802 | 215737563.563 | 318135787.9842 | 498615121.7315 | 137027704498.5444 | 1990477435.819 | 2019876154.0949 | 2136766116.2205 | 193966170.7339 | 556084395.2434 | 687489004.1277 | 755415073.0692 | 303861845.5322 | 558095959.4791 | 23247427.837 | 122459107.1924 | 23971616.2403 | 25845828.2742 | 832622467.9842 | 30702755.9784 | 1102656526.9936 | 6094404425.6452 | 693373074.8467 | 189311329.2426 | 1.3911e+12 | 2675732.3682 | 989379.4665 | 1656053.7488 |  |  | 1.5514e+12
635 | 1001034377.229 | 1149077875.4486 | 197840287.2193 | 158694873.4466 | 1054135070.5595 | 20826971.4662 | 221624723.3395 | 306583134.0541 | 450254925.7059 | 122491455897.772 | 2017418890.665 | 2126486510.4325 | 1969472694.4956 | 170247905.3999 | 682469178.5632 | 687492836.7557 | 554474043.8399 | 321990072.532 | 549778366.4703 | 25006264.7954 | 106944524.1552 | 24775209.3669 | 24684121.9729 | 861366911.1246 | 31582240.0477 | 920746298.0883 | 5638027562.5287 | 608937787.5262 | 181176408.9844 | 1.8273e+12 | 2387135.0049 | 931643.8456 | 1763822.7463 |  |  | 1.9719e+12
636 | 1103198695.759 | 1161610232.4362 | 214840237.0086 | 152954473.6531 | 1061374682.2193 | 22553488.7288 | 200248455.93 | 325004022.0106 | 478497414.7548 | 145566973549.6541 | 1802480956.3857 | 1935530566.7863 | 2156338489.7683 | 195299538.3691 | 559637088.1907 | 710824272.0542 | 779090081.1 | 335924365.7639 | 551010677.7524 | 27086649.6635 | 102027644.3122 | 19202512.9501 | 22068988.419 | 921909575.5935 | 27842824.8113 | 1101346965.223 | 6127703191.8969 | 704259172.1771 | 198016233.6543 | 1.3649e+12 | 2326883.4066 | 955661.4815 | 1721487.6667 |  |  | 1.5335e+12
637 | 1216409010.8489 | 1224274488.1316 | 223580925.4578 | 162919556.4184 | 1026383787.6354 | 24288703.567 | 211705465.6273 | 286000090.6795 | 461392394.953 | 147059997324.4132 | 1581871192.5848 | 1766959969.8766 | 2018033318.9805 | 172162712.1011 | 577450016.7979 | 617566988.3923 | 856470492.7281 | 333746524.5032 | 598578506.2911 | 25587219.7137 | 117267491.6882 | 19099288.1068 | 18475741.9062 | 909382006.0266 | 30483831.8464 | 903171610.4453 | 5917390762.6254 | 647977836.2883 | 166089635.4869 | 2.1301e+12 | 2384332.0557 | 983332.7481 | 1547857.9587 |  |  | 2.2992e+12
638 | 1205027850.8152 | 918045862.1838 | 210284688.9817 | 170309316.5929 | 951579269.4521 | 21675588.8503 | 217069821.5858 | 296795781.2747 | 493808777.5046 | 142818290955.8595 | 1751954179.8978 | 2160372142.1676 | 1915291116.2529 | 190659349.3464 | 605486930.8028 | 570497702.9749 | 836950553.7672 | 353096593.1649 | 591901097.9562 | 23089920.0181 | 125433070.0873 | 24794438.8178 | 24284172.4904 | 813412358.1465 | 30130727.7256 | 1093056358.6211 | 5727217811.8937 | 664114615.8461 | 179372620.4075 | 2.0877e+12 | 2503800.7765 | 984279.3992 | 1683190.6845 |  |  | 2.2526e+12
639 | 1107098451.6402 | 1110869101.0945 | 199052120.195 | 166588534.4899 | 1077809248.668 | 22683858.3889 | 204921679.2232 | 287359937.5226 | 446103836.7255 | 141168150573.9321 | 2062016183.6192 | 1970263999.4246 | 2138009863.4831 | 195701964.4676 | 538765272.2963 | 668979084.3926 | 790216815.2811 | 328767393.7631 | 608197273.4369 | 23969537.9261 | 112978708.2948 | 22949952.8913 | 24181843.029 | 758496375.1118 | 25861697.3929 | 962611121.7329 | 7046263573.5993 | 622831226.7184 | 196932478.6408 | 2.2369e+12 | 2640550.3688 | 997673.3263 | 1545721.5395 |  |  | 2.4018e+12
640 | 1038541009.4544 | 1204957793.4502 | 217503634.1396 | 181011758.9073 | 1069974327.688 | 20796149.8862 | 218942064.33 | 328122888.096 | 440649058.6359 | 136264593916.2527 | 1787690764.9429 | 1585900112.4235 | 1917003747.9351 | 187626999.746 | 489845050.6138 | 687791677.1223 | 735847785.413 | 304921227.1798 | 606696632.0659 | 25575702.0288 | 119157316.6189 | 20213801.654 | 23730949.0088 | 824917017.7579 | 26789319.7246 | 1045947163.2452 | 6151135519.0453 | 698234629.5194 | 152658749.1476 | 2.5354e+12 | 2390299.022 | 965088.1542 | 1588601.411 |  |  | 2.6938e+12
641 | 1144340233.7723 | 1021376697.692 | 207740570.1389 | 176309283.866 | 1072462434.164 | 22414424.271 | 225295454.5347 | 310631058.1967 | 473465833.2727 | 125025645750.8662 | 2038399807.2321 | 1921927474.4041 | 2070932504.7382 | 196620252.7873 | 615345740.234 | 588739124.9946 | 707444035.9415 | 273444701.9306 | 567714670.5445 | 19206596.0552 | 111784488.158 | 19680361.3244 | 25262885.3668 | 840363557.6773 | 27722985.6252 | 877161117.2837 | 6737482428.6241 | 671129793.2651 | 180138201.5199 | 2.1471e+12 | 2404252.7396 | 886297.6614 | 1819528.0851 |  |  | 2.2953e+12
642 | 1193698772.7877 | 1228615796.9031 | 212815040.5869 | 167582946.2728 | 956934695.6947 | 23186771.3106 | 224973857.7813 | 322125740.1444 | 472899774.5881 | 153517068377.7578 | 1781439475.0452 | 2150267920.1896 | 2147949307.1309 | 154000350.919 | 677824784.7395 | 723090424.8363 | 718695886.0604 | 331552189.3759 | 606854336.6487 | 22329698.1229 | 127648967.7092 | 23030056.6535 | 24910176.3681 | 864877344.9316 | 26806503.9664 | 1091491055.6871 | 6958552554.4323 | 584496978.3548 | 190563211.8306 | 1.8887e+12 | 2612669.2505 | 974318.2068 | 1814985.0585 |  |  | 2.0662e+12
643 | 1233581687.9913 | 1147091249.0706 | 209767541.9921 | 170102673.2174 | 1066651942.1362 | 23296324.7145 | 191158797.3091 | 287228882.8467 | 443174021.7968 | 125981728146.8431 | 2071237768.3503 | 1886289075.6649 | 2053214073.4585 | 195144848.8578 | 648910709.5076 | 586600111.1681 | 724778971.7342 | 311867296.8826 | 592447981.7626 | 23625096.9155 | 125782153.0125 | 24158682.3925 | 23682765.6997 | 778838046.8291 | 26578606.4327 | 1123620439.8766 | 6541285420.6058 | 687728543.9098 | 198666219.2784 | 1.5561e+12 | 2580051.4744 | 910373.1751 | 1712402.622 |  |  | 1.7055e+12
644 | 1168932890.621 | 1034384161.2996 | 216068910.1883 | 166009509.1475 | 899976473.0871 | 21493628.941 | 216914551.897 | 328617286.6686 | 420802250.5062 | 146553278503.2772 | 1703222962.6883 | 1994799663.8689 | 2166017722.2371 | 199231746.3035 | 648272907.2904 | 723537847.5829 | 680553594.0467 | 278260501.5571 | 518308416.6181 | 25695134.7158 | 104647167.1643 | 24536588.7061 | 21836325.7399 | 834968540.3271 | 21718962.3978 | 1070527420.4446 | 6736281588.0602 | 684289845.8997 | 200142765.024 | 2.0278e+12 | 2610491.3657 | 913624.5948 | 1697286.7796 |  |  | 2.1975e+12
645 | 1191302574.0284 | 1215547966.2694 | 220294801.0852 | 159506836.1791 | 1087138715.941 | 21011918.9145 | 220569155.3594 | 302912107.324 | 496228446.7999 | 155293683208.5566 | 1851047143.6152 | 2153456877.7071 | 1690949277.2448 | 169976546.3324 | 563628523.3993 | 583704601.3519 | 655952839.0308 | 284374404.2018 | 582045806.0033 | 21820024.8858 | 117457691.4513 | 22752595.6655 | 23065882.0491 | 798970239.9838 | 20151232.8456 | 938156862.1694 | 5834113423.9277 | 675833251.3953 | 199889428.5113 | 1.4216e+12 | 2781184.8504 | 931280.7165 | 1500400.8159 |  |  | 1.599e+12
646 | 1230086792.9418 | 1178602648.9589 | 220933134.5544 | 156595319.7031 | 1086694092.8683 | 22444359.9023 | 178819134.3326 | 295458986.5144 | 495997652.4511 | 159979138646.6171 | 1837898300.825 | 2005185281.1505 | 2167394928.376 | 176379069.8474 | 632181618.8004 | 676565250.8352 | 723211559.6358 | 351030692.2925 | 577699296.6085 | 26460585.2861 | 114607487.6365 | 19448097.2328 | 21538001.7501 | 780985932.9527 | 29659320.3269 | 1148105071.0486 | 7142420513.6964 | 667755213.0009 | 173533077.1609 | 2.0229e+12 | 2674038.8367 | 1012917.6952 | 1755228.9444 |  |  | 2.207e+12
647 | 1108791543.8549 | 1132784630.5243 | 214565858.0702 | 153590004.6719 | 1072737213.8705 | 23496698.3807 | 218338785.6249 | 314993116.4259 | 498496994.5657 | 157352800135.685 | 1936916546.7785 | 1901302945.8288 | 2195820241.8592 | 202953627.2112 | 615639220.1229 | 719541158.0563 | 727623014.3698 | 322883434.4878 | 571949407.285 | 26506821.5041 | 105247879.4593 | 22471087.2638 | 25624077.5798 | 756244808.0212 | 28107728.8537 | 863500694.8954 | 5956429394.3811 | 576662460.2841 | 189027387.1968 | 2.0295e+12 | 2369905.8199 | 916486.1283 | 1807072.0093 |  |  | 2.2094e+12
648 | 1202266166.1528 | 1131724528.2246 | 191086261.2791 | 160124481.9053 | 1044905155.0804 | 21112836.4625 | 217237798.7738 | 323361794.1927 | 482783015.5955 | 142079272206.058 | 1935966539.5562 | 1634421983.9943 | 1658727836.3207 | 174971428.348 | 466363730.4936 | 562037097.9929 | 789974760.2312 | 253692646.9052 | 556630282.2687 | 22539881.5851 | 131490627.207 | 24359654.567 | 22327690.8329 | 822089590.9079 | 29468717.291 | 964621971.2301 | 6848825889.7717 | 556364484.3013 | 179923644.859 | 2.0693e+12 | 2430066.2003 | 920553.3994 | 1841088.523 |  |  | 2.2338e+12
649 | 1131461464.9791 | 1094761371.3038 | 214354880.6277 | 171668917.0176 | 969445803.491 | 28799626.6886 | 216158743.745 | 319345904.1387 | 430394078.952 | 139595182123.5656 | 1994327812.7409 | 2214972499.9769 | 1947565673.4283 | 182892367.456 | 602344575.3588 | 673262677.6176 | 882895606.4285 | 313679804.0175 | 610568434.7508 | 21988243.1273 | 103628282.1252 | 23798923.0135 | 22951423.5018 | 751167362.0458 | 26684467.1757 | 1072166454.0926 | 5345606179.7014 | 622979625.2263 | 173967869.2568 | 2.4504e+12 | 2276220.9134 | 881543.1724 | 1591066.4483 |  |  | 2.6122e+12
650 | 1205125531.4727 | 1125281551.4284 | 209384964.0421 | 158775600.7193 | 1063543954.5073 | 24573198.6987 | 216334228.5043 | 313567071.1358 | 498554008.6923 | 153204411716.1352 | 1769217958.4821 | 1967826053.53 | 2137639688.1514 | 172262443.0381 | 641268944.6828 | 725279672.2192 | 786594826.9578 | 296307514.4703 | 484040803.2748 | 21452272.5156 | 129381268.2124 | 21319723.3782 | 23225346.0421 | 814283300.2273 | 22554798.6302 | 1118617688.5271 | 5693344077.9884 | 686945894.0228 | 194107447.5078 | 2.1651e+12 | 2586819.4579 | 974576.2813 | 1601816.47 |  |  | 2.3408e+12
651 | 1116567989.7522 | 1126284129.0368 | 209991182.9617 | 167160624.5374 | 1013597808.4942 | 26316825.0195 | 219480189.2306 | 295575827.6126 | 456454130.4603 | 149063352867.999 | 1706215862.6017 | 2114516414.6547 | 2203865673.924 | 175834484.9994 | 634333132.113 | 682022504.8125 | 849762604.2395 | 294660816.2373 | 600435399.7883 | 26496406.8535 | 90371353.6383 | 23755532.8372 | 25646130.8088 | 881091047.525 | 27684058.783 | 1109254268.3993 | 6214671970.7479 | 643782833.2045 | 166568216.4378 | 1.6503e+12 | 2243918.7537 | 937338.8028 | 1558347.1332 |  |  | 1.8225e+12
652 | 1231663160.7101 | 1206369764.6361 | 192156406.4308 | 159091724.7182 | 971900034.2687 | 23622855.1091 | 193407299.5637 | 281516139.5596 | 477177508.9458 | 148734508463.4109 | 1588522020.6353 | 1934414550.2736 | 1901120113.5145 | 200499414.3933 | 605700929.1576 | 691543697.5954 | 706645017.9454 | 297020875.3048 | 605888955.1543 | 26702635.5822 | 122828563.6185 | 20897160.6202 | 23312184.3715 | 935552550.2772 | 26061220.5091 | 1123425990.0707 | 5478813537.009 | 587712324.7258 | 183662219.9999 | 2.3207e+12 | 2446919.4549 | 994004.7048 | 1581340.3626 |  |  | 2.4912e+12
653 | 1116826799.9331 | 1206149231.1346 | 187860900.8049 | 179721042.5655 | 1085376547.2748 | 26302650.3734 | 216670189.7904 | 296343982.7351 | 454834294.498 | 142261251038.5963 | 2053055085.8224 | 2083159467.4316 | 2079609994.7326 | 173977855.6544 | 618246288.9584 | 674349435.3294 | 866750844.7554 | 296203014.3427 | 550470033.1063 | 22060630.3439 | 130451948.5596 | 20714644.628 | 25103024.6947 | 774973937.0505 | 25309144.4118 | 954142163.1238 | 7034744485.89 | 704740988.6437 | 196218898.1915 | 1.9137e+12 | 2692797.4678 | 924053.3105 | 1762819.9817 |  |  | 2.08e+12
654 | 1145842139.4205 | 1198895764.1941 | 204074599.6107 | 169509495.3782 | 1064347752.5357 | 22842532.4505 | 199591949.1772 | 327038627.0385 | 465456044.9522 | 140842596547.6494 | 2035804245.0807 | 1923900295.9468 | 1835368041.8817 | 168377543.8387 | 649970616.7332 | 640973502.8853 | 848772495.8713 | 269038318.9697 | 559836537.6547 | 23576696.933 | 107506157.4693 | 16602846.7626 | 23306838.0884 | 922329313.5527 | 28659791.5182 | 1197305576.833 | 6171939466.4758 | 622221043.0869 | 198728807.0959 | 1.8161e+12 | 2852452.1323 | 1005319.6869 | 1564177.3042 |  |  | 1.98e+12
655 | 1004962293.5144 | 1198674027.9563 | 181221098.751 | 174880856.8615 | 913230191.3612 | 24127735.7979 | 221201321.937 | 324085372.2643 | 487343806.2298 | 145905545171.0409 | 1853338705.5106 | 2099272484.2856 | 2065907900.9227 | 154532217.2163 | 532018924.1617 | 689764003.7698 | 883190964.0015 | 309696431.7276 | 607409988.7333 | 21896432.9572 | 105381253.3228 | 20657346.9008 | 18866243.2786 | 879984517.9435 | 24149585.4747 | 1103435748.1893 | 6336128670.365 | 628169608.6495 | 193189198.8013 | 2.6795e+12 | 2797221.5019 | 971429.4623 | 1643478.4766 |  |  | 2.8484e+12
656 | 1234094036.0042 | 993656563.1715 | 195640063.9056 | 176768141.2149 | 1071893801.3418 | 24626908.6557 | 193928623.4545 | 290969635.3877 | 464471325.4963 | 148194574369.7477 | 1657309780.0195 | 1506353655.6773 | 1890032234.024 | 194257024.1419 | 610553044.5604 | 664919669.445 | 868993961.6934 | 318969310.094 | 603800753.1021 | 18373061.7598 | 123532600.065 | 23570322.164 | 25889112.459 | 903480363.79 | 25959336.4475 | 1220298889.9534 | 5928214777.2637 | 691939032.794 | 198813198.9468 | 2.3431e+12 | 2411476.7094 | 959930.6582 | 1622124.3069 |  |  | 2.5135e+12
657 | 1209241594.2852 | 1181425784.1682 | 189598756.767 | 178952285.2891 | 1051378687.8503 | 27880720.394 | 211264103.9541 | 274668707.4193 | 480900271.2266 | 144705938943.7993 | 1716311669.044 | 1794827230.715 | 2128403539.77 | 172007735.9648 | 530238939.0383 | 661438857.4234 | 903330188.1117 | 328388934.5605 | 602634687.6641 | 25247510.558 | 120692391.634 | 23162915.1574 | 23701683.3365 | 757655912.629 | 27011431.7935 | 898543502.0759 | 5975998752.9356 | 690800695.7118 | 182802968.7928 | 2.2296e+12 | 2246006.6375 | 923477.993 | 1778075.4851 |  |  | 2.3966e+12
658 | 1197713303.6017 | 1010820736.5026 | 193006607.3425 | 163798615.8904 | 1055997000.3821 | 26966099.593 | 223410633.9443 | 308357233.8517 | 485987793.4244 | 138346952017.6155 | 2004542341.5813 | 1886110883.537 | 2201066925.5675 | 167592873.0206 | 644158658.6019 | 676320900.0972 | 904158024.3174 | 262795902.3477 | 581473128.6889 | 25838162.0292 | 131914213.3053 | 22659574.494 | 19882899.2107 | 950120383.2282 | 26030808.4724 | 1141540166.8485 | 6464447461.1113 | 651487061.8729 | 200315801.749 | 1.7033e+12 | 2457029.0409 | 912408.504 | 1555971.737 |  |  | 1.8653e+12
659 | 1184235685.466 | 1192261575.0564 | 210663682.6848 | 174372491.9847 | 1015235331.1106 | 22603198.7989 | 205858840.3635 | 315992643.5423 | 401311260.0407 | 146984361293.0219 | 1539365031.2225 | 1505415487.6814 | 2152698998.152 | 179217302.7148 | 640619881.8135 | 600723219.3083 | 850704254.5813 | 345346516.4201 | 546117625.1663 | 26701188.1539 | 131355194.9554 | 23489272.7818 | 21282887.2414 | 794651809.539 | 24150035.4869 | 1041903562.7243 | 6522746005.2625 | 678409811.4444 | 179362644.916 | 1.9933e+12 | 2740966.1362 | 898884.0277 | 1880056.0725 |  |  | 2.1628e+12
660 | 1176954357.347 | 1094921206.3368 | 219081887.0374 | 170376239.4257 | 1067426318.6078 | 24024596.4331 | 175440777.6787 | 282323695.0968 | 424879339.5468 | 147429448249.3314 | 2059089885.1631 | 1927116756.3698 | 1802690603.9424 | 202331792.2557 | 565610062.0261 | 605052104.9776 | 785120303.532 | 314944904.3338 | 608610635.7216 | 23219389.9275 | 102925932.3812 | 23763200.9505 | 20293696.3772 | 880163368.9621 | 27353401.2277 | 999685429.7343 | 6137272737.405 | 652015329.9522 | 199974909.9606 | 2.7201e+12 | 2297153.7665 | 947633.6893 | 1549964.2765 |  |  | 2.8901e+12
661 | 1254538184.6937 | 1213792529.7766 | 222707464.63 | 174383948.8529 | 1053868212.5853 | 23989239.3281 | 215548296.6313 | 325753344.9645 | 497099550.1731 | 143627181958.1664 | 2081390403.5274 | 1949936188.7564 | 2150528169.1816 | 186978006.9766 | 624888900.6753 | 642248195.0451 | 693861612.8665 | 299525348.6807 | 567650586.2644 | 27717245.29 | 133983117.3864 | 22720412.4942 | 24631592.0823 | 935413289.5434 | 31649515.5737 | 1142182984.5761 | 5884852638.3844 | 659561757.1655 | 200659069.1008 | 1.5038e+12 | 2479130.9353 | 958434.151 | 1847402.0925 |  |  | 1.6707e+12
662 | 1149777651.2591 | 1163323329.0046 | 222039845.82 | 168407545.7811 | 1076573381.5961 | 26039883.5241 | 215188712.6344 | 328255499.8722 | 492140219.2984 | 136927717732.391 | 2020629728.5689 | 2020956845.8268 | 2196345510.0801 | 156623450.0334 | 608749975.0522 | 608464056.4164 | 715175001.3933 | 339665256.6074 | 567335876.8428 | 22091822.4433 | 128499549.3162 | 23178221.1377 | 23600054.7937 | 797151848.0241 | 30728740.9006 | 1130913374.6101 | 6399346658.7898 | 675178750.4507 | 198435001.3753 | 1.743e+12 | 2187593.288 | 926372.4063 | 1748266.077 |  |  | 1.9034e+12
663 | 1186348429.3893 | 1224695375.4539 | 189191804.8165 | 154530908.6105 | 907326726.0405 | 21455733.6772 | 222458901.7653 | 306598231.1305 | 421074861.8622 | 155359284025.2829 | 1702013741.1587 | 1880956353.2906 | 2124585011.8372 | 197837357.219 | 508989601.0372 | 671274094.9829 | 807282106.4026 | 332512068.9224 | 583132816.8046 | 24324677.1214 | 122375994.3072 | 17676332.2782 | 25661730.0781 | 918875953.8462 | 30180995.3375 | 1069368521.2082 | 7178399439.3914 | 666726637.3447 | 196589497.8812 | 2.0137e+12 | 2516253.3265 | 940595.2365 | 1688219.1383 |  |  | 2.1927e+12
664 | 1202497678.8341 | 1204197633.1517 | 202941435.9485 | 160309064.7133 | 1001247740.9328 | 20493282.9072 | 191018747.536 | 321716979.6007 | 438811911.0959 | 130186730704.1276 | 1796752731.2615 | 2013415393.4936 | 1989526473.9252 | 182773602.9759 | 567901687.8685 | 655485809.6871 | 858567554.8362 | 256507908.3189 | 557836633.0794 | 24546066.0223 | 125100922.5906 | 24747020.3263 | 24308362.9427 | 788546469.7312 | 29871379.4448 | 979138181.524 | 6613269619.0735 | 624601449.468 | 168025449.0674 | 1.8559e+12 | 2506394.6794 | 954233.6025 | 1524894.1448 |  |  | 2.0092e+12
665 | 1173767699.428 | 1200845897.2644 | 205693114.8372 | 167732340.3888 | 1056667870.4818 | 23531042.1158 | 218541443.0541 | 314370025.3009 | 439371018.4705 | 153266979451.3017 | 1947949081.8296 | 2045511841.8079 | 2200094620.925 | 201299397.0136 | 609891737.1755 | 692966158.978 | 873897846.3234 | 358369516.472 | 553519845.7532 | 23699194.9768 | 128027422.8358 | 23616800.3149 | 24056356.3531 | 891112531.0962 | 25235550.1811 | 1130783275.5807 | 6835085863.6579 | 646236666.0541 | 187735184.1665 | 2.1768e+12 | 2277422.7983 | 910188.3035 | 1556819.2513 |  |  | 2.3543e+12
666 | 1252496416.1624 | 1200151744.6219 | 204501990.664 | 161971553.2433 | 1048765197.2044 | 27514520.1375 | 193901596.5416 | 317812590.5112 | 499696522.7227 | 147800672179.8148 | 1988418505.7937 | 1716163111.2286 | 2183289959.6254 | 167184466.8838 | 550292958.1674 | 632355035.7696 | 656443059.8767 | 302685516.9815 | 568331956.6862 | 26805681.7497 | 120686979.1032 | 24355765.1382 | 23256704.8472 | 915144415.7584 | 28717266.9352 | 1048267014.036 | 6845026317.9017 | 685251717.5842 | 189713393.5108 | 1.6884e+12 | 2635809.7792 | 976472.3785 | 1828433.1536 |  |  | 1.8598e+12
667 | 1136070976.8556 | 1157981006.4365 | 206357700.4184 | 167499864.1218 | 1013100217.759 | 28443211.9133 | 218295813.1536 | 317433956.5216 | 464548527.9395 | 160532054232.7302 | 1940206243.9913 | 2058403500.3742 | 2049368677.6392 | 198591524.2989 | 648503951.5748 | 642406328.9401 | 890136344.1237 | 253915570.2325 | 584580622.8915 | 26907368.7286 | 126847743.7941 | 21239737.6946 | 24320774.3529 | 934603518.1414 | 27425655.7021 | 880491640.8734 | 5960894493.1715 | 553294759.8746 | 191270919.1999 | 2.1889e+12 | 2366132.9735 | 926155.6183 | 1518200.6653 |  |  | 2.3721e+12
668 | 1193689323.9488 | 1157479244.5797 | 215115191.1703 | 172908606.5734 | 1022506897.5575 | 26504290.4021 | 218074086.3973 | 323576210.0764 | 496267298.5268 | 138576724423.5593 | 2068131601.1773 | 1669278806.7004 | 1869809708.6241 | 146047994.3902 | 594955553.9428 | 621795715.0706 | 821186338.5669 | 299003823.2503 | 539173754.2441 | 22106419.9589 | 118592469.0902 | 19254317.1188 | 24670599.3692 | 852997770.7678 | 24670492.1423 | 1007103321.6278 | 6198469840.7211 | 688345493.9225 | 180309154.9784 | 2.0083e+12 | 2573885.3846 | 970132.616 | 1538830.9046 |  |  | 2.1695e+12
669 | 1127236292.561 | 1169604769.9915 | 200723661.7418 | 171466347.8554 | 1087127455.7394 | 20104721.8984 | 198407720.351 | 324289773.4239 | 483355939.5033 | 130222575901.4596 | 1656633649.9164 | 1675149852.2941 | 1956128832.7328 | 195682248.2211 | 637451431.9693 | 673429056.3121 | 764951649.3558 | 247066997.0749 | 570757712.0906 | 22350180.3464 | 122254329.8559 | 23769023.9814 | 23082772.7143 | 905363680.0917 | 29888721.942 | 1104126523.8236 | 4807871839.5287 | 636793509.9994 | 197950047.1747 | 1.7632e+12 | 2525800.8143 | 981710.6733 | 1611857.2097 |  |  | 1.9145e+12
670 | 1198221646.1396 | 1130909688.0024 | 203884805.2707 | 161424586.4444 | 1082184017.5417 | 22965340.1223 | 188680475.3443 | 306019536.8443 | 421652626.3192 | 155464804386.0799 | 1861210842.621 | 2063031005.9507 | 2129094464.8387 | 187162107.7843 | 520503192.4992 | 554362847.0055 | 784700028.961 | 323475341.8245 | 578295661.0435 | 24946899.3628 | 113635435.2478 | 22166457.993 | 23508305.0044 | 895806049.8689 | 27385737.9302 | 1010397940.265 | 5872430626.1309 | 616408961.6211 | 169007126.2101 | 2.1889e+12 | 2421206.7168 | 902654.7324 | 1612795.9688 |  |  | 2.3669e+12
671 | 1206539675.2279 | 1152874170.5575 | 216349751.8847 | 165073985.6621 | 995701792.0625 | 21794404.6426 | 211722799.9952 | 323599124.7948 | 484753842.6981 | 142938982995.7263 | 1744126828.3908 | 2054553607.5119 | 1905593400.0825 | 196725708.9142 | 658389938.2492 | 719503319.9092 | 915618268.3908 | 273659343.9946 | 553830751.9881 | 25211459.9802 | 130131430.3774 | 24653927.7598 | 23603266.9664 | 858352018.4248 | 25334989.7758 | 1046454465.6106 | 6010778128.1146 | 640810357.6123 | 168884621.8425 | 1.8386e+12 | 2629925.9146 | 957612.559 | 1519881.0679 |  |  | 2.0043e+12
672 | 1188558743.8131 | 1148110140.9477 | 199029507.8846 | 149862142.3057 | 1037159752.4868 | 22194273.9285 | 221768737.1923 | 309620146.5466 | 499411803.9968 | 131672199922.691 | 1835252279.2085 | 1996005665.581 | 2123288522.0426 | 202861824.48 | 490646808.2274 | 621357555.9582 | 829186294.0618 | 310550432.3519 | 603296132.1107 | 24077413.3878 | 120675787.6142 | 24484114.5956 | 20916595.4382 | 936481231.0593 | 23086966.7433 | 1076661025.3555 | 6952837180.6839 | 576860220.301 | 189481841.2984 | 1.9439e+12 | 2542945.2586 | 957795.8807 | 1801074.0016 |  |  | 2.0993e+12
673 | 1126309308.3636 | 1216191753.3383 | 199543585.8313 | 151453384.7581 | 1063216526.2658 | 20601355.6884 | 211536438.7082 | 297359778.7041 | 425675095.4929 | 135166972279.3471 | 1610622037.0227 | 1896183222.4015 | 2140308730.9788 | 198851862.563 | 601264221.4202 | 655039028.3388 | 828635603.852 | 338776764.1388 | 586787992.786 | 23014564.8349 | 127168700.2722 | 22592631.6428 | 23385202.7074 | 802912020.4531 | 30177995.1454 | 989707918.8179 | 5612264398.4817 | 574400294.3313 | 197599562.8618 | 2.0974e+12 | 2533490.6574 | 933349.8477 | 1627292.6328 |  |  | 2.2546e+12
674 | 1106767404.3394 | 1192903817.4341 | 195674811.4576 | 177436561.6359 | 1076856765.0842 | 22289729.2337 | 176527333.1355 | 314645142.0625 | 403547238.3735 | 140219135228.4319 | 1930707112.5046 | 2107110454.5169 | 2109022985.0208 | 179507823.2197 | 598228189.8853 | 684932366.6061 | 877131443.6338 | 306989580.7875 | 583822381.8097 | 21737497.8723 | 121177646.3024 | 23279249.9509 | 24487833.4276 | 771417593.6912 | 26575148.4178 | 1055344481.0916 | 6249594776.2173 | 696233248.5671 | 144178435.1792 | 1.9405e+12 | 2424189.2099 | 931011.1045 | 1692063.5373 |  |  | 2.1039e+12
675 | 1187466919.4461 | 1134096887.1214 | 225934902.4745 | 168118513.9517 | 1060235846.1359 | 20817483.5997 | 177245788.1142 | 320894816.8204 | 415533886.9739 | 149428541623.3824 | 1968549491.2292 | 1966645271.6585 | 1974862973.3359 | 200509461.9345 | 500855121.8155 | 682198040.8508 | 851826531.5766 | 294528697.9162 | 601020617.1182 | 22488358.4553 | 106206474.8402 | 23682464.2824 | 20214190.7337 | 886478953.9153 | 28751072.0604 | 1124512016.2719 | 7106378545.1002 | 663292962.1044 | 199179446.2344 | 2.0069e+12 | 2608333.2855 | 966496.9568 | 1631537.2113 |  |  | 2.1803e+12
676 | 1201515888.8908 | 1177824369.8163 | 221910623.7173 | 172472137.4557 | 1082893238.3662 | 27664750.5847 | 221528910.6421 | 272715174.3228 | 457377905.3397 | 142123520561.8023 | 1956087908.856 | 1725824190.9731 | 1989167328.8769 | 176019722.2521 | 642388517.1011 | 601892142.1597 | 849424325.9364 | 267873141.1714 | 498807267.3243 | 23360181.3552 | 115367058.2349 | 20826692.6104 | 21682747.657 | 788567956.198 | 21719357.8162 | 1104608839.7318 | 6393551953.049 | 591165014.1252 | 200887844.1839 | 1.4365e+12 | 2507065.4434 | 923263.7474 | 1539102.4612 |  |  | 1.6014e+12
677 | 1123979646.5177 | 1214703615.3373 | 200765994.6192 | 155349549.5425 | 1066448463.7466 | 22396905.6182 | 225148923.3451 | 295491079.1112 | 453147008.265 | 159008623398.3335 | 2012613485.9432 | 2014310621.5168 | 1741728177.7497 | 201466487.9957 | 645227376.6237 | 672170110.0912 | 847239354.5748 | 292431977.6752 | 503680476.1724 | 22766436.3297 | 107803298.9356 | 22616766.2879 | 23895746.2317 | 823439198.8551 | 26686647.8332 | 1076438672.749 | 6272373018.1964 | 586746719.1436 | 177964021.4265 | 1.9039e+12 | 2524181.2083 | 934058.037 | 1772158.9084 |  |  | 2.0857e+12
678 | 1174119221.589 | 1155162690.9168 | 193558278.4665 | 166448966.4655 | 1076470791.9428 | 24002160.7776 | 197465802.7241 | 311701101.2772 | 485248357.7413 | 149342274205.2781 | 1892316565.9358 | 1580817287.7771 | 2134037755.4509 | 184576765.971 | 605781075.0681 | 612808764.9137 | 835957137.5229 | 287246996.5558 | 512639142.6423 | 22559301.0313 | 120608395.4647 | 21067700.9498 | 25467143.2651 | 761635647.4329 | 23508756.4276 | 1108862736.715 | 6821318563.9421 | 667493223.5865 | 200521237.3161 | 1.6267e+12 | 2590487.193 | 941284.3094 | 1727072.9269 |  |  | 1.7993e+12
679 | 1069096884.9866 | 1152537689.6552 | 204454541.7263 | 171705104.2913 | 949476807.4278 | 23723522.7055 | 200975405.1722 | 303148264.2771 | 418737703.246 | 136303676957.5065 | 1723537990.2164 | 2055538382.2065 | 2183634672.0937 | 198688517.5186 | 592782960.4522 | 711355870.5456 | 892271178.3443 | 327368966.3879 | 595511438.2898 | 27459502.4409 | 117375796.9327 | 22758317.0561 | 22273211.0553 | 852808815.7683 | 27911796.2729 | 839706547.5179 | 6184044829.2755 | 711326385.5117 | 199821153.3907 | 2.1525e+12 | 2397854.7647 | 876913.9305 | 1683100.5774 |  |  | 2.3116e+12
680 | 1153820749.9051 | 1169540332.7825 | 193743381.4808 | 170507109.0463 | 1026745065.638 | 25280368.7127 | 211273224.1315 | 326503551.4438 | 475992409.5961 | 147698131535.1501 | 1866501979.0096 | 1923890689.3238 | 1842891809.7129 | 190277018.4285 | 586019956.5506 | 705722906.2796 | 898142907.7931 | 334210014.2638 | 605243452.9957 | 21994932.9057 | 112177673.2256 | 23791235.9949 | 23477813.1723 | 737809577.9324 | 29178721.9494 | 1023186893.9999 | 6504783346.2908 | 482822696.5708 | 193802129.441 | 2.3594e+12 | 2570458.7203 | 931860.8361 | 1579282.9518 |  |  | 2.53e+12
681 | 1238396242.9656 | 1166552620.159 | 208215655.4877 | 171724686.3202 | 1078146340.5821 | 22999016.2967 | 200622495.592 | 310949302.846 | 420884060.7673 | 154341010859.1592 | 1967868915.0989 | 1725883693.9399 | 2140544194.7125 | 202950763.9409 | 600828725.9426 | 665307313.5913 | 733601818.4546 | 274645897.6472 | 605897825.0865 | 24710100.0346 | 112970934.8661 | 17744375.5578 | 24651968.3792 | 823584741.88 | 30401414.5421 | 1040251973.972 | 4929712877.7197 | 644490990.883 | 181779024.9698 | 2.2622e+12 | 2673696.646 | 970945.4361 | 1664162.0424 |  |  | 2.4381e+12
682 | 1085498043.0297 | 1121271783.0208 | 214498991.9541 | 179436049.2521 | 1081028860.644 | 21142116.4252 | 194159401.5835 | 284459309.998 | 479011760.2845 | 139425504465.62 | 1800362652.9853 | 2026347627.9749 | 1971881940.5062 | 186111258.1152 | 623071736.0995 | 721463474.7927 | 822764254.8896 | 328063599.6235 | 598474992.0297 | 25058853.8404 | 125161122.7877 | 19068056.1817 | 24834990.5606 | 831383102.1699 | 28244619.7726 | 943456475.7668 | 5562413214.5295 | 568246174.5611 | 195773771.7627 | 2.0866e+12 | 2859574.5587 | 985462.6305 | 1661979.2149 |  |  | 2.2481e+12
683 | 1140844671.3028 | 1219389325.9322 | 216298381.7583 | 162816704.4325 | 930104067.979 | 27460669.8616 | 219327247.8866 | 302150952.7387 | 468487522.3426 | 116373793811.2043 | 2076267104.0335 | 2148669318.7682 | 2170412073.0395 | 179392924.7475 | 574511464.9977 | 713805523.06 | 773188126.1295 | 257188962.8429 | 613374737.0867 | 22435832.565 | 111193414.1014 | 17734894.4364 | 23338832.8592 | 767489685.4243 | 28955646.3155 | 1063237902.2265 | 6835409394.3807 | 616620084.3925 | 157749231.4884 | 2.3774e+12 | 2547475.5581 | 930262.4513 | 1602739.2259 |  |  | 2.5176e+12
684 | 1146872576.5541 | 971227700.4316 | 214905331.2464 | 163243705.8199 | 1066772538.4046 | 21605312.256 | 190730163.64 | 315715302.0353 | 462861940.5739 | 148436858942.5108 | 1822543817.97 | 1988009041.3281 | 1556728028.2965 | 202789112.5156 | 669299814.2452 | 674967729.5597 | 885818092.1439 | 314730510.4396 | 589837512.1706 | 22640366.061 | 107146273.2698 | 23545977.2766 | 25254813.6358 | 827830318.4561 | 27374808.5599 | 1205448284.4045 | 6163725187.1563 | 655644541.0048 | 178601631.5617 | 1.6468e+12 | 2555347.9043 | 953757.8721 | 1716692.4968 |  |  | 1.8177e+12
685 | 1236876805.2666 | 1149623413.4536 | 215882976.7962 | 165234635.0958 | 1049471105.385 | 25763781.5191 | 219693305.2135 | 314165320.3324 | 468640795.8386 | 115720587380.8857 | 1944016130.2531 | 1794898800.0264 | 2196914147.5645 | 175415930.5472 | 630369030.8463 | 695092925.3614 | 768523691.5462 | 306856799.1509 | 506706858.853 | 23849267.3905 | 100686427.1008 | 21510452.1387 | 22087765.0189 | 849621670.2432 | 27259791.0257 | 1142143258.3652 | 7232027171.5073 | 697400839.613 | 198842473.9094 | 2.0465e+12 | 2560815.9125 | 977435.3188 | 1763544.321 |  |  | 2.1864e+12
686 | 1085293754.0301 | 1090315121.3821 | 206366334.477 | 140971904.9874 | 1079419381.9646 | 20188173.5996 | 199951512.5964 | 310776811.2673 | 419538146.965 | 152778167554.5866 | 1753347298.8716 | 1678225531.1246 | 2183562634.9753 | 160232230.8049 | 639351703.5914 | 656943661.4668 | 776043123.7173 | 315776782.9009 | 521860634.8904 | 23828090.7421 | 125145823.7754 | 23688075.1237 | 24711983.6609 | 849625275.4647 | 30489615.9557 | 1025943082.9708 | 6573302227.803 | 663310534.7483 | 160786876.4235 | 1.4771e+12 | 2396012.7478 | 938222.2217 | 1483738.5103 |  |  | 1.6526e+12
687 | 1231784178.3538 | 1067483264.6643 | 204011677.1156 | 158272251.8082 | 1020463398.024 | 20947074.6626 | 198313641.8322 | 322334552.5505 | 463725950.9217 | 146369865812.5388 | 2025256179.3219 | 1951040671.037 | 1724622354.4834 | 198336715.6555 | 637603503.1191 | 704779592.1852 | 752101263.529 | 308645609.2495 | 587185761.7897 | 18733239.9707 | 118896190.8834 | 23503680.3023 | 23938720.4415 | 871679062.5133 | 27898307.6724 | 1110312703.2333 | 7172100533.9979 | 577102425.7507 | 198571534.3385 | 1.6506e+12 | 2573629.6537 | 896599.8671 | 1611761.1623 |  |  | 1.8207e+12
688 | 1204879211.0715 | 1187213388.2841 | 215596449.0428 | 179335963.8994 | 873405538.903 | 20772805.5331 | 209914612.3971 | 324461774.3219 | 489994557.5115 | 137130759589.3117 | 2010085156.6759 | 2103127941.9455 | 1937203143.4491 | 191845281.5432 | 603900200.2944 | 711128331.7164 | 787111323.7712 | 329553841.0251 | 549198786.8258 | 25400434.7542 | 121449878.3984 | 20715112.6204 | 21508543.1798 | 918664706.1038 | 30263530.5599 | 1084859698.3766 | 5514105300.2638 | 674454771.0459 | 188395620.9196 | 2.7603e+12 | 2419204.647 | 1000098.192 | 1743967.8343 |  |  | 2.92e+12
689 | 1242891674.3729 | 1142118806.2797 | 225555368.3427 | 169424971.9604 | 1053827360.2132 | 27078014.3768 | 201204857.1696 | 301479367.186 | 432911868.4211 | 162470914300.0042 | 1775324719.5958 | 1876305516.9373 | 2004388231.2869 | 196077923.5189 | 670988847.9786 | 664621977.8805 | 773672734.9525 | 290850120.1835 | 557566203.5079 | 24247842.8091 | 133504779.3036 | 20461541.1007 | 24567054.7485 | 940734663.4322 | 27365364.991 | 1205483565.8873 | 6879785294.8816 | 669943145.3836 | 193063563.8642 | 2.2417e+12 | 2374124.4381 | 963936.6901 | 1646361.6323 |  |  | 2.4279e+12
690 | 1251101493.2701 | 1211635492.4289 | 224724840.5542 | 170295212.1258 | 934674310.1054 | 24300167.0228 | 222300482.7695 | 323104826.6564 | 465599191.4952 | 150191256964.0576 | 1868752165.674 | 2151265471.5443 | 2186133701.1464 | 188697130.6238 | 554499158.773 | 593590806.232 | 846129760.4597 | 288567408.1985 | 607263255.053 | 26678393.1654 | 105801918.0455 | 23228398.9598 | 22086214.9548 | 898149240.317 | 29160252.7316 | 1153545377.7848 | 6691554472.4088 | 603234219.2479 | 182332511.8028 | 2.0929e+12 | 2513979.2113 | 966282.7288 | 1863975.3329 |  |  | 2.2669e+12
691 | 1103765827.6233 | 1155255358.6568 | 173174427.5217 | 163388744.5847 | 1063872934.3251 | 27202031.546 | 207362079.2734 | 283949675.7814 | 447472993.3698 | 159519879647.999 | 1738217605.2072 | 1756448364.8276 | 2192808841.9272 | 165639643.6808 | 513650666.0586 | 713753611.4139 | 831332171.376 | 343910577.0673 | 576856626.9849 | 25843731.7394 | 91327242.2266 | 22454863.8135 | 23713668.5648 | 883677642.6625 | 24590306.1181 | 1166054865.9654 | 5241489934.3268 | 565260989.0975 | 200959099.5494 | 1.6283e+12 | 2490882.9658 | 907021.4503 | 1579018.0027 |  |  | 1.8095e+12
692 | 1203634948.0497 | 1162488944.1592 | 205832984.8122 | 163173946.7077 | 996314867.3573 | 20435282.9155 | 205436402.4432 | 309764401.3115 | 461911689.8093 | 125060031730.2898 | 2053333290.6322 | 1709809692.7362 | 1852787474.2701 | 190361759.5036 | 568299064.3298 | 655529131.1449 | 900960335.6913 | 315861667.6575 | 579045859.7831 | 26371670.5774 | 121537592.1939 | 22489072.2447 | 20065131.8806 | 799895271.3318 | 24143497.0219 | 986162022.5945 | 6856786736.8325 | 655788687.5834 | 181429417.5457 | 2.2018e+12 | 2855827.8336 | 929501.977 | 1630231.8667 |  |  | 2.3501e+12
693 | 1259441316.6049 | 1215889294.5799 | 212793415.6129 | 148197684.1051 | 1082678150.3521 | 20813010.5141 | 212266166.5997 | 323460451.5336 | 499368144.7074 | 149740992899.075 | 1848580726.4136 | 1861050874.6143 | 2043566592.7557 | 185870904.9957 | 592148821.9685 | 659576259.3125 | 769336533.8158 | 356750248.7926 | 515345382.1645 | 22572108.0451 | 105246298.6318 | 23149191.9047 | 23806818.5137 | 897502835.421 | 28194044.8652 | 1020982899.7259 | 6819222316.6902 | 616205997.386 | 200336392.0799 | 1.9506e+12 | 2615010.7482 | 997558.5862 | 1569280.3703 |  |  | 2.1239e+12
694 | 1221524121.4976 | 1214613157.1271 | 198649976.1904 | 176084275.087 | 1086990520.3004 | 20723990.4694 | 186453144.3776 | 326536254.5402 | 487978118.0562 | 140262242042.9071 | 2059861216.6677 | 1980034770.8897 | 2123774401.5094 | 199933878.9928 | 599460031.3988 | 620864940.0926 | 740193671.7789 | 342118885.2472 | 585297306.7024 | 25909710.1007 | 91291444.818 | 23660954.6126 | 21277937.6494 | 840775994.4877 | 27765271.8034 | 1030002243.7691 | 6226799692.3357 | 707053925.1688 | 178639929.3791 | 1.8552e+12 | 2737511.0373 | 927684.3728 | 1642670.6256 |  |  | 2.0188e+12
695 | 1221751861.5755 | 1187842303.9851 | 225916453.9932 | 161456092.9926 | 1035801542.6587 | 25031178.8424 | 204564184.8117 | 298538051.7093 | 430704743.4925 | 147659482878.5675 | 1888041909.8879 | 1572235370.0253 | 2190295801.6292 | 166892542.1904 | 602688510.5891 | 683580257.3194 | 875868596.6653 | 269877852.7059 | 587106103.3936 | 28272113.9393 | 115225262.6399 | 22680758.7989 | 24114184.4804 | 887072541.2593 | 27735662.2084 | 1179321976.7251 | 6802624077.6809 | 632030003.3437 | 169448218.9242 | 2.0815e+12 | 2652559.3859 | 981332.3935 | 1566357.4544 |  |  | 2.2526e+12
696 | 1226804328.2107 | 1097762423.7585 | 190890963.9084 | 173283501.0899 | 921280308.5054 | 25443326.1384 | 206453738.4101 | 310810779.0484 | 450997356.0657 | 156774527964.8834 | 1915795729.6404 | 1619998205.8609 | 1976433147.5061 | 180046560.7226 | 521359779.2464 | 625915636.1448 | 884251957.6151 | 297822730.0922 | 508034831.1975 | 24114584.3979 | 113391914.4586 | 24894690.5477 | 24664853.3768 | 845476318.1521 | 23703092.9893 | 1138860634.3191 | 6147644235.3537 | 697881224.5669 | 162166708.9545 | 1.9938e+12 | 2504449.2644 | 934221.8447 | 1582822.1591 |  |  | 2.1729e+12
697 | 1166530104.9229 | 1191751372.5738 | 203481813.4499 | 162594358.9309 | 1062008911.5599 | 20337369.0406 | 218271323.4709 | 328633605.7676 | 456446421.5001 | 152068464603.0074 | 2008700023.348 | 1727789277.9507 | 2091674911.8767 | 198653834.7019 | 599470310.5075 | 520628009.4407 | 839536427.1141 | 327567858.4725 | 470461440.5933 | 25724048.7279 | 128302049.2173 | 23746204.9603 | 23927676.2787 | 871059230.2556 | 24524815.8569 | 1142175390.7277 | 6324158041.3442 | 700697960.1815 | 193396355.7244 | 1.9356e+12 | 2382820.0214 | 919925.5313 | 1716057.9023 |  |  | 2.1107e+12
698 | 1143994704.0618 | 1196800814.6012 | 210423771.4028 | 170241304.7472 | 1046652761.6569 | 25309849.7081 | 225672525.5549 | 325135139.3641 | 482738772.7249 | 146091639366.5769 | 1807591660.2249 | 1643350869.3963 | 2093536415.1429 | 196817981.3672 | 642420725.3519 | 691000989.5538 | 656208760.3918 | 323088816.895 | 585984508.6971 | 23480527.4465 | 124799966.0382 | 23619510.2678 | 25804437.3671 | 792146848.1493 | 28077284.8449 | 1191545596.8359 | 6464788526.1533 | 713101213.7005 | 194779894.695 | 2.2155e+12 | 2445404.8847 | 993634.4839 | 1667857.0151 |  |  | 2.3846e+12
699 | 1141907710.4789 | 1141584196.6134 | 211886238.1203 | 144962132.2591 | 1001552125.9202 | 22610607.4098 | 191631743.0699 | 316321147.3388 | 493037735.3402 | 156375165852.8903 | 1707166198.0755 | 1975342794.1105 | 2011057375.5076 | 166948185.738 | 575261137.4225 | 711197137.0538 | 816033978.6714 | 345299882.8278 | 605930317.439 | 20495736.6878 | 101901508.8529 | 20568537.5857 | 24040803.4828 | 891293565.2845 | 25442471.3154 | 1137165389.3334 | 5363945219.6373 | 711230601.7553 | 165339821.8276 | 1.5636e+12 | 2830195.7936 | 953345.2896 | 1825289.5174 |  |  | 1.742e+12
700 | 1188662693.6945 | 1152930171.643 | 208996986.9028 | 148231126.0388 | 1003653149.2784 | 28370031.3546 | 194440201.3447 | 288869358.3743 | 461706213.6858 | 135604112193.5217 | 1664326387.5267 | 1889816396.2006 | 2203597628.1989 | 194316826.9521 | 652410714.871 | 725229337.2314 | 761076445.2366 | 272914007.0514 | 490957309.186 | 26248931.9852 | 103514529.8912 | 22983697.1084 | 23677130.7366 | 687471065.2617 | 26945986.048 | 1026669465.7659 | 6701496295.7489 | 602283701.4451 | 197569497.1817 | 2.4629e+12 | 2400379.0154 | 977876.4711 | 1589697.1554 |  |  | 2.6215e+12
701 | 1128602196.1315 | 1172542537.0581 | 192029496.3579 | 170640669.8404 | 1040862352.5569 | 22604986.9044 | 220427144.8309 | 317429587.632 | 491160494.2666 | 117112900617.079 | 1891328054.6862 | 1890916176.2792 | 2095073561.2847 | 194431737.8258 | 565755944.2738 | 679160810.5009 | 796470609.8256 | 254258826.2802 | 540932063.7211 | 22164690.5688 | 126538643.031 | 22514660.9813 | 24888914.5569 | 716298093.6595 | 28103119.475 | 1143990824.3517 | 5854068218.5163 | 590353689.19 | 185805554.3849 | 1.8885e+12 | 2346344.8488 | 1031739.259 | 1604923.6095 |  |  | 2.028e+12
702 | 1129734586.5109 | 1065421376.4522 | 194557675.9367 | 168864924.1923 | 959619651.2633 | 25496264.6766 | 210086624.3659 | 311683401.6059 | 427627903.1325 | 156521011927.9373 | 1952204535.0649 | 1743932622.8016 | 1909534262.2718 | 199227603.4405 | 609874522.486 | 686910382.0382 | 799577300.9664 | 227163776.6156 | 539945044.4674 | 24990855.7257 | 123161404.9387 | 24555326.775 | 24400138.6262 | 906365328.4025 | 25349277.2529 | 895863979.6254 | 6669576221.5295 | 606785532.1647 | 179763418.6622 | 2.0305e+12 | 2626714.0788 | 925460.4952 | 1534655.1397 |  |  | 2.2096e+12
703 | 1219252875.6002 | 1220136247.5582 | 207268987.4413 | 172164691.1549 | 1055293552.2881 | 22819954.2246 | 222131258.6669 | 273789151.0208 | 419850922.4977 | 121800477064.1515 | 1680245905.4307 | 1901436289.2502 | 1925555591.1806 | 179199789.751 | 533061922.6867 | 648660223.393 | 834596507.4247 | 280897251.6322 | 480854181.269 | 27124697.7914 | 120426814.0106 | 15539554.8503 | 20632531.1287 | 793820422.6901 | 23186990.0499 | 1214895315.959 | 5300208094.1236 | 532169330.1774 | 195469388.1492 | 1.7653e+12 | 2473917.5669 | 941829.4406 | 1676367.5974 |  |  | 1.9086e+12
704 | 1056871024.0032 | 1162226318.1234 | 216179808.3573 | 172501294.8168 | 988415696.7509 | 23467655.3669 | 195331554.8192 | 312027540.2241 | 447824197.0778 | 149068019495.7672 | 1731964681.4086 | 1751943872.3419 | 2125206056.5347 | 171234927.6555 | 582075933.6941 | 636262656.6004 | 831024677.3027 | 296443267.2714 | 608076899.9549 | 23343763.7954 | 93522428.074 | 21657186.8456 | 23005534.3159 | 940615182.6556 | 28201322.6936 | 1221312273.3707 | 6619435302.5911 | 582028479.4344 | 200975464.5005 | 1.836e+12 | 2616598.4843 | 1000360.5665 | 1774450.2147 |  |  | 2.0081e+12
705 | 1096105594.1423 | 1079265192.3248 | 218462408.2178 | 179719356.1723 | 1057348573.1011 | 21741512.8106 | 213967025.8667 | 317307434.6186 | 441864148.6824 | 129069959808.581 | 1999075834.3364 | 1697526521.2183 | 2009565244.0463 | 146183815.3895 | 662388871.409 | 546576293.1734 | 758857277.8464 | 287848135.4777 | 569434523.9289 | 24092347.5977 | 131110829.4879 | 21359469.6593 | 20613988.1872 | 792883326.4494 | 24576522.8094 | 1028872208.1637 | 6568569521.628 | 652072857.2289 | 198903872.5372 | 2.386e+12 | 2651001.9516 | 911230.3618 | 1625820.4749 |  |  | 2.5379e+12
706 | 1077573144.2865 | 1181394066.0128 | 212876972.2235 | 173016354.7008 | 1053985725.9067 | 25089732.8948 | 212469339.1484 | 314533452.0717 | 478672728.3755 | 123875205238.1526 | 1987521621.1527 | 2081872895.3964 | 2181858466.4053 | 178721636.4532 | 602393994.2548 | 598052181.6892 | 810543645.1634 | 357033104.1947 | 594351238.7664 | 27233146.6291 | 119129334.8546 | 23851779.2312 | 24283289.7244 | 830340629.9052 | 24376999.8575 | 1158127949.2927 | 5335269849.7321 | 658544693.5616 | 152414366.574 | 1.9925e+12 | 2521222.4046 | 922411.8874 | 1575466.4521 |  |  | 2.1389e+12
707 | 1240403264.4228 | 1051865611.6861 | 214535147.9876 | 164544956.9616 | 1003062779.2859 | 19074457.1516 | 185837061.4121 | 287536000.4491 | 468427536.3405 | 118082294386.9901 | 1963714674.8006 | 1671796900.7719 | 1908784453.5861 | 189438680.3925 | 652270238.4753 | 711245553.6644 | 816691847.9781 | 296154482.3975 | 590961129.6024 | 21731723.2363 | 99800235.7753 | 20076234.1822 | 25125675.0084 | 781068705.1156 | 24575702.2479 | 1025776251.2358 | 6911064152.0338 | 651760305.5762 | 194771309.0542 | 1.864e+12 | 2468370.1309 | 1031809.3792 | 1589377.8528 |  |  | 2.0053e+12
708 | 1091072221.6366 | 1223612384.0149 | 201142266.9111 | 153340988.4108 | 982037822.5913 | 27007101.9969 | 209542832.4267 | 284385033.1444 | 462761882.6299 | 123689113484.0046 | 1688541437.5527 | 1775026503.9693 | 2109937928.4274 | 197218630.3991 | 559602993.8775 | 646651789.662 | 827724434.6858 | 295296223.6459 | 576046532.9862 | 26393911.1413 | 106361388.395 | 23715803.1012 | 25327086.0945 | 921987251.4765 | 24646149.7238 | 953485294.3985 | 6251893135.1626 | 547875638.7523 | 173860222.6172 | 2.0624e+12 | 2319795.6075 | 994836.1317 | 1607703.6253 |  |  | 2.2085e+12
709 | 1209916516.401 | 1075630565.5036 | 208382546.4702 | 177891801.906 | 1024008130.5953 | 21018829.2438 | 207321394.3029 | 307990698.0347 | 458605446.0224 | 128140189324.7182 | 1884351139.1627 | 1914197483.3014 | 2091904297.2441 | 193501597.3583 | 589518268.3802 | 695127580.9983 | 702069342.7047 | 346672515.4076 | 479318172.7093 | 24745714.8751 | 117619862.3259 | 16515641.9187 | 24558875.1764 | 825927303.0363 | 26679956.9421 | 1149603494.9764 | 6680210103.1188 | 671140572.355 | 200391288.3392 | 2.1748e+12 | 2360552.9782 | 961497.603 | 1563747.1758 |  |  | 2.3263e+12
710 | 1155490170.8668 | 1213131343.0686 | 215027586.3135 | 165180274.345 | 1071318002.2034 | 23384461.2868 | 222683504.9907 | 299322523.655 | 499823713.6726 | 159446290076.4326 | 2008440501.3621 | 1972991762.7178 | 2107465062.7176 | 194752709.0365 | 526501123.7622 | 717908818.1542 | 709241585.6259 | 286427357.3692 | 587496597.3514 | 26293033.8986 | 100177963.0014 | 22696920.3723 | 23488105.1273 | 732992414.0218 | 21685873.176 | 1108107391.5274 | 7256574202.2752 | 653820791.1443 | 199205195.6517 | 2.1351e+12 | 2316061.4665 | 931101.1693 | 1551581.0029 |  |  | 2.3187e+12
711 | 1257660868.428 | 1047646554.9962 | 183803057.836 | 175031308.8319 | 1086030332.4981 | 24126816.6272 | 199546028.7845 | 314100010.0346 | 465216567.3047 | 155832798861.2293 | 1722260834.6805 | 1790476730.2274 | 2146115300.151 | 202765243.6868 | 607123683.9701 | 703997299.9678 | 709188042.3636 | 337886741.6397 | 548707490.9461 | 24396195.5255 | 114165370.6643 | 24240664.6381 | 25347720.2923 | 873942255.5483 | 29380571.156 | 1182660650.1215 | 6475773540.946 | 639293606.7062 | 199388687.8355 | 1.4593e+12 | 2421259.1978 | 917001.8186 | 1666671.0397 |  |  | 1.6382e+12
712 | 1129672003.6941 | 1188937251.7483 | 192296039.0824 | 180998084.1921 | 1019876912.2971 | 19432102.6724 | 220047013.4844 | 267578372.0584 | 478501862.4843 | 143190367386.9424 | 2075153491.2087 | 1648746111.8073 | 1936223105.4298 | 196520570.6303 | 538154764.2197 | 713744761.4175 | 893265349.1112 | 322644038.1775 | 513943545.6371 | 22507436.946 | 99927618.8172 | 23062349.3282 | 24082199.9055 | 906729362.2063 | 21812432.5597 | 1044342709.2623 | 6734217354.8348 | 677255248.1875 | 179368219.6062 | 1.9812e+12 | 2721283.6836 | 960996.3528 | 1661146.9661 |  |  | 2.1477e+12
713 | 1117018939.7549 | 1188896582.3244 | 194998040.9159 | 162147622.968 | 1085280942.3784 | 23383776.2804 | 202295498.7376 | 318727610.529 | 489773391.3627 | 133077367908.354 | 2091635184.0659 | 1579708770.5191 | 1924416380.3994 | 183216726.6141 | 599238862.5355 | 602192410.0517 | 841409263.6114 | 330412412.9339 | 534333229.9416 | 27243833.262 | 119380637.0478 | 24776264.4246 | 20704124.6371 | 904178881.9055 | 24808588.895 | 982068548.1688 | 5666613732.8736 | 695950504.7189 | 198025427.442 | 2.5798e+12 | 2255284.4111 | 1000898.8866 | 1535928.5089 |  |  | 2.735e+12
714 | 1128254715.5996 | 1111242030.8714 | 189651785.5322 | 175559462.7994 | 963029532.156 | 25321657.8836 | 193472735.7374 | 312254199.5168 | 477085656.4261 | 122190729956.3295 | 1844610738.7179 | 1496209096.5032 | 2107082197.9983 | 185421214.1085 | 596077195.957 | 606102534.3943 | 716278182.7983 | 255475224.1949 | 596230951.7169 | 27349838.9883 | 97072118.8483 | 22797641.891 | 22507799.2521 | 875926288.1635 | 19888854.3931 | 936334102.4031 | 5007124959.2062 | 479234083.7722 | 164510847.4198 | 1.8555e+12 | 2395295.7615 | 957063.5034 | 1889666.5004 |  |  | 1.9984e+12
715 | 1179628485.3132 | 1115928147.6995 | 203094504.9264 | 158798803.7603 | 930045365.855 | 25444422.8722 | 218884148.1194 | 305713347.9449 | 493854454.7698 | 152062188501.468 | 2007377798.2496 | 1761355311.3514 | 2166980603.159 | 179546064.6673 | 571241931.0208 | 694048216.2521 | 816181104.5141 | 315371560.0739 | 527889699.7807 | 24196302.9153 | 108032271.3134 | 21510211.3245 | 22583721.9774 | 798601141.2356 | 27551125.5671 | 1175980917.5052 | 6026170967.7088 | 583916089.5114 | 184784967.3263 | 1.8456e+12 | 2658496.1589 | 914108.9971 | 1529167.7038 |  |  | 2.0203e+12
716 | 1199051516.1009 | 1132831442.0137 | 187320424.0934 | 175423245.2477 | 1058454418.535 | 23967686.7371 | 188072958.547 | 314227642.5551 | 498124420.4664 | 147274296286.4998 | 2006822826.4363 | 1605445670.2839 | 1932584110.8417 | 195453353.6495 | 668589903.2502 | 709009635.277 | 841353644.3568 | 312301263.5632 | 522305494.3409 | 24261194.6512 | 127408495.7936 | 19504488.4598 | 20779534.6782 | 912492581.8249 | 25730444.2547 | 1169000030.4708 | 7087222992.7929 | 674660160.0759 | 199914028.8118 | 2.0023e+12 | 2742554.262 | 967841.3194 | 1535710.4854 |  |  | 2.1734e+12
717 | 1212180346.4685 | 1109816656.2948 | 211804924.4511 | 176599522.0132 | 935080285.5464 | 25247353.2398 | 222074451.1607 | 263953906.1669 | 471360400.1714 | 156454788800.3669 | 2013857934.583 | 2067283163.2483 | 1890360589.9177 | 196863853.9466 | 532574016.9452 | 594903295.4559 | 830007770.4636 | 328594869.7351 | 566663205.0615 | 25964624.5319 | 117075215.3623 | 20262430.7784 | 23278152.3344 | 884917289.6532 | 30176423.945 | 1008572382.4395 | 6703913428.5292 | 615387734.3553 | 200230260.563 | 1.4595e+12 | 2381520.1324 | 946450.6776 | 1805817.0364 |  |  | 1.6392e+12
718 | 1260145792.7223 | 1181209288.6737 | 220324453.7531 | 169821759.2006 | 1040308344.6618 | 21345125.0622 | 188472417.3248 | 317161454.5813 | 453028755.7176 | 133179275438.282 | 1842952347.4152 | 1773231336.2283 | 2067775780.2924 | 201075280.3514 | 628306126.7716 | 650619531.6042 | 770358131.1297 | 310467435.7944 | 586659545.116 | 21359644.6999 | 137835875.1817 | 22746997.1262 | 24456664.0582 | 745171267.2186 | 29841493.4171 | 955060777.764 | 6276552131.4676 | 530849700.2606 | 200108236.2025 | 2.0033e+12 | 2446085.0843 | 920591.9595 | 1562576.1755 |  |  | 2.1591e+12
719 | 1068067970.3451 | 1212828629.2931 | 199487463.2662 | 174223344.8381 | 1073381025.0734 | 21038445.6503 | 219608193.9039 | 287966688.0422 | 461377207.9778 | 146707078729.5581 | 1776405610.7537 | 2083287068.8417 | 2199652114.514 | 202777488.4509 | 667400464.9929 | 688515710.7183 | 889429165.6228 | 298739417.6063 | 517892454.9158 | 25500165.044 | 113657589.2899 | 20122532.9012 | 21263429.2928 | 920798195.8889 | 26307443.5452 | 1063732493.6607 | 6516114323.5292 | 686065996.2321 | 195502482.1027 | 2.42e+12 | 2597029.6571 | 940710.4806 | 1700565.4196 |  |  | 2.5904e+12
720 | 1093348020.9565 | 1202507271.3157 | 213145586.6062 | 157577589.6874 | 983343691.1839 | 20890686.1085 | 212874681.4964 | 277322275.3066 | 489713966.9089 | 155036147875.2032 | 1743379602.8604 | 2126071408.9502 | 2159424984.7856 | 180968884.6501 | 620161763.5578 | 706969681.6821 | 861052647.8464 | 320759285.5609 | 516124437.6957 | 18216033.0744 | 113405820.2377 | 19019434.0896 | 25843203.256 | 872155513.954 | 25697458.5388 | 1107837148.5088 | 5478866390.6026 | 656776990.3071 | 187741468.1188 | 1.6921e+12 | 2525218.9634 | 920340.1834 | 1740695.6252 |  |  | 1.8695e+12
721 | 1130137164.9328 | 1176592533.3291 | 204504378.6524 | 175709968.6493 | 942348249.8984 | 26697815.0071 | 205676891.736 | 308434171.2548 | 485851600.2409 | 155328520904.831 | 1962696641.4071 | 1719430312.8425 | 2185225487.5192 | 187666386.42 | 625935203.6304 | 721266819.7887 | 726258167.9016 | 301127973.8684 | 609997459.9187 | 24659094.5865 | 123678383.1086 | 25056763.7262 | 25926863.6494 | 807706234.4075 | 26421835.4088 | 1083606006.3308 | 6910108431.4245 | 461584440.3389 | 188832418.5183 | 1.8703e+12 | 2611064.3575 | 960280.2073 | 1563462.2151 |  |  | 2.049e+12
722 | 1210879742.8635 | 1155761521.3115 | 208199057.6793 | 147212498.2441 | 992050375.6681 | 24637050.2581 | 212721593.4453 | 308009502.2645 | 489998421.6776 | 135374414126.6502 | 1980262481.5851 | 1628377738.2579 | 1783507584.7198 | 194473934.1342 | 654085801.6974 | 629413848.8703 | 632922441.9236 | 312445391.0949 | 611423586.9773 | 21917474.6419 | 109608010.5776 | 23919820.9924 | 19840465.4434 | 751057806.6288 | 26359165.7091 | 1158423853.5193 | 7035471142.0911 | 592035165.83 | 195225781.2722 | 2.2058e+12 | 2737041.8902 | 930444.608 | 1563493.1565 |  |  | 2.3643e+12
723 | 1193050118.2455 | 1141133561.778 | 194056501.0575 | 170330936.8008 | 1061145775.4526 | 24187522.8496 | 217873166.906 | 313223386.557 | 434169262.3521 | 145073835619.5156 | 1622033857.6088 | 1997981120.7527 | 1905482898.3407 | 186587434.0171 | 521595933.013 | 718683138.585 | 881926774.344 | 335190419.3849 | 576407153.268 | 21915777.0705 | 96039397.4582 | 20767644.6069 | 23065066.184 | 767035846.1828 | 23696762.0913 | 1162046407.2091 | 5793254716.6447 | 694614300.5536 | 195783600.0926 | 2.308e+12 | 2704402.7184 | 968146.5348 | 1680784.6712 |  |  | 2.4754e+12
724 | 1215981433.0954 | 1227304200.8162 | 221689708.0867 | 166080104.3499 | 1016426727.0843 | 26100418.7343 | 214230180.8391 | 315424841.3351 | 499330553.1334 | 129679573966.237 | 1972115166.3985 | 1710514075.5817 | 2119499032.514 | 183262885.043 | 653027884.2769 | 696418987.8094 | 822018015.9486 | 312242755.5779 | 517108974.062 | 27182994.4196 | 94190097.9626 | 19935359.4469 | 22838981.5195 | 809999400.2165 | 24473830.2647 | 1016414016.4732 | 6063436382.0958 | 649598652.1528 | 186217704.7802 | 2.503e+12 | 2569317.2036 | 922196.984 | 1638172.1141 |  |  | 2.6555e+12
725 | 1117475991.3564 | 1097799344.3708 | 201276447.3102 | 161782700.5332 | 939209301.1935 | 24523805.0301 | 199158880.0821 | 328907661.7724 | 485403225.64 | 132669528935.9909 | 2005645934.348 | 2149199146.7417 | 2103086297.4928 | 173830374.2871 | 630475438.3755 | 693451980.8504 | 752495545.6232 | 281554941.8672 | 575556932.685 | 24710892.9492 | 131866676.8857 | 23887023.555 | 23910948.0456 | 748835775.274 | 24416939.5434 | 974228571.4187 | 6897893999.9403 | 589814607.591 | 190752434.8501 | 2.0012e+12 | 2441581.3648 | 998861.2745 | 1589354.3949 |  |  | 2.1574e+12
726 | 1173994889.0974 | 1184806815.005 | 211552522.7778 | 152612444.9946 | 1043556512.7079 | 24166818.448 | 220448725.9857 | 315592171.9996 | 497942793.801 | 121903980650.5162 | 2064010089.1508 | 1686918435.8023 | 2178029268.3625 | 191595791.7301 | 566930508.2293 | 705910001.9617 | 866437178.9473 | 292779597.4087 | 477187330.2641 | 25115232.1153 | 123682247.4787 | 23045567.1792 | 24759020.1309 | 786206853.4886 | 25397926.091 | 1172293262.8922 | 6237460289.8035 | 659097070.723 | 172046699.5658 | 1.7332e+12 | 2746828.7821 | 977673.0379 | 1737213.6366 |  |  | 1.8782e+12
727 | 1131777870.5711 | 1187848987.2091 | 205472538.9788 | 168576246.7007 | 1022416860.4725 | 21240899.8004 | 223324016.6404 | 302215815.0354 | 498374019.8851 | 135417761609.7055 | 1998438748.3674 | 2182640415.4568 | 2017002527.4709 | 196389485.1868 | 542731024.5046 | 653314803.1377 | 876722551.6948 | 297117128.3798 | 562370328.5441 | 24000384.8478 | 95215234.8373 | 24015287.3986 | 23075079.977 | 719937457.7553 | 27257120.23 | 1110499002.818 | 7238756041.4372 | 633580343.1772 | 145885786.6294 | 2.176e+12 | 2502421.2155 | 951104.8172 | 1676113.0744 |  |  | 2.3355e+12
728 | 1078952459.7126 | 1211575103.3261 | 207457301.7876 | 178192429.2298 | 1078772632.2679 | 27541359.2875 | 185235585.0708 | 302549629.2686 | 432983914.3576 | 147674115346.1778 | 1771724270.8887 | 1559061005.9339 | 2074731677.389 | 190968636.0493 | 529596869.6547 | 621657573.9887 | 822415583.7546 | 288169107.1461 | 535441954.0248 | 21382465.0897 | 95756675.6241 | 22398237.5849 | 22204607.1589 | 871630283.3906 | 24329945.9763 | 1140037147.9134 | 6070338003.4887 | 626823500.478 | 183888267.1434 | 1.8109e+12 | 2512137.8445 | 964870.2039 | 1777214.1409 |  |  | 1.9808e+12
729 | 1068381128.3541 | 1188557112.3226 | 223693705.0771 | 172129229.0278 | 1045973230.1781 | 23139038.0499 | 215780002.0673 | 322012961.9838 | 409908641.9274 | 157124022579.5063 | 2077994468.5038 | 2117365158.2167 | 1863782025.4784 | 184835358.2302 | 587917799.6117 | 700654102.2989 | 760892103.267 | 298108025.191 | 501462573.1005 | 18776348.448 | 105333324.9926 | 20365239.5877 | 24947546.4482 | 819281037.9721 | 29800119.152 | 998900009.0008 | 6151249967.7321 | 711795350.7281 | 188729340.4229 | 2.3735e+12 | 2341332.5602 | 988178.4669 | 1693092.1636 |  |  | 2.5535e+12
730 | 1239367317.8129 | 1179653040.8423 | 224670978.8569 | 167480328.7648 | 1066408178.4234 | 23219445.8377 | 223904050.0268 | 328619145.3109 | 498084408.8219 | 139646163184.1025 | 1983561545.5461 | 1922383652.3168 | 1992063591.8535 | 192600807.9624 | 633617838.1564 | 668634079.0906 | 720103457.5516 | 300112361.02 | 579394094.6388 | 25703152.1035 | 103949917.4462 | 22353019.3315 | 26073682.828 | 875217897.5937 | 28967020.0344 | 1163208114.0609 | 6079768242.2155 | 694993635.317 | 201858935.941 | 2.3268e+12 | 2399524.0653 | 931432.1954 | 1507466.8308 |  |  | 2.4896e+12
731 | 1163159175.5817 | 1172125279.8699 | 208133434.7283 | 143663938.5939 | 1080802288.5929 | 25941866.2707 | 195705027.4278 | 304206867.8832 | 494328416.4109 | 133763128054.934 | 2019413944.0578 | 1942520926.2125 | 1918841256.8929 | 167709002.9863 | 561051232.8215 | 535466829.4595 | 712777123.9915 | 285883984.1648 | 543560654.8753 | 26508209.9729 | 123013296.6735 | 22688840.8289 | 24768716.6317 | 845252094.9539 | 22982339.3944 | 1085751818.566 | 6825283199.1021 | 658945617.2854 | 198993554.481 | 2.099e+12 | 2348260.4854 | 931019.607 | 1697384.5883 |  |  | 2.256e+12
732 | 1181539761.7808 | 1032339806.132 | 187582975.3479 | 174827625.3819 | 896813196.9226 | 23678353.0527 | 176502702.5713 | 312832390.1892 | 448143789.1918 | 154956629853.1443 | 1731711728.2228 | 1807376093.9634 | 1953662079.694 | 143639433.5899 | 604244134.4243 | 724760904.3396 | 650440133.0633 | 342803583.7246 | 550179085.2377 | 28438841.0478 | 133839145.2672 | 19576703.4334 | 24834535.2103 | 936187879.0439 | 27826236.9869 | 1089240779.1419 | 6679748237.8376 | 577662408.5441 | 150672687.1812 | 1.9649e+12 | 2545773.5343 | 916569.9621 | 1683319.5007 |  |  | 2.1425e+12
733 | 1151996314.9677 | 1097361269.8095 | 216060261.3181 | 139434475.0291 | 1049096935.6833 | 24043830.0147 | 224727843.2686 | 286460510.3406 | 474635552.4666 | 142489089339.1008 | 1905123189.0184 | 1923489473.8433 | 2213028764.6764 | 196639717.8759 | 595671144.835 | 631120067.9957 | 790126011.7738 | 262318821.553 | 487902592.6947 | 19552390.6334 | 126681484.4166 | 23952657.0137 | 25086970.8612 | 929509845.0308 | 25151599.2091 | 993572597.9738 | 6374093135.0287 | 646749153.386 | 197452137.836 | 2.2207e+12 | 2465960.2605 | 896583.9302 | 1710497.4017 |  |  | 2.3862e+12
734 | 1134816940.6075 | 1175810186.6879 | 209904289.0927 | 174126696.1262 | 1062391347.8878 | 20748105.47 | 221386997.9564 | 317542086.9466 | 452563518.9647 | 153956835972.8135 | 1854597823.8337 | 1681806634.9728 | 2132497284.0001 | 201082192.0929 | 667889344.3764 | 682809293.3251 | 867578021.2291 | 340281836.4121 | 573138375.3625 | 27898659.2807 | 106544595.2729 | 23342816.5307 | 20750678.8074 | 922304190.1384 | 27073581.4173 | 933296487.4921 | 5125309472.4706 | 597992805.8637 | 176465538.7948 | 2.6156e+12 | 2424583.9188 | 939654.1522 | 1543669.8784 |  |  | 2.7913e+12
735 | 1254019226.0747 | 1150392244.3056 | 191160799.1318 | 178076973.1367 | 1048684485.5827 | 21973439.9422 | 201035854.9441 | 327877030.3421 | 470334286.0508 | 156583814442.837 | 1896568889.188 | 2024698488.6176 | 2052998583.158 | 199223500.388 | 635105753.9039 | 650043099.7883 | 829886490.2445 | 315532851.2785 | 519799543.8695 | 27199072.139 | 125294309.9286 | 23374576.7341 | 22330043.0822 | 835325794.8999 | 26493319.1566 | 983496235.2392 | 5150450416.4465 | 575094341.4416 | 193247736.0014 | 2.4101e+12 | 2355731.628 | 940828.651 | 1513546.7433 |  |  | 2.5886e+12
736 | 1160227228.1767 | 1218566315.9977 | 207572282.3332 | 163381354.3668 | 981462701.0438 | 22849818.6635 | 219868615.8655 | 298751138.5704 | 468914203.8751 | 159429505272.3106 | 1738915869.0015 | 2053044286.0318 | 2127124291.4583 | 183624143.4274 | 574230931.2375 | 639791178.6115 | 782063363.4842 | 361074286.4756 | 539928795.6184 | 25170804.1301 | 130300815.4923 | 22596250.6038 | 25917554.8881 | 764530094.6738 | 27992804.6421 | 1165113196.8084 | 6777207135.5658 | 699879363.9563 | 201184660.328 | 2.01e+12 | 2700467.3693 | 959544.1841 | 1749261.4223 |  |  | 2.193e+12
737 | 1111474047.9972 | 1130415325.7137 | 201777181.7831 | 174134956.2636 | 978126761.6193 | 23512205.5969 | 217216128.3149 | 291544170.769 | 468905915.1622 | 151319389523.6924 | 1821411687.9822 | 2159412105.0591 | 2107044054.1115 | 160172988.7313 | 642533379.2982 | 655235185.1372 | 781237793.5407 | 343842404.6604 | 582140308.0192 | 19920630.6871 | 111407725.481 | 24147205.5838 | 25685512.2251 | 857385192.1956 | 29026042.4111 | 1007794895.7663 | 5855883443.8529 | 687909934.2684 | 147648658.525 | 1.6592e+12 | 2274723.3335 | 1004912.9296 | 1657771.9502 |  |  | 1.8331e+12
738 | 1244475528.5493 | 1150558336.8604 | 218611612.1901 | 159710614.1093 | 1069455026.8664 | 22842465.3453 | 203854997.2249 | 302489628.492 | 491924401.542 | 132159339008.2645 | 1513623449.6866 | 1992950802.2323 | 1903240533.5516 | 194905907.9127 | 647208273.6339 | 651337044.9785 | 881065882.177 | 310085307.3888 | 562620485.1302 | 24709717.8775 | 113016771.2994 | 18660342.8967 | 24740532.3868 | 866252565.197 | 22451906.6005 | 1121355225.5816 | 6734886794.4767 | 699183980.7273 | 198128230.4264 | 2.7912e+12 | 2288553.7858 | 956171.3634 | 1513076.4046 |  |  | 2.9467e+12
739 | 1176615459.3715 | 1009337384.3999 | 195916127.5352 | 173378252.0429 | 1066837770.0336 | 27833783.6086 | 176947941.8746 | 328558861.7626 | 475796421.1345 | 141761616780.4829 | 1776747134.4208 | 1889824409.0038 | 2041518559.8109 | 182372381.8535 | 647308540.9192 | 687735952.3335 | 789950884.4758 | 307416320.2637 | 524197803.0912 | 26284182.1157 | 123713497.1597 | 22820483.4255 | 24202378.5466 | 888712132.7868 | 22752337.0559 | 957072799.6971 | 6428331969.6782 | 515933231.1336 | 196956442.4235 | 2.3295e+12 | 2551004.5939 | 900241.6185 | 1604940.5245 |  |  | 2.4939e+12
740 | 1230131446.537 | 1153968491.8774 | 198333771.0548 | 174257272.6018 | 1074098523.1966 | 24598936.8476 | 186967396.4755 | 322808324.5422 | 469126575.0844 | 154599396874.616 | 1836342334.4527 | 1799276888.8657 | 1983940849.9824 | 193008918.6342 | 575327170.0351 | 719343999.9522 | 717922704.1095 | 346334305.4003 | 501913392.1069 | 22014762.6067 | 97434078.0405 | 24561010.1067 | 25068018.611 | 626669238.5467 | 29436239.9537 | 1184168299.051 | 5845786885.5019 | 702458908.7463 | 197527245.4632 | 2.1747e+12 | 2510920.1352 | 935003.877 | 1617426.6696 |  |  | 2.3516e+12
741 | 1106879350.6873 | 1220380498.979 | 218636920.3824 | 170458559.2111 | 1070619572.2884 | 27473895.0256 | 214525927.5727 | 297202390.6328 | 488172157.5427 | 144422396329.7796 | 2005954523.3034 | 1706572047.9795 | 2091913254.0401 | 185328370.6718 | 621320162.4095 | 631284545.6454 | 873179289.4384 | 276178694.7101 | 614197924.8381 | 26137255.6608 | 118186207.3975 | 21588387.8728 | 24799480.685 | 807064510.9446 | 26540222.7037 | 1161211568.623 | 6860525628.1883 | 695160188.4852 | 198683267.2463 | 2.3714e+12 | 2298961.0317 | 984081.9763 | 1598585.7716 |  |  | 2.5396e+12
742 | 1069276480.8351 | 1159092478.8159 | 207087771.1222 | 174501457.2694 | 1036455672.9686 | 26500230.8192 | 198208627.3074 | 295117917.2915 | 487638413.0353 | 146524718317.7276 | 1572031036.8392 | 2179347375.2768 | 2071320410.0256 | 148360231.5344 | 620176208.5451 | 676815139.8377 | 800040546.1451 | 229381108.4176 | 574350548.5816 | 20808292.9736 | 98084088.1859 | 21433912.0941 | 23831862.233 | 902006230.1989 | 24742716.0413 | 1063761576.0333 | 5926181397.6468 | 707987906.6714 | 141439619.2741 | 2.2091e+12 | 2340396.1866 | 894396.7903 | 1556850.2359 |  |  | 2.3781e+12
743 | 1204058406.6624 | 1209348631.4623 | 217922204.9989 | 179806750.495 | 998557483.3857 | 21270143.8565 | 224723044.1349 | 330100643.3585 | 408124753.9581 | 148617422647.4143 | 2091448264.6348 | 1910586193.904 | 1952335801.0045 | 182448737.9885 | 594370591.8399 | 641220854.5462 | 893646963.1388 | 312481531.9163 | 599545398.6859 | 27060335.5345 | 111650663.8469 | 19103578.123 | 24949501.7388 | 769838366.8631 | 24175923.5351 | 1198864273.5115 | 5706598728.1182 | 678233489.5079 | 197419331.888 | 1.9688e+12 | 2848568.3611 | 902407.4698 | 1617613.3358 |  |  | 2.1401e+12
744 | 1142621218.22 | 1207515224.1901 | 216520201.1371 | 148457936.287 | 992839180.7907 | 27654580.9858 | 220629870.1014 | 293371702.488 | 498774862.0724 | 139379326835.7617 | 1495393846.2222 | 1933371587.4034 | 2056812599.8907 | 191870387.5619 | 617336470.2924 | 635036091.0276 | 803014928.4299 | 279698306.2417 | 557935151.4455 | 26624228.3087 | 94823936.6484 | 18712646.3404 | 18709002.5641 | 765493726.3164 | 25990502.843 | 1127338303.5336 | 5374049945.6879 | 605387350.541 | 141006287.584 | 1.8812e+12 | 2724784.525 | 903237.0665 | 1554418.5213 |  |  | 2.0421e+12
745 | 1159457032.9787 | 1227998314.9277 | 210557241.3345 | 166681548.3367 | 1061910994.8596 | 25069650.8771 | 222804775.5134 | 306047453.8234 | 424933947.4506 | 118996169779.6562 | 1800151903.2307 | 2054920731.8113 | 1947038519.4363 | 184275791.9975 | 544239852.0929 | 722679628.9715 | 740805423.6291 | 315367568.6374 | 426299426.877 | 24959527.348 | 108628920.882 | 24789034.2836 | 24077614.1678 | 770309435.3345 | 30357112.5077 | 1149036204.6293 | 5673242156.7752 | 673002505.9225 | 175695166.6753 | 1.719e+12 | 2539319.5591 | 918733.7791 | 1565863.8487 |  |  | 1.8602e+12
746 | 1205998897.7445 | 1131620455.8764 | 212128306.7679 | 166580468.8917 | 1041281856.5158 | 27147022.2363 | 210028314.4084 | 314379178.6578 | 489553190.5356 | 149416666597.8785 | 1988966004.4846 | 2082146077.3025 | 2141341190.7475 | 198334914.3311 | 524609261.7609 | 682062698.5861 | 720577741.2959 | 296252344.6377 | 594885446.5179 | 23909160.8085 | 91964707.7267 | 21184972.4644 | 25086172.3772 | 780047970.0107 | 27476128.6455 | 1056987483.7759 | 6268555836.3044 | 690119982.8962 | 194584432.9194 | 2.203e+12 | 2643665.0678 | 978412.8825 | 1572380.1663 |  |  | 2.3756e+12
747 | 962199639.2171 | 1217472182.9492 | 210706787.477 | 180690207.4362 | 1013764088.6005 | 22422426.1993 | 192741544.238 | 285051104.905 | 497806329.6578 | 129994757927.8185 | 1930695879.3503 | 1890442881.0141 | 2111251794.5715 | 173128828.8158 | 668442299.8382 | 695171559.5194 | 789723586.203 | 321955375.1053 | 497447088.4697 | 24570174.1919 | 109867027.7044 | 23794532.5462 | 23328300.9328 | 706466932.0106 | 31344749.7784 | 1123906188.956 | 6259185916.3917 | 606001477.499 | 196930953.6988 | 2.7648e+12 | 2374837.4487 | 950695.9062 | 1742299.8288 |  |  | 2.9176e+12
748 | 1195271344.5164 | 1212764517.2536 | 179406889.414 | 173559530.9441 | 990531405.5726 | 27238474.615 | 188104233.7198 | 302801856.2444 | 431058637.4144 | 129898655432.1204 | 1979357701.2421 | 1938526055.91 | 1683857704.971 | 188145981.3861 | 602254839.7689 | 585783366.1211 | 792923680.1644 | 320203467.49 | 584377768.5075 | 23358877.4257 | 123823347.1242 | 24265621.9911 | 25099023.5621 | 894545812.3173 | 23515993.0213 | 1169779907.4054 | 7094002451.2239 | 524605075.3426 | 201449098.6473 | 2.2004e+12 | 2687634.136 | 974713.5303 | 1677182.3961 |  |  | 2.3538e+12
749 | 1170834344.2563 | 1156263903.8405 | 199179955.0752 | 136758080.3861 | 1028700823.7852 | 18883322.8831 | 215646460.3833 | 318202880.5059 | 471852919.2643 | 150971243221.3892 | 1841809633.5301 | 1946144483.5993 | 2075707461.1297 | 198341704.1319 | 613409458.9651 | 668635321.3496 | 928097162.1288 | 312298948.4826 | 614424086.6248 | 19676574.8402 | 117994307.3191 | 23761025.5279 | 21374641.5817 | 859782704.7737 | 22855835.1622 | 1193329517.6287 | 7183567123.9897 | 708791594.5925 | 172090614.6095 | 2.025e+12 | 2604438.8811 | 978769.688 | 1530248.0007 |  |  | 2.2002e+12
750 | 1148318896.9617 | 1225553457.144 | 196023527.1856 | 155115601.3289 | 1077821514.073 | 23286738.5952 | 209200609.6714 | 306971734.2946 | 462661355.9025 | 133546802037.7253 | 2009719479.9423 | 1932236001.7837 | 1840322049.5262 | 195551487.0972 | 513564857.8821 | 652040687.6482 | 890945841.9375 | 299195403.8764 | 614083335.5082 | 23541372.0869 | 130348651.2158 | 21943245.5239 | 25812837.5133 | 843456214.7058 | 26669528.6892 | 1113880358.0742 | 6614507427.026 | 560847054.4315 | 175468039.0017 | 2.5178e+12 | 2587439.5435 | 917261.8763 | 1754685.5712 |  |  | 2.6746e+12
751 | 1101722280.9583 | 1120100964.461 | 213807753.4738 | 165139622.1022 | 1083111411.0195 | 23604852.2955 | 210986577.0995 | 314661669.0621 | 435519788.9477 | 143616803757.7072 | 2095612351.6914 | 1885858041.1385 | 2023633952.1129 | 195826689.1005 | 596434830.7075 | 630776224.0665 | 845316881.5439 | 301699227.0197 | 451776684.4095 | 23956073.1873 | 127736620.7531 | 15218238.9944 | 18115246.0228 | 812834820.2514 | 28077646.7644 | 1083105951.2185 | 6208724249.7819 | 690470602.2213 | 197855918.1168 | 1.2978e+12 | 2468801.0196 | 942178.5506 | 1681601.3873 |  |  | 1.4643e+12
752 | 1187447729.4716 | 1207647181.4105 | 205093028.1904 | 163432085.8148 | 998579728.0088 | 22988104.5799 | 197089961.9309 | 245201155.0016 | 493788593.434 | 147185969373.04 | 1881975179.2283 | 2005946038.9419 | 1695083563.9531 | 184304155.0691 | 504480060.984 | 686476227.5176 | 657745173.2568 | 351014394.5757 | 507190082.9841 | 26799435.545 | 108205136.204 | 23213526.3909 | 25215947.8933 | 741173742.39 | 26226152.5979 | 1118196571.4656 | 5978530518.9926 | 614831321.1948 | 183822348.5341 | 2.0848e+12 | 2639272.3488 | 964015.1995 | 1617002.8489 |  |  | 2.254e+12
753 | 1210543854.2773 | 1207443344.1519 | 212881124.1877 | 173685043.5744 | 1010769178.9932 | 26985069.7231 | 198845563.4902 | 319478428.11 | 434550812.0157 | 147149925917.7799 | 1867261102.7511 | 1932775765.9067 | 2114646968.1212 | 196784122.7298 | 495723443.8352 | 635891463.5246 | 867395978.179 | 355402316.3961 | 562167050.1756 | 26006761.6247 | 118556956.662 | 22487279.0847 | 24628238.6874 | 944384715.8818 | 27183362.9152 | 930626818.4725 | 5443900830.2225 | 679024642.85 | 159822380.353 | 1.7049e+12 | 2488049.0557 | 939554.901 | 1744305.9726 |  |  | 1.8742e+12
754 | 1159231520.4712 | 1202883215.0997 | 191713485.3004 | 152424064.0173 | 1070822890.0885 | 23368520.8721 | 209284793.7316 | 323332102.8969 | 446346230.9389 | 129219069873.2549 | 1700921442.9441 | 1871637860.359 | 1816376310.2538 | 192414698.5465 | 574189685.8138 | 644517007.3325 | 805721198.2747 | 304562115.4677 | 615683138.6735 | 28569534.0258 | 115312090.1774 | 23515074.88 | 24927993.7203 | 870472546.8418 | 24828111.0086 | 1078479789.9004 | 6340259114.7139 | 689065378.8636 | 178256492.5574 | 1.4342e+12 | 2514282.9885 | 1008083.0903 | 1659273.4313 |  |  | 1.5861e+12
755 | 1198757480.3864 | 1198992436.3128 | 212064000.4675 | 173424181.6155 | 1060583331.4512 | 23449908.0458 | 217082685.8847 | 302242884.4952 | 493220053.2004 | 128528493689.013 | 1874358546.9234 | 1905622704.5015 | 2068507203.7599 | 142709770.3059 | 618405776.2885 | 673391966.2335 | 853534914.865 | 319293987.6626 | 477408563.09 | 27711605.8262 | 115704035.6497 | 21267967.035 | 18395933.535 | 691714938.9298 | 27503874.9514 | 1079183639.8731 | 6853722495.2737 | 623816804.4784 | 191348896.7878 | 2.1229e+12 | 2391389.857 | 991236.9818 | 1724166.7654 |  |  | 2.2749e+12
756 | 1184952092.2983 | 1189270568.1724 | 212265908.5366 | 171433420.5633 | 1013351785.5819 | 22906607.6447 | 211035248.69 | 303648707.2449 | 491476172.2895 | 137928845651.5033 | 1884219744.3531 | 1723864896.4123 | 1923983053.6257 | 201316703.1248 | 638983898.139 | 703360584.6489 | 850354373.6034 | 308414795.5753 | 551384124.1322 | 23749150.2822 | 118613976.1814 | 21714568.0194 | 24492932.2433 | 925159544.364 | 30920038.4978 | 1192734578.2633 | 6198539867.6214 | 696029036.7668 | 190641219.4471 | 1.8564e+12 | 2451286.9175 | 997936.3904 | 1523067.7492 |  |  | 2.0173e+12
757 | 1102479573.0194 | 1212203277.2552 | 212178364.7214 | 179414438.8569 | 1080193224.388 | 26901808.1534 | 210181725.8342 | 274737612.3474 | 488976764.0091 | 127208026792.8519 | 2063833164.5837 | 2152694706.244 | 1910766082.4633 | 202705585.4682 | 645641733.3149 | 657347585.0075 | 711556122.5234 | 315132064.6586 | 588144891.4681 | 27008324.6193 | 95172104.2609 | 20043442.7484 | 25496411.1195 | 858524371.2508 | 29518651.3522 | 890172479.3847 | 6927578023.3914 | 687090032.0731 | 183378610.1165 | 2.5538e+12 | 2725764.9443 | 894954.6404 | 1772873.2218 |  |  | 2.7048e+12
758 | 1158719466.8457 | 1162865750.4824 | 217607653.3371 | 172653366.8311 | 1046766469.6825 | 25640629.447 | 216167939.8481 | 325329530.5783 | 426869513.062 | 156456403241.8759 | 1776567986.1076 | 2012099759.8946 | 2176643853.8567 | 202046365.9105 | 476699391.3522 | 636726969.2737 | 850053236.3126 | 311148819.9532 | 543397826.6755 | 27139066.5799 | 123057928.9846 | 23388826.507 | 25233676.0194 | 841278011.7411 | 29780648.2242 | 1123956259.1638 | 6051441792.6388 | 500018629.536 | 191686520.2944 | 1.8811e+12 | 2564668.7891 | 893679.6744 | 1708750.5308 |  |  | 2.0602e+12
759 | 1109472375.3237 | 1221729206.8789 | 205188546.17 | 154256557.9753 | 957193434.7726 | 26042715.7842 | 193763561.8052 | 292108069.334 | 484514931.4447 | 119484530513.0202 | 1594351940.1467 | 1695808798.7488 | 1954735421.6774 | 195527072.7345 | 512011544.5743 | 716581085.7239 | 855312806.1935 | 324906563.7468 | 584306219.1887 | 23678225.9352 | 108610159.0004 | 22967939.1232 | 24976551.8548 | 897519815.6577 | 24128963.7207 | 1133439202.6864 | 5712250701.2305 | 564722275.6107 | 192506195.3656 | 2.3343e+12 | 2601662.3033 | 939948.8933 | 1699193.8356 |  |  | 2.4755e+12
760 | 1253388453.3496 | 1104206645.3618 | 212810884.8766 | 171801837.0398 | 1085974085.8075 | 20975174.5459 | 208737188.8724 | 303191677.4207 | 487213278.971 | 121636000738.1164 | 1753752210.0808 | 2055646778.752 | 2148167028.6212 | 183811684.2992 | 559022921.6874 | 572587750.4703 | 883470486.4828 | 320769195.7938 | 592190583.4713 | 23493680.1411 | 124167466.2624 | 23215612.6697 | 24995184.6888 | 761284373.5103 | 24629631.155 | 1198269424.4687 | 6036667828.7515 | 656721705.283 | 175025582.2452 | 2.8285e+12 | 2298708.47 | 977072.1571 | 1713574.8679 |  |  | 2.9731e+12
761 | 1226846461.227 | 1115846550.7727 | 189574450.9915 | 169483132.3934 | 913188431.8808 | 25115987.855 | 223884143.9766 | 287342763.6462 | 466417571.4955 | 133266798862.0931 | 1856659018.3509 | 1435105813.9805 | 1971199690.2794 | 181790644.0132 | 651023190.1956 | 582475969.4148 | 711504057.9445 | 290392265.2532 | 593225183.1132 | 26858324.08 | 106990200.408 | 21496526.1215 | 25533886.6966 | 793459183.3596 | 26504314.8869 | 1034545399.8377 | 5561034667.6252 | 469210225.6364 | 195730690.3369 | 2.3179e+12 | 2317598.439 | 955593.7431 | 1652649.6381 |  |  | 2.4723e+12
762 | 1197399416.0769 | 1224052926.7239 | 195039239.1198 | 159941425.9278 | 1001606966.1036 | 24700981.1101 | 203723139.7323 | 315924853.2571 | 493736809.4779 | 137096759590.8911 | 1895027183.3754 | 1887439363.9818 | 1914620027.9903 | 186556033.3553 | 561031340.8894 | 693453332.7666 | 839133059.9294 | 335851539.606 | 570800185.1057 | 27738561.6086 | 122570493.066 | 23912519.0844 | 23766876.3823 | 847151945.5747 | 26782762.0193 | 1095665738.2744 | 5944659792.5573 | 636695349.096 | 185220973.3449 | 2.0515e+12 | 2452310.0508 | 988061.4833 | 1794098.3922 |  |  | 2.2112e+12
763 | 1238512569.4977 | 1223382648.9298 | 217481481.6768 | 168091618.2869 | 1011129607.3769 | 21234600.3325 | 210691345.8611 | 286141482.298 | 464982206.8997 | 135133892651.2428 | 2005675967.7853 | 1984104207.1524 | 1774203686.6137 | 196122493.9308 | 597851567.3038 | 666877545.0743 | 851822566.6845 | 350483583.9284 | 588798165.8139 | 28354307.9192 | 92809130.8643 | 18811575.9737 | 24798789.0098 | 783146440.5923 | 21721464.0836 | 1123912209.3648 | 6663054252.1233 | 662716281.8199 | 188767065.3322 | 2.519e+12 | 2578984.5259 | 935484.3496 | 1680121.1037 |  |  | 2.6776e+12
764 | 1214970628.4499 | 1182371869.114 | 203892006.8066 | 172639286.7499 | 1084262699.8768 | 21083443.0498 | 190603734.9273 | 330260120.025 | 484583969.9883 | 149286584104.2756 | 1765945483.3461 | 1839036815.8123 | 1815371546.4549 | 200168256.8476 | 532969132.4199 | 623949374.5367 | 740313718.8276 | 338991406.9106 | 565588700.1286 | 21899903.5236 | 108833186.1875 | 22246173.1833 | 24067655.4561 | 735069963.6142 | 29358609.6765 | 987662042.5142 | 5973339705.046 | 610014849.6057 | 188807587.1171 | 2.0484e+12 | 2487532.5371 | 953151.142 | 1804154.0227 |  |  | 2.2197e+12
765 | 1166213759.61 | 1034394540.3877 | 215026468.9034 | 173065338.1104 | 948142543.3568 | 25698412.3958 | 224704419.0753 | 317798242.2848 | 480662057.3427 | 140715361902.4814 | 1800154170.4428 | 2026597454.9243 | 2160236254.1923 | 183942785.4342 | 657193410.0913 | 683375145.6901 | 736149400.0865 | 323196523.1075 | 583180726.3086 | 25125492.3104 | 98836759.15 | 20253497.8616 | 19742082.3928 | 775077083.8941 | 28351488.8734 | 985192957.7996 | 6274686894.9653 | 659004807.8927 | 156038257.8062 | 1.9639e+12 | 2575329.9274 | 954607.0761 | 1636721.3524 |  |  | 2.1274e+12
766 | 1073285358.9843 | 1227674240.0063 | 186620324.8982 | 180387999.14 | 1031472665.7887 | 21952384.5325 | 206380426.2481 | 316791954.8181 | 486425842.4613 | 151747815922.4434 | 1824812889.5148 | 1816581489.0447 | 2186337861.8271 | 195900212.3872 | 645825071.0449 | 700477612.0827 | 876190439.7565 | 351565373.7241 | 573360213.6584 | 26948324.4891 | 92673478.5439 | 24323082.4406 | 25803340.7706 | 795057917.1812 | 22394477.4008 | 1089347538.298 | 6613376266.8606 | 634756363.6033 | 184482075.855 | 1.7882e+12 | 2255581.7974 | 893976.9356 | 1688570.6523 |  |  | 1.9634e+12
767 | 1238327780.077 | 1191471267.8884 | 208784651.5534 | 158836360.5855 | 987958699.25 | 24855542.1388 | 201333570.4159 | 327327554.1575 | 485007925.0832 | 146343251683.3698 | 2012455002.6499 | 1999408428.9002 | 1939951729.2767 | 190860741.6493 | 657550612.2449 | 645380766.6798 | 765860917.6381 | 297898741.4902 | 418463481.9355 | 27696326.1788 | 129634405.4057 | 22073850.0143 | 25434264.9402 | 835764633.1388 | 29332564.2114 | 1115270571.3132 | 7067913602.483 | 657555825.7113 | 143698614.8635 | 1.9843e+12 | 2563386.3516 | 894845.8765 | 1633730.639 |  |  | 2.1545e+12
768 | 1025597307.5945 | 1204938265.1008 | 200532972.4973 | 157912055.402 | 1026496364.956 | 19775560.3603 | 214114579.9968 | 290657964.4296 | 413974546.5112 | 137588489266.7455 | 1779080116.8222 | 1822916192.0591 | 1999538217.5283 | 171692472.5695 | 663960126.5932 | 614555967.2682 | 706245752.9323 | 313367297.1271 | 572670906.7211 | 25224140.3873 | 113475796.4214 | 21452904.0125 | 25541633.4445 | 746984176.6593 | 26324421.9715 | 1075289512.512 | 6747523071.8887 | 635659151.2468 | 171560713.9762 | 2.2787e+12 | 2613360.6108 | 966901.2087 | 1684316.129 |  |  | 2.4391e+12
769 | 1175302975.1679 | 1222795386.9396 | 193850324.9875 | 175385099.513 | 1080376304.154 | 23741370.1226 | 204121418.0621 | 293561594.3802 | 479866190.5369 | 132433393346.7251 | 1937259780.643 | 1851729999.1659 | 2089002998.1002 | 202758559.8885 | 574773511.9369 | 671956835.0263 | 809101893.091 | 303706406.3396 | 561170624.6694 | 25350146.9826 | 118159946.4775 | 22281755.6349 | 20987726.6296 | 841025047.1213 | 27082769.201 | 953209807.9031 | 5960957656.1046 | 610489826.5629 | 191806609.6308 | 1.993e+12 | 2545765.5191 | 958769.0087 | 1616689.4284 |  |  | 2.1481e+12
770 | 1123539132.9087 | 1220417004.3861 | 219480930.5013 | 156811334.5492 | 1077723734.804 | 25129121.0696 | 211655150.5846 | 325222452.3538 | 430328797.6014 | 157938157534.2552 | 1566866561.7418 | 1981149694.8267 | 2024329062.0915 | 159615731.3824 | 566064172.7539 | 670771998.4157 | 738860888.6699 | 336884681.5181 | 568161698.8441 | 19837241.3465 | 127269376.2063 | 21795344.3553 | 20365908.1946 | 833587586.9728 | 24680334.6675 | 1021106450.7635 | 6752484980.6317 | 671932777.6321 | 179128400.2956 | 1.9192e+12 | 2269555.7892 | 964298.0638 | 1792535.8697 |  |  | 2.1002e+12
771 | 1208199310.7751 | 1176780829.1442 | 187356106.1139 | 180474590.0805 | 1062436643.588 | 25401355.9072 | 209744920.0471 | 316425895.5527 | 472979197.3471 | 131480388890.3017 | 2046718055.8389 | 1699349885.8593 | 2051612587.1167 | 161717543.1734 | 509904434.0535 | 692637697.4642 | 811267000.3409 | 328399459.5993 | 573576325.359 | 23800495.2464 | 122859690.7407 | 23812711.0498 | 25105413.8188 | 864716960.1259 | 25870273.7076 | 1091176622.8282 | 6402971918.2361 | 690630659.7033 | 196995977.6285 | 1.6955e+12 | 2461047.7458 | 974843.4118 | 1661993.1534 |  |  | 1.8502e+12
772 | 1140642685.1831 | 1182587659.2628 | 207457509.4371 | 166468797.9061 | 1054218021.3686 | 23359929.9178 | 219102357.1564 | 310944408.1815 | 477812697.4065 | 141863429635.7449 | 1705886559.2281 | 1776689857.4814 | 1896266263.9154 | 156818025.4399 | 603302118.7061 | 698873097.7548 | 854022232.4138 | 326431760.4343 | 586398799.9239 | 23954532.0265 | 129983439.609 | 17951808.8004 | 23567590.6237 | 678548671.5147 | 30215413.1136 | 1156151384.3442 | 6712253300.4302 | 508325304.4312 | 200983803.6285 | 2.0985e+12 | 2442988.7942 | 1052074.8586 | 1617572.3694 |  |  | 2.2632e+12
773 | 1166844192.72 | 1142887881.7058 | 170827569.0371 | 150338542.8763 | 1086645470.2642 | 28035460.8105 | 193037348.7801 | 297804707.6113 | 491073794.8114 | 125532587650.3734 | 2061589293.1604 | 1841456828.294 | 2005947779.6805 | 173131175.8792 | 632440156.6833 | 687480698.2341 | 813250013.2572 | 264950829.4559 | 554430692.666 | 20845077.0112 | 98847446.3881 | 21900991.728 | 24525022.8195 | 752151226.9462 | 29764361.9995 | 1030318742.4274 | 6322890634.1275 | 696469293.3538 | 198439753.516 | 1.8179e+12 | 2457961.5404 | 1006865.1638 | 1739157.8906 |  |  | 1.9664e+12
774 | 1019871324.625 | 1227654758.0714 | 221704409.3749 | 146295785.9798 | 981150283.5759 | 23564047.7023 | 204609520.1173 | 309463140.7961 | 424694870.5123 | 141620812645.2765 | 2006832793.5411 | 1972987387.541 | 2134737130.5216 | 172293604.2998 | 640166438.8149 | 709875820.3333 | 880358687.8746 | 328229288.0781 | 599128198.2841 | 26280034.2984 | 102957489.8351 | 25000107.1689 | 25801441.1554 | 883416897.2647 | 28842989.4633 | 949275986.3645 | 6428504553.128 | 657453507.5858 | 193234761.9223 | 2.2224e+12 | 2488084.5272 | 960502.5508 | 1859581.2877 |  |  | 2.3874e+12
775 | 1180253100.8698 | 1224254762.6566 | 196838343.0087 | 180614898.5674 | 1040163822.9116 | 20019129.5734 | 203555392.7176 | 289682815.4507 | 497346659.2396 | 146654496527.6869 | 1919988541.1658 | 1997457917.8196 | 2063166795.6525 | 179429297.2871 | 602881447.8684 | 711316131.5792 | 824640276.5591 | 309346001.8959 | 607863654.6713 | 25622955.9065 | 119416100.8332 | 22811192.9025 | 24196085.6328 | 653790022.8315 | 26876209.4146 | 962284603.6461 | 5350812063.8244 | 670928266.1912 | 186153704.1931 | 2.65e+12 | 2653321.8967 | 952046.3456 | 1757434.8566 |  |  | 2.8188e+12
776 | 1230892149.8125 | 1152182092.475 | 199927864.3172 | 173562712.9017 | 1007925747.824 | 24626476.3066 | 212526839.3825 | 283916482.067 | 419634493.0309 | 154382353579.0527 | 1662098095.2367 | 1807942593.9123 | 1872441314.7883 | 173409100.0452 | 667323236.6896 | 720514676.7041 | 890831452.193 | 275441852.9994 | 560516042.6717 | 25602942.0534 | 130518490.8279 | 20396529.5883 | 23252212.524 | 867635289.2424 | 29255484.4211 | 1145001632.1283 | 5425969871.6183 | 672994268.1909 | 177705331.4788 | 1.871e+12 | 2399872.082 | 989824.2451 | 1518182.7619 |  |  | 2.0472e+12
777 | 1127077869.2567 | 1168171926.7441 | 213901532.6415 | 165982211.7452 | 1049449657.2994 | 22539448.3401 | 198999799.2748 | 323816590.1153 | 475713823.3856 | 131569307897.299 | 2008722056.278 | 1726830594.5112 | 2013505681.7093 | 190810137.2087 | 624802070.1791 | 616181831.0024 | 773855536.021 | 299888859.5934 | 611639628.6894 | 24757825.169 | 122915677.3913 | 21259506.2312 | 20865057.7549 | 909375986.2681 | 23940615.5684 | 1157773703.9173 | 6134158240.8294 | 655233190.5285 | 180889355.651 | 1.8554e+12 | 2746195.3697 | 951240.6357 | 1687805.2386 |  |  | 2.0098e+12
778 | 1130082658.6788 | 1129835489.6114 | 209242484.8829 | 144203576.4473 | 1068363655.6503 | 24804088.6582 | 215644000.8255 | 327956161.4121 | 484164373.6036 | 134989843177.0223 | 2044457210.3689 | 1998051063.3073 | 2138884523.4205 | 196163734.8279 | 629120436.0681 | 635242610.243 | 831685055.0895 | 323336519.485 | 535173578.969 | 22348743.5095 | 108571054.1041 | 23264391.2467 | 22583670.6688 | 839734247.1652 | 28158043.6669 | 1181982055.1388 | 5565060470.0965 | 689309114.6346 | 180424523.699 | 2.0712e+12 | 2309231.3565 | 925269.7128 | 1585351.4065 |  |  | 2.2289e+12
779 | 1256579516.6346 | 1118467574.1876 | 219962278.4333 | 162967546.7804 | 1064594056.2959 | 21761074.9147 | 202029402.9299 | 280212739.2177 | 457490671.5515 | 153341057561.344 | 1591933492.9463 | 1778806562.5755 | 1877836268.3169 | 185127510.9185 | 664175593.2928 | 560126434.253 | 909251109.4859 | 309491819.4235 | 500904998.5258 | 22235264.5281 | 134537650.9902 | 23923452.5988 | 22843570.3292 | 848029172.4074 | 31263652.4618 | 1006257508.1322 | 5036699129.2499 | 547453719.1667 | 181448436.8267 | 2.167e+12 | 2615619.2726 | 948078.44 | 1628774.967 |  |  | 2.3414e+12
780 | 1083093600.6475 | 1136277696.3791 | 226496634.1234 | 173511525.7244 | 1029621671.282 | 24616961.4117 | 219621958.0781 | 305650800.1682 | 496970229.5112 | 131079057454.3445 | 1618521853.9304 | 1934952827.6729 | 1968638294.0822 | 194956844.741 | 652415318.592 | 618501515.3029 | 854728957.7014 | 308148938.9133 | 551010874.7279 | 23251081.1397 | 115815270.4197 | 21557313.7939 | 21485224.3079 | 816901203.0766 | 30728497.4164 | 966381621.2323 | 5520318980.7932 | 675886080.1368 | 175786684.9447 | 2.0029e+12 | 2400482.2311 | 937045.7878 | 1552813.7335 |  |  | 2.1558e+12
781 | 1125219849.2655 | 1208881942.6033 | 192679054.5812 | 167202031.6547 | 986400644.2174 | 22919680.621 | 222529604.6488 | 320100844.2489 | 461448019.7803 | 145680669466.8314 | 1938734270.3818 | 2079325491.2844 | 2141294583.8718 | 186748455.9064 | 661606842.0083 | 723130357.8709 | 821141671.1025 | 308760593.1247 | 582763332.9383 | 26385070.8094 | 94758254.7766 | 22705330.7865 | 25311268.4888 | 850396171.379 | 24064543.3618 | 1083352934.7945 | 5789378664.5525 | 688454250.5468 | 192021458.0391 | 2.1493e+12 | 2662858.2573 | 979977.3285 | 1664017.4951 |  |  | 2.3179e+12
782 | 1158606846.8852 | 1204396436.167 | 186478445.332 | 142736551.0939 | 1059443492.6604 | 26604267.1163 | 224556816.0803 | 278691791.5283 | 491365496.4077 | 150580089081.5381 | 1891276063.1719 | 1877121692.6438 | 2198850996.1551 | 195606164.4845 | 650590775.1086 | 644064791.5505 | 765813208.3646 | 268035873.8527 | 526617379.5044 | 24424298.9033 | 127104861.2977 | 21140460.8135 | 23735307.2302 | 687190073.5716 | 25317714.0517 | 967973567.5871 | 5731421165.3239 | 552244462.6192 | 181564144.3076 | 1.9628e+12 | 2449370.5159 | 949360.5588 | 1611705.4182 |  |  | 2.1355e+12
783 | 1140702840.5571 | 1063252066.0056 | 222748096.0477 | 171901763.0062 | 1034424405.1283 | 27565035.9586 | 198309228.833 | 288064814.5369 | 494732159.1354 | 140903016924.3873 | 1790623674.2882 | 1740974844.5584 | 1808702607.6186 | 196617715.5244 | 624359573.6743 | 719070921.8332 | 671569575.5714 | 339311855.0779 | 586830931.6416 | 22461369.923 | 121087369.3709 | 23221490.0998 | 18872347.0352 | 842260235.1589 | 25064854.8628 | 932852221.4868 | 5665990081.3972 | 679981879.4477 | 194236573.6527 | 2.2363e+12 | 2407166.7457 | 957774.0078 | 1686652.132 |  |  | 2.3989e+12
784 | 1210150272.6002 | 1189752912.2979 | 189760104.7383 | 177168111.4002 | 1086498644.0057 | 26228117.2608 | 207605957.0996 | 326702991.0886 | 466663794.4742 | 140323764749.9352 | 2029671967.8843 | 1533884499.9236 | 2128366177.8251 | 177043693.6821 | 629371785.4856 | 655561756.4712 | 867598527.717 | 331589705.0504 | 582146036.4162 | 22632055.4755 | 100597625.036 | 16964056.9303 | 22407255.9832 | 804903863.2083 | 27382623.2946 | 1050165698.5594 | 6855302983.9152 | 654499535.3283 | 195398030.1888 | 1.9427e+12 | 2316074.9149 | 969532.5027 | 1638617.6844 |  |  | 2.1066e+12
785 | 1220354704.1772 | 1219535251.9322 | 192214985.6382 | 167568449.2234 | 1015325436.9561 | 24485350.6654 | 211619132.2338 | 320701362.2646 | 432914702.4422 | 132760773777.6046 | 1988818432.0053 | 2060160339.0777 | 2104702469.0682 | 173833223.9293 | 430134421.5893 | 723790386.8593 | 836549565.1872 | 304026815.6292 | 493975617.6014 | 24710586.2703 | 103871960.1604 | 20865213.0889 | 24735840.4259 | 709577228.9022 | 22831435.1747 | 1102980036.637 | 6775268049.1885 | 678921658.7269 | 186659470.4887 | 2.4624e+12 | 2729018.8969 | 912756.0483 | 1607626.4649 |  |  | 2.6187e+12
786 | 1183265438.8952 | 1207502543.1744 | 185838156.6398 | 167193849.4326 | 991038752.845 | 23489625.7573 | 203067145.8021 | 309889963.2271 | 468408580.642 | 138592645343.6148 | 1857035305.402 | 1686925962.7946 | 1790644356.7475 | 183857059.6652 | 594498335.4131 | 566297932.7619 | 814790941.2852 | 341627795.3047 | 606437641.1138 | 26629357.4178 | 113312649.0828 | 23537811.5123 | 23842666.7527 | 743539530.4437 | 28444087.4913 | 1123249327.7833 | 6072375555.9548 | 493164519.2289 | 169474112.9439 | 1.7708e+12 | 2403552.0084 | 952126.1088 | 1697135.0213 |  |  | 1.9314e+12
787 | 1209069586.6492 | 1130998434.829 | 208279260.5982 | 169564743.0447 | 1021010897.2741 | 22888197.3942 | 176857559.5566 | 324450909.1015 | 438878190.3672 | 155644879768.4655 | 1918501513.0593 | 1891703209.5311 | 2145321304.4597 | 188264925.0812 | 623470066.0289 | 695046090.4503 | 798243528.9069 | 290161334.2857 | 607270168.7356 | 27557052.2349 | 110760755.9581 | 24768590.9842 | 22518671.6513 | 931501794.8288 | 30950055.9874 | 1179055209.1417 | 5284801270.7704 | 627566657.3037 | 193776036.0868 | 2.4587e+12 | 2271998.4552 | 975628.7489 | 1629877.2002 |  |  | 2.6367e+12
788 | 1211747118.2718 | 1219658339.9727 | 188824194.5917 | 173083016.3266 | 1044138802.0361 | 25942911.5931 | 208658022.8331 | 308310747.5969 | 486110319.1979 | 126254629259.3306 | 2076548951.9203 | 1922404230.4293 | 1999318887.6886 | 173105492.7788 | 481836265.6965 | 659224997.2493 | 847242920.1938 | 258616047.5694 | 608772590.1641 | 28213988.8903 | 125416155.8505 | 22391584.3575 | 23960642.1386 | 953281745.5927 | 23352534.671 | 981637170.4743 | 6827163864.4236 | 604370826.3183 | 151106263.6431 | 1.6759e+12 | 2480157.754 | 934309.6999 | 1700171.8595 |  |  | 1.8258e+12
789 | 1183344728.2579 | 1184347339.6835 | 218949500.8879 | 149401782.9486 | 1084131025.2591 | 21964650.3422 | 191923792.8699 | 315833516.7318 | 424330781.8344 | 147532956749.9236 | 2002838620.2531 | 1937614924.2468 | 2213197125.0383 | 196633112.0531 | 649568458.5795 | 707508292.0172 | 898994534.4201 | 311105365.4221 | 596068841.2016 | 22579410.3354 | 121152666.5919 | 20146567.4257 | 25439308.6186 | 717377092.0042 | 25066547.5258 | 1076910384.3978 | 6178459829.4925 | 656397130.1206 | 190768078.9604 | 2.3121e+12 | 2457278.5654 | 906903.8724 | 1627961.5443 |  |  | 2.4829e+12
790 | 1187454582.766 | 1216898042.4127 | 218746996.3482 | 166739579.8745 | 1087046452.8514 | 26558931.783 | 196017139.0462 | 325546949.9444 | 490351722.9141 | 128762489182.1458 | 1765185432.2662 | 2156002892.5218 | 2202741929.4907 | 168452126.0967 | 621384112.5934 | 692536587.5769 | 783802762.1175 | 329447099.5205 | 599495123.0332 | 25024656.9783 | 110418522.777 | 22310068.4537 | 23646366.07 | 930728816.1446 | 26916687.3286 | 884402382.4428 | 6097498714.535 | 558581960.9303 | 190381172.0375 | 1.6727e+12 | 2722318.7495 | 1002447.8699 | 1475259.6307 |  |  | 1.8246e+12
791 | 1102031164.3073 | 1173105568.7825 | 225827191.5725 | 174364239.1219 | 1064962977.9077 | 23313351.1189 | 220056374.5922 | 323396405.425 | 475721971.6216 | 128659578953.0339 | 1826016942.6388 | 1689679914.9282 | 2163468137.5558 | 196249752.3133 | 570127969.4419 | 701095605.925 | 757688188.2321 | 297867029.4314 | 525500373.7996 | 25039140.9978 | 113682832.6236 | 20747063.3183 | 19501913.8459 | 729691688.6477 | 28130287.4615 | 1131665612.8023 | 5835450218.0459 | 673602248.5498 | 179979887.865 | 1.8209e+12 | 2455584.6288 | 927338.0822 | 1786902.6681 |  |  | 1.9718e+12
792 | 1102556166.3908 | 1099015561.5924 | 195613358.444 | 174572381.3813 | 1084338278.7096 | 25263651.6794 | 192270255.7703 | 319486638.7391 | 484129912.7603 | 152276026445.1395 | 1985270671.3152 | 1975109967.7914 | 2208341033.4776 | 168586998.5998 | 602874989.5643 | 659430369.0423 | 724769583.107 | 317759015.1785 | 550691407.1016 | 20990464.728 | 109116050.6608 | 21162479.9331 | 25995375.1843 | 693999454.4081 | 26584972.3414 | 1098833107.6783 | 5771449822.4237 | 698125209.019 | 178606854.0592 | 2.1672e+12 | 2306357.9118 | 934944.4834 | 1532607.6809 |  |  | 2.342e+12
793 | 1190672765.571 | 1123711405.2412 | 212968704.3404 | 163608527.0064 | 945178885.3764 | 27072404.5298 | 218104072.252 | 310819499.1534 | 398721339.3131 | 156446310270.0039 | 1919629065.7954 | 1653617121.086 | 2056624361.6908 | 200189077.1465 | 621409780.693 | 578495937.3469 | 738435588.4979 | 336808888.9363 | 594317362.2766 | 27142214.0958 | 132414759.1019 | 22208244.6848 | 23339737.6541 | 689909214.9032 | 26245322.2615 | 1036152555.6835 | 5897182646.1711 | 618220740.0002 | 195218527.442 | 1.5774e+12 | 2269613.3137 | 938392.3473 | 1659953.0323 |  |  | 1.7558e+12
794 | 1201630954.153 | 1098950915.7042 | 191528944.6995 | 172810131.0351 | 1043536360.4204 | 22040136.5028 | 218858524.0513 | 311276941.1563 | 492237330.0659 | 152902237192.1639 | 2023693879.515 | 1928211886.0123 | 1757936813.811 | 201801168.7546 | 544212657.4049 | 563758889.5551 | 883739285.1674 | 334205711.1326 | 597648157.17 | 26847163.0278 | 101034295.0022 | 19117523.8446 | 24095905.9981 | 766203428.9807 | 22791334.5324 | 1151339317.7758 | 6888380878.9244 | 637669654.6854 | 195780130.777 | 1.8772e+12 | 2319577.6249 | 908124.422 | 1552775.6811 |  |  | 2.0535e+12
795 | 1168085116.1993 | 1211840217.5534 | 208767639.4761 | 166149461.8592 | 1053212123.4555 | 23848747.4721 | 207903381.4469 | 308524395.3437 | 479881065.2716 | 108076931053.2566 | 1738647210.2339 | 2001781059.8599 | 1662579324.0048 | 166091956.6888 | 607337543.8903 | 662954093.8907 | 847901898.142 | 329180606.835 | 513982405.3234 | 19953577.0127 | 87800676.7365 | 23434237.6496 | 24184274.5764 | 871799199.047 | 28715870.6848 | 1142083330.4048 | 6034763940.7899 | 639127930.5843 | 197614414.4293 | 1.4541e+12 | 2697156.4995 | 940855.5018 | 1559552.8974 |  |  | 1.5846e+12
796 | 1261947947.923 | 1224064077.9881 | 210717311.7178 | 145651192.4808 | 1066880866.4545 | 25983102.1181 | 221715948.8583 | 319309435.7628 | 463915148.3803 | 160098299413.904 | 1916954472.2911 | 2087328673.2493 | 2159747978.4427 | 179009442.495 | 538975291.1678 | 706548038.5367 | 827841247.9518 | 328169014.7211 | 598212720.5033 | 25595033.8869 | 104911897.6375 | 24238003.1872 | 24075188.5848 | 937628222.1267 | 28688564.0281 | 996813172.2381 | 6520526098.1303 | 629736345.6638 | 196588148.2591 | 1.3986e+12 | 2357280.6877 | 960998.0136 | 1556875.2863 |  |  | 1.5825e+12
797 | 1221650432.946 | 1072009643.5172 | 210191461.3003 | 139223929.0883 | 1068798864.2329 | 23333054.594 | 208435030.5745 | 320344271.3926 | 491450070.9135 | 151448850502.2984 | 2075744410.3955 | 1484298365.2499 | 2146411034.3395 | 201728761.9017 | 624705736.3025 | 657123116.8772 | 816233624.8643 | 294745344.8864 | 579681885.7158 | 24500179.632 | 107901232.9794 | 20267361.2506 | 22269182.3403 | 776957102.1978 | 26059487.5158 | 1060624337.9304 | 6953906522.7645 | 686331059.8337 | 170269522.8703 | 2.0527e+12 | 2419244.9456 | 915975.084 | 1803411.5852 |  |  | 2.2276e+12
798 | 1023132596.0988 | 1119894679.7886 | 208605558.2166 | 181230365.0369 | 1087223097.1461 | 24584056.8639 | 205920213.6719 | 327637777.3253 | 485465083.3181 | 159425024983.8395 | 1786137173.7166 | 1982525584.8698 | 2063601295.8363 | 189951296.3454 | 557705855.5994 | 699973395.9777 | 824773064.5808 | 274926001.6558 | 524915727.3072 | 23487843.3533 | 112335321.2291 | 23791852.3663 | 22926924.2731 | 901813698.4432 | 27628215.6492 | 1148449438.696 | 7033800532.5448 | 646586654.3783 | 164037341.2178 | 2.0272e+12 | 2317763.443 | 932468.7918 | 1540212.0912 |  |  | 2.2103e+12
799 | 1123700369.9114 | 1171079357.0001 | 214760004.9637 | 158226139.5876 | 934322077.0393 | 21993126.7414 | 212161816.3701 | 324730732.822 | 500190633.5496 | 142670589669.7548 | 1965091969.9591 | 1831316649.5788 | 1804048736.7302 | 179635920.5722 | 559180322.0753 | 714549631.8759 | 880402144.517 | 293758479.5959 | 596366185.1576 | 24808555.7194 | 109836176.6947 | 22202127.353 | 25778537.9343 | 857557932.3404 | 26159279.1002 | 1213840159.7005 | 7265348554.445 | 592908415.2356 | 173007960.0703 | 2.0538e+12 | 2644562.8018 | 941679.034 | 1562714.8808 |  |  | 2.2203e+12
800 | 1096155423.5691 | 1227449678.2193 | 186391221.2233 | 148379749.1517 | 1044253890.9659 | 22866378.4877 | 218096977.2535 | 319681544.4735 | 460555450.8544 | 144142178892.1479 | 2023990168.5982 | 1596807545.7148 | 2172925241.1518 | 199909155.9451 | 648608662.0448 | 629410364.2193 | 868896303.1611 | 286742292.5912 | 538955026.9238 | 24712912.0371 | 120166235.421 | 20921324.1312 | 24434673.9576 | 911297019.503 | 20938911.8193 | 1178912864.1232 | 6287472617.4975 | 629713540.127 | 200163720.4414 | 2.5004e+12 | 2363747.9978 | 907374.0874 | 1745530.0146 |  |  | 2.6677e+12
801 | 1224396626.3616 | 1092761411.2846 | 218111846.3671 | 157353744.647 | 1086743755.1424 | 22418611.6433 | 204859037.5543 | 289744669.1262 | 489967684.0552 | 138590796709.4826 | 1595425457.5622 | 1585299672.7304 | 2117098141.6498 | 199981958.4079 | 514871628.6929 | 687491765.8872 | 821217936.0242 | 333923455.0623 | 595254172.5123 | 23146980.6313 | 122001542.1678 | 24809702.1355 | 19796110.2102 | 917234494.6088 | 28200354.5922 | 925707365.2457 | 6975458105.3722 | 597024331.274 | 171331108.6684 | 1.568e+12 | 2489173.2871 | 936120.4158 | 1640131.0592 |  |  | 1.7296e+12
802 | 1135562239.553 | 1192454405.8419 | 210975412.7894 | 178293870.4909 | 1045554392.641 | 23195192.3339 | 190910765.755 | 305056352.5886 | 426540463.2432 | 147195540338.8826 | 1894196119.419 | 1809897419.6902 | 2148295476.9628 | 186143796.5779 | 665973601.5466 | 631551487.4499 | 834815616.191 | 276722761.1502 | 545313531.6076 | 23028733.5493 | 136171327.1083 | 20368561.7157 | 22584529.0775 | 848746918.5244 | 28705051.6253 | 1030924021.2224 | 6631082661.5884 | 664590118.2844 | 195745679.8464 | 1.7764e+12 | 2361218.8434 | 1009771.8617 | 1695888.4151 |  |  | 1.9469e+12
803 | 1191183046.9658 | 1054035999.0523 | 224340874.6343 | 178620135.6736 | 962199168.3394 | 22130404.6236 | 220986793.0764 | 323034848.673 | 468235719.43 | 141209956265.0039 | 1856638716.6518 | 1688566761.4982 | 1956748108.3926 | 156008069.2979 | 603963666.1498 | 695062058.7357 | 672144588.5326 | 273731784.5086 | 605700853.5969 | 26348627.8216 | 121778629.0973 | 23130888.1007 | 21305045.295 | 853397212.9395 | 24466269.4988 | 1177303822.5271 | 6672073640.4371 | 689667895.3757 | 186396997.5315 | 1.7742e+12 | 2276427.8039 | 935058.2296 | 1725895.308 |  |  | 1.9384e+12
804 | 1225369929.9641 | 1214235781.5771 | 195637529.9496 | 155258672.2397 | 1008880051.3843 | 23293913.4674 | 216740540.8086 | 323939970.8524 | 475956011.0987 | 153748668981.931 | 1868924851.7605 | 1763975292.7387 | 2104397585.2471 | 184922146.1755 | 568104204.3112 | 603804056.9725 | 867322035.2619 | 269354804.7311 | 584878565.1395 | 20580058.3108 | 131232392.8676 | 21080354.3249 | 25545911.7172 | 869061906.2281 | 26561722.1883 | 1000442276.998 | 6423294707.574 | 692014869.9257 | 201020923.6574 | 1.9024e+12 | 2696776.1756 | 943253.5249 | 1515922.4768 |  |  | 2.0792e+12
805 | 1091701995.4877 | 1189051970.6666 | 219109957.8013 | 153177605.4284 | 1085047611.0792 | 26552600.6596 | 196585076.1518 | 300950008.6223 | 470126421.3826 | 161451153220.6909 | 2038981035.057 | 1831015211.8558 | 1783581670.4885 | 198092685.2767 | 654730557.4463 | 628120936.6869 | 903368376.8251 | 289871497.6353 | 527016326.3763 | 21604441.3767 | 106324173.9434 | 22628749.8111 | 24205205.2973 | 873902815.6339 | 24528138.8984 | 1170203829.4872 | 6848778724.3698 | 613726035.1943 | 179792755.1685 | 2.1686e+12 | 2528405.296 | 981023.2685 | 1553323.1549 |  |  | 2.3535e+12
806 | 1227251747.9389 | 1226743906.1443 | 194026454.0603 | 157503643.5124 | 1070306619.2294 | 24274185.5534 | 209895293.7222 | 310976176.6724 | 475364089.3919 | 154793086514.8478 | 1957728357.1533 | 1942470168.9581 | 2043103890.8936 | 198255501.1894 | 556760623.6049 | 533002545.1852 | 730494405.4605 | 243995105.4126 | 584883040.3871 | 27787449.0972 | 101133482.9367 | 23458938.2576 | 20518245.1899 | 700209529.4174 | 27665166.5941 | 1197060979.7991 | 5692973285.719 | 700109469.2453 | 178772864.2459 | 2.3668e+12 | 2413454.6357 | 918338.5293 | 1706552.8323 |  |  | 2.544e+12
807 | 1202097048.6916 | 1201629500.8685 | 214545939.0311 | 169928797.9944 | 1066665428.3495 | 23484803.1875 | 202155936.4397 | 322432554.8634 | 433463985.8033 | 140991269121.6518 | 1954634766.9342 | 1988433096.2227 | 2075564456.6882 | 186629460.7758 | 529309867.6328 | 689750157.4224 | 836522044.4513 | 276291937.5682 | 592033139.2712 | 23564254.6415 | 95084169.0457 | 21777108.0685 | 22465203.6419 | 785607286.6868 | 23924603.784 | 1091467531.1708 | 5951070575.1139 | 689152999.6446 | 199502459.2833 | 2.5175e+12 | 2347613.1658 | 944222.4521 | 1724193.3093 |  |  | 2.6814e+12
808 | 1127007326.2447 | 1126148268.1219 | 208778132.4112 | 162675317.6605 | 1073660320.0878 | 26250013.2853 | 203193275.8826 | 288748281.5727 | 414573366.1413 | 130050930318.1302 | 1887034880.0527 | 1875990612.8939 | 2121245105.2555 | 189962673.6755 | 606741680.8032 | 521845106.0169 | 891082679.55 | 341346826.7283 | 604203091.6089 | 25923195.3648 | 97351404.9401 | 22409828.9502 | 22522198.4798 | 890372518.0969 | 28221159.6404 | 1113255549.1046 | 7308284797.23 | 687614595.1783 | 197389420.7263 | 1.5098e+12 | 2393896.7796 | 1014957.1627 | 1537680.3874 |  |  | 1.6639e+12
809 | 1219704875.7693 | 1133696798.0255 | 206222847.1393 | 160284727.7413 | 1033404112.675 | 27723151.478 | 207909384.0349 | 321763388.4859 | 458693383.3182 | 135847344376.0004 | 1935337244.1242 | 2048058835.6156 | 2071458034.989 | 190662070.9173 | 594562998.9022 | 646406256.6922 | 865900700.3405 | 331684857.0164 | 590416798.893 | 24391862.968 | 126658321.4359 | 24092080.0799 | 23589290.226 | 907312930.6574 | 29306033.4134 | 964974355.4301 | 6584181309.559 | 649226538.6588 | 173875739.0293 | 2.5143e+12 | 2548742.1628 | 904621.4399 | 1816279.3198 |  |  | 2.6737e+12
810 | 1222057172.2936 | 1086305585.8051 | 191808280.5627 | 151640008.2714 | 1077654833.0505 | 22446107.1876 | 203242120.4818 | 325129318.1737 | 482572439.8766 | 149753659839.4128 | 1907588539.3301 | 2009724487.8916 | 2099423995.247 | 198352425.2849 | 489363204.0085 | 598217548.2105 | 781419729.3728 | 291825140.9879 | 490907207.0037 | 26695801.4329 | 116942550.7901 | 20295592.8101 | 23094698.0203 | 855018227.7009 | 29465731.4707 | 1187143556.899 | 6118511670.8893 | 684239819.4981 | 201046190.8025 | 2.244e+12 | 2560443.9822 | 979372.5667 | 1834976.0048 |  |  | 2.4166e+12
811 | 1219160225.8524 | 1188236521.4281 | 224140584.2135 | 180223432.2377 | 1056892473.2914 | 24586309.3404 | 217206858.9321 | 302356849.6101 | 448227807.5327 | 141116678714.7041 | 1873673114.1211 | 1664592410.5645 | 2104727453.1198 | 191966627.4199 | 587414780.8033 | 688515175.9399 | 820298418.2587 | 278792720.9348 | 561620064.21 | 24936539.8108 | 121046553.1521 | 20562890.055 | 25710508.8911 | 942055312.1277 | 24122319.3001 | 1064456172.7711 | 6040428470.5705 | 624792801.0938 | 201679634.137 | 1.9994e+12 | 2437945.554 | 980769.5054 | 1689656.5156 |  |  | 2.1633e+12
812 | 1207888822.49 | 1077378294.1865 | 190185311.4703 | 179036464.818 | 1062001702.7876 | 22128873.0747 | 207542816.2342 | 266479687.4255 | 452909058.8132 | 143101166933.8044 | 1859126973.2897 | 1659783638.3886 | 2001455753.7662 | 171930948.2514 | 532319609.7863 | 724678513.8601 | 737809697.6114 | 354197611.3371 | 495284900.5396 | 18906181.8732 | 122898992.1493 | 20915162.3977 | 22689735.5424 | 863184236.8433 | 27623363.7839 | 1045212860.0975 | 5981825748.7281 | 643219143.0009 | 183032372.1493 | 2.258e+12 | 2334075.9017 | 952083.697 | 1611640.8983 |  |  | 2.4232e+12
813 | 1182506040.0401 | 1128772087.6825 | 191842856.9149 | 176495618.6359 | 1084884151.9288 | 22313540.3915 | 200917266.3301 | 315289457.7526 | 485469310.8893 | 145916474172.8475 | 1624150874.2284 | 1572223122.2061 | 1881867619.4792 | 183436548.5836 | 551717769.481 | 695331576.1571 | 825333868.4628 | 352991778.1997 | 564514423.5489 | 23939708.4184 | 120353596.4774 | 22522585.5817 | 24495477.9918 | 728728348.6323 | 25866216.5176 | 1139377544.0727 | 6627979179.2897 | 648614365.5705 | 158120920.5462 | 1.5094e+12 | 2386790.8697 | 960827.2285 | 1656883.3537 |  |  | 1.6778e+12
814 | 1195434559.9445 | 1115781071.4043 | 216667699.4233 | 156912609.6361 | 1084486680.4007 | 24656307.4559 | 219225003.5346 | 320950720.4195 | 488261252.031 | 134018066247.8489 | 1880161642.6819 | 1636685632.3872 | 2209069878.0229 | 156674354.8386 | 620892605.4776 | 715765234.5341 | 715817648.5525 | 245383760.651 | 484152919.0276 | 25673274.2085 | 104509074.1908 | 19506135.2943 | 23231665.6495 | 911705307.9651 | 24742235.2502 | 1211381408.0359 | 6474563945.9422 | 686818874.5189 | 196644258.5093 | 1.8555e+12 | 2242303.1159 | 945040.4687 | 1673252.4165 |  |  | 2.0127e+12
815 | 1212809794.1131 | 1163357247.4452 | 189820788.6024 | 175215340.7324 | 1073369357.2924 | 23373341.6671 | 193469384.0429 | 322345901.7014 | 425565812.723 | 156946713281.1312 | 1465465408.1542 | 1822879729.8343 | 2166839061.1115 | 145895827.0016 | 569335250.596 | 650311547.5615 | 885603667.2278 | 305423216.4641 | 565311649.2009 | 23084194.1068 | 111830277.6275 | 23016975.6565 | 22328374.0748 | 933973964.9754 | 31041306.0348 | 961350112.3843 | 6201528852.1808 | 705638835.4439 | 147221915.7215 | 1.9023e+12 | 2390051.4696 | 1023482.4001 | 1693740.2663 |  |  | 2.0817e+12
816 | 1104267320.3835 | 1215360297.6407 | 202186357.9203 | 162562588.7947 | 1058908568.7003 | 20540372.9499 | 221124239.289 | 330227656.0248 | 472224235.1867 | 125657582075.9169 | 1980552302.5386 | 1990688411.687 | 1727920289.415 | 200148396.1396 | 541155716.5924 | 509732455.1442 | 902429397.8924 | 337049399.0048 | 531467226.9671 | 22828052.0042 | 127588354.4608 | 19825912.8555 | 25570909.4412 | 852464167.9794 | 27994968.7499 | 1048684758.9107 | 5968462136.9275 | 570874117.3339 | 197575871.899 | 2.3333e+12 | 2831462.9914 | 910765.9175 | 1561323.6428 |  |  | 2.4814e+12
817 | 1040288826.908 | 1032512487.34 | 222959102.8851 | 149438495.2552 | 1046778813.9779 | 22204377.6112 | 212362128.1061 | 321963794.5787 | 447710524.5147 | 137478418068.6607 | 1988661748.9585 | 1813325911.3538 | 2141518776.7767 | 156897080.3858 | 554604400.4747 | 624265973.5146 | 854988878.5189 | 297832648.2933 | 471024361.7505 | 24109379.2157 | 116405767.6118 | 23239121.6997 | 24935993.6211 | 786039294.9362 | 29363676.4222 | 1041398747.0941 | 6041062598.4585 | 650251845.4103 | 197986614.8215 | 2.3935e+12 | 2556982.8337 | 1016684.9444 | 1860380.0776 |  |  | 2.5534e+12
818 | 1165628448.0953 | 1204640586.3914 | 219619423.4107 | 165064879.4944 | 962494784.9117 | 25768895.3608 | 203268436.6732 | 322002205.5338 | 459982305.804 | 156705269614.6709 | 1909057657.8225 | 1889283121.057 | 1954516849.302 | 198745354.9943 | 475716478.7247 | 708116529.1265 | 819421524.7351 | 316677936.8148 | 479652445.3617 | 24436934.7932 | 104546489.8249 | 19295099.7124 | 24491893.1372 | 837309988.5336 | 22340365.5634 | 1040936344.952 | 6460035222.922 | 669192281.8927 | 201406622.0721 | 1.9526e+12 | 2665241.4784 | 924506.3598 | 1810196.8669 |  |  | 2.1321e+12
819 | 1044794947.8872 | 1163375084.1154 | 208095335.1621 | 182832104.8348 | 1082542411.0319 | 22172442.1651 | 213057233.4567 | 307276981.5875 | 469638919.4922 | 146331988583.6266 | 1894215218.3669 | 1790645875.1885 | 2098295388.0762 | 188903957.6411 | 480428389.0965 | 688813030.6376 | 880966686.0101 | 277805464.1532 | 510826665.4346 | 25060826.6304 | 124727700.8303 | 24147982.8592 | 25046795.3468 | 779075542.0668 | 27520666.8023 | 1130735499.2245 | 6738402587.6119 | 679163170.7852 | 194797580.9994 | 2.2078e+12 | 2554440.857 | 898152.3287 | 1750101.2729 |  |  | 2.3774e+12
820 | 1059935948.0469 | 1174474329.4952 | 193438054.6353 | 170499699.1019 | 1067421008.0663 | 22557734.1109 | 215803139.066 | 324500092.9481 | 467643875.6531 | 153985264907.2664 | 1753582762.7617 | 2106748694.0228 | 2162378743.8518 | 174199932.4827 | 658674573.4853 | 723376340.6613 | 837246842.2673 | 311506058.2324 | 569016861.1858 | 22496844.1626 | 115102036.4738 | 22280028.0478 | 22975893.5294 | 841384065.5983 | 29083579.7336 | 1147346654.532 | 6136053014.1616 | 567431991.5967 | 165478598.4525 | 2.6442e+12 | 2559814.1976 | 943472.0656 | 1607586.2591 |  |  | 2.8213e+12
821 | 1253827372.5518 | 1062316469.1444 | 224621466.8627 | 156116402.7959 | 1021709975.1324 | 21606643.3986 | 204874694.2253 | 282477564.6746 | 471542431.1648 | 145803225492.6511 | 2057101822.3668 | 1710323704.6381 | 2090456304.8291 | 200977039.0006 | 544552071.2513 | 695893310.6266 | 795316701.5518 | 361793692.2011 | 586241286.5127 | 20660774.9173 | 95461680.8074 | 22879632.7507 | 24723956.4078 | 839887721.0642 | 26756623.4347 | 1003018358.152 | 6947463514.5373 | 708960869.9252 | 198616042.983 | 2.4188e+12 | 2624075.695 | 961985.8353 | 1733383.8157 |  |  | 2.5882e+12
822 | 1237176854.4238 | 978872769.9016 | 222691551.258 | 169192817.3521 | 1071754175.7339 | 27163673.0912 | 214615221.1527 | 328256812.2486 | 498280335.2627 | 152510852718.829 | 1881661143.0319 | 1759180089.5644 | 2101503823.9738 | 186694797.576 | 620707881.1474 | 686231997.7223 | 791147706.2644 | 333873126.8665 | 595410089.2768 | 25111967.711 | 109894439.0752 | 18988402.2014 | 19284186.1153 | 762670785.7318 | 25699437.6427 | 959654474.7786 | 6103338382.2501 | 653142930.2864 | 181414770.8038 | 2.1794e+12 | 2560687.7899 | 956502.3093 | 1613087.7381 |  |  | 2.3545e+12
823 | 1153008936.1018 | 1147402294.7988 | 207284158.8098 | 172436137.9681 | 1065075411.4117 | 25652552.6691 | 185114216.9762 | 324707525.9471 | 493968840.071 | 158095019347.1937 | 1290046134.1986 | 1890137590.3799 | 1674500349.3679 | 175248323.8717 | 675311944.037 | 589093983.147 | 831551622.1806 | 276898912.6338 | 539794066.2436 | 20533918.7511 | 107437660.3447 | 23241064.6562 | 23167958.0793 | 825569845.7413 | 29034339.6482 | 1076189771.8985 | 5412649679.1201 | 652312866.7836 | 196163959.1057 | 1.9661e+12 | 2512234.8642 | 967817.0447 | 1576742.4776 |  |  | 2.1453e+12
824 | 1200174675.4412 | 1216894942.5928 | 215676733.229 | 159752071.1049 | 1070871411.7204 | 23610041.3635 | 216720284.6488 | 296362280.3678 | 434886495.4383 | 138974385629.9242 | 1912181711.5406 | 2093690943.3135 | 2208616346.5993 | 196537840.1768 | 591683204.4652 | 574043838.5918 | 780233926.1595 | 258372689.9576 | 594974388.7305 | 27423480.7434 | 110604171.3073 | 21171306.6227 | 25389412.0968 | 837918183.8469 | 26975312.9141 | 1049378193.6633 | 5673575671.7928 | 703911130.4736 | 170675138.0965 | 2.4794e+12 | 2416493.8331 | 946125.7398 | 1717252.4632 |  |  | 2.6411e+12
825 | 1115209032.2997 | 1113390975.208 | 224265481.5338 | 173029257.9818 | 1052928440.2425 | 21286261.1665 | 206574452.1921 | 310706841.9331 | 452684219.1918 | 144701783151.3193 | 2010815508.4594 | 1762689792.9618 | 1668347320.8042 | 196049019.7328 | 608489901.0396 | 552372678.0364 | 827333462.1387 | 338540128.1434 | 594857818.0613 | 22091196.8258 | 119277371.5961 | 23712422.7882 | 25010191.0308 | 923433947.4337 | 26029927.0355 | 1229272829.5936 | 6543614315.9414 | 683368117.7366 | 180475035.4713 | 1.9852e+12 | 2465004.9126 | 1025363.0363 | 1805088.041 |  |  | 2.1529e+12
826 | 987265583.6966 | 1187811355.264 | 215347395.2057 | 175598349.9547 | 1050851086.1923 | 23739431.4467 | 223961203.5472 | 313669423.5718 | 488130364.103 | 126626909650.0353 | 2026588040.5078 | 2054054518.968 | 2129639142.8981 | 168454391.3437 | 649849516.5789 | 682661212.8519 | 816003310.7428 | 303372145.5481 | 587015221.7847 | 26912317.5354 | 106064439.3494 | 22691437.132 | 25746856.4705 | 865374325.7374 | 26959196.0436 | 899432702.7937 | 6564856194.0515 | 573413056.0373 | 187710109.3928 | 2.0207e+12 | 2304420.568 | 952285.064 | 1582708.5782 |  |  | 2.1707e+12
827 | 1248850546.0931 | 1205977479.0155 | 198878794.0357 | 164839103.3113 | 1074164029.364 | 24031947.2812 | 206874203.1978 | 324720697.2789 | 413831591.1035 | 139395769028.3033 | 2013601478.7678 | 2037180946.75 | 1636268951.1069 | 195651133.2271 | 625479335.4902 | 691813082.9006 | 796254587.084 | 300122426.1166 | 592376543.5064 | 24037364.5804 | 132539792.0843 | 22030762.1139 | 22609489.6616 | 907998850.1784 | 22782692.4093 | 1195828654.3896 | 5975770598.9056 | 674256033.2744 | 181470529.6718 | 2.6221e+12 | 2355160.1203 | 893305.464 | 1691615.312 |  |  | 2.7844e+12
828 | 1082998930.9419 | 1152591951.7644 | 200591956.6684 | 176452560.3995 | 1085355986.6223 | 21963654.6384 | 204977237.8715 | 276699292.2353 | 490955626.4066 | 134984607446.3246 | 1829239718.214 | 1841299000.9363 | 1999602303.9143 | 200529511.5966 | 523318454.1286 | 594069934.6476 | 822282112.6115 | 246622843.5795 | 569243003.3077 | 27931023.6457 | 123865518.5769 | 18756054.1246 | 22530889.7334 | 788344979.3766 | 29177239.978 | 1000364976.4574 | 5941866357.9205 | 559147121.168 | 193629680.9373 | 2.108e+12 | 2730259.6261 | 921992.1035 | 1507633.6999 |  |  | 2.265e+12
829 | 1095309536.1972 | 1154304166.2546 | 226058449.9278 | 151052898.1848 | 978012211.8359 | 21817689.318 | 206404079.8514 | 294832587.4718 | 495321720.8843 | 110063251165.0049 | 2086108040.2573 | 1851602318.2298 | 1754597425.947 | 197385884.3948 | 552343723.6463 | 621414889.1339 | 821957238.8154 | 313664721.1701 | 588624186.9584 | 24132937.3824 | 124738860.1273 | 21370406.3166 | 24377224.0991 | 949923476.3505 | 26478478.1719 | 1056083391.431 | 6531103180.5906 | 678296897.1397 | 194402740.241 | 1.6604e+12 | 2501045.3452 | 1026320.8074 | 1626632.231 |  |  | 1.7935e+12
830 | 1236375037.9028 | 1177513287.6032 | 203189382.631 | 182506016.4499 | 1015288252.1097 | 21237512.1253 | 219884253.5534 | 322415842.0752 | 456747179.1455 | 129660817553.9178 | 1613163749.0502 | 1990420484.259 | 2049143637.5797 | 194755434.2547 | 567261454.2179 | 666632622.4174 | 753818581.9715 | 289540667.0779 | 483171510.9082 | 23050241.7508 | 95178505.2027 | 20784712.3376 | 24204890.8373 | 832766810.3694 | 22439303.2339 | 850784108.6138 | 6018878938.7781 | 520956444.3002 | 178564689.2033 | 2.3655e+12 | 2406169.0941 | 1010795.249 | 1689049.0733 |  |  | 2.5172e+12
831 | 1215228995.4726 | 1213813452.2091 | 205865382.8063 | 159550709.0347 | 1039040874.3812 | 27423674.4125 | 192978167.6673 | 315430191.5609 | 412403418.2887 | 133419415402.0178 | 1918631929.9208 | 1892545209.1762 | 2134664880.0794 | 190570127.5834 | 490080971.7888 | 709803051.8077 | 889898860.3796 | 321548833.8852 | 552616173.7115 | 25396916.4595 | 109131752.5589 | 20506696.8471 | 25456579.3025 | 791173333.9391 | 26523423.1612 | 1174944895.7339 | 6452407402.264 | 617858633.178 | 198295780.952 | 1.8991e+12 | 2433800.2945 | 997681.0301 | 1712803.6332 |  |  | 2.0559e+12
832 | 1251054581.3813 | 1222519077.9883 | 226604483.5469 | 162510144.8055 | 1055246713.0133 | 23891137.6839 | 226930656.4303 | 286644137.0592 | 425065634.6332 | 143682216810.3185 | 1992294606.7427 | 2034580282.3359 | 2113569423.3323 | 193325951.7989 | 598042889.1647 | 602176494.5939 | 900318393.7237 | 323457657.6978 | 605943209.6662 | 27752938.0715 | 133893286.7976 | 23711671.2854 | 21461627.718 | 912652018.3499 | 25516592.1422 | 1075046946.1819 | 5868956906.4687 | 693722738.8008 | 188976282.9477 | 2.8008e+12 | 2452227.4154 | 967908.1346 | 1640250.3997 |  |  | 2.9677e+12
833 | 1107957029.2663 | 1155094442.8705 | 168374343.2867 | 146969987.2607 | 990742944.5861 | 24251957.1061 | 226666807.0939 | 328703424.7933 | 488825988.2819 | 153360311572.1012 | 2060668546.2993 | 1925353466.2708 | 1864988453.1052 | 184655296.0873 | 652608435.777 | 712179014.5827 | 668238046.5155 | 319014592.935 | 458289264.6966 | 23487023.7304 | 136428510.8607 | 22577386.7686 | 25110243.4517 | 859685147.8011 | 22279858.7257 | 1099921858.7609 | 5074442653.5386 | 660242198.8759 | 174712027.1399 | 2.3857e+12 | 2527567.8532 | 981693.1051 | 1727304.2612 |  |  | 2.5607e+12
834 | 1111825159.1491 | 1091797899.5287 | 195486151.2571 | 172816624.6334 | 938447612.2725 | 23783581.3122 | 218288643.7682 | 304951836.9717 | 460469426.3818 | 148149818248.775 | 2067310256.6815 | 1931673587.0352 | 1773827469.4372 | 201881240.4272 | 630834791.7894 | 676515915.312 | 669791236.9556 | 342356414.7384 | 614124239.5657 | 25410726.9432 | 98130446.6674 | 24715409.0066 | 26011182.1816 | 738840610.9036 | 24164873.1409 | 1016440911.7528 | 5302798808.6742 | 673991158.1483 | 190398456.7561 | 1.9677e+12 | 2541580.5324 | 922609.845 | 1749255.5967 |  |  | 2.1374e+12
835 | 1086399681.5625 | 1079261413.8501 | 210420671.0873 | 170266372.8725 | 1001074850.7068 | 25887990.2093 | 212173975.2595 | 292331329.0591 | 491916614.7091 | 149929983739.8163 | 1864733365.099 | 1871677090.9227 | 1758797936.0779 | 186717463.7619 | 574099134.1675 | 717310805.5187 | 921267730.6081 | 327793028.3749 | 508317462.8828 | 25194387.0971 | 105085372.1161 | 15979141.7423 | 24633684.1056 | 791869699.9607 | 30337075.8038 | 1126716115.4926 | 6062130883.0705 | 549743022.1712 | 200994081.3653 | 2.3107e+12 | 2603347.5571 | 934224.9606 | 1640385.5725 |  |  | 2.4829e+12
836 | 1174205843.106 | 1169181918.1111 | 206272581.5076 | 152619081.3667 | 1084826698.547 | 22267398.1378 | 220949200.9426 | 307706442.7662 | 478043513.5991 | 155587837479.4861 | 1846331111.0238 | 1726498726.2993 | 2163170058.5738 | 188167840.1794 | 623132002.5874 | 716208255.8226 | 826708114.5397 | 325895867.2851 | 577312871.9245 | 23253981.6836 | 117809903.7811 | 23464622.5026 | 24165547.6866 | 937517864.1852 | 24513436.9111 | 992548466.3142 | 6493527771.3885 | 622817669.8177 | 169445875.7689 | 1.5775e+12 | 2422413.18 | 982071.2638 | 1666823.1694 |  |  | 1.7564e+12
837 | 1182397222.6316 | 1227019048.8525 | 211284189.6931 | 173760137.2873 | 1059427519.932 | 26341174.1106 | 221885693.067 | 318104698.2775 | 479304605.7214 | 145085434437.3315 | 2050666843.6788 | 2086283750.7453 | 2164553827.1112 | 183665303.2504 | 509516320.2295 | 715521133.7806 | 812487972.3204 | 312814735.7282 | 499150979.1659 | 25369688.1421 | 106596457.9027 | 24707522.6702 | 25069782.7791 | 864346196.9225 | 31018304.6936 | 1158970216.8284 | 6487740771.6492 | 669539760.4638 | 200292115.4964 | 1.4519e+12 | 2454743.5643 | 895829.4824 | 1722322.5119 |  |  | 1.6208e+12
838 | 1181136584.1565 | 1153832067.9898 | 214157994.3284 | 172925235.0351 | 1071059139.1506 | 22287415.4357 | 218817783.1252 | 271912284.5161 | 427552713.6025 | 153366173791.0397 | 1796210900.6582 | 1993664221.4875 | 1956301300.7741 | 181934202.0136 | 633726184.1927 | 652777769.1938 | 917067907.0887 | 235866752.0921 | 524863839.1398 | 28119060.8729 | 128943376.0542 | 20648641.5671 | 18594921.3003 | 812555412.5996 | 21944609.6632 | 781152822.1091 | 7099534179.8567 | 554308691.6377 | 181947736.0036 | 2.0127e+12 | 2597731.2973 | 908961.7524 | 1791157.4001 |  |  | 2.1893e+12
839 | 1158687885.8163 | 1178979918.3467 | 224622317.8435 | 153952125.7511 | 900368228.5581 | 25272164.4374 | 217083715.6335 | 296325881.9904 | 485931968.739 | 160106035777.5232 | 1879559976.7843 | 2173822170.4894 | 2011692653.925 | 199533537.5474 | 598717162.2077 | 673146000.325 | 835163169.6737 | 300961110.5425 | 600656792.0969 | 24780062.0136 | 127469531.4448 | 20333442.9735 | 24859827.2287 | 899356363.333 | 23219430.8268 | 1227339229.0749 | 5767412414.234 | 627892956.7649 | 187960008.905 | 1.9599e+12 | 2307280.6279 | 966023.3122 | 1520607.067 |  |  | 2.1429e+12
840 | 1212399096.3349 | 1218678840.0502 | 198961838.7351 | 177018455.6758 | 1060012730.0661 | 18859966.9229 | 206091922.4418 | 289622162.0737 | 474950142.1515 | 159013435871.5398 | 2090648170.0893 | 2163279238.8444 | 1985865917.291 | 174686255.8653 | 603037510.5297 | 673688691.9729 | 703006671.0973 | 352029850.7452 | 614833745.8942 | 20803002.7344 | 110981805.7035 | 21239667.8519 | 19686890.0737 | 839006885.5227 | 24913013.2617 | 1065496972.6146 | 6566770018.9951 | 660664976.2321 | 170856920.8986 | 2.1158e+12 | 2426769.3089 | 918782.4107 | 1609265.4725 |  |  | 2.2986e+12
841 | 1223686010.0995 | 1226805291.3276 | 211655087.8433 | 150091712.4706 | 1061257518.9732 | 25822733.4795 | 203597335.74 | 310205055.2496 | 495573813.5101 | 152553537345.1463 | 1882455307.1347 | 1777587145.8676 | 2192886342.1045 | 186649756.0835 | 607433969.3097 | 608930171.9996 | 765063426.2334 | 327424977.3172 | 576571928.5944 | 24913657.4157 | 109860755.9714 | 21873014.1005 | 23285482.1362 | 922008031.9966 | 22978777.5743 | 970014676.5726 | 6729149649.2264 | 616294190.4158 | 187950584.3801 | 1.5424e+12 | 2592372.9908 | 1009994.5811 | 1606797.5633 |  |  | 1.7184e+12
842 | 1130498720.5035 | 1114523890.9998 | 215441067.4139 | 148366479.8425 | 1038802544.1991 | 18335685.8216 | 214350455.2127 | 292711223.1564 | 457618170.5406 | 122009719237.0703 | 2020821651.9871 | 1796202454.6367 | 1889933765.3722 | 198584174.5577 | 569167922.6794 | 653363245.5093 | 774278870.1157 | 317535348.8439 | 575616676.1352 | 22169446.4803 | 116398244.8256 | 21380774.807 | 25897994.4549 | 864335033.9476 | 30069805.2969 | 947715205.8448 | 4781763007.3405 | 708194914.0781 | 199943402.5656 | 2.1095e+12 | 2328391.0682 | 988515.9866 | 1655527.6751 |  |  | 2.2526e+12
843 | 1192296221.4446 | 1192706533.9202 | 213833164.6525 | 140750408.9746 | 980752947.6756 | 23104777.2882 | 197806878.702 | 307294768.4855 | 481943487.858 | 143856637455.2733 | 1768188154.5849 | 2103750320.8663 | 1952035958.9967 | 185269939.5952 | 646625259.4219 | 720292508.2929 | 826194731.2142 | 322976484.274 | 519186194.2832 | 25723371.4804 | 135007207.1513 | 23231418.7334 | 21754077.6968 | 865120746.9963 | 24609246.8628 | 1077505334.0726 | 5665495086.0774 | 641103527.3668 | 194571741.2736 | 2.041e+12 | 2460613.3459 | 950445.3079 | 1658845.4895 |  |  | 2.2073e+12
844 | 1026560242.1223 | 1224532297.0498 | 184616890.8342 | 179234523.5445 | 1084041736.8177 | 22284106.7975 | 197706391.7459 | 309887768.1504 | 468349912.1575 | 140430749735.4579 | 1704906158.4183 | 1792136352.9438 | 2138866536.2386 | 191823297.9952 | 587408774.1212 | 695239729.7377 | 746353038.6217 | 274356748.0079 | 615205089.5636 | 20280078.0769 | 109501324.2266 | 23216550.4969 | 24279070.3014 | 933784263.7111 | 28893390.6155 | 1201368484.9227 | 6546147206.5244 | 695789977.2824 | 182703782.1488 | 1.853e+12 | 2653484.5783 | 934376.5196 | 1559868.3203 |  |  | 2.0167e+12
845 | 1198754763.8889 | 1218582670.8834 | 216641368.9558 | 169908174.6812 | 1044020580.0679 | 22022266.1235 | 175019545.9919 | 287884871.2505 | 470882575.5845 | 139888497916.5369 | 2053662503.5874 | 1811787511.1299 | 2204507519.902 | 201626961.7695 | 641210369.4433 | 712968162.3762 | 819165227.8123 | 309815111.4531 | 573448905.8149 | 25397733.5699 | 114343304.7162 | 21556529.6894 | 25493010.4299 | 910914716.6809 | 26102491.232 | 1069528446.8142 | 5564939946.3537 | 666098138.7305 | 189768690.4212 | 2.1555e+12 | 2442377.8287 | 1022339.9452 | 1713854.0023 |  |  | 2.3182e+12
846 | 1212227793.4417 | 1201193224.7433 | 191986925.6779 | 181229556.5716 | 1044237743.7703 | 22520948.6442 | 217523255.5448 | 306046079.0639 | 470673003.7671 | 155145087841.5336 | 2043408254.1856 | 1837509767.3654 | 2212063604.7871 | 187717854.6011 | 666792868.0828 | 715052251.5392 | 864287332.8639 | 273522435.2459 | 606243857.9028 | 23555285.5878 | 113577420.0224 | 17502012.4985 | 22307408.8407 | 918610827.6665 | 28143730.1843 | 1197111290.0625 | 6097477403.8743 | 588467331.1642 | 189834117.7947 | 1.8896e+12 | 2261339.6161 | 1004132.0144 | 1471746.9449 |  |  | 2.0682e+12
847 | 1188851448.9923 | 1188761960.2209 | 207736954.2231 | 180674483.5215 | 999789924.6777 | 25912948.6679 | 206880041.4524 | 310296231.0609 | 465473565.6523 | 131987076292.8611 | 1702148070.6262 | 2159678241.571 | 1918017302.5399 | 200543394.19 | 628768278.3497 | 670424025.8824 | 868066819.2484 | 328976874.3032 | 608653686.6557 | 23280201.391 | 99167841.4947 | 22926003.8468 | 23430231.162 | 862619652.1842 | 25366249.2746 | 1048579333.9087 | 6976272897.2559 | 680690279.1281 | 201389311.4251 | 2.3923e+12 | 2549104.0208 | 971516.5983 | 1588841.6489 |  |  | 2.5481e+12
848 | 1167221228.4763 | 1218987972.3804 | 204020161.5784 | 171855400.5135 | 1066580789.0125 | 22225812.5974 | 223267869.4508 | 294143097.8941 | 432952384.4176 | 146321173449.4348 | 1959782286.2822 | 1703925923.6867 | 2145900483.879 | 191097872.5558 | 669689177.9039 | 678540582.1127 | 837266939.0325 | 333166167.2111 | 570512554.0572 | 27704237.7216 | 126717173.0447 | 24160474.6631 | 20363533.3417 | 752280035.4505 | 27001677.2943 | 1000802122.1501 | 5230532279.5507 | 632607551.2399 | 187062658.2107 | 1.9369e+12 | 2460052.0019 | 968979.4231 | 1700099.5464 |  |  | 2.1051e+12
849 | 1236189671.9774 | 1105060189.2898 | 221381871.9156 | 170794279.9653 | 1064330441.4153 | 22191002.2962 | 217044657.6173 | 330563276.2643 | 486542944.9126 | 137278407995.8653 | 1585081232.0664 | 1637125868.4106 | 2106883320.3128 | 182668555.9661 | 473564076.557 | 682517387.2634 | 811142898.949 | 272058490.7425 | 590723552.0616 | 28016273.2409 | 110086870.6958 | 23473445.9633 | 24140031.7626 | 887938962.6303 | 29689955.8612 | 1047663772.9277 | 4630250386.1218 | 665014511.7422 | 200176724.295 | 1.869e+12 | 2557590.6954 | 952340.5294 | 1603382.9306 |  |  | 2.0271e+12
850 | 1186575954.1496 | 1216906295.4202 | 224856503.4209 | 150409892.893 | 1036452822.8073 | 22340728.391 | 183462321.9784 | 319822002.7374 | 484750365.8552 | 130757599301.101 | 1796626644.2003 | 2145865061.6234 | 1993908097.3796 | 174305446.4662 | 448297321.4332 | 689190581.9168 | 752963088.9946 | 296262843.7614 | 603045742.1947 | 21079760.2342 | 135000777.2383 | 23847626.5969 | 20055323.496 | 733366774.6062 | 24193932.0516 | 1100255130.3584 | 5011290703.2545 | 538705825.5043 | 196291922.8478 | 1.8966e+12 | 2530847.0844 | 1030330.4646 | 1644757.4919 |  |  | 2.0489e+12
851 | 1177399667.9013 | 1127432667.9363 | 212866341.3412 | 156805484.1213 | 846419506.4461 | 22048138.4385 | 218305395.3046 | 327040331.6363 | 473949773.0065 | 135515487104.5509 | 1719215047.7289 | 1710004089.14 | 2166276053.597 | 152190728.0132 | 507798360.2407 | 705142635.6728 | 808634606.7841 | 336618126.6458 | 560312300.0161 | 21807540.5894 | 116639053.8367 | 22599731.219 | 25804537.6318 | 819479531.7915 | 24012662.6211 | 1074669078.4215 | 6243767436.0978 | 677856304.9247 | 159186560.6369 | 1.6427e+12 | 2442956.5187 | 940922.2456 | 1649878.6517 |  |  | 1.8007e+12
852 | 1212395073.8054 | 1165806316.4464 | 214274187.1901 | 174980383.4519 | 1028195947.8444 | 24410539.0459 | 182607525.7049 | 306284142.8262 | 468817890.2604 | 156975222126.537 | 1965383248.994 | 2053715799.9938 | 2053903514.0192 | 173522506.6008 | 507893906.5658 | 717100557.5514 | 890263765.9098 | 325035211.9276 | 522427295.5606 | 23347490.227 | 92328092.7196 | 24250859.6667 | 23653217.964 | 906140918.1162 | 28121357.6614 | 1044249871.979 | 6412873639.0304 | 670763191.7502 | 159276270.1087 | 1.9191e+12 | 2456136.2602 | 949301.1789 | 1705495.2605 |  |  | 2.0995e+12
853 | 1136970328.2279 | 1179512059.0712 | 194314127.3152 | 176897272.0893 | 1017743994.5609 | 20136586.1076 | 221420433.0883 | 270556598.6108 | 471244479.1667 | 141111567933.9713 | 1898113886.011 | 1748016453.8014 | 1848243101.6003 | 182584853.5361 | 647863441.2814 | 690689039.0909 | 694741700.4244 | 346890533.6509 | 481868979.7054 | 24680475.3698 | 110750911.86 | 21063552.0161 | 24916732.1767 | 918430601.5278 | 28539030.1418 | 1156699557.8857 | 6074439206.4269 | 659912092.5656 | 151913738.3176 | 1.7165e+12 | 2591516.9667 | 999291.5154 | 1725054.7504 |  |  | 1.88e+12
854 | 1144552217.8793 | 977918261.5488 | 212769388.0572 | 162864296.5474 | 1063882141.5252 | 26682931.3785 | 224734521.1307 | 326470626.4987 | 450717174.4332 | 137455962732.7244 | 1781578153.8826 | 1742636845.4692 | 2213659252.9312 | 172949022.002 | 619213522.8329 | 666125516.0148 | 738406723.2112 | 298763945.2425 | 497474576.7531 | 24656906.9023 | 124140921.2864 | 22511817.0762 | 25487248.4864 | 895698163.612 | 28395476.1027 | 967873339.1134 | 5563390120.2335 | 650318573.635 | 189699205.421 | 1.9176e+12 | 2277724.9418 | 976616.1583 | 1636510.0089 |  |  | 2.0769e+12
855 | 1225595196.9347 | 1220664521.129 | 207628450.4441 | 159038111.705 | 1021572010.9936 | 23004515.922 | 211404016.4349 | 316229278.8976 | 486240652.1929 | 148479166037.9821 | 2088119285.1442 | 2119384499.2258 | 2082186452.3099 | 202047571.8497 | 572072647.8232 | 644494956.9842 | 893893926.3374 | 264316398.305 | 607963581.1639 | 19966515.2512 | 126500725.9069 | 18198731.0911 | 23330532.0871 | 861982498.2633 | 27475238.0061 | 979973629.2862 | 5388694513.6325 | 695915991.6483 | 189981684.5956 | 2.0026e+12 | 2399509.1261 | 890607.1129 | 1690381.9946 |  |  | 2.1738e+12
856 | 1228342326.4235 | 1211367877.3211 | 216606282.017 | 178000332.5638 | 1000331553.9735 | 25493005.0871 | 206088346.7678 | 329363862.4512 | 492233840.4156 | 149800812278.7337 | 1928524092.6091 | 1842815140.4387 | 2208755316.932 | 184559052.4822 | 535218826.1872 | 595729671.0998 | 840018344.5931 | 327837564.4746 | 560478430.6556 | 26682713.2665 | 117761144.2766 | 20874612.607 | 25631114.3395 | 776942190.5389 | 28575862.8196 | 1060780168.1368 | 6471775136.4503 | 646606987.4123 | 177192490.7404 | 2.4734e+12 | 2591309.7072 | 953888.4705 | 1679747.5818 |  |  | 2.6464e+12
857 | 1197670058.7077 | 1227902995.8656 | 194937978.6212 | 156392457.8724 | 1062169723.7265 | 23828257.845 | 210133665.1651 | 323194947.0612 | 469600446.5686 | 149912001251.7622 | 1940593620.897 | 2033383275.5031 | 2150917955.1115 | 159482273.5062 | 623002019.1451 | 636394997.6699 | 762547914.1891 | 345011174.8036 | 591925029.5818 | 21459682.2085 | 116677732.4 | 23043847.344 | 22650744.9871 | 889933364.8805 | 22031550.4322 | 1211258900.3435 | 5940978704.3111 | 582230083.1517 | 171639337.0486 | 1.6264e+12 | 2696603.2859 | 950616.29 | 1579903.8745 |  |  | 1.7995e+12
858 | 1168806180.8526 | 1199987053.8083 | 215252315.7186 | 165827180.8491 | 1036147366.8871 | 21851978.9893 | 211028955.9836 | 272267009.4808 | 496305026.7668 | 141578236440.7516 | 2007285211.2716 | 1934120717.0087 | 2195504569.3424 | 191001187.2673 | 676199838.5596 | 639983148.8548 | 794709686.0993 | 275367883.3968 | 575247725.7018 | 26232168.3988 | 126423288.8641 | 22842537.168 | 21141527.5718 | 868009985.7577 | 24092700.6279 | 1151798935.8656 | 5531284912.0741 | 693844860.7025 | 197229164.5901 | 1.7574e+12 | 2613728.1174 | 984089.0962 | 1602490.4495 |  |  | 1.9218e+12
859 | 1176539006.8426 | 1123325380.5402 | 210958935.7971 | 178030216.1006 | 1033416212.3818 | 24417581.2968 | 218110847.5148 | 305241522.4177 | 452564741.5667 | 159874157650.1571 | 1763951289.6681 | 2014434769.9717 | 2123331322.2301 | 179013973.7831 | 628227193.4337 | 589170425.4341 | 816241398.7445 | 306940914.4499 | 613621551.5151 | 21750451.3413 | 117727720.7154 | 24233550.5424 | 19261142.903 | 849365741.9954 | 29459414.8564 | 1169240335.0416 | 6958375713.3552 | 704006235.3156 | 197261701.2058 | 1.996e+12 | 2453817.8404 | 955711.0325 | 1646805.3291 |  |  | 2.1798e+12
860 | 1212435960.0666 | 1186129451.7313 | 207419949.8175 | 169257416.6605 | 1037156350.8821 | 22405339.128 | 216872447.4545 | 293182776.9964 | 432113148.1335 | 153412038722.2938 | 1851763323.9004 | 1685916861.568 | 1972211707.767 | 198585516.6294 | 617172200.091 | 711518388.7423 | 788765613.627 | 310820447.2833 | 580333409.3351 | 24675133.3763 | 128499771.7311 | 21029701.1794 | 21874313.4421 | 867192920.741 | 31041652.9083 | 1115948163.7034 | 5896757499.5582 | 628728472.6478 | 174737823.3659 | 1.977e+12 | 2474018.1722 | 959425.7541 | 1506869.6304 |  |  | 2.1529e+12
861 | 1113653318.8099 | 1139067482.4469 | 192186039.9268 | 160010615.6679 | 1077543138.1365 | 23547014.7435 | 222883458.065 | 320871690.339 | 482158848.3032 | 133914889650.0342 | 1659098290.2593 | 2123666360.9911 | 2188681865.9747 | 200602317.0094 | 600320421.5988 | 601338087.575 | 751966373.0842 | 350990078.8791 | 590151582.6365 | 20838850.8408 | 97560632.1551 | 24156876.115 | 25176888.9565 | 908909841.9716 | 26825035.3065 | 991393952.2302 | 6578059287.3631 | 600139885.6142 | 185879892.0125 | 2.1131e+12 | 2645631.4991 | 980748.0388 | 1695085.5444 |  |  | 2.2703e+12
862 | 1199453457.6008 | 1109809744.6958 | 211086967.1929 | 175795218.4832 | 897468457.312 | 21811036.4177 | 213027119.2899 | 299612343.3885 | 443736058.3712 | 146448225568.2176 | 1863414860.5914 | 1876425994.3391 | 1769313843.7589 | 191709917.0362 | 587544275.5769 | 625311018.4617 | 865158187.4647 | 252755614.0495 | 598262723.5945 | 27783199.9218 | 102734456.5097 | 22675009.2219 | 20829475.9801 | 832403939.4593 | 26095019.6672 | 846102063.8133 | 5323582992.7736 | 700006859.5927 | 200362388.6364 | 2.3375e+12 | 2790429.4277 | 929785.4574 | 1529205.8831 |  |  | 2.5053e+12
863 | 1139578801.639 | 1021558615.699 | 203109478.0123 | 150486810.3354 | 1066850422.0723 | 22613242.8014 | 189136830.5947 | 312612966.4822 | 467539608.8717 | 137664584399.7441 | 1657691332.7782 | 1612590180.0614 | 2182541236.6877 | 164729676.7026 | 550035145.5989 | 670899989.997 | 784392888.7973 | 323909482.4787 | 589175017.9448 | 24748129.7629 | 117606666.1854 | 24428333.6328 | 23659354.418 | 745638424.9134 | 25419100.0019 | 826426368.5012 | 6474795624.5172 | 709838230.8133 | 196241527.9362 | 1.7572e+12 | 2664567.9735 | 959224.5235 | 1719725.2595 |  |  | 1.9171e+12
864 | 1193003284.1583 | 1137265323.8527 | 215091033.5984 | 166058800.9258 | 1045522817.8372 | 26762474.6063 | 180649635.6532 | 316690561.582 | 483836167.2261 | 146233559687.0226 | 1847151952.2555 | 1626897250.9879 | 1994849933.7068 | 193063558.3939 | 558228710.2794 | 674148128.0306 | 651992832.9191 | 277960455.3557 | 595771262.9798 | 27051360.5576 | 116515451.2051 | 21253318.5262 | 22685396.9698 | 930085497.3294 | 24956998.8261 | 869963879.8038 | 6829905347.4372 | 686842086.5832 | 162612086.5463 | 2.3702e+12 | 2523088.7642 | 958411.1446 | 1542524.797 |  |  | 2.5393e+12
865 | 1248111172.2716 | 1180969570.4751 | 195004529.8526 | 178307303.9948 | 1065776123.4992 | 23881977.1514 | 183871094.0172 | 323327128.8339 | 465528497.7123 | 143726228961.9502 | 1471608456.1009 | 1982479226.3019 | 2121996130.6705 | 160375274.9976 | 657670817.8314 | 718067002.6895 | 904243830.492 | 342051113.2493 | 558795411.434 | 24302431.5132 | 100961297.0321 | 24207287.8293 | 19315268.456 | 732045912.1003 | 27003189.9289 | 1195407564.5568 | 6943280173.4065 | 706157265.1561 | 184749038.8856 | 2.1854e+12 | 2300423.0294 | 927289.1231 | 1675330.2648 |  |  | 2.3528e+12
866 | 1237717593.4805 | 1099288705.4224 | 206645334.0162 | 172418735.3971 | 876256278.7749 | 21275368.4868 | 181021313.0246 | 308857301.8027 | 491079917.6833 | 147183564403.3733 | 1764603979.6381 | 2208064847.367 | 2158321769.31 | 182091863.6576 | 647282344.9603 | 723973522.6344 | 743523568.9837 | 270607602.9926 | 438906624.6199 | 23712470.8256 | 93499775.2658 | 21533848.7558 | 22893306.933 | 789030055.6773 | 29985051.3938 | 1008572675.9767 | 6797501660.4881 | 693534297.9664 | 202010686.7041 | 2.2339e+12 | 2602565.9433 | 909250.4315 | 1707065.727 |  |  | 2.4045e+12
867 | 1213332871.0183 | 1214804028.089 | 207890245.4956 | 159018153.6888 | 1028526742.644 | 20890516.1712 | 198535758.0634 | 306684728.7121 | 493770408.3077 | 138234255477.82 | 2033240328.3425 | 2027229380.6428 | 1856738269.0735 | 185699604.955 | 634970151.87 | 702989449.8895 | 814065644.9053 | 304649440.0187 | 606142470.9384 | 18826242.8297 | 119006059.2971 | 22223106.2907 | 24883145.0078 | 907129472.1951 | 26133585.1578 | 1171809026.9341 | 6397354412.504 | 634360958.8173 | 201203091.5411 | 1.6716e+12 | 2485248.6932 | 975764.979 | 1559073.5397 |  |  | 1.8334e+12
868 | 1241652352.3418 | 989533205.6138 | 214875070.3712 | 168257556.8764 | 892095321.0279 | 22871328.3274 | 216578319.9707 | 277558471.3225 | 446915055.8387 | 130658960179.256 | 2048267442.4586 | 1979414939.8062 | 2175097339.6632 | 190152000.568 | 521620061.422 | 677794706.8848 | 785184233.9169 | 283467874.4347 | 593452805.1919 | 27053502.9232 | 117000323.0312 | 24061160.4563 | 21876471.8399 | 820890358.5137 | 30329422.6663 | 1186194256.7408 | 7053579708.304 | 633860488.9152 | 198386259.173 | 2.3043e+12 | 2650291.2557 | 926888.9192 | 1708825.3444 |  |  | 2.4588e+12
869 | 1215750739.5678 | 1184026389.9727 | 195129653.1404 | 171388847.9605 | 1008484795.7624 | 19331510.7674 | 215298825.5823 | 303132520.518 | 491406121.06 | 126311829004.6671 | 1849404562.8342 | 1832326937.1053 | 1685801121.2395 | 198083604.3327 | 627565842.4636 | 689371502.952 | 769660519.165 | 285768654.6867 | 589523609.7106 | 25015169.459 | 113024735.7613 | 23923866.0818 | 23639238.2795 | 884101890.8501 | 27625504.6895 | 1038136296.8054 | 6058287199.4741 | 679588938.7236 | 188353746.0932 | 1.8611e+12 | 2527822.6041 | 949938.1274 | 1808246.8108 |  |  | 2.0098e+12
870 | 1154352069.2953 | 1198792682.5917 | 218025188.1771 | 175407840.8718 | 1085488975.2573 | 20546213.0105 | 221271994.8861 | 305067049.2565 | 485794120.9621 | 134907627096.6996 | 1647101456.922 | 1754535800.5638 | 1600615976.7895 | 202593627.8011 | 506616601.4454 | 704682460.2808 | 672658935.8379 | 321900112.6183 | 600625789.0268 | 21354420.6814 | 110999135.5477 | 24445245.0842 | 24406068.0055 | 707514640.8494 | 28892155.2637 | 1068734838.5826 | 5493502750.7695 | 687834526.1645 | 194952708.5581 | 1.9864e+12 | 2721566.145 | 905632.4738 | 1627895.558 |  |  | 2.1426e+12
871 | 1221791344.5245 | 1088311528.7925 | 212265256.3352 | 156815701.0705 | 1021471457.1786 | 24007845.4573 | 224333705.4064 | 309949883.1945 | 495695079.8303 | 145492127075.0728 | 1784059524.3051 | 1794527834.5265 | 1701949286.4049 | 181194680.8543 | 686341494.9214 | 652265679.0894 | 863782620.577 | 246628287.3899 | 561547060.9167 | 26027705.3627 | 131095853.2501 | 24635500.7176 | 24195721.4602 | 868059173.6059 | 28766427.8094 | 997714361.3102 | 6933775984.8901 | 545368086.4611 | 195504888.3228 | 1.79e+12 | 2567123.3946 | 936249.2758 | 1645742.3493 |  |  | 1.9585e+12
872 | 1188927533.7462 | 1140635814.9751 | 200518511.351 | 180192200.8201 | 1074988125.9954 | 20938348.8129 | 216457429.7976 | 331125490.5353 | 477840630.3635 | 140986871605.829 | 2082088525.663 | 1958217936.5958 | 2138285581.9252 | 185933813.3409 | 640958491.488 | 705683307.5211 | 832891869.4838 | 235033343.0889 | 472788740.9878 | 23953256.8454 | 108584587.1032 | 21548515.0011 | 24271249.7593 | 924115815.1414 | 27372052.6645 | 1015509512.0438 | 5231529560.7293 | 708398881.266 | 160769696.5556 | 1.9609e+12 | 2476949.817 | 988115.7273 | 1771080.7722 |  |  | 2.1243e+12
873 | 1175353713.166 | 1109652773.1794 | 211900365.5777 | 177902099.1902 | 1008662930.3172 | 25469621.1829 | 214107625.3576 | 315011197.1041 | 466382372.7875 | 156949847449.0081 | 2033040185.6462 | 2059403400.4192 | 2195449864.15 | 178232774.7991 | 596788427.4122 | 599460482.002 | 840001302.363 | 336919493.8418 | 596440659.9902 | 24015671.3903 | 119481552.1857 | 17773831.8607 | 22937689.747 | 693708921.3476 | 27680784.3803 | 838329313.6376 | 6770807652.7723 | 598464871.4942 | 194963034.4293 | 1.7928e+12 | 2684075.7934 | 902906.5797 | 1518382.8538 |  |  | 1.9732e+12
874 | 1178986353.6105 | 1164918880.6476 | 171635727.1755 | 162714676.8778 | 1007256829.9726 | 27890060.5853 | 212649347.2239 | 313484883.6404 | 448110155.1591 | 115519436321.8861 | 1965659648.5201 | 1823244700.6959 | 2138181562.0613 | 199126885.2339 | 592569276.5306 | 634866815.9567 | 745875760.3619 | 283375647.6825 | 613642836.081 | 20770332.3515 | 92475891.2602 | 23800746.4166 | 20479151.9221 | 899911048.1947 | 25476847.2021 | 997888783.7523 | 7305000688.2194 | 682195993.5082 | 187257867.7481 | 1.8518e+12 | 2844269.9851 | 951718.3387 | 1630011.2065 |  |  | 1.9913e+12
875 | 1095352854.4922 | 1163551390.3137 | 202281336.1827 | 164646444.6441 | 1085444195.1846 | 22730208.8313 | 209624546.5587 | 329362916.3124 | 493231295.7611 | 141720070745.6422 | 1557681105.6674 | 2069578212.5047 | 2186141985.7232 | 201900959.9542 | 592454480.7804 | 653722187.7461 | 770704197.2838 | 336233970.465 | 615565815.8607 | 24781745.7722 | 119625792.1305 | 21537565.4561 | 22977787.0257 | 858630384.1739 | 29458010.125 | 868540904.9603 | 7055617494.2682 | 548288441.2406 | 182272565.1315 | 2.0102e+12 | 2642345.7085 | 969047.3406 | 1491700.8074 |  |  | 2.1754e+12
876 | 1249016911.8504 | 1011798989.6351 | 216190764.5555 | 165941683.1846 | 953662131.5599 | 18916783.1337 | 188854569.8308 | 330885401.6513 | 451128961.4999 | 98683842404.0243 | 1822518916.7023 | 1931124936.0834 | 2169323397.5116 | 171034952.3852 | 564618344.6667 | 682327800.5728 | 788986461.9835 | 332340725.411 | 609129281.2063 | 21365588.5412 | 134139538.9222 | 20734498.5144 | 25327876.2201 | 821375175.7418 | 21400582.6467 | 1130933062.9949 | 5035170552.4359 | 684300545.3107 | 194176724.9687 | 2.0324e+12 | 2706284.2819 | 890884.358 | 1854412.5963 |  |  | 2.1528e+12
877 | 1225554937.236 | 1220928651.1584 | 202518536.5082 | 159598499.3598 | 986620497.1136 | 22501490.648 | 192694489.0674 | 308556669.8673 | 478229478.438 | 132191665167.4783 | 2025762509.9141 | 2076269269.4217 | 2114429931.7023 | 185618873.8527 | 587767432.6286 | 644108612.0278 | 715544616.2462 | 270470461.0253 | 481935376.1832 | 25360432.7702 | 116385248.6902 | 19168620.3491 | 25838338.1677 | 862430405.4943 | 30823265.1197 | 1068574590.8746 | 6546617417.382 | 566146819.6788 | 169060290.72 | 1.7061e+12 | 2720759.6762 | 922343.5354 | 1703597.7256 |  |  | 1.8616e+12
878 | 1133374385.1062 | 1116598404.7214 | 198244873.6087 | 155953341.502 | 1056458347.6736 | 24767909.0817 | 215395250.0535 | 299845653.8412 | 486085920.0028 | 127715474523.1971 | 2063932007.3932 | 1725621977.1931 | 1949067711.0515 | 186500474.1921 | 579473589.5759 | 686771216.2942 | 902898730.5334 | 274285428.7088 | 588018534.2631 | 23612026.8576 | 116813146.5294 | 20330004.4075 | 25367364.3253 | 833473010.6929 | 23937282.678 | 1115280218.7973 | 6400134864.0482 | 581348444.3352 | 181370943.5944 | 2.5584e+12 | 2237877.8761 | 905556.7738 | 1731867.591 |  |  | 2.7091e+12
879 | 1147812871.8585 | 1033344473.3291 | 204037793.5329 | 171030113.7674 | 864204134.1884 | 25169702.2302 | 216670082.7651 | 326582334.1678 | 451017283.9802 | 136452727479.3535 | 1949744650.4937 | 2044601746.9876 | 1858812109.9164 | 194800592.7115 | 599056312.5181 | 649393458.7339 | 876637551.6224 | 343878947.9233 | 611396574.2237 | 25866124.2121 | 114753880.955 | 19139200.9135 | 24350511.3463 | 745698849.7939 | 31060429.8152 | 1077051769.7226 | 6597272162.8123 | 619475847.9773 | 186030275.5534 | 1.9295e+12 | 2368370.4658 | 980501.7328 | 1707088.0566 |  |  | 2.089e+12
880 | 1224953337.2446 | 1172941933.3851 | 218806210.8726 | 174767070.51 | 1048694021.2593 | 21470300.3837 | 215593861.668 | 330397406.3584 | 485441571.7137 | 132118345217.0819 | 1786117508.5166 | 1637712573.6452 | 2132234535.4054 | 176882730.1621 | 621367898.3918 | 696102199.117 | 881188065.3504 | 297190649.6274 | 541248817.7005 | 20484460.0746 | 119029124.7535 | 20226948.2907 | 21912932.6111 | 822858425.9325 | 28686723.2083 | 1036753585.2196 | 5440350782.6965 | 660021484.3877 | 176074341.9626 | 2.4061e+12 | 2263104.8027 | 936357.1149 | 1699981.2739 |  |  | 2.5603e+12
881 | 1208577765.8097 | 1213987734.6137 | 213236491.0388 | 173349294.6349 | 1079013772.9052 | 20640971.1368 | 217996316.1181 | 320290662.6405 | 434717325.6189 | 134216418237.7015 | 1821995859.563 | 1691711929.1441 | 1956176632.3995 | 185405618.5126 | 609768483.1448 | 668935405.1967 | 914974026.1376 | 331037671.6203 | 585416835.8776 | 26847252.8174 | 108263430.4218 | 22705283.6673 | 24336071.603 | 917360779.4983 | 29660390.2809 | 1092156224.7639 | 5060960600.8798 | 621479837.9226 | 159392157.1853 | 1.6696e+12 | 2177119.7858 | 909296.3814 | 1631321.0563 |  |  | 1.8255e+12
882 | 1178019388.481 | 1038178497.1284 | 197251610.4419 | 176764392.8832 | 1011910009.7097 | 27564155.4012 | 199126124.4888 | 324332595.8555 | 499427848.6592 | 142973284255.7282 | 1801359474.6189 | 1602270594.6534 | 2189037048.3102 | 182880470.3793 | 656595841.923 | 670294911.054 | 877735586.106 | 285993827.115 | 612671773.2548 | 26191446.7719 | 125873276.9337 | 24382936.0923 | 23597730.1358 | 868300570.981 | 28206074.5715 | 983552212.6645 | 6654711674.5132 | 609965302.406 | 196711898.0433 | 1.863e+12 | 2452387.6522 | 935661.9578 | 1647761.6923 |  |  | 2.0291e+12
883 | 1224587783.7173 | 1222614512.1845 | 216285613.2974 | 167224946.1935 | 1039861839.5022 | 24863290.6941 | 221610784.1615 | 287671280.8031 | 490048550.5906 | 160006523283.6194 | 2025211472.258 | 2028593238.3361 | 1799905766.3791 | 194682557.9781 | 575437407.4265 | 620713325.6749 | 740408227.8854 | 241159029.5785 | 581831985.5726 | 24502156.596 | 121565838.5922 | 21586994.9259 | 24090328.3718 | 886585000.7849 | 26470932.0789 | 1132558653.6654 | 6650198866.6256 | 597806873.0962 | 201755716.3588 | 2.3068e+12 | 2596542.6939 | 939010.9264 | 1690619.1224 |  |  | 2.4902e+12
884 | 1171254174.8435 | 1141348103.4607 | 197976633.0355 | 169932878.4272 | 1034636003.2561 | 21704206.7773 | 205522134.7189 | 320364245.7252 | 435497060.2971 | 142300677404.8314 | 1920224732.8257 | 2104103040.196 | 2149460579.1185 | 168069840.9209 | 621659942.0041 | 658888165.1026 | 776704990.0139 | 342822600.0912 | 564033533.7286 | 25422665.0243 | 129001832.0353 | 22084157.0735 | 24930630.1865 | 840146798.0991 | 28448634.9545 | 1086973573.093 | 6293327518.222 | 609400008.1114 | 180941661.3903 | 2.4301e+12 | 2530783.6148 | 965365.1313 | 1551374.048 |  |  | 2.5957e+12
885 | 1139785912.8907 | 1122720392.7574 | 220929138.4642 | 166908098.6376 | 874238167.2199 | 24132031.5766 | 184696548.3589 | 324268639.9116 | 478317600.7115 | 142490175078.6498 | 1611543134.789 | 1837798050.7119 | 2078400956.1689 | 171296662.3529 | 660541356.646 | 668921155.1817 | 813410905.5292 | 329924831.7852 | 615773704.145 | 23913216.4139 | 99471441.8356 | 20006584.3822 | 21008163.0083 | 798311297.332 | 29037926.2955 | 1100284249.4914 | 6553920998.8591 | 652965459.7345 | 192932522.3376 | 2.2827e+12 | 2368006.2484 | 919274.4227 | 1724712.4282 |  |  | 2.448e+12
886 | 1153244296.1762 | 1015878381.7527 | 209501568.56 | 162728778.734 | 1080821931.1653 | 25688105.222 | 214424512.3011 | 290641038.0321 | 496322463.5912 | 138624412296.4307 | 1891719401.067 | 2198723663.5447 | 2044894371.061 | 171343443.2023 | 669649678.6556 | 721321955.6795 | 839414859.6258 | 299203812.8456 | 533879101.487 | 25006369.5116 | 122516582.0837 | 24353192.4933 | 25879443.4325 | 844624460.2349 | 26092809.8443 | 844316819.4046 | 6702998115.1184 | 668151974.9752 | 188635539.6412 | 2.1124e+12 | 2634745.2255 | 982135.1015 | 1538521.1923 |  |  | 2.2745e+12
887 | 1223956258.0275 | 1200554489.4995 | 208750371.5974 | 169953069.3172 | 1073990975.3204 | 21083706.8521 | 195729079.3228 | 319015986.9565 | 469239582.1438 | 144153081313.7583 | 1628453049.6961 | 2049815817.449 | 2076028848.5804 | 191111514.5504 | 562365771.63 | 657180701.042 | 894017518.7222 | 305531315.4067 | 511712471.7179 | 19495769.1792 | 124619234.2453 | 20401765.009 | 26033619.5719 | 785496976.0428 | 24487514.6885 | 1163230543.0072 | 7228404666.1894 | 695971550.4056 | 198754293.3286 | 1.6749e+12 | 2871600.1022 | 973968.5139 | 1552243.9604 |  |  | 1.8431e+12
888 | 1101699244.8262 | 1211660290.9504 | 206766898.522 | 179408661.7447 | 1078448639.108 | 26899701.208 | 213295183.7312 | 321383013.7077 | 434824215.1128 | 138890204419.3894 | 1974382280.3997 | 2168724600.6034 | 2143614803.2898 | 163856623.065 | 653171330.6496 | 665659212.2189 | 933046649.311 | 320540050.9682 | 575644971.2528 | 26622488.402 | 135484150.1578 | 21912393.37 | 25043530.0618 | 940693153.9091 | 24574670.9753 | 886126361.7049 | 6637357329.9781 | 699528053.4127 | 175711859.5409 | 1.7757e+12 | 2485997.3615 | 905601.9411 | 1598641.6837 |  |  | 1.9386e+12
889 | 1197447142.6773 | 1196009658.015 | 226931946.0194 | 177859673.8341 | 1061751865.0971 | 26981847.7768 | 212172583.3568 | 292444750.7742 | 459790284.5282 | 128878071843.3504 | 2064774803.922 | 2104122144.3 | 1734690336.4403 | 196441000.1877 | 632489141.1825 | 597058581.1857 | 872361304.8179 | 240333750.9801 | 491888053.0431 | 26940618.2594 | 113460627.2702 | 24455954.7086 | 24731111.3213 | 878628496.5897 | 28722546.3557 | 1115340111.8412 | 7194148302.1301 | 646364851.2771 | 191605809.1324 | 1.8125e+12 | 2299103.0223 | 921030.3721 | 1554852.1061 |  |  | 1.9654e+12
890 | 1248218372.0108 | 1187235118.8753 | 217327036.848 | 161169229.0684 | 1066753756.0889 | 23203127.8258 | 212375733.2632 | 316503451.947 | 497349278.8386 | 132518096590.0505 | 1625939776.9127 | 2118650417.7164 | 2001427245.2861 | 190289139.8578 | 528256870.5678 | 710187911.8129 | 927295200.0094 | 342974747.5793 | 587730999.6312 | 19201771.4813 | 110951265.9799 | 18019929.3167 | 23704167.8758 | 803589927.4485 | 30009316.4465 | 1103802573.735 | 6013000533.259 | 443805123.5713 | 183945347.356 | 2.3282e+12 | 2689891.5026 | 955367.801 | 1582550.2277 |  |  | 2.4834e+12
891 | 1194822483.5215 | 1102085033.8152 | 192778864.6511 | 158417141.8163 | 1035785596.0856 | 23895993.4363 | 210087178.2075 | 313880972.8036 | 441717708.5719 | 145956959313.7156 | 1965366938.8532 | 1978948029.8905 | 1952128283.7919 | 187394712.4023 | 592686846.713 | 655145175.6693 | 792486467.6758 | 254050842.8058 | 554424451.8232 | 26782804.9387 | 111873536.2509 | 22592290.3258 | 25641899.0523 | 845839510.4411 | 26701097.1695 | 1109740808.8117 | 6092910148.4344 | 525089591.0772 | 142804939.1527 | 1.8776e+12 | 2670448.8147 | 992451.5401 | 1746465.2824 |  |  | 2.0461e+12
892 | 1089579170.7433 | 1197865741.5188 | 208493014.0793 | 168233696.0406 | 1049228752.7273 | 22540014.2369 | 221969640.0108 | 325173414.692 | 499183873.2994 | 152447029364.9751 | 2003363754.7051 | 1949528492.4284 | 1981566129.7759 | 162122436.0989 | 623972411.1496 | 664257514.0032 | 807040494.5042 | 305670963.592 | 614147604.3762 | 26732449.7205 | 95552945.0073 | 17479014.4912 | 23211778.9602 | 736246781.8847 | 27576815.26 | 957637915.1774 | 7101096466.699 | 703664935.0893 | 170820914.7305 | 1.9904e+12 | 2230576.5451 | 962220.6174 | 1810806.1005 |  |  | 2.1666e+12
893 | 1241232196.604 | 1066505820.4507 | 196573319.241 | 148941979.5096 | 1030504310.3369 | 22385920.112 | 200676997.73 | 320288567.6667 | 462883427.426 | 143537639411.1292 | 1964930158.7339 | 2006528409.198 | 1801918679.2422 | 170141905.7008 | 644253343.7735 | 602151005.6012 | 653009621.3803 | 252188194.7972 | 558677703.8847 | 26097330.7908 | 111455872.9226 | 22174234.0342 | 25047261.6428 | 596478662.6052 | 22978813.6201 | 1136319677.0061 | 6854086081.5374 | 579852500.7308 | 167212570.7066 | 1.9772e+12 | 2416375.6734 | 1012994.639 | 1635835.6897 |  |  | 2.1436e+12
894 | 1244831518.5202 | 1155712381.8954 | 224128078.3648 | 175090007.8158 | 1087547532.2932 | 19603267.6733 | 222994719.1116 | 320987237.8344 | 425514997.4542 | 135541523142.3769 | 1791776896.3968 | 2124667933.6288 | 2117095024.3932 | 193998474.1252 | 593107714.5279 | 721412260.5504 | 809934686.9258 | 287856320.9865 | 578775405.3468 | 22272379.272 | 103189233.3877 | 17850057.7576 | 22267859.4756 | 812226958.642 | 26529429.1248 | 1003478644.5442 | 5837957478.8611 | 508227144.4731 | 191917132.6338 | 1.985e+12 | 2344361.6742 | 955335.9982 | 1493748.1933 |  |  | 2.1432e+12
895 | 1213645861.0258 | 1112264667.0712 | 224097235.5672 | 164726310.4733 | 1073182043.1081 | 24831233.5456 | 220484097.1044 | 299308971.3628 | 489048907.7566 | 130392979820.7119 | 1760692934.0838 | 2071904712.6311 | 2099491521.4232 | 199746502.9563 | 590921600.8664 | 534026633.8397 | 827057820.8894 | 293224813.6412 | 594487458.9393 | 26441097.8032 | 120752358.6782 | 18833588.593 | 24758532.6381 | 833041918.1097 | 31326464.6835 | 1169903461.7517 | 5991089928.5835 | 576192635.8134 | 181796714.8013 | 1.6889e+12 | 2280746.0784 | 982066.8842 | 1752753.8835 |  |  | 1.842e+12
896 | 1260447049.0616 | 1038446487.9179 | 206237115.8395 | 152040158.7439 | 976055598.3309 | 19191987.0067 | 217250795.2713 | 319285479.4498 | 495650983.1434 | 148298356516.8733 | 2081357508.3038 | 1648997949.4492 | 2160774561.8415 | 201843202.684 | 509116937.0188 | 660306866.0612 | 747931904.0221 | 275865614.9345 | 465158705.2784 | 26916646.8893 | 108095332.1756 | 19421197.636 | 24102235.6306 | 924722518.3316 | 27014090.195 | 950579514.0285 | 6220914074.1955 | 638898538.8006 | 189195237.0723 | 2.0841e+12 | 2353467.0676 | 922268.9974 | 1587073.3864 |  |  | 2.255e+12
897 | 1131205535.9436 | 1179307302.6816 | 211131085.8478 | 175178451.7995 | 897273106.7043 | 24655989.0964 | 211455912.2733 | 311226717.6418 | 472586823.1751 | 145168293164.4265 | 1976905856.282 | 1944600093.7672 | 2211625141.0691 | 155537035.7703 | 672208827.4855 | 598722532.0149 | 791828468.6853 | 349278572.6618 | 601670666.2591 | 23753490.0563 | 97108659.2716 | 23352091.0365 | 24380889.9114 | 848859685.8286 | 28013366.5078 | 1112583705.5953 | 7046897665.105 | 509312812.9423 | 195705031.0692 | 2.1158e+12 | 2503770.5482 | 937796.9398 | 1622687.3512 |  |  | 2.2848e+12
898 | 1212136048.1876 | 1116681105.8584 | 185507813.0616 | 155807905.8843 | 1062630330.7478 | 20872368.5508 | 204180810.9056 | 322732825.2956 | 462991610.8624 | 145524627980.7675 | 1895770957.1379 | 1897785218.383 | 2194511198.7351 | 181975033.3899 | 562539817.3527 | 607454090.5447 | 868640151.9334 | 273700182.2953 | 595643833.5167 | 24918819.9743 | 124008252.1263 | 18636655.1508 | 24668706.6272 | 841493333.9317 | 29964132.5108 | 1142867602.3649 | 6040894947.3468 | 622907183.7156 | 189520527.686 | 2.4804e+12 | 2330700.7811 | 887974.1013 | 1604370.169 |  |  | 2.6488e+12
899 | 1204892843.3836 | 1174814158.8883 | 225319696.7827 | 168215344.005 | 1051240106.6455 | 21541401.939 | 202501568.4253 | 304299623.3376 | 460018237.0738 | 116508082924.1801 | 2060067860.094 | 2152605005.3554 | 1950867711.0092 | 158716320.9594 | 670801938.0485 | 629897318.299 | 731160581.6103 | 333715582.0621 | 552604842.7815 | 24864312.9871 | 113876289.0414 | 21085331.1248 | 19166331.653 | 792647731.5319 | 23126865.4601 | 1134477128.1263 | 6240974868.4012 | 684595525.5893 | 184004080.0248 | 2.614e+12 | 2455496.9701 | 968054.001 | 1573224.0337 |  |  | 2.7538e+12
900 | 1180060238.2277 | 1111089493.6364 | 214968056.0853 | 170513664.3094 | 962649196.8467 | 20421423.1571 | 194741286.4659 | 321403514.874 | 477926615.3421 | 138627230848.5386 | 2076510741.2585 | 2144896069.6102 | 2093012403.2599 | 194730525.1582 | 564099261.014 | 661524980.7832 | 859690534.9696 | 248131408.2056 | 576223589.7485 | 21774196.9183 | 104019407.9473 | 22742912.8644 | 22318044.4344 | 850631744.1601 | 28107418.8921 | 1180819016.9839 | 6160939351.4419 | 706540214.7652 | 158479209.5687 | 2.1104e+12 | 2535481.8487 | 990049.6093 | 1569294.4223 |  |  | 2.2724e+12
901 | 1249445677.6122 | 1223940590.266 | 202357928.2193 | 165669760.2659 | 1055255873.6383 | 19686659.3539 | 201733773.4066 | 321683057.3168 | 444645944.233 | 148647212930.8576 | 1753212890.4741 | 2042758489.4807 | 2187053523.8703 | 181881917.6211 | 646330069.4739 | 684801123.6342 | 700891107.2909 | 306396644.6023 | 594995843.64 | 25508074.7463 | 124183245.4726 | 19427173.3682 | 24652530.8072 | 894430719.9163 | 28358231.0088 | 1190348581.9914 | 6286374132.0019 | 711348852.9756 | 172291355.9199 | 2.6987e+12 | 2499214.2619 | 992765.8846 | 1744777.4847 |  |  | 2.8708e+12
902 | 1157565317.1697 | 1174321544.2149 | 191871516.0014 | 153030530.6874 | 1055533568.8805 | 24390237.2624 | 225118730.0559 | 279179643.2048 | 466733232.527 | 154008024683.0735 | 1944294404.9792 | 1798355500.3921 | 1922546843.713 | 188216695.0677 | 500268305.7734 | 597912153.348 | 790773302.2095 | 357268500.2675 | 525560562.8189 | 20198949.1899 | 100241861.8275 | 20268388.8038 | 24401847.122 | 857587017.3806 | 27627565.5497 | 1133621613.5524 | 6091990623.8356 | 582412251.01 | 188155206.4041 | 2.031e+12 | 2333675.2182 | 893832.3736 | 1683627.7317 |  |  | 2.2074e+12
903 | 1234116213.0126 | 1071486456.5304 | 217755006.0508 | 164400415.3299 | 966310431.689 | 26038369.6283 | 221655762.1231 | 291092398.1871 | 486328806.074 | 137035311993.5658 | 2009198949.5137 | 1957391876.8315 | 2106149148.4036 | 192867124.7417 | 592576257.9508 | 662962808.8915 | 821632907.9474 | 342913366.778 | 572096410.1791 | 26571532.1205 | 134617373.353 | 23741894.6474 | 23221400.7237 | 747007018.6279 | 25086640.8914 | 1206546495.5797 | 6054327895.6233 | 654678360.8555 | 197892821.1258 | 1.82e+12 | 2487429.3898 | 927287.9624 | 1538478.769 |  |  | 1.9801e+12
904 | 1170262754.5441 | 1202463833.0965 | 210044259.0396 | 179666129.7155 | 1082557102.6935 | 22790553.4983 | 217262695.2507 | 317665431.8206 | 493579489.4735 | 156566825650.4991 | 2053929352.7483 | 2077639847.632 | 1926874568.0109 | 188772518.5312 | 649033219.358 | 564225504.603 | 878565474.0855 | 265620668.4628 | 528853722.4409 | 23143609.1897 | 120545186.4916 | 19382428.8691 | 20659070.7104 | 692758557.3086 | 27578963.1193 | 1204101376.5519 | 5378500647.7496 | 538222662.7752 | 171417193.2627 | 1.9179e+12 | 2568758.1375 | 963171.6551 | 1526364.5172 |  |  | 2.0966e+12
905 | 1220584966.4189 | 1140116635.6767 | 215488352.2034 | 138467067.5264 | 1055163318.2559 | 19756746.2466 | 211137617.2074 | 321365718.8819 | 467154602.3866 | 134031761575.4215 | 2063886242.973 | 2151663994.3943 | 1674949439.7931 | 190095848.4603 | 645423329.0112 | 641593157.2893 | 760047399.1788 | 330697075.6708 | 575155822.1097 | 27439139.9698 | 102199909.6957 | 18538459.2955 | 23447825.7409 | 860538283.9244 | 22584507.679 | 1162086264.3258 | 7040876125.3533 | 654278778.6638 | 198646026.5971 | 1.7031e+12 | 2691702.0499 | 971159.7182 | 1548408.0598 |  |  | 1.8611e+12
906 | 1226068870.4945 | 1193352900.3299 | 205639682.0051 | 169051653.2646 | 1032472265.6501 | 26597867.1592 | 215190231.8929 | 274756232.8264 | 471614543.3602 | 134370270687.2423 | 1990917259.8706 | 2132025603.5758 | 1476619351.0815 | 192695414.1339 | 628697682.0354 | 709552507.8278 | 628644146.5433 | 285482378.206 | 585838055.2979 | 22530557.1349 | 102491954.2851 | 24659760.0626 | 24996753.3416 | 669776025.6969 | 28884429.4713 | 1152462113.3149 | 6302770521.7132 | 645006120.175 | 174503293.3964 | 1.6594e+12 | 2428688.0262 | 1028942.946 | 1736896.9089 |  |  | 1.8163e+12
907 | 1228917717.4028 | 1059516884.3206 | 204946531.3367 | 169744628.1215 | 1037417773.3627 | 23309986.6455 | 212167131.5563 | 294742242.2554 | 425060114.3354 | 146326953910.716 | 1892077540.8006 | 2008354399.8286 | 2125886478.6704 | 197845243.4014 | 543034735.0912 | 548776503.7112 | 712224346.7895 | 341515353.4521 | 601715793.287 | 22604078.48 | 123310410.7981 | 21270935.7895 | 25378486.9516 | 816068308.4143 | 31936495.8938 | 1070281233.9855 | 6843057765.4919 | 579458868.5815 | 189238890.169 | 2.2144e+12 | 2488802.2698 | 986484.0784 | 1617643.8944 |  |  | 2.3841e+12
908 | 1067967931.0002 | 1205961249.1014 | 189803554.4895 | 154355833.501 | 1086431518.655 | 22140093.4856 | 214845690.3532 | 307642801.4219 | 470392983.6341 | 162741249354.7233 | 2043232481.087 | 2034641750.1079 | 1997878710.9132 | 183080606.7885 | 537678479.6138 | 669972844.4957 | 696277829.1525 | 358719207.8296 | 559674289.3897 | 24896504.6835 | 121061936.0566 | 22439679.7108 | 23673803.8922 | 952280374.424 | 24433278.3335 | 845238930.1606 | 6878877880.8998 | 638712060.021 | 177351219.8666 | 2.5388e+12 | 2420602.3904 | 954946.4912 | 1767294.6456 |  |  | 2.725e+12
909 | 1190693792.8556 | 1077151767.2139 | 220901212.7226 | 182236742.4224 | 1087419481.8147 | 23999218.2591 | 211400579.1488 | 327519493.2632 | 447783466.6383 | 137477865236.2756 | 1988011662.8652 | 1923991356.4597 | 2047097105.4988 | 201645597.8164 | 637791521.4127 | 563238432.7584 | 804492275.0178 | 324673027.5274 | 554968788.8264 | 22029548.8089 | 109988149.9009 | 21941818.5619 | 23766913.3147 | 892964926.4206 | 25692292.9876 | 1102490074.1716 | 6156551542.5988 | 568687978.3627 | 192886910.902 | 1.7342e+12 | 2355638.6982 | 996329.3436 | 1808157.9961 |  |  | 1.8946e+12
910 | 1226694582.8915 | 1204648630.6219 | 207149837.0463 | 172510941.3136 | 1024126596.9159 | 26799831.9889 | 191877920.2185 | 314311046.0846 | 447376824.6881 | 140130691026.9471 | 2079239039.8988 | 1925243550.8652 | 2183727212.7314 | 180027004.9512 | 531191788.621 | 705026473.9702 | 799052038.4389 | 301916124.968 | 455398817.7359 | 26479538.0675 | 116148153.7343 | 23278102.9627 | 22049526.7666 | 759875724.2864 | 26996609.0618 | 1199005871.2191 | 5922120246.0758 | 671516712.374 | 187490208.0278 | 2.1992e+12 | 2359880.6196 | 917135.1005 | 1706356.2495 |  |  | 2.3622e+12
911 | 1021792512.4537 | 1119561198.1459 | 201757566.9177 | 168129193.4171 | 1062133276.589 | 23908844.7723 | 196785295.8261 | 304237180.544 | 476970174.0299 | 131662876273.7491 | 2040412509.6913 | 1937739842.6717 | 1780950709.8413 | 178482693.6154 | 554082331.017 | 694914226.4003 | 858351330.3094 | 327160558.5774 | 452349265.5191 | 26489355.9488 | 120076070.634 | 24196036.0097 | 24515993.3554 | 689756615.4582 | 27313691.9561 | 1141727669.4996 | 5962190555.5356 | 667384434.8292 | 171315364.7528 | 1.8851e+12 | 2283620.6175 | 903102.3361 | 1647268.0285 |  |  | 2.039e+12
912 | 1190387681.2237 | 1122996058.4883 | 215755749.3193 | 165855942.1616 | 972044778.3333 | 25514051.9214 | 189924506.2707 | 324602440.4537 | 423489018.6989 | 143457052182.6766 | 1868902722.2917 | 1605839257.3253 | 1661981952.3004 | 152886589.1299 | 601153418.527 | 719774239.2714 | 823502148.5262 | 325600947.6511 | 528851830.8844 | 21594848.8352 | 126797118.1916 | 20924391.2152 | 22346687.832 | 944540813.4862 | 29450239.3515 | 1081868777.7923 | 7070163805.5128 | 568309316.8809 | 199978766.7855 | 2.3085e+12 | 2288178.9388 | 894598.9617 | 1656515.3298 |  |  | 2.475e+12
913 | 1151721910.0832 | 1208156371.2553 | 213406524.1293 | 162560280.1354 | 1025652872.2051 | 22744841.804 | 202237197.6816 | 307735734.3614 | 433888211.2596 | 153320877673.9448 | 2052922513.6451 | 2154563321.5194 | 2124230504.9559 | 177348508.5689 | 651996147.2602 | 564053151.4848 | 772914663.055 | 292476635.6282 | 589372235.6404 | 27631546.9503 | 94258266.9889 | 19603777.6718 | 25062570.7805 | 879896969.4822 | 28912500.5181 | 981155349.1802 | 5797790505.1003 | 501407964.3131 | 179702012.748 | 1.8669e+12 | 2520262.0736 | 926071.5342 | 1551638.3826 |  |  | 2.0429e+12
914 | 1221401280.6216 | 1156959577.9503 | 223519511.5994 | 160485369.4517 | 1085093518.4925 | 22684272.9351 | 220064253.4718 | 324941567.8233 | 475996147.3307 | 159567072064.9807 | 2088033042.167 | 1809495461.9896 | 2134834438.5236 | 200008605.8226 | 649294560.0542 | 651502485.673 | 911867075.5018 | 243537303.3726 | 492939337.3266 | 20879025.7929 | 104116274.7317 | 23303853.7075 | 25895926.6471 | 856623158.7419 | 28891712.9862 | 1126966699.2589 | 6694088129.0864 | 621812306.0745 | 183810588.6075 | 2.0051e+12 | 2625349.9052 | 966395.503 | 1705544.5286 |  |  | 2.1884e+12
915 | 1055796128.7709 | 1217228097.4595 | 190289767.9128 | 175226601.0922 | 947290923.5561 | 19898616.8857 | 208735664.1955 | 284648646.0481 | 479319061.87 | 158173724848.448 | 2069165611.4598 | 1920581412.2979 | 2045980478.3581 | 148136833.9117 | 634111046.0348 | 626238192.203 | 906310743.702 | 348337792.5266 | 573489415.0004 | 25890032.5316 | 109650229.887 | 20519222.5579 | 24192744.53 | 849622601.0345 | 20108275.0632 | 1082386541.1587 | 6917596787.9192 | 700874287.7237 | 200833344.4973 | 1.5445e+12 | 2665403.7059 | 946627.261 | 1600096.7539 |  |  | 1.7265e+12
916 | 1110773980.0272 | 1201918856.8897 | 212560777.2921 | 169933635.149 | 1016652768.8948 | 23518735.4462 | 210542661.2931 | 309281390.2942 | 489770965.1842 | 149753391597.0927 | 1987967544.1329 | 1745436952.5765 | 2211229250.8207 | 193513520.7585 | 598386266.7668 | 628628555.6208 | 935886907.3124 | 289612106.5199 | 595895876.0554 | 25783617.3927 | 116184483.559 | 24830113.742 | 24980092.7996 | 928045027.9341 | 28513558.0532 | 921791508.2236 | 5467547642.3949 | 647179075.3346 | 194342823.2991 | 2.3322e+12 | 2482227.3267 | 944788.3111 | 1658338.8192 |  |  | 2.5042e+12
917 | 1132231675.7086 | 1027132939.5733 | 209627638.6774 | 153318760.4333 | 1051730836.1736 | 20796239.6469 | 209031593.5457 | 289398727.7106 | 488641202.6412 | 149784244039.2863 | 1966284238.7026 | 1958074929.7707 | 1734757473.7781 | 189027631.6254 | 601138437.7337 | 714429408.372 | 824132603.9061 | 288553481.04 | 554400494.427 | 23414869.7598 | 131523014.0836 | 19595416.8421 | 24345590.6993 | 859250299.9252 | 25930848.1339 | 1174901766.8921 | 6558048161.152 | 700774372.7356 | 168489418.2185 | 2.0496e+12 | 2350543.8253 | 1033281.2139 | 1675621.9162 |  |  | 2.2225e+12
918 | 1187392916.2784 | 1104746515.4289 | 202715437.9482 | 175294524.2582 | 1074600882.4154 | 26237657.3822 | 225453911.8089 | 320951092.9171 | 488529954.8464 | 157132240174.4387 | 1904331960.2005 | 1996940446.5045 | 1879186768.4058 | 190263699.6747 | 650607156.4741 | 702456869.4524 | 824521707.7058 | 312239216.052 | 482624151.4543 | 23851199.7843 | 120410800.9311 | 24861385.359 | 19879771.2599 | 868202054.0201 | 27716297.112 | 1022736564.939 | 4993422248.2062 | 632676899.5252 | 176153707.9985 | 2.0835e+12 | 2618552.5719 | 978323.3141 | 1702372.5895 |  |  | 2.2623e+12
919 | 1218416301.8543 | 1189203517.1992 | 201624916.7033 | 170371273.3061 | 882421753.6151 | 24043584.7082 | 195572237.896 | 294919917.9073 | 477629338.8414 | 149557838615.707 | 1802744120.1667 | 1808572096.9509 | 2100579360.0003 | 195482303.7727 | 543507745.3301 | 615096998.4567 | 870556812.9431 | 276759124.3477 | 586080734.1407 | 24630941.9808 | 122482975.489 | 20300294.5072 | 26061886.2508 | 925011905.5504 | 29072670.6651 | 1172798147.808 | 5631390696.1438 | 678748319.1508 | 192973678.9408 | 2.337e+12 | 2309587.7124 | 1034934.4762 | 1668656.4308 |  |  | 2.5088e+12
920 | 1176244240.5044 | 1186734111.8762 | 195707988.6286 | 179585034.6636 | 1031832863.1332 | 24930445.2463 | 205556396.7309 | 311465918.0756 | 498533818.9605 | 156556892320.6557 | 2028896721.4434 | 2176187115.5071 | 1927681237.1508 | 202361760.2329 | 604532726.0423 | 665520988.5902 | 844585451.6369 | 315730770.0943 | 562403874.4765 | 22560078.3022 | 112934461.8578 | 22792949.467 | 21486117.3554 | 940650477.4488 | 31455424.2645 | 977589148.9784 | 5896027450.6761 | 632287146.481 | 166128858.2727 | 1.6965e+12 | 2375515.074 | 1021009.9165 | 1584731.2227 |  |  | 1.876e+12
921 | 1150620060.752 | 1218523936.1715 | 220582432.4194 | 159637639.0114 | 1072302481.3364 | 25160760.6926 | 180823583.2296 | 316829498.0158 | 456982298.4748 | 134014865070.8249 | 1926696751.4961 | 1829209426.1644 | 1896765007.5093 | 165130559.9972 | 695498570.3001 | 652251753.808 | 768977097.908 | 347274992.5106 | 560206284.9908 | 24778690.109 | 123637649.8165 | 23932633.4718 | 21342472.5912 | 755453443.792 | 28244762.1089 | 1109471727.0641 | 6862737299.9295 | 704550253.1812 | 155826849.3912 | 2.6118e+12 | 2653280.2893 | 904588.3994 | 1681346.1213 |  |  | 2.7693e+12
922 | 1198384943.4732 | 1127805567.4995 | 214235415.9826 | 138004555.7266 | 1007378334.8141 | 23338277.7641 | 217698328.1286 | 322287843.4876 | 406676379.7999 | 154889356264.704 | 1737396677.6624 | 1905911373.1033 | 2119736179.1722 | 163222652.0699 | 601552811.1273 | 722385390.9305 | 681390934.5839 | 323405518.8505 | 591833303.5088 | 23961650.8138 | 121086163.8536 | 21399629.3376 | 23027182.2949 | 739226221.4404 | 20489780.2665 | 795780706.0807 | 7075135493.4101 | 690726426.577 | 193551406.5901 | 2.3587e+12 | 2671553.4989 | 983152.34 | 1553753.7109 |  |  | 2.5368e+12
923 | 1179206592.4454 | 1203249243.6477 | 222031589.7592 | 174468775.6509 | 950796218.4143 | 25004538.6641 | 209800580.1798 | 268676060.6645 | 483116507.3342 | 121732619348.3694 | 1863051362.0589 | 1996005826.2553 | 2130422373.5543 | 201575890.8481 | 592289583.4882 | 712624832.5831 | 786372049.5879 | 296036909.2397 | 554623899.0929 | 27465491.5856 | 126192141.9918 | 21662158.0548 | 24326184.0582 | 760715804.4698 | 30647143.2477 | 1102682563.3994 | 6158164584.0191 | 489268880.6416 | 179377632.3183 | 2.4572e+12 | 2634154.9372 | 914343.1567 | 1687231.232 |  |  | 2.6017e+12
924 | 1203941568.2793 | 1219231497.4094 | 189977109.5257 | 166470811.9482 | 976960726.2775 | 22756872.0358 | 188389072.8339 | 316584020.8951 | 468300270.2768 | 160393499518.9327 | 2036002815.3805 | 1804891330.6775 | 2160081395.6582 | 195392372.4394 | 642636460.9101 | 660945022.9319 | 734007142.4089 | 260488044.6673 | 614022605.6881 | 21887146.9193 | 132734068.7386 | 24184756.6876 | 24285099.3555 | 942196879.3887 | 25656324.4983 | 1060497225.3998 | 6112452067.9381 | 669395842.0788 | 200107576.2034 | 1.9773e+12 | 2667213.2085 | 973346.5185 | 1734882.0067 |  |  | 2.1608e+12
925 | 1182631066.6808 | 1221623237.999 | 225511049.2047 | 176005789.9657 | 875499373.2823 | 25688651.3212 | 196504500.1727 | 314336222.4375 | 463297299.1734 | 153940053959.6568 | 1767830614.2956 | 1981969933.7179 | 1864398861.3374 | 175786272.2663 | 592428119.2634 | 711775303.2568 | 765761934.96 | 311426036.4453 | 576275137.2864 | 20177532.1384 | 119596233.7376 | 24599691.1874 | 23036044.768 | 856751860.2353 | 26625273.7302 | 1206246977.6094 | 6703771829.5144 | 612593834.4596 | 184872143.5005 | 1.776e+12 | 2441330.5115 | 943691.2828 | 1619248.679 |  |  | 1.9532e+12
926 | 1234408513.9194 | 1127992450.117 | 217295137.2429 | 172969289.11 | 1069825970.0177 | 26380026.5554 | 211937200.0881 | 320176587.5504 | 468119095.9224 | 133108977410.5204 | 2022300334.5941 | 1759848213.8189 | 2056539475.5901 | 187300693.9666 | 532397012.571 | 718945294.5113 | 791331529.1041 | 246745126.0548 | 529132797.4739 | 21490464.6019 | 96055810.1335 | 21719838.0192 | 22866297.8754 | 938349178.1334 | 26869843.4511 | 1194336683.1577 | 5522243736.6736 | 634484700.0502 | 185348058.2194 | 2.3023e+12 | 2431996.1692 | 1034645.1358 | 1688662.2732 |  |  | 2.4578e+12
927 | 1187595131.2711 | 1175140987.0893 | 195913378.8205 | 143403137.7174 | 1058739589.7768 | 22825846.3991 | 209389921.3514 | 303215212.4783 | 474170651.4459 | 146568239131.5588 | 1709341130.3745 | 1953182378.6423 | 2194077194.8258 | 198580361.573 | 569860124.3068 | 575463309.8361 | 865615579.3862 | 343213866.8173 | 549969592.9553 | 24035040.8299 | 100073924.6277 | 20191702.211 | 24441979.1941 | 913189651.4872 | 23956880.9913 | 1078888928.9818 | 6643030218.1942 | 630166095.2892 | 188982620.3826 | 2.4581e+12 | 2558258.6385 | 932393.1146 | 1509137.1283 |  |  | 2.6281e+12
928 | 1143609929.4544 | 1219713872.928 | 223243892.5608 | 181715829.6736 | 840515976.4547 | 22422274.738 | 187912635.2601 | 300395940.068 | 474526349.3065 | 139363121276.8236 | 1743345389.5941 | 1964751423.7725 | 1608951787.8628 | 179017672.7416 | 607437820.2738 | 712542462.0242 | 933656866.2945 | 313148287.5942 | 609738743.6056 | 23900276.2916 | 125125629.9188 | 23335425.1482 | 21739027.7299 | 738248641.962 | 25520939.6522 | 1001054141.8201 | 7190693736.5962 | 669407837.1975 | 173019602.686 | 1.8609e+12 | 2523280.4919 | 944120.7326 | 1593096.8076 |  |  | 2.0235e+12
929 | 1120195016.4844 | 1173319660.04 | 184946145.0941 | 177538051.2952 | 1031779972.36 | 22339741.1844 | 216021915.2229 | 310352320.864 | 442698243.6363 | 134228712713.5509 | 1655547591.0842 | 2039936598.3162 | 2147381283.9691 | 182651939.5498 | 543940687.3775 | 669949399.8882 | 870941351.7861 | 267897455.9387 | 531824636.8843 | 24134206.1126 | 86103044.6681 | 23216718.2365 | 24004640.6924 | 735804702.1232 | 23330675.9159 | 1192954937.9188 | 6997591172.2673 | 513762244.7587 | 191273212.0333 | 2.2166e+12 | 2560823.8478 | 1027630.4749 | 1518168.6035 |  |  | 2.3743e+12
930 | 981402112.3843 | 1113583195.163 | 195338333.8354 | 169912550.884 | 1046018280.9908 | 21231360.5677 | 175631553.1034 | 313081194.6849 | 442695963.6679 | 157350315737.6749 | 1941657273.1288 | 2136281984.3275 | 2140935305.8583 | 202227061.6304 | 652343911.68 | 627606409.6381 | 716005544.0525 | 308812563.8879 | 544600389.5962 | 25492746.3658 | 114391971.4636 | 20749021.1028 | 20354731.7106 | 948936738.557 | 22947632.8013 | 1022157384.4951 | 5433088055.3546 | 703761100.1009 | 199346004.776 | 1.9385e+12 | 2449328.1197 | 980078.8981 | 1718942.7032 |  |  | 2.1181e+12
931 | 1212357266.7524 | 1228119555.4721 | 192964328.472 | 158424287.3296 | 1048081626.2391 | 23676702.7145 | 215474369.6725 | 291878673.4726 | 480046676.6035 | 156260288247.736 | 1846944252.8619 | 1804446970.8611 | 2208596156.1401 | 192672126.2153 | 610719353.3112 | 716066740.5633 | 806815206.3215 | 254515714.9606 | 600301396.69 | 24160731.8149 | 129419026.1669 | 22973143.0407 | 24465122.0457 | 895507026.5639 | 29123930.909 | 1138815116.8248 | 7147711900.5542 | 670686899.3724 | 187081611.8065 | 1.7726e+12 | 2625201.2104 | 936387.6064 | 1630104.6196 |  |  | 1.953e+12
932 | 1126259415.8361 | 1197937326.5382 | 205732951.2659 | 174186165.8296 | 937558902.6236 | 23582794.9291 | 186899807.2391 | 325707694.3776 | 489268843.2695 | 143477882109.6395 | 1784719958.1558 | 1724476569.5165 | 1843728123.0223 | 182068322.4922 | 565713001.6449 | 712132799.1847 | 905331395.6856 | 320222366.5814 | 578880925.2003 | 26807125.5028 | 126365728.525 | 16638336.9251 | 22781378.6404 | 818906092.9885 | 25687986.4809 | 998852049.7148 | 6365121098.2742 | 631802904.9805 | 201158264.4606 | 1.9559e+12 | 2349302.1858 | 945285.1526 | 1661855.7455 |  |  | 2.1219e+12
933 | 1170750280.97 | 1170560919.2247 | 209273022.0729 | 142882435.6994 | 1037524490.9161 | 22350157.085 | 220154980.5181 | 321515924.2788 | 472714466.7987 | 155476930214.4682 | 1904644337.9917 | 2039715333.2457 | 2086692053.5242 | 150175635.1083 | 610423434.703 | 636042680.0414 | 841474632.8353 | 333713856.7492 | 560932245.1657 | 22880387.812 | 112360491.823 | 19805203.938 | 23996542.4858 | 893121994.9728 | 23934141.8593 | 1151900830.7592 | 5824986613.8449 | 641912350.2942 | 200100380.7324 | 2.6749e+12 | 2385115.9204 | 969695.7174 | 1748906.1316 |  |  | 2.8532e+12
934 | 1120234413.585 | 1218395013.5953 | 210235802.7276 | 177180970.0692 | 1036444331.3993 | 25076223.6521 | 199689678.5086 | 315675343.2131 | 496422151.2557 | 120055693938.9158 | 1835596835.6783 | 1915372234.7238 | 2161635458.6364 | 196051442.1491 | 511381296.636 | 714316860.6405 | 847148461.8658 | 270963712.3001 | 580764395.3639 | 28591920.3462 | 126787205.8538 | 23753733.1156 | 25000594.174 | 831660901.0168 | 27624320.1327 | 1218032624.8114 | 6962844697.3207 | 648311751.2372 | 194685284.3362 | 2.5154e+12 | 2455675.0324 | 938477.0136 | 1723474.4804 |  |  | 2.6594e+12
935 | 1236808955.447 | 1148467605.9636 | 205677483.015 | 137998790.7463 | 1030368383.1977 | 26719512.6381 | 191628505.6536 | 299333532.8451 | 487463975.5627 | 152542685309.1072 | 1951326954.6343 | 1860700811.7088 | 1945580960.3476 | 190529970.3039 | 530472314.9778 | 573279993.8765 | 891328619.9888 | 328476431.8351 | 554323150.6113 | 27053334.0428 | 124604872.6617 | 19953634.5389 | 24241888.7478 | 773227679.0704 | 31460098.1388 | 1049891365.9482 | 5451625223.9662 | 652443391.6971 | 178893459.3301 | 1.9233e+12 | 2486762.4261 | 983121.5941 | 1533788.136 |  |  | 2.0978e+12
936 | 1244851960.7919 | 1006002905.793 | 227280229.4353 | 159599421.6329 | 969135918.8823 | 27431824.3279 | 208643712.5563 | 316909058.3147 | 449920273.4576 | 132356652499.9871 | 2067373355.9353 | 1741316525.4632 | 1807969991.5435 | 147479127.7585 | 596067137.8524 | 698906915.7549 | 717505715.4901 | 343570449.48 | 525382231.3719 | 25768558.0493 | 99917742.6098 | 23580886.7904 | 24109769.561 | 693053890.5249 | 29755653.7665 | 930516996.1517 | 5914648401.6223 | 688636046.9341 | 153500416.0931 | 1.7967e+12 | 2540568.4312 | 951471.7167 | 1642377.941 |  |  | 1.9509e+12
937 | 1225909811.8341 | 1202948418.9342 | 227416688.2884 | 174066856.354 | 1076781195.3679 | 19715126.1451 | 213193017.3886 | 307327515.6085 | 477081036.0163 | 139379308949.476 | 1886392497.6542 | 1699199899.4518 | 2132285378.596 | 202902600.2859 | 610666751.6122 | 723242895.2401 | 904441387.8013 | 318611125.5811 | 530349529.0272 | 21306868.8821 | 98490887.2468 | 18581484.9559 | 24021709.7352 | 931612681.8077 | 25758994.7124 | 1112640343.4421 | 6006495949.4627 | 691060605.6591 | 181766709.5903 | 1.3975e+12 | 2712278.931 | 934549.3122 | 1642701.4167 |  |  | 1.5599e+12
938 | 1121235314.6809 | 1062516492.9005 | 192948505.447 | 160606091.9298 | 1009213167.611 | 24275168.5059 | 190258774.1301 | 306705209.5438 | 460051966.5065 | 102924263397.6185 | 1899142488.0113 | 1843325356.2067 | 2097404872.3407 | 175603295.5383 | 557367732.3599 | 725083928.6506 | 865947255.8235 | 231180648.5026 | 571281080.0082 | 28271405.8042 | 119620838.342 | 24465861.9304 | 24834841.7662 | 939233109.708 | 30121867.4606 | 959598645.1178 | 5724934077.4138 | 642478058.7889 | 201764882.8935 | 1.9073e+12 | 2594989.4786 | 1007312.9332 | 1668857.1237 |  |  | 2.0325e+12
939 | 1242201271.5386 | 1160692721.7684 | 195842429.3779 | 169057888.9708 | 1007463788.3219 | 22173165.6772 | 199802051.9728 | 322791714.2474 | 497826987.1963 | 140899592136.2344 | 2003614284.9509 | 2089465456.4376 | 1662492683.7029 | 201656195.6624 | 569258243.0931 | 722122491.2605 | 913631701.0554 | 362493034.4992 | 549308781.914 | 25222104.3705 | 124087930.5447 | 20581435.4852 | 22826441.575 | 889766865.1614 | 23484206.7137 | 1012328965.0178 | 6358924531.6664 | 627728593.1137 | 168386856.8317 | 2.3464e+12 | 2608194.9369 | 1008369.7356 | 1587580.9335 |  |  | 2.5105e+12
940 | 1132115983.9217 | 1195175693.1822 | 193073936.0654 | 180036804.4066 | 1046171533.4489 | 22833667.4 | 201919906.2852 | 313216861.7291 | 460513601.4258 | 144941524201.2079 | 1859072347.9385 | 1837306199.6358 | 1990777055.7486 | 199383067.1928 | 588413214.0327 | 721881559.7576 | 818231724.0743 | 299414054.5041 | 610025324.4932 | 25945790.7175 | 114864213.1 | 21756273.8422 | 19486772.5785 | 825469913.2096 | 22668072.3519 | 1153350460.9205 | 7321122895.8047 | 696327004.7891 | 173431176.407 | 1.5099e+12 | 2521765.2592 | 949937.5247 | 1649142.8594 |  |  | 1.6789e+12
941 | 1223907220.6278 | 1025255436.4606 | 201347744.097 | 157035781.4417 | 1083553646.3121 | 23275010.6582 | 210929139.5572 | 296082489.8762 | 461091995.2605 | 142412104224.9455 | 1899646730.7228 | 1917097032.1869 | 2165534892.9744 | 199581879.9865 | 467589599.6593 | 669871245.4794 | 917394411.7858 | 312166192.7063 | 561859526.22 | 26645499.6236 | 115577007.4958 | 18962149.5374 | 25896503.1356 | 652695746.6805 | 28901414.8546 | 1133220136.4785 | 6717184006.0764 | 668770135.3192 | 189013321.6611 | 2.0335e+12 | 2560364.9636 | 1002372.6082 | 1501858.8523 |  |  | 2.1993e+12
942 | 1226107468.3717 | 1022186903.2222 | 213989175.4721 | 168950756.6364 | 1087427132.1588 | 27360769.8328 | 193435594.912 | 280715306.9983 | 488412035.4591 | 154333299575.465 | 2039855316.4024 | 2027643043.0605 | 1886771447.8539 | 188527577.7453 | 504816104.8222 | 722468541.7084 | 822662639.2149 | 269834205.2419 | 441797843.0837 | 26815276.391 | 119027781.9324 | 19813096.8311 | 25245777.9203 | 806666397.2622 | 25776309.8695 | 1033240088.7106 | 6869938385.722 | 646465899.2171 | 153098275.4859 | 2.351e+12 | 2488595.447 | 962633.284 | 1675798.7866 |  |  | 2.5286e+12
943 | 1181536631.7142 | 1168394879.3963 | 207198084.5219 | 178927769.6911 | 942411736.2373 | 19078419.4156 | 194218764.2605 | 308557716.7154 | 486410114.5749 | 130809402606.0204 | 1885829946.8529 | 1927783579.8388 | 1992963371.8431 | 192814835.2 | 621166573.5085 | 672604906.6459 | 842695129.5122 | 333049104.7795 | 602295317.1212 | 27073908.002 | 105114951.5155 | 17805871.7559 | 22048569.655 | 821202484.9162 | 29985517.7326 | 971609720.7628 | 6941860383.147 | 666654751.4454 | 174577691.6403 | 2.0115e+12 | 2319245.66 | 916964.9059 | 1550934.7234 |  |  | 2.1659e+12
944 | 1219250339.0929 | 1225169563.7508 | 199182932.1287 | 181899810.9776 | 1007915468.6622 | 20021352.1177 | 209176566.1363 | 316509304.5514 | 448592500.2937 | 141334954589.3624 | 1674124315.3915 | 1456479167.5907 | 1969311069.9793 | 186026519.2264 | 521626533.3627 | 680897065.83 | 746622373.2706 | 272728787.1268 | 525356904.0816 | 26062625.5994 | 102957032.8751 | 23385799.6633 | 24755822.8058 | 898147788.7505 | 27243560.7941 | 1033524451.9308 | 6987838038.8528 | 687902827.4593 | 185624288.143 | 2.4e+12 | 2521149.6087 | 1019568.8046 | 1625257.6323 |  |  | 2.5642e+12
945 | 1196062622.6902 | 1217446361.5527 | 207988910.5202 | 178124777.8608 | 1044611333.8257 | 22825464.7445 | 205437622.358 | 310745553.8944 | 489397460.367 | 150621487369.6451 | 1436324331.3419 | 1642041778.0574 | 2022154184.7324 | 189451033.49 | 614721491.9402 | 700434748.4307 | 887001397.1817 | 319610623.6525 | 524906823.621 | 27470220.8025 | 103717769.3968 | 21143373.3233 | 23646696.126 | 900428456.2635 | 30664282.8083 | 896831616.7476 | 6740072587.6674 | 658524806.6562 | 171028602.0062 | 2.3865e+12 | 2709069.6615 | 926954.2454 | 1542071.1807 |  |  | 2.5599e+12
946 | 1236626117.1123 | 1171789274.4229 | 190342539.7297 | 161748736.8075 | 1059573340.3009 | 20882479.6102 | 205924235.7282 | 325414908.7688 | 482818622.0348 | 134207434664.9132 | 2040783961.8176 | 2037969233.4539 | 2211184910.9173 | 178321270.2827 | 615113383.2588 | 702248708.73 | 842360881.2641 | 312411845.1914 | 512263384.9102 | 26710910.5295 | 114508565.6051 | 22298907.9782 | 24336274.1559 | 804217446.4106 | 26181159.8968 | 929262339.2827 | 6040034673.2965 | 640924682.9797 | 187413143.3063 | 2.2674e+12 | 2577945.0248 | 952793.8775 | 1682414.3905 |  |  | 2.4248e+12
947 | 1245144340.9151 | 1179996451.6118 | 223397661.8424 | 151571838.1215 | 1083507218.4533 | 24883681.5428 | 223891584.8579 | 331163683.4112 | 465286424.884 | 129030978530.3777 | 1805351108.0118 | 2129047538.5921 | 2199080774.4564 | 185075652.171 | 586365359.8862 | 590562415.2992 | 833171804.8364 | 323426623.9596 | 589121137.6554 | 21658477.7474 | 97619516.9161 | 24312888.0317 | 23424961.9712 | 810610203.5526 | 27415238.6878 | 1091438697.5988 | 5575028401.4062 | 669901411.2777 | 161101181.9168 | 2.1247e+12 | 2409873.8248 | 932306.7299 | 1539375.4098 |  |  | 2.2764e+12
948 | 1224775558.1403 | 1225479466.7144 | 189384068.929 | 154244424.8443 | 1052878412.9722 | 24279741.3666 | 222401679.0107 | 324092625.5114 | 490969420.2517 | 138542079662.4105 | 1700628391.2743 | 1921180176.7485 | 1915878972.919 | 181195318.4594 | 583658453.3921 | 662662639.5714 | 695200846.376 | 283322887.7939 | 601759405.2417 | 28003048.9635 | 124017069.8614 | 23380285.9505 | 23849729.2798 | 910893911.5551 | 21813140.4078 | 1137905034.4143 | 7366965993.7169 | 677481862.2293 | 194169849.3159 | 2.0453e+12 | 2361236.9405 | 976464.3092 | 1544077.9009 |  |  | 2.2078e+12
949 | 1135171093.0018 | 1076982399.2144 | 178445323.4263 | 161026863.0434 | 1034859792.7576 | 23458540.2811 | 216000106.1593 | 313046060.2099 | 477244614.5165 | 142850866975.3204 | 1867149214.4153 | 1982427681.0056 | 1887886067.8034 | 193737566.52 | 631384668.3362 | 709285469.5652 | 775162800.8337 | 337366582.187 | 611688823.5361 | 23477908.6115 | 123921603.7421 | 22893851.763 | 23295322.4536 | 920093008.8599 | 29104894.9506 | 1009063330.7979 | 5762431332.9829 | 696807589.5798 | 185722536.1026 | 1.9009e+12 | 2530960.8975 | 931818.3019 | 1845459.2763 |  |  | 2.0662e+12
950 | 1093476693.4884 | 1166085437.203 | 217661546.0986 | 167911399.6761 | 1008149465.7292 | 27663037.8108 | 224497168.9069 | 312919881.1274 | 497833179.6657 | 150346887276.4279 | 1908899252.8903 | 1770915021.4492 | 1479742360.3738 | 195705589.7976 | 549267052.3777 | 680990008.8962 | 922468779.1677 | 315027925.8413 | 553536783.5143 | 25743981.5425 | 119764982.264 | 23877070.3397 | 21750806.6497 | 800954317.2369 | 30666901.1733 | 1169429146.8308 | 6382057222.0294 | 622455246.9721 | 188532583.7644 | 2.0029e+12 | 2442719.2073 | 987781.9762 | 1639885.1051 |  |  | 2.1757e+12
951 | 1250586647.2601 | 1080083641.4527 | 205392640.2958 | 157126586.6403 | 1063773904.6769 | 25345928.8948 | 213335758.5845 | 330709057.6821 | 475981760.9186 | 149280101247.1689 | 1919510946.4719 | 1899069655.2766 | 1962822252.7508 | 201892143.8003 | 598627494.5531 | 683540637.6684 | 861656009.5651 | 299048389.7355 | 612844526.679 | 27618779.1765 | 135574390.0785 | 18186814.9041 | 20515778.1195 | 804895381.8172 | 28053003.9488 | 1089177493.2972 | 6202490649.5911 | 552792405.4337 | 195872582.1076 | 1.646e+12 | 2462734.8873 | 977832.5108 | 1700039.0509 |  |  | 1.8182e+12
952 | 1199551236.164 | 1158418960.2375 | 203676642.484 | 170808021.4407 | 1030332793.8774 | 26371109.648 | 223887418.1034 | 321113252.2569 | 452340844.8961 | 144518907996.0035 | 1798312355.4045 | 2057015546.1013 | 2129602614.4247 | 199980672.5919 | 607269884.7749 | 598944589.2827 | 841561667.5942 | 312704392.6533 | 611162643.7287 | 19635001.4034 | 113771705.3269 | 18006726.3038 | 23533137.5582 | 881605331.1923 | 29244294.6084 | 930030538.0024 | 6462921689.8501 | 624565683.785 | 201741732.2072 | 1.934e+12 | 2604886.714 | 992326.1055 | 1492818.2703 |  |  | 2.1018e+12
953 | 1066405310.0047 | 1168865706.0923 | 195194954.5575 | 156744412.0063 | 993240855.5014 | 23501429.093 | 218826699.3124 | 269891997.0519 | 494092219.612 | 138364937986.6084 | 1832701477.7696 | 2179527220.0163 | 2129584195.9613 | 177622260.0179 | 622974654.3637 | 685042275.0195 | 711993165.4624 | 308155561.731 | 469638634.8607 | 26164344.5233 | 136740965.9827 | 24958626.5845 | 24783896.0532 | 919439335.718 | 28751608.7057 | 1057852857.5408 | 6187047136.3083 | 557537202.7321 | 182668286.5215 | 2.2122e+12 | 2353872.3646 | 978343.5904 | 1562098.4003 |  |  | 2.3734e+12
954 | 1207419810.1535 | 1210127816.7452 | 210155898.9378 | 169855798.5802 | 1068959252.7344 | 25804662.7667 | 212578658.7631 | 322167767.08 | 488530148.2831 | 132797371902.9866 | 1859734516.7064 | 2014039586.081 | 2094057070.984 | 194866343.0482 | 637119074.8783 | 617220339.2862 | 859259544.5736 | 318087024.0298 | 483887150.5712 | 25047753.676 | 126496343.4984 | 22981753.4985 | 23316124.1996 | 782099310.8813 | 24661063.8823 | 869026625.7618 | 6489830105.1739 | 630751585.9193 | 190527543.1664 | 2.1809e+12 | 2585852.1017 | 904352.9815 | 1706425.1602 |  |  | 2.3369e+12
955 | 1186348806.3189 | 1199256609.0557 | 201847672.9522 | 175959313.3547 | 1015981772.0382 | 22091297.6087 | 226780601.8055 | 294987326.7357 | 464993454.1536 | 156970623433.3127 | 1648311373.4048 | 2127209402.6618 | 2212290847.9251 | 189810396.1685 | 607336637.7796 | 622938809.8089 | 816795511.0176 | 343575352.5749 | 580227533.7194 | 25469459.6569 | 112318210.1075 | 21964188.283 | 25440630.1486 | 698642428.3362 | 22799114.3325 | 970572929.792 | 6230322965.0735 | 584447170.8049 | 198006349.1762 | 2.578e+12 | 2473348.5977 | 924322.36 | 1701007.0037 |  |  | 2.7578e+12
956 | 1189769164.5221 | 1118565844.4428 | 208913310.4786 | 168252789.2079 | 1077891829.6938 | 25317893.1724 | 182889764.9241 | 319880988.2807 | 417294587.6182 | 144592826892.1692 | 2007590469.8002 | 1771150214.9093 | 2169460099.9326 | 154077245.1977 | 595589429.3239 | 703146416.175 | 852123419.9591 | 294480684.5027 | 564023842.3119 | 20588168.3201 | 106066093.9699 | 21510391.5183 | 18878033.5019 | 917887835.088 | 27301793.137 | 1069341226.4329 | 6546264945.7211 | 610397250.425 | 201275680.5697 | 1.7992e+12 | 2405747.7304 | 951423.0368 | 1628087.6723 |  |  | 1.9672e+12
957 | 1215843162.877 | 1091447060.5834 | 175258274.8831 | 165515729.8606 | 1025343030.4616 | 23405525.2936 | 214780361.4833 | 329020870.1518 | 447832473.3819 | 151592637912.1105 | 1773968108.4805 | 2026286981.9126 | 1790367837.1034 | 202330324.9833 | 615233600.5056 | 554488057.9799 | 795210183.3142 | 324165399.9418 | 474542296.39 | 20810589.6036 | 122014011.666 | 18814685.2848 | 22817712.003 | 719299890.2267 | 25430263.1472 | 1190293352.7718 | 7174892432.4908 | 567160262.6423 | 197551212.254 | 2.1377e+12 | 2329301.5317 | 942922.2616 | 1651709.1363 |  |  | 2.3126e+12
958 | 996776165.1015 | 1152120778.5147 | 210083201.5498 | 164013678.3716 | 1021577567.9558 | 22180936.0146 | 204096418.5826 | 317249503.1943 | 492525635.4168 | 151188645757.8071 | 1803977626.9661 | 2165176563.6988 | 2075029429.4586 | 189609224.6141 | 553693547.5697 | 698795600.1806 | 714217390.3316 | 313772668.9021 | 609250377.9712 | 17906111.5875 | 96258118.1981 | 24677287.3296 | 25928541.5782 | 813382517.5872 | 28838855.2931 | 928208018.5016 | 6507988593.4699 | 602264464.443 | 201188937.4746 | 2.1005e+12 | 2541108.9295 | 900118.4946 | 1693554.1254 |  |  | 2.2747e+12
959 | 1226127597.2589 | 1065639186.8809 | 214964833.4315 | 172407411.8268 | 1008591452.3744 | 22625515.9903 | 214803601.9471 | 296808537.0656 | 494016786.3836 | 117193650865.7344 | 2071810170.5293 | 1948076964.0339 | 1833506999.6327 | 193378610.1899 | 489552545.7162 | 699398631.8398 | 789919248.6379 | 246355160.5207 | 529677461.2836 | 28242954.3029 | 121343016.8342 | 22061805.631 | 22010362.0474 | 770611116.9939 | 26430555.9056 | 1142608293.3228 | 5340620140.9112 | 595273313.1456 | 179629899.1044 | 2.2472e+12 | 2569309.1204 | 928500.5557 | 1555937.5933 |  |  | 2.3862e+12
960 | 1170575437.0083 | 1167419369.6504 | 220469905.3013 | 165567481.8698 | 1013615185.2178 | 23637797.4624 | 209875296.304 | 329091279.532 | 449541128.3523 | 150776504085.2533 | 1730592788.935 | 2036639454.0963 | 2018507011.9736 | 150070706.536 | 579786988.368 | 720695059.246 | 845804397.1369 | 342827424.9944 | 567621379.9192 | 18809175.6534 | 135113116.7974 | 21307491.0449 | 23864493.5621 | 792567832.4238 | 23979140.642 | 937411061.4706 | 5124881429.4026 | 589392937.9345 | 183565038.9958 | 1.9964e+12 | 2571836.5767 | 1005131.9323 | 1747754.7211 |  |  | 2.1688e+12
961 | 1225300875.7328 | 1046757012.7845 | 217590363.1213 | 165804094.464 | 974366338.0805 | 26040402.3307 | 185720285.9895 | 314945004.3014 | 471432836.0309 | 144989061262.2059 | 1930701294.9659 | 1647977065.8724 | 2112536221.5845 | 156824764.5544 | 632520422.038 | 719684182.3422 | 819112839.5996 | 295262863.3974 | 541360118.303 | 18772385.8716 | 123527431.3472 | 22608240.4219 | 22606140.1572 | 915921713.8537 | 29963029.8532 | 1163287135.4869 | 6399326777.2277 | 692763177.0431 | 170220917.8637 | 1.6732e+12 | 2664267.7844 | 1041442.228 | 1584905.1388 |  |  | 1.8413e+12
962 | 1258796894.9904 | 1205119086.4211 | 224376143.1078 | 171580574.7144 | 830073761.8004 | 20784867.1426 | 215899297.4413 | 326076476.2148 | 484865172.9355 | 134298802921.7921 | 2017215735.8903 | 2015405204.5925 | 1973384278.5897 | 194126440.9043 | 613823667.4867 | 664351478.6624 | 683578985.679 | 342207857.3494 | 554855712.3934 | 22693757.1576 | 122502321.5096 | 23375897.7802 | 25115970.721 | 906851831.0795 | 23358919.1302 | 1079317795.8826 | 7031494279.3906 | 679509544.5554 | 188832231.919 | 1.7223e+12 | 2688342.4245 | 907881.7699 | 1601778.6565 |  |  | 1.8805e+12
963 | 1222525681.3315 | 1200514090.2432 | 192217895.8783 | 163662841.3772 | 918192103.4522 | 23378305.7499 | 196850291.3419 | 318675895.6502 | 465229221.7834 | 121108333932.6427 | 2071604828.7856 | 2057572259.352 | 2059572798.0318 | 190222158.7996 | 552453101.6286 | 654666123.1408 | 679033354.5675 | 312924388.7024 | 527237266.5803 | 25259126.2619 | 129917186.2077 | 19816556.5729 | 20501967.5208 | 749398570.9086 | 30373656.008 | 987311597.378 | 6059375020.2659 | 652736897.3576 | 194117984.9802 | 2.7747e+12 | 2461986.4379 | 986866.1881 | 1612700.8667 |  |  | 2.9185e+12
964 | 1160972685.3354 | 1206266022.2058 | 208833862.2699 | 171508513.438 | 1076602346.3288 | 24836391.9692 | 200226124.6689 | 317153199.8554 | 462807723.5996 | 154284016014.7678 | 1900337191.5682 | 2115563636.0199 | 1859999474.7347 | 180427571.2513 | 656396601.0317 | 683768436.4261 | 631500361.2788 | 298862877.542 | 580050676.1847 | 27932260.7061 | 110403130.9214 | 24134558.8334 | 21557066.3934 | 815214735.3825 | 29277658.2953 | 1023398896.9439 | 6964598034.7366 | 680715623.8482 | 199710176.8855 | 1.4516e+12 | 2519527.9437 | 915366.3512 | 1555834.4046 |  |  | 1.6295e+12
965 | 1145003724.5428 | 1092524025.5552 | 216718884.4434 | 173087262.5745 | 1072704759.5475 | 22640205.6393 | 220668875.7236 | 326124335.6381 | 486912366.428 | 153048573199.9685 | 2030622792.92 | 2137997719.0006 | 2168574447.7444 | 177535897.3108 | 592542059.5671 | 688107970.0297 | 679733085.183 | 328787562.3862 | 554526418.3194 | 23650439.7759 | 137543619.085 | 21770903.1526 | 25754287.1303 | 857150005.3629 | 25109071.7529 | 892837370.8255 | 5596161630.4798 | 669064653.8884 | 176009282.0054 | 2.2096e+12 | 2262271.1485 | 930213.9787 | 1747795.0578 |  |  | 2.3852e+12
966 | 1165678959.1355 | 1124482549.8678 | 204548999.7573 | 151759155.8389 | 1086412448.9576 | 22505656.5156 | 209462349.4069 | 302652800.8273 | 459476648.4912 | 142491030746.2763 | 1846484956.5091 | 2132476462.9883 | 2117158161.6724 | 196594970.9133 | 582479175.6643 | 593186516.3292 | 785776191.1 | 324371900.8571 | 573690526.0319 | 20540063.6826 | 133402259.6672 | 24369978.8499 | 25054372.3948 | 896339286.5921 | 26478797.4352 | 1201138612.4866 | 7011783525.4685 | 596370040.1703 | 189336451.6996 | 1.9287e+12 | 2445285.4587 | 912982.0366 | 1820403.6535 |  |  | 2.0952e+12
967 | 1216345253.7255 | 1082699789.1971 | 207149579.5696 | 179097240.8474 | 1061107283.7972 | 21563154.7172 | 219846625.4715 | 308212549.4038 | 499998971.9547 | 117923322489.689 | 2019914173.0281 | 2118865766.7954 | 2202420676.233 | 164160097.4374 | 628648381.2983 | 701532380.9928 | 810457228.5575 | 273074934.1917 | 610138075.6372 | 25412423.6905 | 130762780.3591 | 21929564.4256 | 21543981.6424 | 831026677.7809 | 20687778.2983 | 1104197600.955 | 5989330077.6938 | 547429863.5996 | 198679511.6021 | 1.866e+12 | 2678863.4947 | 953082.7791 | 1595424.8793 |  |  | 2.0071e+12
968 | 1138803215.2999 | 1196592320.6614 | 222625150.8885 | 175197625.1702 | 1003012176.9432 | 21354408.448 | 222087525.5016 | 304420141.587 | 472281059.5817 | 106771837035.0954 | 1972200567.6638 | 1967216556.6269 | 1971906840.1037 | 203000940.7847 | 649313158.9853 | 665102700.5657 | 838789867.6485 | 312326662.2219 | 465574995.173 | 27262736.2251 | 106136765.7894 | 21200535.9897 | 20033247.7081 | 862602007.2386 | 25310153.0335 | 1170138433.3487 | 6815122434.8996 | 675958674.9408 | 196774206.0675 | 2.068e+12 | 2733406.2622 | 901174.3976 | 1727136.662 |  |  | 2.1985e+12
969 | 999205896.4765 | 1187034426.3162 | 205883572.3011 | 174575755.6949 | 1020935842.3769 | 26207769.5252 | 223628335.137 | 293710742.8151 | 451152415.6203 | 143608381689.8486 | 1795557258.2266 | 1890714737.243 | 2184756271.5395 | 193595178.2547 | 603535941.3457 | 704336932.8402 | 922865648.36 | 293944983.2878 | 589626191.5905 | 23274825.9617 | 88153318.1455 | 24715048.5651 | 23633368.6869 | 881321302.1115 | 24657584.8304 | 1090338511.7394 | 6389107525.1843 | 593135201.2837 | 180327744.6446 | 1.5651e+12 | 2319532.2644 | 896290.0228 | 1634952.0921 |  |  | 1.7318e+12
970 | 1180484732.8617 | 989813466.5365 | 211740034.8591 | 164516173.5409 | 1064007652.0943 | 24182926.567 | 223886218.2936 | 292817091.5016 | 466738818.3148 | 157280643414.7544 | 2056388077.7046 | 2130776112.9516 | 1607571093.6973 | 188001087.8083 | 668873772.7275 | 664681435.5143 | 707124124.2462 | 282979760.9668 | 604321298.9742 | 24267985.0213 | 126078762.7783 | 22451898.7721 | 23580438.3659 | 917234153.0758 | 30072601.8122 | 962473254.6506 | 6389333554.3399 | 703410008.3052 | 182069045.586 | 1.5571e+12 | 2638890.9223 | 950243.7401 | 1730813.1706 |  |  | 1.7373e+12
971 | 1121020949.0204 | 1142213852.1822 | 200735106.8146 | 162186837.303 | 1013536259.3775 | 21492523.9056 | 210321051.9329 | 313914157.6449 | 482910567.0364 | 152213689608.4144 | 1923863695.9352 | 1814600415.7864 | 1956247342.7865 | 198115421.3321 | 622767823.9136 | 675635321.1205 | 902724030.5397 | 311620071.0138 | 524254290.4519 | 24195139.6872 | 115516796.1694 | 24366952.8183 | 24787810.0801 | 754480087.0888 | 27078039.0816 | 1181279101.9121 | 5425222157.5053 | 623343812.7735 | 148166782.1106 | 1.9946e+12 | 2662804.8008 | 935157.5866 | 1742558.7776 |  |  | 2.1688e+12
972 | 1061144843.8359 | 1181053082.5641 | 192951048.4498 | 162352157.3249 | 1035502614.3885 | 21128965.0304 | 188901117.7257 | 302449661.2355 | 476002407.9084 | 156689873188.228 | 1961101869.3695 | 2078533102.6168 | 2204344955.8675 | 183610983.6914 | 566133625.2529 | 663465136.4364 | 728742141.0329 | 280218993.2942 | 605174088.1553 | 27222656.9515 | 111330955.6849 | 23529759.8823 | 22190429.8271 | 846833716.3073 | 23346952.2244 | 1208277640.9571 | 6480706191.3918 | 572843368.6974 | 182782102.2413 | 1.7802e+12 | 2251972.9104 | 975728.5926 | 1698674.6574 |  |  | 1.9603e+12
973 | 1211996166.2704 | 1207989936.7987 | 219189743.2441 | 180740145.4109 | 1061516002.0487 | 23686577.0602 | 191449028.7256 | 294766962.6773 | 493412884.3999 | 138841094345.1628 | 1784733839.4503 | 2007572619.2562 | 1462409616.5321 | 197594879.4465 | 601773419.9795 | 458530475.366 | 881863631.2979 | 317822019.6538 | 520432729.7577 | 23826303.6427 | 111365274.9518 | 24200256.3487 | 20531405.2026 | 724975339.0439 | 26357659.1515 | 1022572108.4629 | 6414786551.3532 | 639237165.9866 | 181903561.4852 | 2.3426e+12 | 2467944.4218 | 992985.8511 | 1645016.6895 |  |  | 2.5038e+12
974 | 1220509653.6641 | 1182254473.2524 | 214050367.0599 | 170456678.5304 | 1067982166.5121 | 26776612.2431 | 190859118.0682 | 320287258.6357 | 499581287.7609 | 153137617634.9703 | 2035667734.4531 | 1563098896.1909 | 1775006032.0081 | 198681562.0629 | 658886844.3321 | 633649476.8266 | 835981437.8252 | 264938333.0754 | 584805316.3439 | 20829099.7604 | 104765773.8563 | 22872558.2533 | 23322088.8265 | 927644339.8691 | 24744050.8787 | 1142594787.9127 | 6335306681.7755 | 558090498.3472 | 186726035.5167 | 2.4629e+12 | 2429412.0287 | 946578.1637 | 1621560.8695 |  |  | 2.6388e+12
975 | 1239599845.2818 | 1198985980.7228 | 213765923.3546 | 175287695.4305 | 1066641665.2501 | 21231568.9381 | 223259121.9165 | 297402986.5153 | 479800471.7481 | 139637754213.2562 | 2000996308.619 | 1486816512.2441 | 1663464798.1737 | 173089575.9147 | 552683714.7579 | 682125448.2721 | 814997613.5505 | 315051822.0623 | 609669634.1095 | 26241641.5735 | 134474817.9324 | 21223841.3508 | 22512412.2853 | 938220909.6631 | 30344136.665 | 1108957195.7418 | 6580580751.2577 | 481230949.5914 | 177147299.9429 | 1.5919e+12 | 2526485.0149 | 940055.1871 | 1755809.0018 |  |  | 1.7542e+12
976 | 1072078632.9403 | 1145108865.9976 | 222891363.4383 | 171713237.3608 | 1082342166.883 | 24754102.6041 | 201265318.978 | 277070498.6745 | 494990676.3949 | 150413288576.7357 | 2012865556.752 | 1775890874.1024 | 1952211120.2514 | 191155838.0881 | 559197420.1257 | 583127312.0037 | 807699983.0173 | 345566628.2724 | 581903640.7429 | 22355252.1407 | 127331166.786 | 19771157.6565 | 23406430.6197 | 843978740.6124 | 25562645.8488 | 1062645734.9372 | 6471019987.4002 | 614788831.51 | 200874011.0837 | 2.5824e+12 | 2705104.0074 | 927811.278 | 1620743.6529 |  |  | 2.7558e+12
977 | 1081188806.4781 | 1133543548.5991 | 208574264.667 | 178576078.966 | 1077299578.9437 | 23548808.8712 | 209452630.6669 | 275197112.8697 | 470837734.0948 | 135467287765.0198 | 1931880094.3921 | 1891320288.1235 | 2186331111.6835 | 191205152.9183 | 539495682.0896 | 677259590.482 | 901544456.6017 | 267977212.2777 | 593014545.393 | 22878616.0369 | 127858405.8539 | 24433598.9389 | 19841518.8504 | 851184749.8454 | 29632291.3193 | 1197280014.3671 | 6208504726.5945 | 702466995.4714 | 144217652.2624 | 2.2453e+12 | 2418605.0502 | 931466.3487 | 1631163.5494 |  |  | 2.4039e+12
978 | 1047309706.8912 | 1189703909.3455 | 213301103.2603 | 159909730.6187 | 1054575560.0672 | 26050308.1304 | 209913191.7186 | 274628926.785 | 473654848.9036 | 140608689600.6458 | 1805114686.1805 | 2150773540.7631 | 1480063818.1606 | 187461163.0572 | 672999774.0437 | 685487032.5431 | 761502028.9379 | 248673066.5308 | 607452469.7977 | 25903517.325 | 98178961.3209 | 23330640.0337 | 22347501.6695 | 791108918.1698 | 30863230.8745 | 1100092524.3501 | 7197146490.5356 | 630552860.8748 | 164755902.3473 | 2.2066e+12 | 2497164.8886 | 944003.8571 | 1676321.1586 |  |  | 2.3705e+12
979 | 1206509497.1772 | 1182474282.0713 | 183961996.5204 | 164785899.4314 | 1086429387.0267 | 22936842.0253 | 213065664.2478 | 325225557.1164 | 472599854.7936 | 152152038786.5792 | 1989920505.2586 | 1965974224.1369 | 2174187497.8828 | 185618587.5511 | 620465418.8381 | 666832468.4024 | 737381320.7691 | 319617459.8871 | 573037636.8128 | 26178320.0534 | 118822401.7676 | 23165882.9541 | 24425493.6706 | 833639781.4629 | 21534818.4578 | 1175009839.5501 | 5487925912.941 | 608275397.3036 | 187244075.2223 | 2.6212e+12 | 2389180.3742 | 958937.3713 | 1538160.6997 |  |  | 2.796e+12
980 | 1215928213.0727 | 1194242667.0253 | 192456906.9868 | 167007246.8654 | 1076400112.7729 | 21298621.1717 | 214015652.0502 | 320633996.3551 | 492015922.4689 | 154196625760.3546 | 1848757670.9828 | 2051120312.3228 | 2019461347.4434 | 143373422.2585 | 652790756.5595 | 666207357.0543 | 908039198.1335 | 320811163.5311 | 582383849.5704 | 25074325.6241 | 124778072.1743 | 23152101.4905 | 21396629.9783 | 937177405.9418 | 26175433.5772 | 1048965932.3428 | 7017760442.7274 | 708321158.3571 | 190185403.383 | 2.3857e+12 | 2235630.6675 | 987473.4068 | 1641319.501 |  |  | 2.5641e+12
981 | 1160059702.405 | 1084877180.838 | 195254588.2572 | 174863392.8981 | 1071669732.0711 | 20878278.5292 | 204110921.9955 | 259741874.1315 | 389716679.1557 | 145520620158.0339 | 1733392026.5707 | 1969363778.6465 | 2153420276.7004 | 174470725.0589 | 479059216.7964 | 687666292.9518 | 763053524.3867 | 278545272.2738 | 492824715.1117 | 25666572.5781 | 106772726.9984 | 22078295.9681 | 22482204.4625 | 902166194.3195 | 26987526.4679 | 953878915.5698 | 6165755780.1115 | 685019037.537 | 187421925.3118 | 1.6898e+12 | 2652575.7734 | 911771.2795 | 1637318.4437 |  |  | 1.8577e+12
982 | 1219522631.6016 | 1096666199.054 | 200912215.3215 | 167249559.0427 | 1045288155.0278 | 24751998.402 | 209241295.3174 | 292344177.9531 | 445089227.4572 | 143371787001.9338 | 2017603994.4674 | 1651989870.5209 | 2199296760.7766 | 164480044.7614 | 631285733.2094 | 670413776.7211 | 847639337.7361 | 322782962.7634 | 532809998.8272 | 23527218.5254 | 109832602.016 | 23950420.1113 | 23149054.6717 | 938637415.6696 | 26159580.2548 | 1106264009.1344 | 5604704343.9055 | 705035464.1256 | 173249821.9423 | 1.791e+12 | 2419101.3404 | 920685.4161 | 1577547.6172 |  |  | 1.9568e+12
983 | 1246861928.3038 | 1215252447.4239 | 224210204.6959 | 151906381.3889 | 1070533190.669 | 18563972.1547 | 190142681.5471 | 305165237.5753 | 438478324.3879 | 155484377309.5042 | 1547391606.9325 | 1671026702.9019 | 1926194876.9614 | 195034214.5393 | 560661819.6457 | 650809836.2239 | 869657975.2113 | 261461332.7982 | 598433120.7912 | 25393830.3026 | 105093423.132 | 22310943.3566 | 17990033.2138 | 924822672.5909 | 29884252.3128 | 1227431528.4547 | 6265312759.1465 | 598098474.1547 | 195153725.4848 | 1.8619e+12 | 2334000.4218 | 961185.019 | 1523340.1354 |  |  | 2.0399e+12
984 | 1180687594.1105 | 1197279474.871 | 216308319.3375 | 170148593.3824 | 1038052886.2872 | 22883001.5762 | 176651197.6213 | 295130617.0199 | 402459514.5916 | 153109043259.8073 | 1885442633.7027 | 1911312258.1017 | 1988398359.2907 | 196660335.0493 | 657259223.1453 | 680766370.6778 | 865577246.4567 | 325934394.52 | 576348288.9573 | 28093011.9353 | 117275752.4105 | 22350748.2533 | 21305101.9614 | 885670875.7955 | 27906716.0139 | 1209967931.5321 | 6761594667.9668 | 617942164.7262 | 148949922.3638 | 2.6786e+12 | 2380268.9087 | 919580.8687 | 1535866.0276 |  |  | 2.8554e+12
985 | 1128561653.2053 | 1216659667.8961 | 197944988.7626 | 178940721.5167 | 1039093701.4208 | 20129079.0124 | 224860221.4039 | 320555392.1824 | 430771200.7135 | 138549581706.5905 | 2021115933.7697 | 1981391911.6842 | 2195894847.0778 | 187841329.8994 | 502098888.1106 | 651576650.056 | 692261114.6077 | 318103184.9434 | 599868876.3085 | 28929905.9386 | 116836132.6176 | 19178279.2472 | 23144492.9662 | 773472569.8301 | 23407880.493 | 1132106176.1649 | 7151755652.9449 | 653737885.6545 | 193726126.5353 | 2.1064e+12 | 2320418.7914 | 997709.696 | 1685200.0282 |  |  | 2.269e+12
986 | 1115894146.358 | 1106107693.5641 | 216142062.487 | 180709088.1117 | 1006067952.8735 | 23117958.949 | 204176071.8061 | 298108809.1594 | 470289246.9112 | 131254352662.1886 | 2023092661.3799 | 1794865104.0778 | 1910811524.9405 | 197928808.2426 | 454270448.8294 | 699416746.6487 | 860634142.0505 | 329479932.2327 | 588583792.5775 | 26351784.619 | 122450530.1554 | 23136784.6358 | 24169203.9749 | 943658057.3675 | 30077580.4165 | 1170172371.5813 | 5514738389.5826 | 628327099.2532 | 197842712.4063 | 2.2733e+12 | 2756564.3261 | 926347.04 | 1822509.9749 |  |  | 2.4268e+12
987 | 1100467934.7597 | 1218597214.9798 | 203921594.1501 | 179178187.6629 | 1084248344.1421 | 20780775.5612 | 192590363.8017 | 299924722.1671 | 447839645.4928 | 131001791587.9456 | 2010884624.2439 | 1678723372.4181 | 2122602498.505 | 173375716.8682 | 577244562.295 | 658745787.0762 | 908697695.0544 | 349614863.3225 | 584806976.3043 | 27240674.4081 | 108705784.3314 | 22612107.0915 | 25558559.0066 | 815114254.2108 | 30888384.1691 | 1125272672.4187 | 6974630959.6676 | 642860595.7462 | 182709069.1411 | 1.8836e+12 | 2459619.0822 | 970931.0383 | 1702816.8118 |  |  | 2.0383e+12
988 | 1092728549.41 | 1225014562.0977 | 221289728.8687 | 162860841.2428 | 1048700734.9916 | 27152720.2274 | 191256463.4394 | 290500951.7753 | 467885129.896 | 138782413890.124 | 2008364342.2014 | 1815798912.0364 | 2135417675.201 | 179562697.6825 | 589525842.6793 | 632613815.0287 | 778154344.5768 | 331902298.3982 | 558399682.2458 | 25678749.827 | 129191340.5115 | 24112256.2582 | 23507124.8728 | 875933369.3667 | 24263689.8809 | 1121300671.7251 | 6952828220.0355 | 704955017.1704 | 191593351.928 | 2.2133e+12 | 2635617.1026 | 1013796.9117 | 1610178.3587 |  |  | 2.3759e+12
989 | 1141779046.5607 | 1080691794.9368 | 189067186.8293 | 147133854.2798 | 1058458659.714 | 27745445.6138 | 206298710.4283 | 270711164.831 | 481553089.3447 | 122881774326.4353 | 1935500765.752 | 2060619796.7447 | 2129793419.7483 | 198063262.5039 | 573055854.938 | 720167749.0745 | 721600730.8058 | 308140881.1136 | 597875286.7033 | 25814497.6287 | 111679779.1518 | 24394752.211 | 24365846.5196 | 856671922.1411 | 31811954.3546 | 1100257547.0574 | 6922312068.2819 | 621921600.4055 | 182295868.0167 | 1.7027e+12 | 2449697.2658 | 945511.4127 | 1642580.6152 |  |  | 1.8493e+12
990 | 1179306208.6326 | 1211079883.182 | 220075621.1317 | 144078004.2833 | 1045068229.4143 | 19996394.2352 | 212097803.8561 | 315658534.2949 | 440426121.3156 | 144361069560.2515 | 1966498144.8353 | 2157398139.9223 | 2114182796.2127 | 194084608.6713 | 638177548.4108 | 678978672.3075 | 793168014.1373 | 309796165.6835 | 611625870.796 | 27119945.328 | 123870764.5535 | 22031734.3966 | 26006069.5607 | 835887539.8195 | 29832828.1596 | 1148167276.0491 | 6331703198.4258 | 642156961.0344 | 191137139.7687 | 1.7339e+12 | 2531134.1847 | 915790.4008 | 1775551.179 |  |  | 1.9019e+12
991 | 1171513864.3403 | 1089776323.4131 | 185807221.7809 | 169483886.125 | 1069761770.7772 | 22735595.6392 | 203646786.713 | 291982553.9358 | 468460479.5532 | 149259776488.3119 | 1807350457.262 | 1739628840.2932 | 2134937468.5142 | 176344544.4936 | 612702563.1295 | 655231625.1582 | 673772167.018 | 339806003.31 | 523937978.6817 | 20620535.319 | 126966713.7631 | 24095772.4122 | 24352212.3093 | 837873551.5477 | 28992500.1423 | 1053084314.9185 | 5191004989.5079 | 678421477.626 | 170024916.7109 | 2.7892e+12 | 2497947.7307 | 918527.5514 | 1694805.8401 |  |  | 2.9599e+12
992 | 1068375614.5472 | 1116779983.1187 | 190178382.408 | 179054352.0192 | 1043734588.0443 | 27034276.5947 | 206993684.2603 | 291696482.1254 | 491318751.9679 | 147873241559.6906 | 2022997367.6084 | 1727820619.7939 | 2131338612.7997 | 187372299.7467 | 618669587.336 | 719646300.7021 | 865014063.7034 | 250437694.914 | 595104186.5903 | 27966964.365 | 94084084.9092 | 22028727.2014 | 24986710.9108 | 884320018.1104 | 26911563.9706 | 1037611722.3853 | 6737901366.8459 | 581495870.7251 | 187943637.5609 | 1.9942e+12 | 2483640.542 | 920387.9613 | 1636207.487 |  |  | 2.1654e+12
993 | 1239505636.4847 | 1159480417.7578 | 212603129.6638 | 172008859.4546 | 1028983543.9112 | 28591321.1182 | 195972657.3061 | 308881986.1319 | 460762732.9151 | 146568307484.3228 | 1987965033.7546 | 1616820797.3829 | 1993972258.0109 | 191787239.1947 | 486828119.1853 | 700732461.278 | 662442765.0327 | 306133378.4203 | 549752009.0507 | 21254668.2472 | 113165019.1711 | 19882483.6756 | 23755474.801 | 881432000.0846 | 27938112.154 | 1184280448.2101 | 6976037278.4302 | 626283303.8037 | 184569084.6035 | 1.6092e+12 | 2792015.7374 | 933203.5193 | 1592605.2156 |  |  | 1.7792e+12
994 | 1169264575.932 | 1146716029.7462 | 219886129.0464 | 173646090.9156 | 1053760303.5968 | 21141283.4871 | 199184264.4966 | 325940727.2045 | 462255881.0707 | 145403344637.3445 | 1753129842.5911 | 1966408659.2276 | 2155090337.3838 | 190206327.4133 | 547203671.9558 | 600146905.5658 | 819627112.3539 | 315439091.1821 | 606772280.0348 | 23078553.5828 | 125260979.6384 | 23397973.3878 | 22611993.0074 | 933772027.6576 | 29293528.8759 | 954283404.8297 | 5803618952.401 | 609062396.1591 | 174433948.796 | 2.0783e+12 | 2481721.6136 | 909799.5544 | 1673733.8031 |  |  | 2.2462e+12
995 | 1258271502.291 | 1177893274.5804 | 207617254.0595 | 181076610.3766 | 1074479987.0597 | 22569339.4392 | 190984359.0657 | 303539469.3992 | 474651584.9408 | 148204820661.3967 | 2091832832.2852 | 2130974083.649 | 2130146613.7719 | 167963657.6366 | 636415366.1282 | 723551658.0016 | 878509865.5439 | 303810760.8162 | 524693283.3621 | 23918401.5724 | 119879565.0448 | 23813939.9228 | 24878117.1127 | 852394570.7597 | 26032173.7157 | 1164332216.0436 | 6405100749.1437 | 634716074.5627 | 193344845.2609 | 2.742e+12 | 2622803.2315 | 1013143.9299 | 1727750.6507 |  |  | 2.9142e+12
996 | 1219487736.0745 | 1217359464.2133 | 198610194.2967 | 167320088.1185 | 1071960832.3003 | 21713594.7408 | 216414524.803 | 328724659.1307 | 463529264.699 | 144619709065.9713 | 1822200152.5446 | 1759870937.5621 | 2068432178.8456 | 187798678.0535 | 636508518.6243 | 651716941.4265 | 732423215.4065 | 300545350.9714 | 561049162.3219 | 26317527.0064 | 118096167.5007 | 23987383.8022 | 23106635.9628 | 894071309.5485 | 25266414.2387 | 1179114711.16 | 6905136894.8492 | 663994996.4257 | 159181096.1652 | 2.1555e+12 | 2338307.3142 | 900423.2371 | 1611048.9123 |  |  | 2.3238e+12
997 | 1160591605.8619 | 1184887106.2138 | 206947065.9497 | 145223536.0399 | 1073075326.1114 | 26143610.2802 | 217695813.0757 | 305422356.7483 | 478391973.4043 | 158620884908.3801 | 2039617135.1251 | 1635995865.1083 | 2112886142.0868 | 202079069.1095 | 600708547.9411 | 711310856.6433 | 730406519.2871 | 344978158.5814 | 563370253.442 | 27731222.8013 | 97301739.274 | 21813661.4068 | 25379606.7219 | 738011057.0002 | 29593835.9692 | 1190947334.3688 | 6261802694.7179 | 457779333.8166 | 162729829.7896 | 2.0002e+12 | 2371820.3427 | 991170.7534 | 1622390.9375 |  |  | 2.1816e+12
998 | 1205954831.019 | 1064495925.565 | 222261177.5441 | 170969176.2603 | 954501122.7758 | 23770817.8691 | 197063920.6757 | 318795641.2217 | 476830964.2003 | 141971905148.2893 | 1513451106.9756 | 1970831150.4527 | 1933849071.3155 | 180636474.9107 | 618978879.0606 | 639950195.2526 | 907672258.0398 | 286864575.1625 | 608637110.8686 | 28443599.1518 | 135987456.99 | 23041305.3919 | 25467027.056 | 899145262.8243 | 30692738.7222 | 995990247.9079 | 6724012309.8078 | 695546536.9919 | 199309205.6622 | 1.9641e+12 | 2508100.7365 | 965185.7905 | 1816675.464 |  |  | 2.1291e+12
999 | 1235474146.823 | 1183894655.3493 | 206684206.6282 | 168397735.6266 | 1027362206.5045 | 24197674.7177 | 202635734.7946 | 288208832.5437 | 491399729.077 | 138751421546.9969 | 1984507670.4727 | 1950356734.68 | 2150313421.5234 | 201040713.8146 | 606109987.6985 | 651208049.4992 | 875151552.4205 | 237932125.4771 | 571554190.1493 | 26538114.6196 | 112748293.6099 | 22963070.4015 | 25893475.1329 | 846772296.5553 | 27830270.3688 | 1059441415.2156 | 5699543313.3084 | 607678808.0821 | 201305725.1978 | 2.426e+12 | 2632996.1191 | 935883.1813 | 1820038.4083 |  |  | 2.5875e+12
1000 | 1181304707.4341 | 945617305.8907 | 204602442.0989 | 152129773.0429 | 1087366661.3237 | 25955854.7158 | 211680452.1015 | 274656214.0236 | 425428272.8397 | 140346911526.2309 | 1922230082.8195 | 2123311615.591 | 1855350618.9764 | 194328300.2632 | 625942988.8585 | 705638896.7768 | 868820480.9716 | 253961806.3822 | 550954133.2198 | 27175794.3778 | 123664513.2667 | 23830895.3857 | 25527761.2312 | 772249911.5051 | 23833898.3726 | 1136469658.7388 | 5901690933.8333 | 668137306.9691 | 195574006.3553 | 2.1842e+12 | 2500826.1212 | 978729.9197 | 1751545.7032 |  |  | 2.347e+12
1001 | 1212638259.7604 | 1170880067.4312 | 215125000.1151 | 173217552.5559 | 1067813206.8634 | 26848482.4522 | 222157823.5925 | 306918116.9607 | 481086537.8168 | 125852034555.0262 | 1690157611.0293 | 2057602765.1657 | 2087022274.8943 | 173997676.8261 | 604474402.0624 | 663405300.3988 | 858720229.7278 | 307904733.6952 | 608993366.4206 | 26296325.5144 | 114294282.8292 | 22974957.6943 | 25334850.6682 | 849360646.6944 | 23781088.1272 | 1047227873.5035 | 4896890413.9667 | 615857675.6628 | 201656789.9762 | 1.9411e+12 | 2370314.8383 | 965598.4912 | 1675879.6083 |  |  | 2.0887e+12
1002 | 1241044223.3848 | 1051428640.7245 | 213006965.124 | 155725659.6986 | 1021080575.184 | 23063574.6151 | 186599553.0623 | 282479890.4209 | 484351598.4388 | 133281085666.0475 | 1883118803.048 | 2191537637.7485 | 1998271372.2747 | 193598037.8827 | 475447683.117 | 709830477.568 | 824505483.1054 | 281227297.3394 | 586991386.369 | 20041287.0234 | 112891733.7125 | 24729141.7328 | 23155360.9427 | 861252606.6894 | 26416926.1214 | 1165576210.8051 | 5175318042.0396 | 707104522.6754 | 197228751.2542 | 2.5873e+12 | 2265005.219 | 957637.506 | 1578215.4843 |  |  | 2.7427e+12
1003 | 1169387869.0458 | 1153147862.9257 | 211372612.3031 | 180699212.5151 | 1087065190.351 | 24047206.0245 | 222572446.7398 | 309113690.6036 | 441563059.5747 | 156532473057.7047 | 2003023583.5844 | 1926642893.6738 | 2163154198.7113 | 173004356.7822 | 612922736.5746 | 686130355.5978 | 872582893.463 | 330041295.1598 | 533824174.66 | 25473300.251 | 96762231.2334 | 22956538.0612 | 25772300.2076 | 733589308.4387 | 30732068.7194 | 1199675459.0102 | 5644602568.3547 | 699703055.8629 | 178175579.1554 | 1.5332e+12 | 2400097.3934 | 928125.6818 | 1690951.634 |  |  | 1.7125e+12
1004 | 1262312811.8221 | 1149079760.0865 | 215268810.858 | 175239553.48 | 1019155914.9164 | 23183604.9611 | 224626380.2743 | 317198300.3648 | 456350342.8969 | 146724710664.1307 | 1867865014.737 | 2178157095.5412 | 2059647735.7053 | 188771174.2253 | 636162719.3992 | 706913118.5284 | 788589491.5698 | 229337573.9187 | 585967729.2759 | 28347197.2196 | 127918209.1636 | 20426147.0573 | 18514377.5272 | 768836622.377 | 26985395.1923 | 1190656513.8558 | 5677359118.2067 | 651755886.2611 | 196735396.6541 | 2.2451e+12 | 2504761.8571 | 982551.0416 | 1587571.0112 |  |  | 2.4146e+12
1005 | 1224400981.3972 | 1141745441.6294 | 213201828.0353 | 180907375.7837 | 1038021654.776 | 21698957.6469 | 211367895.7261 | 318974379.9353 | 454736233.296 | 118137810293.7589 | 1815286800.3878 | 1870935005.3232 | 1678096902.7805 | 185091116.8255 | 535411607.9442 | 639534873.8947 | 838029797.7615 | 252171393.102 | 597215420.9112 | 22107728.0212 | 110950710.2107 | 23463844.929 | 24369184.9689 | 854970153.9443 | 25362956.4565 | 1050578414.2211 | 5851257426.8953 | 666651539.6779 | 181983838.1373 | 1.8573e+12 | 2858944.7353 | 950398.8115 | 1690942.352 |  |  | 1.9975e+12
1006 | 1090550470.6519 | 1228573078.3283 | 219575203.0861 | 181359976.5637 | 998271776.2719 | 20617813.3768 | 210785328.0198 | 286049129.5846 | 414609703.8011 | 145342196473.5334 | 1877305044.3629 | 1590467880.5481 | 2188786270.2198 | 193739525.2128 | 601955655.2214 | 659683684.7987 | 752355451.476 | 326901883.4662 | 548015429.3953 | 21234168.7014 | 101806460.9798 | 24558591.117 | 23685699.5975 | 781558333.3705 | 25751534.9964 | 866777227.5626 | 6917644184.6586 | 635768589.9282 | 199867654.1296 | 2.153e+12 | 2397128.2148 | 925565.2048 | 1684330.4944 |  |  | 2.3213e+12
1007 | 1195644851.0279 | 1184316700.069 | 218606989.004 | 177678456.9087 | 1009186715.9852 | 21906842.7354 | 219759382.7486 | 296464720.5716 | 486309640.6877 | 110879804452.134 | 1905245476.7101 | 1751771320.1246 | 1615901280.3756 | 173230815.9462 | 621153014.6108 | 680126844.6302 | 762240085.0572 | 299552331.1593 | 591087319.9031 | 24339475.5294 | 122630730.9214 | 23261779.0172 | 25677428.6493 | 836668846.4891 | 30237233.8409 | 995628306.917 | 5800676557.4178 | 575658142.2744 | 198702185.2464 | 1.549e+12 | 2268058.6248 | 883245.8656 | 1634041.7651 |  |  | 1.6818e+12
1008 | 1195959176.7337 | 1196245607.4998 | 205234895.6051 | 172223116.4391 | 948951054.6034 | 24052446.6472 | 220918786.2635 | 317379987.5997 | 402824166.2959 | 159875347724.4333 | 1772300426.2297 | 1750040412.5499 | 1908958566.7169 | 197462662.473 | 604328016.3576 | 696252596.2604 | 849794685.5918 | 348805817.4363 | 591158543.5849 | 21145123.9714 | 126799901.4061 | 21537695.9883 | 20850527.896 | 897530948.1355 | 23718767.7528 | 910055868.9682 | 7044860215.5527 | 688781393.7591 | 171724036.4918 | 2.3547e+12 | 2416926.5568 | 934556.4931 | 1748938.494 |  |  | 2.5379e+12
1009 | 1179848847.7271 | 1056162857.5973 | 213856702.4796 | 162012523.1737 | 1068891732.6818 | 24341255.9543 | 192935701.5299 | 325550642.1353 | 431292035.1216 | 112505034312.3925 | 2060758766.0428 | 1860191714.7499 | 2098084966.6258 | 198980051.4378 | 635525479.6106 | 647287626.8571 | 736095962.3306 | 260898980.8215 | 584904046.214 | 27593467.6325 | 109424534.3955 | 21535546.7778 | 24792818.2472 | 896817644.8442 | 27254900.8622 | 1140128888.0596 | 5916151155.5274 | 681801423.7288 | 181090601.6338 | 1.643e+12 | 2308610.8128 | 973445.6727 | 1615666.4629 |  |  | 1.7783e+12
1010 | 1253722676.2409 | 1205458192.4645 | 196803277.8569 | 157183147.5426 | 1081260824.671 | 26643980.4043 | 201895791.4958 | 287586614.91 | 478497809.2136 | 143300279629.2719 | 1886038561.6014 | 2082559976.2058 | 2163462171.2179 | 195993027.6548 | 639208259.8209 | 622297972.2107 | 923360199.0266 | 265173104.9561 | 565877268.7367 | 24193214.6101 | 134029042.5283 | 23890301.6658 | 26003563.5876 | 891961913.8334 | 27625958.7374 | 1045944773.9784 | 6475481506.8282 | 645749200.0024 | 166233831.8859 | 1.7017e+12 | 2459927.848 | 901800.269 | 1656671.4913 |  |  | 1.8687e+12
1011 | 1144834596.6966 | 1184764155.5744 | 208319346.4249 | 177353742.3145 | 1045194046.7981 | 25602946.8077 | 221565350.867 | 322666043.8868 | 424145933.4946 | 152731757918.9048 | 1958957157.3034 | 1494959576.6619 | 1759051269.7771 | 180868177.5861 | 629236194.6678 | 640705334.8944 | 806065161.9019 | 272494812.0997 | 571566441.8208 | 25385453.3474 | 112344081.8235 | 22876120.3958 | 22415390.4058 | 696596648.3644 | 23955103.4619 | 1172276492.5315 | 4868601722.958 | 569768523.2577 | 179936041.1428 | 2.6815e+12 | 2294895.5929 | 933903.3702 | 1571415.1726 |  |  | 2.855e+12
1012 | 984837074.8557 | 1101592208.1552 | 201006443.1717 | 151072400.7787 | 1032442449.2415 | 22225363.8427 | 202375344.3633 | 325949872.2432 | 464015561.4328 | 146742533632.0541 | 1944666844.3474 | 1578041444.6736 | 1724485857.5955 | 178688452.8543 | 647983688.8246 | 583299252.6374 | 834851883.8774 | 309299307.4891 | 596255375.943 | 21910562.256 | 125490191.2621 | 22629553.8991 | 20152134.3319 | 869219273.7858 | 28662691.087 | 913790562.5815 | 6892695694.942 | 518400812.829 | 192749661.9939 | 2.6786e+12 | 2437631.1041 | 1006845.535 | 1700631.6948 |  |  | 2.8478e+12
1013 | 1149911282.4646 | 1183760019.4517 | 202538391.0229 | 169097224.7994 | 1084198159.695 | 22487472.2908 | 185048308.7113 | 263501809.1923 | 494958355.4207 | 152099507183.1659 | 1911651097.2801 | 1646236503.1265 | 2088530059.3308 | 193972381.6285 | 572305520.3207 | 597204360.5213 | 783868596.6681 | 334016712.7279 | 592764733.5917 | 26670357.8703 | 120319628.1683 | 23533752.7313 | 25479407.5287 | 797302845.1584 | 29291758.0543 | 1121088093.45 | 6187739863.079 | 624668613.6333 | 195233828.9983 | 2.0978e+12 | 2322736.4343 | 954115.5412 | 1691064.6633 |  |  | 2.2725e+12
1014 | 1173627140.8678 | 1208016131.5412 | 210887283.3672 | 169389290.1183 | 1081295863.1024 | 19297364.3957 | 219118009.061 | 319102214.7447 | 424070409.2633 | 121412629127.5463 | 1947365519.3058 | 1833426551.8652 | 2213464532.8729 | 190516757.3155 | 593018574.7461 | 677023015.5382 | 708841360.7737 | 301394450.498 | 610226020.7818 | 17811291.2547 | 98546985.6688 | 24300332.5975 | 22503238.2776 | 797393450.7125 | 30242772.4162 | 768033575.816 | 5603015925.6807 | 670407464.4915 | 187258948.3638 | 2.7374e+12 | 2438029.7553 | 986890.7859 | 1584544.428 |  |  | 2.8809e+12
1015 | 1223241089.3452 | 1194846162.7395 | 199800897.8248 | 177507554.3106 | 1078990898.5466 | 24833673.0735 | 208885433.7372 | 293289301.3096 | 388230153.3427 | 157417848740.8753 | 1937771794.5959 | 2117388104.6124 | 2024898065.2141 | 198033252.1939 | 595499657.9499 | 718214587.2932 | 743006633.6555 | 263750359.4066 | 571127552.5609 | 23799467.4633 | 121402896.9395 | 23287558.4197 | 25999922.6298 | 874855923.1982 | 26185055.7579 | 934408406.0379 | 6992321833.1577 | 711945685.7111 | 184944815.253 | 2.1087e+12 | 2298113.5667 | 888162.463 | 1756987.3682 |  |  | 2.29e+12
1016 | 1128015679.0698 | 1085085050.4979 | 208339719.5294 | 175919870.3289 | 1082712282.7358 | 23711768.2399 | 194756759.8718 | 307466583.7069 | 470901195.0544 | 142896204330.9836 | 2009969797.2324 | 2039743252.1371 | 2074187752.4292 | 182393139.4856 | 617066270.1288 | 652442429.2926 | 896299027.9049 | 286159863.6763 | 541751503.1751 | 27932463.8607 | 123574467.2736 | 22410855.7704 | 24767423.2534 | 837963242.8842 | 27288942.5018 | 1092246919.927 | 5456326263.8965 | 645418204.5201 | 201279094.2766 | 2.778e+12 | 2602843.822 | 949708.6784 | 1698099.5856 |  |  | 2.9433e+12
1017 | 1132990667.1062 | 1136707344.1289 | 187344800.1495 | 172470300.6477 | 1080817104.7918 | 24472136.3196 | 202441883.6218 | 324264288.7362 | 436175591.4331 | 147441781905.8116 | 1684092272.1887 | 2104419675.9165 | 2187410370.8181 | 193969646.805 | 652660487.3879 | 607713475.1583 | 653068445.7092 | 278103188.1172 | 576767592.7172 | 20854489.9287 | 115970386.9147 | 23795915.0872 | 21944137.3198 | 877816498.3119 | 26456164.1229 | 1088536469.9413 | 7069511851.4772 | 700768675.5959 | 174763653.4542 | 1.7177e+12 | 2849601.0738 | 978174.3209 | 1508320.0312 |  |  | 1.8889e+12
1018 | 1171579423.8524 | 1200296968.9667 | 221085927.7193 | 160702096.1102 | 976513468.5356 | 22516677.5835 | 224683773.9179 | 325907638.7419 | 495362288.318 | 130276351630.8132 | 2033585772.027 | 1836948421.6876 | 1770572570.9582 | 185378266.8517 | 562846540.0911 | 608803032.4701 | 849240483.7993 | 355116367.9657 | 569262675.9603 | 24368937.4926 | 98012740.0953 | 19968372.7029 | 25989050.2974 | 783441813.7632 | 30011104.5434 | 1200380714.921 | 5708017170.2066 | 697069278.6184 | 181152954.0343 | 1.8978e+12 | 2634931.6208 | 927562.7893 | 1542214.6367 |  |  | 2.0504e+12
1019 | 1193183791.6545 | 1218608041.0932 | 221219862.4549 | 172032197.3651 | 1053924474.3887 | 24736923.9647 | 224029596.9911 | 285952414.4312 | 486659678.5972 | 144453026517.3484 | 1919574033.2275 | 2171036611.2602 | 1993373732.3517 | 169600250.0631 | 542688292.1132 | 724006108.4489 | 809481330.2668 | 318947925.3492 | 610296563.2974 | 20589414.4199 | 129040494.8945 | 20788703.6127 | 24636508.2108 | 794859211.3657 | 26758214.9271 | 1119722100.2201 | 6728679064.3465 | 614817045.2188 | 178677187.2543 | 1.8416e+12 | 2665713.6389 | 1042442.7262 | 1675312.5455 |  |  | 2.0099e+12
1020 | 1124570300.8743 | 1194686389.8643 | 202133867.6552 | 166357897.4305 | 1044833312.3398 | 24247827.1989 | 189417873.7917 | 326208589.0549 | 485500276.9071 | 132906234279.0616 | 1992146206.0894 | 2052649184.5222 | 2205275084.7876 | 158511449.8495 | 580801949.9825 | 683925431.192 | 831957286.1996 | 292576725.2902 | 521951641.7197 | 25107167.2292 | 112636753.0808 | 23896932.2891 | 24620355.7472 | 810958068.0599 | 25021126.7253 | 1166498022.5645 | 6209139585.2114 | 694879920.6323 | 170729203.0014 | 2.478e+12 | 2514688.8224 | 918505.6807 | 1726862.8129 |  |  | 2.6342e+12
1021 | 1062273953.1314 | 1008795849.5844 | 196896286.1575 | 176712782.3285 | 1064141329.6669 | 25593045.8531 | 201590380.1034 | 284476078.1882 | 491320400.6031 | 150943366159.216 | 1880931400.73 | 1873995915.2917 | 2126988164.3488 | 186053864.2632 | 549351539.681 | 670685465.2978 | 862623586.1593 | 320841415.3739 | 572915583.7123 | 26220767.0027 | 112459146.6474 | 23153574.6445 | 19291920.1698 | 906094630.5288 | 27410720.3016 | 1210152135.1086 | 6712628256.9763 | 544924283.294 | 183145278.868 | 2.0875e+12 | 2596732.2019 | 904901.6981 | 1671913.5424 |  |  | 2.2617e+12
1022 | 1215755352.5535 | 1145177193.8214 | 211533748.0488 | 172710127.0712 | 968591986.2361 | 24208613.1264 | 197689302.2888 | 281196123.3717 | 488394591.1132 | 135062727378.8621 | 1931347567.7171 | 1516581369.6725 | 2045376524.8803 | 180432325.4604 | 673230903.4257 | 670652444.845 | 664187587.4817 | 295409307.4615 | 610140879.4583 | 21128464.7847 | 107924813.6875 | 23492437.8926 | 25702698.7432 | 757733823.9746 | 27653041.205 | 1005239102.9935 | 6053617028.4145 | 704884882.3452 | 196476623.6024 | 2.4653e+12 | 2458656.1034 | 950484.3086 | 1647863.6924 |  |  | 2.6226e+12
1023 | 1168391565.6767 | 1215192777.6662 | 220102664.822 | 172244063.4909 | 1055187628.3077 | 21769020.6139 | 201167511.8108 | 297653591.4744 | 464769144.3107 | 128014451297.5213 | 1930760998.2729 | 1574633888.0746 | 1792144832.1871 | 197133681.9241 | 615707971.0815 | 644016642.4604 | 692818866.5534 | 340836891.1363 | 606069705.9431 | 27010471.9794 | 128265672.4409 | 24149072.7107 | 24451727.5347 | 918855713.3389 | 29150104.7684 | 956542325.6478 | 5945911371.1207 | 672942134.0841 | 171332970.1581 | 2.5229e+12 | 2604488.1291 | 896805.2141 | 1606350.5314 |  |  | 2.673e+12
1024 | 1041748792.3934 | 1209287400.0029 | 226330769.6789 | 177323797.5968 | 1079203610.2627 | 22821491.875 | 180595313.5366 | 298185515.4406 | 498089305.7507 | 130089567994.4088 | 1976354457.5945 | 2152266219.4052 | 2194306427.7471 | 189316450.6792 | 553332198.6705 | 615726204.6626 | 793529813.9435 | 321985180.4628 | 559177808.8317 | 24051372.6245 | 123366041.4552 | 22164746.53 | 20638527.9881 | 831455004.5171 | 27640313.1948 | 1161776478.3121 | 6169736831.2248 | 697686714.2026 | 148289397.5121 | 1.8847e+12 | 2340344.9593 | 913364.5858 | 1751232.479 |  |  | 2.0381e+12
1025 | 1136672039.717 | 1213881349.4894 | 215052225.8963 | 160687821.9694 | 1055546552.3163 | 23716903.8043 | 207880331.04 | 312205276.0557 | 476312136.6995 | 141751518958.3402 | 1802100318.9391 | 2006318661.1825 | 2102380252.9139 | 202318095.4809 | 501876407.6129 | 713240486.8174 | 915043927.3861 | 307215096.7172 | 581288684.3538 | 24012545.2639 | 105405858.4853 | 20604689.8396 | 21556193.1734 | 756511992.1101 | 29117050.7802 | 1161032338.2214 | 6603003820.0975 | 670172551.5243 | 201550071.9041 | 1.7748e+12 | 2377479.4811 | 935994.1398 | 1773598.0986 |  |  | 1.9401e+12
1026 | 1068203713.9544 | 1136550749.8273 | 224342539.7874 | 171028536.0346 | 1069570370.5578 | 24814825.3386 | 212370313.5073 | 323898749.0146 | 437769398.7321 | 129068381570.3033 | 1919740264.648 | 2054201435.714 | 1630279386.947 | 189558631.7344 | 637785651.7338 | 658052613.1153 | 904762788.5479 | 356656975.6372 | 616223609.7653 | 24126237.0675 | 133740796.4176 | 23442294.0058 | 23319703.066 | 826078929.5976 | 24621571.0417 | 901364081.4095 | 5913414309.9072 | 623795159.0161 | 189056564.144 | 1.9085e+12 | 2259827.3724 | 959175.9244 | 1580422.1588 |  |  | 2.0599e+12
1027 | 1019591735.6791 | 1159683064.1043 | 214301482.7429 | 158669000.5894 | 1035081042.54 | 26343838.5927 | 202376175.4099 | 321571042.053 | 463055825.9045 | 156147061371.3263 | 1860572072.3049 | 2104722579.4568 | 2197991175.2087 | 181929055.1056 | 497572749.9391 | 699623654.8209 | 896488778.5318 | 300642899.893 | 589308860.4466 | 24862516.0786 | 99493357.4235 | 20680144.9432 | 22213087.0394 | 795791120.014 | 19908026.5828 | 1108253133.7491 | 5368214467.9163 | 655327939.4741 | 197150535.4084 | 2.095e+12 | 2577824.3188 | 936824.5839 | 1628425.2196 |  |  | 2.2734e+12
1028 | 1235662941.802 | 1225937599.2787 | 204995118.0502 | 159943866.0284 | 1079210936.5571 | 23311353.0246 | 208847209.7847 | 290871832.1697 | 491443926.9589 | 143294462799.8152 | 1900532405.132 | 1696199513.013 | 2071354863.1345 | 168063425.1292 | 539632136.5985 | 699816060.5337 | 794237432.4228 | 338195841.3235 | 555664110.2562 | 26650593.1022 | 122160604.432 | 24713082.5405 | 24087957.4742 | 902249936.8268 | 25975184.081 | 1171114228.8974 | 6599008605.2283 | 713031463.2971 | 183520257.6912 | 2.4484e+12 | 2527434.8662 | 887123.2617 | 1473416.7164 |  |  | 2.6152e+12
1029 | 1062258275.6203 | 1217642355.964 | 207759103.7137 | 159078930.6231 | 934562245.0912 | 21289838.2022 | 212815756.3841 | 309229459.0889 | 465382741.5937 | 146868062696.1616 | 1648276269.0313 | 1878768983.9153 | 2065287082.8548 | 177278680.6251 | 652350953.0143 | 664098235.3166 | 840923720.5415 | 299726213.6419 | 523792905.3498 | 23527490.1805 | 106776710.8986 | 17448878.0162 | 25792983.1302 | 635841161.1717 | 23882292.2828 | 1196773398.41 | 6285714589.6464 | 688964383.3724 | 193957690.6873 | 1.9383e+12 | 2282663.7616 | 1068086.263 | 1577638.5921 |  |  | 2.1077e+12
1030 | 1177451265.6772 | 1167941828.7107 | 196251311.8196 | 164660369.446 | 1000001131.5916 | 23875111.5178 | 206579148.013 | 311421146.2363 | 498225031.2937 | 158838463515.347 | 2019924186.8042 | 2032243034.6184 | 1945091719.4197 | 181917125.8839 | 575127316.9078 | 725559500.278 | 797035056.9595 | 272075444.1741 | 543966690.2325 | 24968654.8166 | 100894701.0683 | 24260387.4616 | 20847682.6283 | 859640197.176 | 31369689.4282 | 1170734890.0218 | 5497701683.6969 | 657287198.8211 | 199138854.5688 | 1.79e+12 | 2780502.4716 | 924284.7749 | 1742394.2505 |  |  | 1.9713e+12
1031 | 962597490.8039 | 1177324600.6181 | 224263797.9857 | 137014619.7767 | 1040743364.9853 | 23414010.3509 | 221693451.1273 | 324834891.1576 | 480678426.7317 | 152691152231.1958 | 2002860470.8036 | 2027519914.3838 | 2187416995.1635 | 177257680.6105 | 538458865.9778 | 606485241.4047 | 711634539.3858 | 318721663.062 | 556495525.5651 | 21401854.796 | 111004784.7175 | 22929914.0535 | 25029332.8419 | 896036527.9301 | 27777551.6764 | 957411861.323 | 6785230416.4256 | 637854071.9752 | 195082714.4757 | 2.4018e+12 | 2672745.2942 | 1008375.1905 | 1597868.0615 |  |  | 2.5779e+12
1032 | 1179755053.6404 | 1226753184.3677 | 214971974.6123 | 171012527.9588 | 1071411938.6213 | 24883339.4913 | 222822525.7391 | 326096332.3662 | 413621072.3155 | 150331476407.5482 | 2058317421.6006 | 2043778994.6308 | 1671379675.4222 | 180592938.889 | 515481059.4439 | 653093479.91 | 857850798.6227 | 330152651.5344 | 600128185.6206 | 24792137.5608 | 114490278.9134 | 23603478.0455 | 25561600.2255 | 780220052.9281 | 27906157.2114 | 1129032235.3815 | 6412243529.8136 | 620178929.687 | 201508526.0301 | 1.5912e+12 | 2385172.8004 | 923888.7629 | 1540903.8184 |  |  | 1.7646e+12
1033 | 1189261309.8064 | 1179111161.612 | 220676812.6192 | 155854009.4703 | 1026292534.322 | 28175698.1983 | 184561947.3907 | 283178820.1344 | 498437001.7749 | 149672894987.9549 | 2001834652.1448 | 1769569151.515 | 2199509561.2556 | 188032420.6341 | 608693244.8622 | 674181153.9912 | 713687180.1927 | 288465977.9472 | 597102974.4045 | 25435772.4971 | 120667928.2293 | 23008892.8387 | 25903423.8843 | 929805978.2692 | 27178750.961 | 1104213364.7903 | 6704719677.7089 | 528643146.3759 | 185135933.1751 | 1.8825e+12 | 2365659.7842 | 919768.7249 | 1452009.2339 |  |  | 2.0557e+12
1034 | 1042302120.8043 | 1223276183.878 | 202479290.435 | 179808257.7944 | 1075900299.565 | 26329499.0255 | 205031078.898 | 289613202.3558 | 467977571.4109 | 122383317206.7439 | 1952647655.8606 | 2071504019.1988 | 1739477231.8029 | 186527491.2597 | 641155023.5904 | 674778324.4923 | 778358266.5815 | 245169857.909 | 560065899.3817 | 23267114.7743 | 93141061.4121 | 22653124.2686 | 24997531.4959 | 910120331.6066 | 24591410.2356 | 1200717432.3414 | 7070522039.4044 | 670135879.0135 | 200642239.7974 | 2.0175e+12 | 2290125.02 | 934654.8967 | 1621085.7495 |  |  | 2.1637e+12
1035 | 1212855181.8376 | 1138070524.2162 | 199027700.7144 | 154055104.6906 | 1013303987.1387 | 26135083.0266 | 219947863.347 | 293228925.0505 | 469328097.4861 | 118066827457.2079 | 2024125962.3653 | 1881649717.4374 | 2022560372.8829 | 201984186.7088 | 489963839.6527 | 617071243.8239 | 880815759.2693 | 324997280.4384 | 516126902.9461 | 26484575.4087 | 130729430.5526 | 24366501.7393 | 25656242.976 | 752849068.6308 | 26930848.8464 | 1166299540.7779 | 7268739935.2081 | 644011694.1816 | 175089718.3574 | 2.1942e+12 | 2462550.8511 | 1038464.9672 | 1783500.5915 |  |  | 2.3361e+12
1036 | 1194805024.2178 | 1141294046.5748 | 210847295.6848 | 174193580.0212 | 1034201638.7249 | 24409980.6877 | 207548346.8239 | 288408872.8603 | 492760813.9836 | 157012734835.7131 | 1844245503.8002 | 2133783382.7264 | 2118941851.8805 | 180801763.7292 | 628047414.2783 | 694926389.8101 | 875846042.2112 | 309932749.2991 | 606818695.0925 | 27637485.9841 | 111152727.4296 | 19859616.8179 | 21652261.8082 | 901796339.8944 | 29744810.7652 | 1070454810.4058 | 6580480156.5948 | 551935315.0784 | 187646906.9847 | 2.0695e+12 | 2426298.0173 | 923093.807 | 1801521.6058 |  |  | 2.2502e+12
1037 | 1211966698.3898 | 1211079924.5722 | 221760056.6602 | 173010247.8729 | 1081485940.6092 | 22415201.5575 | 216773978.9232 | 303985527.8409 | 475552404.5691 | 151914096624.0901 | 1562771304.8458 | 2126681261.3244 | 1787451414.2033 | 197166442.7478 | 586741052.8037 | 707907232.731 | 852374812.3376 | 340974081.5884 | 594057633.7296 | 26438326.8187 | 115432358.1233 | 22957678.3154 | 25258642.4953 | 888100299.5084 | 30379806.855 | 1032385413.5637 | 6807839908.6791 | 661891612.7675 | 197920459.9126 | 2.1878e+12 | 2616209.0743 | 909692.8098 | 1841644.0151 |  |  | 2.3632e+12
1038 | 1186749760.278 | 1091129244.7899 | 206586392.7997 | 177582370.3102 | 952617512.4454 | 22300611.7074 | 185571888.9856 | 318371840.26 | 407861472.8713 | 129419863274.1673 | 2062010758.1485 | 1900103970.7837 | 2032314577.3028 | 195549883.5037 | 475828600.1022 | 689859364.356 | 800415588.9958 | 358713393.7163 | 567929630.6367 | 24912081.4076 | 123839752.4798 | 18307036.8713 | 20197514.8716 | 745881178.1351 | 24384686.9202 | 1120591325.1278 | 6189082612.4663 | 677001484.3922 | 194785845.5796 | 2.2514e+12 | 2626485.3483 | 941427.0351 | 1590293.0325 |  |  | 2.4036e+12
1039 | 1141713855.0193 | 1160736513.9621 | 199431133.1775 | 176531599.4334 | 1068261363.2183 | 23331969.9624 | 198762396.8053 | 326960032.3303 | 476524046.3948 | 157598567504.07 | 2031941480.7147 | 2141572985.4597 | 1679622424.1485 | 182695492.5256 | 476954392.7263 | 689017986.3587 | 655149828.7538 | 335831901.7198 | 566263078.1237 | 26477767.2902 | 120637320.9949 | 22071141.5158 | 24578556.5727 | 830464255.8468 | 22980828.797 | 1123287371.3913 | 5955582768.0563 | 638097145.3644 | 152944872.8646 | 2.2053e+12 | 2566092.8875 | 963256.5813 | 1573950.8481 |  |  | 2.3854e+12
1040 | 1098455484.9382 | 1169923271.6099 | 192910978.0453 | 175405705.2574 | 1083485252.0432 | 22746638.8643 | 208921951.3026 | 302834104.2376 | 469967906.3623 | 152734435498.6429 | 2016689985.4261 | 1923560514.7197 | 2141085384.4331 | 178272150.7234 | 518280483.1928 | 635463221.0477 | 814447698.868 | 291094847.8101 | 569389422.7618 | 22674963.6236 | 118415098.9988 | 23617702.8578 | 24327018.843 | 898281061.5625 | 27723503.9578 | 1180784393.9588 | 6516866090.2151 | 679208072.6376 | 191606582.5281 | 2.1257e+12 | 2380245.0215 | 969007.8629 | 1524569.716 |  |  | 2.302e+12
1041 | 1163638515.7441 | 1185551108.8034 | 219287951.8261 | 163683495.9116 | 1049210364.5363 | 23805797.8414 | 218628633.2022 | 315462351.6465 | 435397960.6266 | 160099124598.358 | 1904555130.6607 | 2028993766.4 | 2212227785.2183 | 195568319.3437 | 533122108.8195 | 619212421.2434 | 779476553.5738 | 308821091.3101 | 575888804.3483 | 27385507.5504 | 104106509.4775 | 19901767.2895 | 23646102.7714 | 794785789.7552 | 27528560.6876 | 996258436.4525 | 6016500974.7881 | 700152182.3867 | 200466647.4837 | 1.934e+12 | 2415625.0941 | 961380.3954 | 1528203.5723 |  |  | 2.1169e+12
1042 | 1055848112.2183 | 1190324138.4504 | 198712866.1436 | 179004848.1067 | 1069793745.7041 | 24742343.2354 | 211689906.8594 | 279870945.0352 | 465591114.2727 | 132140242026.1615 | 1799592563.2747 | 1928724547.9515 | 2082747176.9067 | 200303903.2234 | 656764190.6011 | 690851519.0326 | 910085301.4559 | 346841243.4121 | 551085591.7994 | 27071996.0426 | 132656359.8007 | 18702065.7699 | 23322743.8254 | 819939200.4458 | 26943850.6408 | 1048072121.1879 | 5778240034.4508 | 631356741.5239 | 174208827.7063 | 2.1392e+12 | 2316174.3413 | 929456.7882 | 1646615.2437 |  |  | 2.2938e+12
1043 | 1096304727.9909 | 1199509105.1532 | 207508360.3752 | 167780693.6805 | 1069532909.0936 | 25614310.7495 | 203938221.5453 | 318475376.6138 | 498145231.071 | 142519555463.8541 | 1455957963.3999 | 1737542155.2785 | 1883511691.2733 | 172620675.9268 | 546800057.3247 | 620202054.3744 | 827668871.5646 | 307840474.5514 | 603832987.6918 | 25843296.9868 | 107558035.4263 | 23956395.8089 | 19632231.3914 | 895065460.0076 | 22644250.9248 | 936934204.8667 | 5562767516.8051 | 639909777.2719 | 181840245.0484 | 2.0518e+12 | 2373592.9237 | 914724.0555 | 1786000.0448 |  |  | 2.2157e+12
1044 | 1106607615.2028 | 1221955785.663 | 220727630.5353 | 175621067.7902 | 1057035634.0751 | 24083121.8193 | 196658275.4802 | 325951562.7841 | 422578426.8618 | 128966905209.9724 | 2076371182.2643 | 1687299898.3634 | 1746847556.9135 | 201055914.8455 | 681858749.9162 | 532798041.221 | 783531501.8273 | 291903703.2534 | 603922824.198 | 24666014.8864 | 127816726.9422 | 19194245.6387 | 24338616.034 | 838673143.0204 | 27834972.5732 | 1062603736.6515 | 5485581573.1068 | 630456394.7307 | 199277989.9618 | 1.9739e+12 | 2425508.4588 | 958036.0787 | 1677020.2839 |  |  | 2.1247e+12
1045 | 1189563593.2183 | 1221336548.8154 | 191532124.8474 | 162714973.2224 | 957577605.8443 | 19142174.3712 | 184062114.0119 | 328636605.9829 | 497311562.8348 | 138762961249.4351 | 1696508563.4665 | 2129756398.9407 | 2134762305.7799 | 186682337.2029 | 608560801.7963 | 630210525.575 | 734059172.525 | 309038323.6296 | 489249480.7491 | 23975793.5333 | 105314725.5037 | 23895459.5848 | 22854995.5152 | 775908113.317 | 27361374.0193 | 1038962419.0833 | 7019074865.9243 | 608553472.5075 | 195007818.3384 | 2.2395e+12 | 2325294.0424 | 885120.7323 | 1651716.1928 |  |  | 2.4018e+12
1046 | 1210501990.489 | 1188101896.4565 | 207706007.2483 | 161597672.6145 | 1049564339.1003 | 21169014.2175 | 192764005.6077 | 317572985.4486 | 496753457.7297 | 126337366347.3165 | 2098090794.6335 | 2159341604.6838 | 1522975744.9368 | 200532686.956 | 630805432.6486 | 694760268.4388 | 820990412.3021 | 288949077.6966 | 415943080.8307 | 23064562.4087 | 125634495.4029 | 23115136.0808 | 23648421.7983 | 854438643.8018 | 31720019.0892 | 1028043520.2006 | 5868308493.539 | 552644778.9124 | 199506702.3555 | 2.5384e+12 | 2538610.2014 | 974124.3786 | 1569676.6279 |  |  | 2.6872e+12
1047 | 1104556411.4443 | 1229035301.9662 | 203567890.657 | 159985381.0417 | 990319214.357 | 28437546.7783 | 201760840.1702 | 330190212.7141 | 460949184.7517 | 151221736802.1466 | 1995997428.9915 | 1945278382.9894 | 2115907597.4512 | 201580296.6107 | 569465185.7197 | 669254153.2034 | 750135097.433 | 308523049.0524 | 608873843.7665 | 24058799.1858 | 124732742.3079 | 24680402.8219 | 25573738.3804 | 836924018.7243 | 25025208.9424 | 1010535370.0505 | 5434155799.9752 | 632251306.0413 | 199945142.0129 | 2.2775e+12 | 2484042.8656 | 1043092.1255 | 1664147.5811 |  |  | 2.4509e+12
1048 | 1060249837.2235 | 1161296917.5265 | 208358273.1375 | 171626212.5378 | 971507408.7305 | 25709600.6388 | 192666187.2325 | 329527739.336 | 456023661.7908 | 138093337657.4271 | 1946237514.6768 | 1800734538.7918 | 2058860007.7867 | 184489758.9004 | 619930162.7543 | 688532861.0257 | 926199712.7939 | 285832460.4251 | 498967828.0888 | 25465166.1316 | 130859381.5695 | 24825826.7938 | 25792153.8827 | 887198967.5362 | 28969465.4858 | 1070058310.7563 | 5528948848.4809 | 660289847.0235 | 179167545.4003 | 1.916e+12 | 2627106.1158 | 958163.0194 | 1647178.9973 |  |  | 2.0762e+12
1049 | 1208305285.8537 | 1214326843.202 | 217089963.5918 | 172770756.6177 | 1085611165.7037 | 25635604.792 | 227017616.7919 | 305006425.6909 | 438981412.3673 | 130121004639.9568 | 1808215051.2397 | 1941410417.6214 | 1865458860.2121 | 172572285.8084 | 595485747.5864 | 715704817.5679 | 840356343.4876 | 295071610.037 | 474918836.9969 | 24505871.8474 | 118195422.7564 | 22471885.7055 | 23863801.8845 | 870680241.7048 | 21615727.1448 | 990102494.0966 | 6184679339.4226 | 661733671.3672 | 145688773.2431 | 1.6088e+12 | 2411599.2275 | 974672.514 | 1678385.7812 |  |  | 1.7616e+12
1050 | 1257565367.5114 | 1126919430.4195 | 200340238.8436 | 155351311.8073 | 902304751.5596 | 23318632.2955 | 218538152.2701 | 315159076.4979 | 481376986.356 | 127164026421.2797 | 1978310638.9303 | 2087445006.5121 | 1982450862.2146 | 182652227.9753 | 536765681.2485 | 669928837.4659 | 799844646.9041 | 275851468.2807 | 580056564.6067 | 26555089.8376 | 99804991.2341 | 20713949.1371 | 24520165.3872 | 909067364.0789 | 29103415.6331 | 1126027969.4447 | 6309491673.7557 | 648861956.4398 | 199857019.6536 | 2.3987e+12 | 2600315.0854 | 960344.8726 | 1547869.8103 |  |  | 2.5491e+12
1051 | 1246432651.7917 | 1125620954.3496 | 216833080.0384 | 174237313.3112 | 1038604022.9317 | 26879725.2219 | 188619401.391 | 324834244.7085 | 435347077.9626 | 155904247989.9514 | 1996371836.4493 | 2020859601.01 | 2117988842.9405 | 202006018.7148 | 646450986.7443 | 651066387.0076 | 886722510.254 | 280772297.0962 | 508615771.0514 | 24355262.9943 | 115460332.8218 | 24241842.2148 | 22806262.9392 | 902840524.7765 | 24570587.7205 | 1115399067.1186 | 7009351698.8768 | 666196327.2877 | 167965091.8888 | 2.0334e+12 | 2479413.6713 | 916825.1059 | 1770015.009 |  |  | 2.2134e+12
1052 | 1138331095.5615 | 1090104439.9787 | 217599433.4258 | 152040347.7692 | 1058740744.1901 | 26591028.3253 | 212535602.2041 | 315315036.6715 | 496307075.4396 | 158164893191.3928 | 1833386090.0074 | 1844131406.4953 | 1721868222.6997 | 199065137.5907 | 568193944.6583 | 679244085.7089 | 782449600.7591 | 305910153.0373 | 595280482.4034 | 24834914.1481 | 127396277.5739 | 23455637.7929 | 24682763.4759 | 892090319.8408 | 29263874.7156 | 1038732762.5705 | 5093914894.3323 | 692331473.4635 | 180614541.6226 | 1.5573e+12 | 2723205.3591 | 928499.3203 | 1743646.4713 |  |  | 1.7369e+12
1053 | 1189728140.8576 | 1130980095.032 | 199166254.7581 | 180690138.2301 | 1086288237.3279 | 27131998.6045 | 224252485.597 | 323529795.3963 | 479833377.5085 | 148858450920.8043 | 2010621403.4703 | 1919959441.8192 | 2197451693.8383 | 185012132.7983 | 563348035.7481 | 662497086.2549 | 811259464.3937 | 277098712.3791 | 585522811.3321 | 24345199.4641 | 118104599.7703 | 23824341.3271 | 22631408.8493 | 811480496.5524 | 27637803.6216 | 1089022738.0365 | 6205515195.2789 | 689876834.2542 | 170125523.3943 | 2.1247e+12 | 2518776.8949 | 954506.7099 | 1683827.4239 |  |  | 2.2968e+12
1054 | 1222023713.2672 | 1139767332.615 | 204771006.6949 | 167334588.6912 | 1062881114.3953 | 23346588.5846 | 215006565.0293 | 331220292.2718 | 449961675.6841 | 162129212464.6138 | 1940219123.2491 | 1959142053.7462 | 2003321878.1836 | 197661167.3871 | 635291412.7404 | 652650508.1947 | 884788015.5123 | 304198593.0218 | 555460775.7715 | 24320803.8022 | 103358018.685 | 18906025.2169 | 22158427.3475 | 748152167.6283 | 21415163.1873 | 1175677197.7476 | 7139579866.3305 | 601501853.7314 | 197518263.2049 | 2.0198e+12 | 2569023.5415 | 970038.359 | 1569895.7969 |  |  | 2.2059e+12
1055 | 1219872823.8399 | 1197607643.9992 | 217330432.3522 | 161231380.4956 | 1077457994.7538 | 20185874.2595 | 205893875.0683 | 330123490.6792 | 494146846.9603 | 125283071254.3742 | 2045203425.1241 | 1731492391.3658 | 2212856677.3471 | 169911742.3983 | 650469112.4164 | 670226422.5643 | 726731442.0367 | 318015507.1395 | 593776436.395 | 24400333.4054 | 124961637.3557 | 22917107.8078 | 25793292.881 | 679380744.9931 | 28794645.1793 | 949647948.8146 | 6407405813.8712 | 623613415.7384 | 192192972.0972 | 2.2331e+12 | 2689803.2622 | 937060.3931 | 1649560.2277 |  |  | 2.3815e+12
1056 | 1213148342.6754 | 1122087173.3508 | 220547258.6281 | 141528713.0293 | 998997523.3368 | 25762084.3913 | 218293379.9495 | 300207138.5879 | 486418597.4727 | 143068487736.096 | 1998358969.197 | 1726966767.6029 | 2158495442.3473 | 201333538.2885 | 646185873.7568 | 593345306.5449 | 804898636.4364 | 317059371.2142 | 511300291.6842 | 24894898.8871 | 129728687.6648 | 23006642.8706 | 22961523.478 | 892105256.2624 | 26280839.911 | 838577723.4585 | 6062954955.2004 | 686048868.1891 | 174309280.0833 | 2.2969e+12 | 2456771.6552 | 938640.3881 | 1871616.3618 |  |  | 2.4626e+12
1057 | 1191831103.9534 | 1223769986.017 | 207171055.744 | 143450441.8294 | 876078882.2878 | 23275445.087 | 211808603.9899 | 313691515.6064 | 467477973.1549 | 128061825775.5459 | 2035893174.006 | 2082583891.342 | 1912337842.9685 | 195296112.0565 | 587367321.467 | 584683612.4915 | 826538466.442 | 315265065.8 | 612804305.8479 | 26320029.7266 | 111263159.7763 | 22560231.2752 | 24835026.2907 | 891767351.6071 | 25124178.6885 | 1129610327.5226 | 7170632510.9382 | 480729733.5859 | 174753901.2429 | 2.157e+12 | 2388795.9417 | 1005102.1208 | 1571543.6464 |  |  | 2.309e+12
1058 | 1142517397.7614 | 1220498456.3288 | 222614095.3791 | 153055253.1387 | 1007887732.6782 | 24264692.99 | 207904730.7929 | 289145182.4979 | 466699615.8916 | 150529582445.0676 | 1956508681.5556 | 1922930961.8211 | 2070653151.7371 | 196362463.1497 | 665686688.494 | 674516634.7557 | 845400447.4447 | 278540846.047 | 595834262.0964 | 24345913.6378 | 123019969.8234 | 22974862.0915 | 19062786.3551 | 925819817.6354 | 24978291.693 | 1083365446.8647 | 5154992767.4485 | 651357310.8056 | 192593714.8564 | 2.5958e+12 | 2385738.0406 | 911899.4657 | 1515978.5242 |  |  | 2.7684e+12
1059 | 884748155.8395 | 1206062891.2153 | 203523629.5429 | 161568779.6155 | 1066743087.37 | 24496672.2843 | 211102340.6684 | 308500496.6689 | 494455942.511 | 136303654735.1632 | 1780020985.1066 | 1881434004.9025 | 2191302379.0572 | 177595102.8947 | 612715952.7548 | 702989798.8449 | 747898289.542 | 324610684.8712 | 519874657.1963 | 27260373.8055 | 114466276.5871 | 21325154.1494 | 20247824.2079 | 849765866.4447 | 22044049.3377 | 977240598.1334 | 5803872050.0309 | 585424365.4534 | 192332378.9288 | 2.4317e+12 | 2580617.6992 | 997536.2642 | 1539327.6435 |  |  | 2.5901e+12
1060 | 1103639516.6705 | 1219698336.3455 | 214526997.949 | 170841364.0677 | 1046718837.6199 | 22622850.2844 | 189568808.6548 | 308647801.7007 | 486916594.1021 | 155685135531.8048 | 1947969153.7708 | 1861354672.2975 | 1944212991.7241 | 197945276.9394 | 586232246.7774 | 689024720.6437 | 861474265.2594 | 321174670.6824 | 598024732.9537 | 26895488.1877 | 116367658.694 | 23130231.6231 | 25185541.4592 | 808840755.5448 | 27768327.8228 | 964328592.6053 | 7370579602.2984 | 682455450.0939 | 192308370.9041 | 1.6876e+12 | 2505957.2202 | 914433.4678 | 1623473.0651 |  |  | 1.8673e+12
1061 | 1182512980.9545 | 1190045601.2228 | 208286485.6386 | 178285709.853 | 1081123422.7898 | 21191960.6462 | 212050048.2087 | 329710938.6355 | 448815085.2043 | 134693387545.0529 | 1896067013.5614 | 2049128949.2015 | 2006927128.7359 | 179562787.011 | 593828549.8563 | 724609810.8461 | 747957734.5911 | 292523794.0015 | 527631350.3965 | 21290157.234 | 112346769.5047 | 24338081.1971 | 21742738.1544 | 856036753.7442 | 28285487.0165 | 1058237261.8952 | 5652689954.3574 | 688274544.8086 | 188636646.8934 | 2.0839e+12 | 2207091.7762 | 901630.8009 | 1628226.244 |  |  | 2.2411e+12
1062 | 1213194942.7896 | 1147319166.4749 | 219262473.1837 | 173036963.7338 | 1075561217.6005 | 25229256.6415 | 207105024.2284 | 291110321.2617 | 498540485.082 | 135958766329.5923 | 2054169065.8979 | 1775984001.3804 | 2005811542.1047 | 182632633.7494 | 604992637.6047 | 637706935.5706 | 847301477.3504 | 296639972.3173 | 542190867.8926 | 23786501.4586 | 130212389.7753 | 20536821.783 | 22835304.7543 | 719406028.3118 | 26916179.0767 | 1056887357.0961 | 6611883338.9408 | 632120470.0283 | 176131915.1897 | 2.1461e+12 | 2762073.1105 | 952988.7695 | 1509833.386 |  |  | 2.3053e+12
1063 | 1264089848.8176 | 1051295869.2354 | 195179241.5143 | 177477671.6876 | 1046148877.106 | 25835245.1877 | 223030995.0687 | 311050365.9363 | 466853263.2482 | 131798530587.6006 | 1938787538.1005 | 2043833381.3683 | 2159599624.7523 | 162983399.2113 | 666631676.168 | 685803481.1796 | 761240637.9081 | 271063205.8304 | 586210321.9355 | 26943000.8928 | 123679823.5769 | 21888525.5263 | 25335637.1524 | 897193985.2727 | 30731398.2346 | 1032531571.1239 | 5881045120.6779 | 678406861.7872 | 154889223.1106 | 1.6096e+12 | 2321125.462 | 889299.5855 | 1562682.2907 |  |  | 1.7643e+12
1064 | 1214873794.1676 | 1212448993.9943 | 202415021.9281 | 170180752.5035 | 1069957732.0655 | 20041659.4384 | 188852200.9605 | 328253968.9796 | 482780712.2835 | 134891258401.5326 | 2031891159.2967 | 2063698844.8931 | 1871397218.4816 | 185303554.283 | 582341771.5893 | 689863162.1511 | 734002303.0533 | 264142575.5028 | 554288368.6899 | 21224421.6013 | 128140726.2737 | 20829212.5035 | 21441130.2838 | 883929868.1179 | 25560776.5449 | 1060108117.3257 | 5393884588.0583 | 683239317.7367 | 183772892.9996 | 2.2163e+12 | 2401742.0563 | 924284.5216 | 1708569.5152 |  |  | 2.3735e+12
1065 | 1082192740.2154 | 1178014781.6745 | 215396877.0364 | 177842188.5802 | 1025061029.9423 | 24861395.2746 | 206159045.3276 | 321265103.7609 | 495437730.6612 | 155420512327.5035 | 1785728786.5079 | 2150119219.7965 | 2089032099.3765 | 192738478.8142 | 532329083.3152 | 575613680.0746 | 894889783.6733 | 326081353.3479 | 610732459.3127 | 27176766.6439 | 102123694.0131 | 21131183.2114 | 25997810.2269 | 937430840.9371 | 25094022.1668 | 1206320527.0941 | 6351787543.1126 | 654905800.7809 | 170512890.5781 | 1.8015e+12 | 2428062.454 | 939879.642 | 1620775.9901 |  |  | 1.9803e+12
1066 | 1174949945.9327 | 1210927881.0919 | 211480820.9376 | 172534989.1378 | 1063143759.7633 | 24563389.7958 | 206976021.5942 | 304633157.0519 | 432089957.6034 | 130518981043.3222 | 2013388001.7365 | 1605612046.6386 | 2040480955.2193 | 192669965.4846 | 592418287.9962 | 641166741.355 | 820318419.2921 | 240129370.2406 | 604374703.8175 | 24437736.1296 | 108573488.4289 | 21513497.7118 | 21550742.9485 | 924475449.2917 | 26137548.1528 | 953466701.9957 | 6916408595.7698 | 626683959.9159 | 201526145.4736 | 2.0676e+12 | 2452288.3285 | 976107.175 | 1572541.7404 |  |  | 2.2215e+12
1067 | 1228683897.3025 | 1162807455.8483 | 219313001.5104 | 167686550.4446 | 1077277822.1158 | 18381578.7471 | 219766117.4205 | 314489968.8495 | 489303796.8812 | 150289213366.1374 | 1961425249.6319 | 1859957879.4066 | 2009662868.0608 | 182303682.6658 | 626660432.6713 | 655164508.4571 | 667212349.4902 | 345848149.8997 | 536929280.1397 | 26804311.2812 | 129142346.769 | 23987237.3394 | 22037705.9697 | 738625260.7315 | 28440684.6576 | 983849569.7552 | 6523061452.7022 | 710227954.4683 | 193352714.1868 | 1.4804e+12 | 2559008.2324 | 961969.559 | 1491866.0774 |  |  | 1.6538e+12
1068 | 1089074093.8606 | 1177760996.9777 | 218430528.1041 | 171663816.6723 | 921352774.5944 | 20393927.5773 | 224491369.1542 | 320335900.3283 | 491270387.2458 | 149536485996.2086 | 2099771527.9031 | 1987565368.5608 | 2015804289.9576 | 201470524.5513 | 596687821.1832 | 699059812.4754 | 793128109.3571 | 259517977.1662 | 575605024.7474 | 22584867.1706 | 126438539.4063 | 20827736.2316 | 23391219.6301 | 820313249.8648 | 23092714.5202 | 722767306.2097 | 6587017737.1587 | 650668710.3202 | 142952576.8604 | 2.8041e+12 | 2646583.7697 | 992645.1647 | 1625136.3237 |  |  | 2.9767e+12
1069 | 1238567952.5005 | 1197817097.4853 | 218920317.8788 | 179717137.0686 | 1053241957.7396 | 24036513.9775 | 217199995.8791 | 317152575.1936 | 462218687.8092 | 142418299971.7949 | 1857590458.2775 | 2122346063.3623 | 2120971748.5438 | 175285542.2706 | 575841751.3523 | 723708613.8153 | 768790022.0649 | 271935279.7572 | 478849664.218 | 22188651.0342 | 129353315.1401 | 21119286.2731 | 25368975.6196 | 945957645.3139 | 28758699.8067 | 1012181953.69 | 6188906307.4439 | 649109258.6513 | 195844004.6763 | 2.1815e+12 | 2357803.4822 | 881599.3917 | 1623582.2982 |  |  | 2.3471e+12
1070 | 1247750146.7402 | 1102043559.6148 | 220030570.6787 | 177234255.0146 | 1046896045.1399 | 26188126.1536 | 204359976.1051 | 307041241.4391 | 431742012.2893 | 151406377933.2351 | 1971904991.1859 | 1793144122.023 | 2011726866.3538 | 202473523.698 | 584758126.707 | 687221777.4378 | 885546739.2772 | 290989128.1732 | 483238647.8128 | 25756630.6461 | 118613065.728 | 23162998.7308 | 24890427.5123 | 927537971.275 | 28079022.3472 | 1102587395.404 | 6391835680.1343 | 704298012.7968 | 160930720.511 | 2.0778e+12 | 2695938.9412 | 870868.3789 | 1527630.2473 |  |  | 2.2524e+12
1071 | 1253040183.2975 | 1189924932.7703 | 200029681.4369 | 172894082.2229 | 1014043071.6835 | 19651697.568 | 206256763.7145 | 290860973.2257 | 492458333.7183 | 158606141831.5163 | 2019343419.298 | 1749093477.9571 | 2158839141.4527 | 191011609.0561 | 581102076.0392 | 634198817.0805 | 759698208.7909 | 252537669.1224 | 522507881.6403 | 22094895.4466 | 119691475.2363 | 21752754.1086 | 25731172.364 | 803410075.2635 | 24742403.1119 | 1191981209.7697 | 6701227859.7085 | 632230250.0356 | 181935796.131 | 1.8087e+12 | 2412385.0641 | 907944.165 | 1574175.6123 |  |  | 1.9907e+12
1072 | 1146343932.6469 | 1109530478.9308 | 213627025.443 | 156775617.6976 | 925869798.5593 | 24935141.4453 | 224941217.6963 | 305639970.8281 | 456782621.9971 | 141958245549.6212 | 1830752129.6796 | 1820283989.2522 | 2022465666.2356 | 194616414.6698 | 475812343.4691 | 696651414.4535 | 849173918.3671 | 344689646.4672 | 595920953.5013 | 22468055.5548 | 125562962.6508 | 18353754.5647 | 18867891.7426 | 858910923.3901 | 27510254.0145 | 985643123.7803 | 7066339831.3394 | 607794132.1471 | 187767633.9352 | 1.6868e+12 | 2252507.4452 | 954565.5073 | 1694706.919 |  |  | 1.8521e+12
1073 | 1233376035.3996 | 1223080606.8268 | 208950458.2791 | 168711056.713 | 1085491743.1311 | 23277541.9788 | 227197544.4897 | 308334254.6057 | 487911865.6388 | 158693194691.1721 | 1995281875.216 | 2013876372.0707 | 2170512120.8865 | 200144633.7464 | 614802505.5372 | 691460073.7339 | 790570175.8143 | 298333179.037 | 605559261.6952 | 23138849.1363 | 107027806.0792 | 21205362.3395 | 22860970.0216 | 824302566.9278 | 30446704.4963 | 1063132535.8295 | 6126257351.2198 | 611065186.6778 | 191966548.7928 | 2.1379e+12 | 2349397.1365 | 905556.8869 | 1686242.6511 |  |  | 2.32e+12
1074 | 1093581835.4462 | 961053665.1444 | 204057835.0835 | 152416812.7915 | 1081600176.8748 | 26335232.5047 | 200761353.3681 | 330600345.5929 | 451060969.5337 | 123918782127.698 | 1948778797.6509 | 1893352814.4144 | 1652391652.7613 | 176201188.6089 | 548265495.1639 | 681415512.7469 | 823269711.7674 | 349741516.6839 | 595355849.1622 | 22248589.1374 | 134488290.9857 | 23358127.7268 | 25961164.8752 | 821623387.803 | 27391016.4387 | 916476312.7227 | 5756274244.3626 | 659977491.6629 | 195496125.7943 | 2.4927e+12 | 2562710.0812 | 1037994.1144 | 1549739.4586 |  |  | 2.6384e+12
1075 | 1199237498.242 | 1151075429.788 | 210831262.0771 | 172175558.7474 | 1039465706.5055 | 24909028.5342 | 204861868.6568 | 329569358.9516 | 491419885.7039 | 152014768990.9773 | 1944223847.9362 | 1608611469.0104 | 1788096263.7598 | 200699324.4545 | 582577543.5582 | 698692834.9723 | 817899627.7953 | 292626200.1466 | 472241383.7198 | 26201082.2938 | 107980127.9206 | 22289706.0991 | 25891633.7281 | 850742594.1842 | 29372060.6328 | 1084722591.6968 | 7104338758.7127 | 659594519.9979 | 181313870.9791 | 2.4433e+12 | 2286575.3246 | 1017217.9285 | 1862092.1459 |  |  | 2.6186e+12
1076 | 1152596134.7701 | 1202297909.7534 | 203055280.4294 | 181530262.645 | 1072686477.3569 | 22251626.1021 | 213051537.7876 | 324475478.9108 | 429933621.2269 | 158802249889.6345 | 1940074279.1258 | 1759827431.2921 | 2114819841.5857 | 194868812.5443 | 584327530.3308 | 563762738.9786 | 767771060.846 | 353746959.1562 | 614737889.6481 | 27117747.8628 | 106769454.9503 | 19712739.3272 | 21886694.3982 | 909493525.8283 | 30755886.4191 | 1144277830.5742 | 5536958063.8235 | 624556443.2867 | 182503205.1535 | 2.1313e+12 | 2248937.1605 | 1040035.246 | 1576412.9988 |  |  | 2.3124e+12
1077 | 1197387501.8052 | 1188222825.2873 | 213131931.7162 | 169164907.7079 | 1063125930.4117 | 22763317.2993 | 213440134.7938 | 308458677.1966 | 473566184.6246 | 159483127595.2098 | 1886076959.2498 | 2122568731.1797 | 2202586028.2026 | 202780822.2692 | 618691649.7443 | 710541321.5443 | 809856431.9015 | 314128746.998 | 614179759.1518 | 21488926.5402 | 129848618.8989 | 24465457.2238 | 25220552.1556 | 821798637.1457 | 28551607.9923 | 1072019791.8857 | 6557402976.2562 | 629391919.5912 | 187715863.6543 | 2.0666e+12 | 2488956.4074 | 1007725.297 | 1770293.4669 |  |  | 2.2499e+12
1078 | 1217493529.0936 | 1228631511.1824 | 209993375.3006 | 171310056.7381 | 1014329361.7496 | 26074381.5872 | 216971830.5024 | 328669276.5335 | 491951895.8686 | 119446845749.972 | 1860262107.773 | 1990052139.0962 | 1916659249.2109 | 184954714.2593 | 616350346.5745 | 659656187.0692 | 843861988.7582 | 328802333.333 | 554719499.5659 | 26707725.1588 | 127456293.1774 | 22027712.8039 | 24339584.8156 | 797108058.6972 | 29486307.0131 | 1103635656.3222 | 5647469621.1737 | 684222576.1601 | 179393540.3871 | 2.3865e+12 | 2490270.3916 | 942419.3711 | 1658276.0709 |  |  | 2.5284e+12
1079 | 1127606730.0259 | 1184286930.0963 | 222979095.0887 | 160813746.1993 | 966026783.9591 | 26065104.9599 | 215592524.2222 | 313712694.9661 | 459731222.1555 | 146298988425.4336 | 1918712338.8534 | 2041569807.6637 | 1931731419.3519 | 195687898.0294 | 513448136.888 | 627575148.2012 | 825734370.9869 | 322924443.5663 | 604719168.5913 | 21888480.8931 | 131678000.3058 | 20369083.5658 | 24077764.5781 | 664268262.8047 | 24348899.5403 | 1142663099.0545 | 6290104306.9736 | 591720253.0163 | 189444769.8451 | 2.4612e+12 | 2508764.4112 | 960585.5452 | 1548885.4311 |  |  | 2.6303e+12
1080 | 1040486638.6396 | 1176570967.6478 | 209732648.6737 | 148568751.7661 | 1038137797.3362 | 20648241.4867 | 219832886.2499 | 329187994.8793 | 462878930.1842 | 157554363832.6584 | 1957818345.0886 | 2139582492.9511 | 2174856427.5985 | 201583353.2651 | 564935398.1467 | 667278248.6769 | 711532711.0235 | 257812528.9561 | 560792679.7026 | 21345698.7429 | 92244655.724 | 22665317.4655 | 26037639.5212 | 882012729.4028 | 23891755.2304 | 1101164775.1199 | 6081328071.0261 | 633016400.0547 | 163179940.3013 | 2.2634e+12 | 2434606.1375 | 928212.0349 | 1684887.6405 |  |  | 2.4439e+12
1081 | 1257484501.6173 | 1106879175.2577 | 213544809.5659 | 176914576.8844 | 1055831403.9277 | 17676627.4479 | 211823280.1225 | 320271002.708 | 451307341.9111 | 153865139646.8259 | 1986485970.6581 | 1936018245.3191 | 2147190831.4016 | 151517553.3624 | 675896858.6861 | 652227140.8759 | 795130223.6875 | 316689733.3533 | 533675948.3994 | 27329692.4588 | 120519487.5473 | 23460474.6445 | 22581681.372 | 911602643.9455 | 28038994.6478 | 1005997955.4801 | 5758698603.7148 | 678158058.4866 | 183189474.8664 | 1.4776e+12 | 2688424.7765 | 1041433.7215 | 1562721.7974 |  |  | 1.6543e+12
1082 | 1215926410.8165 | 1136904539.731 | 200870360.5423 | 154300713.3098 | 1013184433.6942 | 24893306.6049 | 204816840.5613 | 293446817.9066 | 459603017.046 | 133782454434.5163 | 1851506470.4155 | 1916338478.8112 | 2191549969.9217 | 186248892.8667 | 592925930.587 | 686531406.8694 | 920632892.8924 | 257276842.5457 | 573083586.8961 | 27634827.3186 | 92076915.7471 | 20123368.8909 | 21370688.5327 | 781269732.6455 | 28412701.7991 | 1141904799.7954 | 4906600803.4525 | 573199822.4581 | 182979073.0081 | 2.3743e+12 | 2522376.5592 | 906763.5017 | 1665231.9465 |  |  | 2.5297e+12
1083 | 1203965257.7179 | 992062148.9098 | 199245485.1449 | 173514173.0049 | 1069306357.8955 | 23707470.2508 | 211000165.1367 | 287177525.5289 | 499830744.0598 | 140402858315.4986 | 2004322004.1519 | 1987055601.6201 | 2000996903.8546 | 168273622.1056 | 597284243.3358 | 691676742.4289 | 809060537.2083 | 289823737.9058 | 608500348.1496 | 20819359.0046 | 129210366.71 | 23834122.8286 | 22969031.2043 | 738716998.256 | 30008438.1369 | 1074895548.8727 | 5436163041.2763 | 667688993.5659 | 169827484.3605 | 2.0765e+12 | 2544396.2939 | 1009348.6148 | 1533662.0521 |  |  | 2.239e+12
1084 | 1049724705.3645 | 1221572644.2673 | 207213330.4591 | 174304184.928 | 1064177984.535 | 21527496.7237 | 193959441.8079 | 330377646.7675 | 468133339.9912 | 149831068654.8123 | 1726079642.0173 | 1382737532.4145 | 2054296116.3668 | 196923786.8592 | 613601578.0484 | 651963396.8831 | 781971858.2653 | 341798593.29 | 588892793.777 | 24487272.4994 | 114177377.0902 | 24497402.404 | 22492934.7344 | 897546633.6289 | 24173223.7868 | 1046231798.3862 | 6902959598.9636 | 704460192.7413 | 177221446.0604 | 2.2735e+12 | 2804465.5496 | 977100.6108 | 1562143.454 |  |  | 2.4464e+12
1085 | 1259818466.0034 | 1068854541.8928 | 200982152.7836 | 165289728.1186 | 1014665020.0946 | 26505264.1517 | 222442697.5571 | 278016064.902 | 497866130.8813 | 128954755797.4651 | 1946283293.5676 | 2053517105.3354 | 1946521991.6759 | 196616441.4401 | 622670538.8599 | 650537309.1965 | 829602348.3178 | 285173155.0962 | 505692462.2429 | 23281655.0439 | 107957792.9554 | 22657441.8706 | 25995126.1661 | 871097531.7214 | 30561974.3063 | 1169009660.0366 | 6642184644.3313 | 645794005.1292 | 182129853.0332 | 1.4811e+12 | 2573800.5097 | 910238.1235 | 1699046.9677 |  |  | 1.6335e+12
1086 | 1180964219.075 | 1192773221.2884 | 203450311.7165 | 162433388.972 | 1005674976.0612 | 23371352.0105 | 207305731.401 | 328041884.9 | 477060660.3993 | 135665056453.966 | 1798139252.3116 | 1877636607.8772 | 1784556155.2944 | 192930105.2803 | 633180856.2326 | 646849278.4221 | 640841242.3745 | 302884443.5594 | 615345351.384 | 27428320.6737 | 120208901.0629 | 23493831.1446 | 25645736.28 | 858359841.8467 | 29096168.8673 | 1181599937.4223 | 6903448472.272 | 580169823.8992 | 195886099.6601 | 1.6705e+12 | 2548324.5044 | 992107.5502 | 1663795.6196 |  |  | 1.8294e+12
1087 | 1217673427.1471 | 1155581532.4987 | 208274184.0794 | 164557095.504 | 1067405231.6128 | 21213365.4625 | 215942769.682 | 312386304.7552 | 483905374.4953 | 144138199042.7432 | 1491733072.8151 | 1878325592.4501 | 2188656330.1313 | 191101886.4269 | 531268784.4981 | 662235345.1862 | 788750052.4265 | 319005489.4959 | 561870240.0247 | 20208337.2607 | 119289889.2856 | 23591436.9041 | 24908956.7503 | 914088492.0498 | 27832150.5981 | 1091024627.9114 | 5467704332.4113 | 695425690.586 | 167604277.4843 | 1.8723e+12 | 2307885.5672 | 905127.457 | 1614909.3094 |  |  | 2.0384e+12
1088 | 1204683541.3915 | 1201261952.4427 | 220666606.9885 | 165879036.0851 | 1036247593.4213 | 21236100.5172 | 184001472.2244 | 285504819.7368 | 483953887.9787 | 141816023607.9594 | 1765664306.8666 | 2096814772.0139 | 2195063609.8814 | 172528459.7857 | 505834029.8117 | 667134132.077 | 858417301.1541 | 352210927.9735 | 603325813.627 | 20971260.114 | 122645734.9323 | 22339874.1495 | 23497194.7801 | 843141566.7399 | 22629534.364 | 1096061025.7458 | 6012872312.6526 | 622638032.4681 | 164062037.3786 | 1.9124e+12 | 2464183.9871 | 1010267.4996 | 1546841.0614 |  |  | 2.0772e+12
1089 | 1110186182.5228 | 1170323998.6252 | 199735051.8518 | 155309010.2393 | 1017129956.4573 | 24052826.3415 | 216360993.8676 | 306212539.9756 | 495158511.4221 | 132418527097.3896 | 1686673226.649 | 2152091082.2219 | 2154137025.1806 | 197690516.3304 | 653713862.8213 | 694462550.7978 | 640505968.1619 | 299509001.5963 | 410216663.3613 | 26996690.788 | 103651457.3928 | 21106849.6026 | 25124513.2696 | 866253857.7332 | 24598782.4455 | 895512451.2579 | 6687024465.1349 | 707586968.2273 | 200182270.2014 | 1.7226e+12 | 2299111.6517 | 889956.246 | 1623715.8516 |  |  | 1.8782e+12
1090 | 1092567600.7308 | 1141430648.2681 | 192577354.8212 | 175240374.8095 | 995755331.9551 | 22851114.899 | 185158016.3367 | 313617816.6587 | 499244510.2036 | 148474708342.3787 | 1833561346.6475 | 2156925413.8111 | 2147036105.765 | 201024020.5673 | 582474704.0033 | 632786205.7682 | 807718655.6988 | 298256311.9579 | 477941732.4288 | 19464949.1943 | 114469248.7919 | 24101664.9797 | 21166823.0766 | 945942526.3993 | 27196772.6428 | 1162149346.8182 | 5936069888.1348 | 650067992.8817 | 181088662.2724 | 1.8003e+12 | 2447970.3032 | 1032005.3214 | 1564558.9559 |  |  | 1.9716e+12
1091 | 1140160954.3663 | 1185035043.9693 | 207869174.9412 | 153793198.1618 | 1077932902.6362 | 25108973.4185 | 203286530.0306 | 318536854.3684 | 433808860.5359 | 135208860264.4488 | 1855172753.025 | 2003536096.2916 | 1923297954.3334 | 195005882.218 | 631159013.9405 | 707241332.3287 | 887224403.174 | 325469017.3067 | 603558878.0986 | 23058899.5906 | 131125216.7389 | 21495164.7622 | 24223261.3317 | 869661851.7396 | 25634034.7258 | 969816750.3693 | 6163924474.0365 | 646084303.1563 | 180484774.9297 | 2.6887e+12 | 2671194.8105 | 897478.4601 | 1614855.5931 |  |  | 2.8469e+12
1092 | 1059706192.9362 | 1018788148.6052 | 207644965.9116 | 165938751.4331 | 1071634811.3057 | 24179853.1415 | 223812833.8591 | 314766354.7695 | 482225978.9933 | 155482490560.9335 | 1985300640.4339 | 1694389440.9739 | 2127905247.3405 | 198034019.7398 | 648958345.5135 | 712934753.6092 | 782246903.8001 | 333298128.583 | 567367727.0488 | 19315611.1636 | 122908881.9722 | 21339093.9449 | 20979939.5756 | 805807619.6789 | 30569779.7574 | 842245333.8029 | 6722454655.7774 | 684897833.6785 | 172432815.1223 | 2.0914e+12 | 2486131.4074 | 890919.4729 | 1570373.8628 |  |  | 2.2699e+12
1093 | 1191038267.2431 | 1188433545.0548 | 220453207.9298 | 170618569.0287 | 1067718914.7045 | 27639578.2839 | 224483571.3388 | 304410136.4939 | 484159868.2807 | 116739331550.9134 | 2052076478.4 | 2171332002.5195 | 2184831249.1862 | 197708797.6182 | 591593169.7891 | 700743798.8802 | 911053672.4447 | 358202061.8542 | 502089160.1826 | 28100465.3649 | 116768830.5373 | 23622108.3896 | 25317356.4588 | 842967514.5475 | 25990375.1397 | 1133620793.3432 | 6261872067.8956 | 693916364.1084 | 172540207.6426 | 2.3034e+12 | 2558773.3985 | 906999.9991 | 1481364.7886 |  |  | 2444048570103
1094 | 1073943748.2565 | 1168442493.1391 | 209382946.0799 | 163977281.2027 | 1071723667.1508 | 22259667.8478 | 186995663.6989 | 296050974.52 | 447964490.0845 | 140495174896.5775 | 2000060990.0447 | 2139093711.0467 | 2055281470.1716 | 192719899.7627 | 579309085.5715 | 676669857.7504 | 896001671.8817 | 300748705.1336 | 599657946.181 | 25390093.2931 | 103579846.6389 | 19951846.4429 | 23646755.246 | 885133035.4148 | 26957725.3755 | 1038037633.3824 | 6484396706.8805 | 502461525.417 | 160917969.6729 | 1.6039e+12 | 2565669.4043 | 933167.9669 | 1641935.4696 |  |  | 1.7678e+12
1095 | 1156899012.3899 | 1224367866.6946 | 196151466.7933 | 169870360.203 | 983929888.1451 | 20459655.9803 | 199995758.4341 | 316029712.7559 | 470482071.9654 | 129100835479.162 | 1869353231.2277 | 2047319936.7299 | 2174369563.5687 | 171153536.523 | 629282250.3129 | 688643317.7702 | 812790858.886 | 326693979.7896 | 582724554.3866 | 26247018.7827 | 124162123.9275 | 18628517.7102 | 23422104.4472 | 896854366.7351 | 26079683.3654 | 1017845198.9075 | 5639753796.4194 | 676710426.4567 | 180251325.7287 | 1.7681e+12 | 2466108.3471 | 939461.2412 | 1609612.5576 |  |  | 1.9198e+12
1096 | 1216550984.2955 | 1202863255.4435 | 211018818.9575 | 172383890.4083 | 1011806771.0208 | 21858968.475 | 218472606.2856 | 308882548.5945 | 467502699.6482 | 149821952718.8098 | 2037588043.7246 | 1805101255.9159 | 2195331143.2517 | 176501673.5633 | 611944080.7479 | 706014651.9564 | 816922668.886 | 311428983.6645 | 568344748.2075 | 23814442.9174 | 112475834.6028 | 20914541.0923 | 25696128.153 | 823713863.6 | 26076199.5609 | 1150686809.3293 | 5844105059.2657 | 686626823.2357 | 181703199.6033 | 1.9653e+12 | 2462682.8806 | 963028.1567 | 1835172.3605 |  |  | 2.1381e+12
1097 | 1190156173.9055 | 1229086978.2406 | 205150466.2647 | 150229141.1047 | 1082811169.9661 | 27093339.2221 | 212099252.7609 | 282728841.3061 | 477395138.2847 | 137558061148.7748 | 2068345416.3708 | 1835904573.2012 | 2045673834.5932 | 200198153.6539 | 577667069.064 | 650318821.5137 | 770698516.7127 | 342477121.65 | 541277901.9431 | 25063191.6199 | 112802453.5473 | 21559531.2803 | 24578138.1006 | 923603087.35 | 30362074.6847 | 1065013808.3997 | 6370107587.6188 | 704556950.814 | 188521770.3794 | 1.7287e+12 | 2570284.6394 | 957754.109 | 1754080.8723 |  |  | 1.8897e+12
1098 | 1212564716.0438 | 1215577945.76 | 214953054.4559 | 177275778.6105 | 931741522.5592 | 22999210.3341 | 224001692.0959 | 322842956.7375 | 397508729.672 | 133591774230.6308 | 1864062013.4789 | 2027768968.5752 | 1986190516.0308 | 194279508.9812 | 657322927.348 | 664424532.0105 | 729138552.8 | 289322497.6568 | 589932532.3525 | 19692124.1337 | 135546082.3724 | 24773491.8185 | 25112582.4553 | 904947678.7042 | 25874267.9173 | 1136724422.2167 | 6384617930.1669 | 592733841.2526 | 194421872.4617 | 1.5171e+12 | 2421147.6881 | 942937.0202 | 1603295.0374 |  |  | 1.6738e+12
1099 | 1129473424.951 | 1042078488.1338 | 217279640.0661 | 177339535.2182 | 1032974355.8421 | 25541431.274 | 204735293.3593 | 320130207.0261 | 481602993.8461 | 143682010326.3685 | 2083415789.2004 | 1845921889.0256 | 2169985469.5183 | 201276104.8473 | 552527146.868 | 651265180.2213 | 836506284.7358 | 326326012.4261 | 480329938.0321 | 25127532.4348 | 125207584.4033 | 16379558.9743 | 22172781.6283 | 684685433.9363 | 23220008.1149 | 1179481419.8888 | 6968187741.5379 | 673795795.4395 | 184003781.3505 | 1.9844e+12 | 2442085.5406 | 960383.484 | 1561657.5677 |  |  | 2.1518e+12
1100 | 1239110317.2855 | 1213546292.1464 | 204703114.507 | 162574666.1756 | 870630271.0911 | 24064852.2381 | 193385896.0157 | 306560376.2444 | 466434706.7103 | 129671510373.0018 | 1890376964.9547 | 1871281974.1554 | 2209352921.6721 | 184351883.7016 | 579761772.174 | 644327031.2648 | 774594538.2798 | 220215541.1668 | 594966166.5046 | 24256970.7061 | 115296535.343 | 24736653.9838 | 23825726.6315 | 786118251.7291 | 23364545.2997 | 1099564776.4614 | 5966810018.114 | 662619365.9814 | 166779898.787 | 1.4875e+12 | 2490087.159 | 910826.4151 | 1557848.3445 |  |  | 1.6397e+12
1101 | 1154206006.1974 | 1126612274.5499 | 206116641.4904 | 178807097.0027 | 953325609.7758 | 22636787.248 | 218122870.6138 | 258079602.6773 | 455570379.4097 | 152821250234.0259 | 2010507395.5864 | 1862211808.6275 | 2113216654.8156 | 158696900.5627 | 574738355.5121 | 612948325.8929 | 765371446.4622 | 314193456.0413 | 610718075.8273 | 20664497.5771 | 114465406.4005 | 23149701.4842 | 21451058.7309 | 651279062.3655 | 23617158.7729 | 994439932.3943 | 6259524499.226 | 586611501.9277 | 179371410.5217 | 2.1064e+12 | 2608134.1932 | 999882.2315 | 1681852.1044 |  |  | 2.2817e+12
1102 | 1042497592.0888 | 1220133745.5641 | 225783910.1719 | 170314792.7564 | 1075896983.6638 | 22318507.2153 | 215023181.6864 | 304956578.3946 | 500227296.0286 | 109266954761.3118 | 1995416015.787 | 1791541459.0124 | 2131463595.2972 | 171598770.629 | 684071225.0442 | 622589720.4281 | 677616308.3107 | 311825489.225 | 557901358.0499 | 26377241.1817 | 126861796.9076 | 23556176.027 | 25572778.4863 | 930284497.0515 | 23793786.292 | 1018175000.2343 | 6163860366.8837 | 644682779.3619 | 183278911.7212 | 2.0159e+12 | 2525038.1652 | 918000.201 | 1665922.386 |  |  | 2.1481e+12
1103 | 1191427514.9243 | 1119940681.3362 | 198753322.7439 | 174993872.9269 | 1040186036.357 | 18884752.0967 | 210858738.4104 | 314129096.9927 | 468158880.6634 | 132753755335.8353 | 2046356405.8095 | 1957272253.657 | 2118077929.9188 | 186371974.4944 | 637073983.5388 | 647370013.2996 | 824803030.0696 | 314231120.5999 | 563944948.9462 | 23197867.3083 | 125753944.3349 | 21361048.9384 | 21127573.9563 | 908926363.2627 | 29436877.5424 | 942576053.4544 | 6601790432.9649 | 614157794.5665 | 200327679.0004 | 1.9535e+12 | 2520729.9263 | 914285.4959 | 1648312.6209 |  |  | 2.1098e+12
1104 | 1195275047.6406 | 1120299037.3461 | 222591121.9987 | 181230905.9118 | 895444561.1957 | 26267840.7602 | 215008449.7596 | 281919417.1426 | 473780826.7664 | 153685887490.5118 | 1924231990.5299 | 1782546530.0613 | 2125290025.6658 | 158901377.4457 | 635128529.2308 | 708576805.3743 | 802064412.2841 | 347926001.4692 | 609234492.16 | 26314391.3726 | 105448758.0917 | 23699398.6743 | 24803167.5709 | 795891370.0988 | 20376340.6013 | 1219106678.1494 | 5842707640.5233 | 681150485.7817 | 193805594.6567 | 2.2455e+12 | 2521408.4947 | 911581.8076 | 1590036.8874 |  |  | 2.4219e+12
1105 | 1065629752.6806 | 1199618303.407 | 213552834.2913 | 180411255.2402 | 1071619374.8545 | 25518742.862 | 217989603.2095 | 304190615.4929 | 430221299.5963 | 143807712364.2273 | 2099152613.1964 | 1995085070.0272 | 1943846166.646 | 158100525.899 | 517089994.3691 | 638796426.5874 | 743270294.994 | 346696319.8802 | 548392776.4315 | 22672754.4355 | 115484712.734 | 20305568.7186 | 25307185.1263 | 856409647.1645 | 26725230.684 | 1113827974.8329 | 4904939923.6957 | 711486928.9631 | 155619833.8075 | 1.8776e+12 | 2256309.0553 | 944565.8478 | 1514559.2936 |  |  | 2.0431e+12
1106 | 1232040653.6743 | 1202930123.9419 | 217423104.4081 | 141520399.8703 | 1068793127.6084 | 21668054.3086 | 221325940.3559 | 315977732.1703 | 468512456.6601 | 154194230433.3704 | 1801217379.4002 | 1724910499.4327 | 1878796109.2024 | 167237776.7211 | 521125027.8169 | 493530719.7517 | 781107690.7716 | 307740239.1243 | 571166427.5356 | 26397302.8321 | 91059257.2368 | 20196353.1201 | 24264019.205 | 755373746.91 | 24161108.9694 | 1113112487.9318 | 6980203946.3133 | 554254743.8263 | 194101145.3387 | 1.5387e+12 | 2579927.7932 | 941930.2554 | 1647961.3124 |  |  | 1.7158e+12
1107 | 1188015281.2228 | 1077806175.5616 | 221464226.2075 | 165433590.1626 | 942532448.3085 | 23074239.1905 | 226386299.226 | 329525036.369 | 469883343.997 | 146959205472.1477 | 1845648547.7337 | 1752953460.8862 | 2073350417.4708 | 187821497.0917 | 584196619.5774 | 697804822.1874 | 611572652.1362 | 330690089.6718 | 500257547.6083 | 24028030.8901 | 95726009.3228 | 22332320.2312 | 25446923.9085 | 693303062.7599 | 23243330.2341 | 996353352.6665 | 6678226910.1988 | 700238733.0999 | 201873403.4748 | 2.3321e+12 | 2334481.9086 | 953733.6766 | 1568727.6353 |  |  | 2.5017e+12
1108 | 1149158531.7366 | 1180216275.1743 | 226009223.6778 | 153893523.8546 | 1024411991.2068 | 26818325.8322 | 211674818.0248 | 327986129.9462 | 461204372.0102 | 150491592595.9055 | 1959804957.1103 | 1956874286.6976 | 2117373149.5999 | 163034712.6247 | 599368949.9158 | 583134317.3031 | 844345755.2884 | 340149348.5551 | 528984195.0066 | 25799154.7268 | 109177967.9016 | 23528366.7838 | 22293592.8048 | 816728161.5901 | 26167721.3267 | 1171693850.0023 | 5824596032.8739 | 592297522.1131 | 163547075.0465 | 1.863e+12 | 2637813.1024 | 947818.5564 | 1530170.8092 |  |  | 2.0362e+12
1109 | 1160772928.1867 | 1078433476.5872 | 217205166.5351 | 151148559.8169 | 1046238471.0048 | 25169026.2339 | 200306089.0167 | 252594813.0333 | 494277273.8276 | 123590658430.1356 | 1687660577.8539 | 1651487915.0002 | 1900257358.1788 | 187854997.9154 | 688106735.3662 | 666724525.8203 | 828466134.2964 | 339109136.561 | 538610050.5773 | 22291654.2437 | 115023844.1103 | 23588480.2632 | 22118320.1823 | 939873281.5725 | 26000016.7099 | 1147250084.6807 | 6251993374.5158 | 588694093.1743 | 185231976.0229 | 1.9758e+12 | 2507749.2873 | 1006107.0414 | 1535378.899 |  |  | 2.1218e+12
1110 | 1178612478.4602 | 1079185135.3171 | 205934890.2117 | 159948704.1055 | 940224292.4159 | 23504572.842 | 205142099.4068 | 291428121.1772 | 441611846.4892 | 121054166011.0296 | 2055769990.548 | 1785261921.6696 | 2021997926.4092 | 184374013.0221 | 551045490.7703 | 603721970.2017 | 868529341.1568 | 336881207.6444 | 412593371.0742 | 22356511.7607 | 126765439.6246 | 21134887.626 | 25034639.7326 | 881689939.6338 | 29003178.8433 | 1022264143.7706 | 6343368499.4442 | 591038633.4166 | 194573819.6387 | 2.4051e+12 | 2545346.2504 | 889946.8248 | 1594192.6265 |  |  | 2.5488e+12
1111 | 1202548108.2201 | 1198124947.0618 | 211492077.3014 | 159975662.2883 | 1067796296.2814 | 27243671.3396 | 210140109.5954 | 323816833.6377 | 477165939.6841 | 130723006288.137 | 1825064405.9976 | 2177137970.8284 | 1740201884.8476 | 201298768.7064 | 614284534.337 | 637521054.4529 | 732851401.097 | 275042881.7651 | 602896822.384 | 23272567.68 | 104236834.2426 | 23765042.4803 | 24924680.7631 | 633658438.8305 | 29075807.0949 | 1199390159.2516 | 6391538228.8517 | 696433179.6071 | 193896926.6737 | 1.8363e+12 | 2487728.8996 | 969655.165 | 1714020.3164 |  |  | 1.99e+12
1112 | 1148805727.5428 | 1154139408.4726 | 224153960.5652 | 154397581.7095 | 1027096213.5941 | 26970121.8766 | 217991361.9061 | 302281506.1706 | 446188836.8403 | 138222079734.055 | 2074601670.8026 | 2048924487.9671 | 2016179083.7308 | 185138037.8146 | 613841422.3114 | 583295330.9662 | 711254217.3049 | 303159744.2359 | 609274702.1418 | 21971729.8549 | 112499306.6877 | 22701583.5341 | 24535141.2018 | 843898647.5831 | 28049447.934 | 1012631096.0018 | 6420037639.4309 | 504083400.3732 | 157970663.3134 | 2.485e+12 | 2319402.2258 | 984772.2326 | 1774041.889 |  |  | 2.6462e+12
1113 | 1189466712.6781 | 1125977348.9149 | 219775962.1351 | 167388717.9898 | 1041106487.5892 | 27575693.0371 | 202762049.7426 | 310489476.4172 | 492713874.4144 | 134960017508.9472 | 1958594952.8943 | 1923309716.5319 | 2115300196.0844 | 201047952.8852 | 480031790.9627 | 664838398.0712 | 796797071.4712 | 301283455.8243 | 581775654.7703 | 24074455.7289 | 129857042.7326 | 21238976.0579 | 22523808.4874 | 833276868.8062 | 27644070.5423 | 1052462626.2317 | 6826603533.2132 | 589699298.6887 | 170320598.8362 | 2.1213e+12 | 2530459.0422 | 1000614.2296 | 1583508.9601 |  |  | 2.2797e+12
1114 | 1067059434.4197 | 1106627171.3908 | 180800220.9726 | 163765153.1272 | 978903048.5627 | 24912308.934 | 195562400.3465 | 319088945.7971 | 451559079.6094 | 125108221993.6924 | 1835979332.6617 | 2032767014.0364 | 2159327242.6676 | 171695023.6761 | 644574122.9022 | 709277086.5327 | 800542457.2705 | 264248981.3348 | 549011897.6651 | 22394544.6199 | 119557226.5241 | 21726626.7179 | 22989313.7637 | 821818242.6543 | 28005213.1745 | 1093389070.7446 | 5866142279.7356 | 552315504.1223 | 192771430.8566 | 2.2919e+12 | 2384309.5679 | 945325.7036 | 1799533.7766 |  |  | 2.4394e+12
1115 | 1104757829.5877 | 979745505.38 | 190896121.7177 | 150438955.3093 | 1077278357.0737 | 25014382.2889 | 212260349.163 | 302018383.2431 | 499877212.0258 | 150630957969.755 | 1858617189.8943 | 1947047335.927 | 2085197043.1731 | 195526066.0034 | 549242363.5949 | 613438637.6655 | 891801483.814 | 332822015.3312 | 583156534.6436 | 25035062.91 | 125463960.1395 | 22992608.8415 | 25595009.1334 | 849295779.2953 | 26692963.5477 | 1057819697.8366 | 6838507165.7343 | 583228841.7453 | 199537449.3044 | 2.3819e+12 | 2469229.3546 | 1011399.4369 | 1653105.9708 |  |  | 2.5558e+12
1116 | 1262964453.3216 | 1080195941.3212 | 224408611.5528 | 166172753.6704 | 1087200050.9645 | 26918424.9572 | 218105460.5264 | 318711222.6506 | 481564586.589 | 154888052843.8341 | 1631729728.6314 | 1601271835.0828 | 1718276064.1161 | 177189663.2956 | 669833786.2891 | 635326615.9871 | 839225867.0107 | 289874625.8677 | 599935627.6916 | 22567527.3875 | 109780676.3253 | 17058426.1521 | 24664068.0427 | 803170603.0721 | 25973223.7414 | 1117884279.0795 | 5291493727.8404 | 595683928.1169 | 175459930.6652 | 2.294e+12 | 2495059.0215 | 995615.4635 | 1543406.5468 |  |  | 2.4701e+12
1117 | 1043042036.1933 | 1122547655.5199 | 214464011.6676 | 176397873.9475 | 1076718973.5261 | 19718093.657 | 205434593.0229 | 331322206.0923 | 476092445.368 | 116679173866.8495 | 1990145633.651 | 2021064246.7336 | 2007716224.5776 | 186165556.0855 | 601810519.8138 | 686013814.6221 | 800220123.2814 | 297846867.4206 | 462681738.2974 | 24859552.9137 | 131971904.8185 | 23816732.5811 | 23711959.1606 | 910891085.7644 | 22617651.4828 | 1192729571.0363 | 6963494742.962 | 672203164.0483 | 188251483.9854 | 2.2307e+12 | 2601973.822 | 981241.2078 | 1678652.4104 |  |  | 2.3713e+12
1118 | 1252987261.8407 | 1217423315.5731 | 224202633.9627 | 153285435.5886 | 1052206248.2938 | 23649700.2832 | 195614036.9181 | 327414983.3162 | 472533254.2797 | 139491097893.329 | 1945387747.9051 | 1714557292.9761 | 2125235169.7163 | 198654960.3851 | 626856585.1724 | 544128626.8867 | 830597053.7921 | 336930046.8136 | 603654233.2197 | 24233279.3492 | 133622412.175 | 24239671.5909 | 25497611.358 | 845663841.8438 | 18688195.4672 | 1084768021.7101 | 5971747717.8389 | 712803719.8987 | 201885914.4568 | 1.8641e+12 | 2585566.8339 | 946079.5084 | 1571260.0296 |  |  | 2.0265e+12
1119 | 1150439711.8965 | 1141731391.8169 | 214938893.3478 | 163123925.856 | 1067726779.6612 | 26177621.3127 | 212004010.5083 | 298605992.4721 | 496709877.9856 | 161261782479.4718 | 1984639549.7199 | 2043805403.228 | 2109922343.7832 | 195237857.2126 | 569586220.5279 | 678900104.1061 | 703462973.7682 | 315215577.7242 | 593701077.7124 | 25324794.4073 | 107756834.9029 | 23460160.4352 | 25516481.3504 | 813537636.3112 | 25975869.4723 | 1174545764.6616 | 6000870136.8522 | 633992738.6015 | 178015037.415 | 2.0162e+12 | 2321376.8459 | 1008836.8528 | 1465797.9183 |  |  | 2.2005e+12
1120 | 1208641127.5374 | 1210590517.5986 | 200674476.5949 | 142421325.8557 | 1068884750.0939 | 19596312.8391 | 213983187.9616 | 304204414.6707 | 477521451.9559 | 141542909818.9766 | 1924822743.9972 | 1946083746.7214 | 2083397955.4601 | 202379265.4583 | 585873488.0225 | 679054810.6225 | 926766045.6737 | 329169967.1316 | 602782722.0913 | 25603428.5484 | 115300232.4843 | 19781296.8913 | 23746210.0052 | 863884208.1179 | 25688796.7618 | 959113164.6548 | 5963834443.7303 | 633470017.8964 | 175693795.9667 | 2.1683e+12 | 2383816.7226 | 916432.9506 | 1827480.6919 |  |  | 2.3328e+12
1121 | 1131965852.6488 | 1163145976.3485 | 213569744.7588 | 176713679.4695 | 1015364580.741 | 24423833.2905 | 201992205.2303 | 271613426.1695 | 490888668.084 | 132890492864.4723 | 2039940046.8053 | 2042655353.039 | 2097578233.1506 | 184506832.7946 | 616599065.3768 | 627074979.1874 | 832404778.5993 | 233706664.6286 | 439040066.5286 | 27077045.2083 | 114961128.8877 | 21648318.4989 | 24267812.2863 | 878767806.1547 | 26358645.2162 | 1054558974.9038 | 6384688774.6622 | 517670022.4639 | 181521606.6627 | 1.6403e+12 | 2793809.8144 | 926174.3874 | 1734521.5601 |  |  | 1.7962e+12
1122 | 1187838865.8641 | 1128414542.2996 | 212848487.5556 | 158390592.8953 | 1061229318.2045 | 23494937.5732 | 191237305.5652 | 315181967.9537 | 452959851.0151 | 146961702184.9873 | 1940831454.8189 | 1769692364.8892 | 2005473841.6193 | 179188599.1036 | 511838077.4494 | 624921607.8299 | 758440636.2333 | 351625096.5232 | 584243041.5837 | 22723529.1741 | 119890374.5099 | 23408637.5078 | 18702033.947 | 850117946.3843 | 28677844.3951 | 1205022074.0487 | 6342544572.2119 | 573118418.2917 | 195587171.7223 | 2.4839e+12 | 2604200.6114 | 941855.3828 | 1558221.9353 |  |  | 2.6538e+12
1123 | 1118122432.6481 | 1041083325.7798 | 202796673.3043 | 162529335.5102 | 1028880531.1101 | 21902403.6665 | 214449955.8039 | 307425316.3269 | 451465787.6675 | 126840522767.3845 | 2035663048.4767 | 1474437953.0473 | 2092959232.102 | 186322845.3542 | 496425199.9567 | 521435476.2156 | 887935848.2815 | 276995593.5974 | 527875711.8975 | 23121763.0085 | 122663153.8226 | 21826217.318 | 25517184.8609 | 908817905.8129 | 28882780.329 | 761032213.8236 | 6446926074.9476 | 686948619.6933 | 196557128.1505 | 2.1199e+12 | 2408930.9712 | 926950.046 | 1531688.5453 |  |  | 2.2691e+12
1124 | 1226541089.1296 | 1220610882.4123 | 195868412.4427 | 171533137.6964 | 979422336.3328 | 22372533.0931 | 207806040.2487 | 308606946.8616 | 495674130.3188 | 152080594685.8574 | 1874469574.3235 | 1533085116.5481 | 2153406227.3433 | 194629810.6942 | 593387471.5778 | 709999778.8228 | 899309744.8874 | 338820842.7482 | 595799755.0463 | 24031458.9417 | 104922615.6776 | 22763528.0712 | 25435881.1575 | 857185497.5675 | 27367347.5338 | 1177684588.5412 | 5726519028.3241 | 703935968.8187 | 201649313.0019 | 1.7183e+12 | 2528726.0531 | 1003255.1795 | 1592687.5164 |  |  | 1.8929e+12
1125 | 1264623410.9018 | 1182911436.2982 | 218076998.2266 | 169038280.9719 | 1056718363.2255 | 28051834.905 | 192323101.3871 | 264140681.0405 | 423318330.9621 | 139076611983.6399 | 2059418239.7396 | 1743125321.7205 | 1804735633.7308 | 173270436.9908 | 616084681.6697 | 710666257.2324 | 827600506.5053 | 317265752.6466 | 575738664.1943 | 28590613.0196 | 93724761.171 | 20628572.6811 | 21396961.7419 | 888856862.7916 | 23605339.3405 | 1071790776.2562 | 6558323023.7921 | 596078410.4834 | 195706217.428 | 1.477e+12 | 2624406.6057 | 937412.7743 | 1764402.6225 |  |  | 1.6392e+12
1126 | 1184166699.4895 | 1216460280.4803 | 213345126.7987 | 176600373.6719 | 847909083.4099 | 24292320.2648 | 195475249.3712 | 326467359.2059 | 498566173.8335 | 150824021811.6707 | 2060721080.7953 | 2044293165.0099 | 2077681039.3426 | 183324174.7151 | 631746384.53 | 716511428.3414 | 879976468.6692 | 284664508.4064 | 492422662.0886 | 26033149.9238 | 106367979.9562 | 21281496.653 | 25509189.4302 | 868088315.1882 | 30059042.7129 | 1141417533.3026 | 6107361890.422 | 658733122.3479 | 180383135.6249 | 2.6668e+12 | 2431052.0095 | 883370.343 | 1784432.1089 |  |  | 2.8409e+12
1127 | 1171016787.0283 | 1209092944.97 | 216169451.2156 | 155947717.1389 | 1019551524.1194 | 23618497.161 | 222439737.5179 | 326109446.3736 | 439705147.9471 | 139860773368.66 | 1855590055.7583 | 1932838861.2338 | 2142076986.0922 | 202233470.4321 | 656392293.5333 | 694383091.0545 | 816302069.3304 | 331532627.5384 | 566426595.1433 | 20517562.1866 | 113225298.344 | 20863151.968 | 20955601.6892 | 685032981.3337 | 26627605.8767 | 1009720597.8241 | 6514753979.126 | 644481283.3701 | 193669695.4835 | 2.7733e+12 | 2244968.8057 | 951157.9231 | 1556394.3468 |  |  | 2.9364e+12
1128 | 1136525283.4985 | 1139719764.5687 | 216072154.4084 | 169157077.5796 | 1044814618.9033 | 25700863.2301 | 218798786.781 | 297299872.7858 | 483518080.6814 | 130784774712.7765 | 1862701773.7797 | 2090731877.715 | 2179321704.6992 | 180792610.9159 | 496473669.8966 | 625224334.9925 | 798352113.8936 | 302130338.8156 | 561645423.7479 | 27443940.9792 | 114944573.8983 | 21787066.1419 | 20226681.1048 | 900098540.2909 | 22742428.0037 | 1197935886.5422 | 6446514127.5616 | 583619547.3437 | 174022041.4815 | 2.4895e+12 | 2427208.9609 | 904611.6853 | 1787690.6926 |  |  | 2.6436e+12
1129 | 1176784469.3507 | 1192721952.2285 | 216742192.8135 | 162736847.1466 | 943788497.459 | 22549078.3582 | 203259742.0185 | 322518064.5202 | 481684655.4827 | 146690121894.0134 | 1948827725.3316 | 1800991862.1902 | 2151382965.561 | 191106303.1514 | 592253859.7895 | 627380700.4174 | 784054621.6769 | 328126709.1269 | 588400586.137 | 25626389.6253 | 102664392.3296 | 22976926.5341 | 23732364.385 | 852898352.27 | 22024208.9262 | 1109826182.794 | 6613949208.6879 | 673985587.8366 | 190525346.1686 | 1.5895e+12 | 2570352.0437 | 1037973.9156 | 1652173.7812 |  |  | 1.7596e+12
1130 | 1187811945.1229 | 1172420264.6941 | 216238482.1237 | 168030179.4268 | 1082204441.3823 | 23680986.3534 | 206604026.0081 | 315882560.7153 | 483367286.4077 | 115441076265.9841 | 1916648375.397 | 2046153650.8113 | 1947173553.659 | 177865762.8674 | 616461260.1195 | 684545737.7719 | 802642985.1553 | 337963025.2872 | 583827098.1233 | 23060152.8998 | 131770418.3693 | 19778494.1157 | 24686524.011 | 756191936.3931 | 29321146.9395 | 987467606.3322 | 5341331094.0215 | 689348383.6076 | 187308774.1846 | 1.5791e+12 | 2460702.8016 | 891586.1479 | 1590844.8699 |  |  | 1.7167e+12
1131 | 984430293.8398 | 1112359702.603 | 217321643.0312 | 172787090.7167 | 1060429806.0918 | 21738626.8403 | 188338093.7937 | 325504649.0956 | 470278501.0328 | 155454108239.7121 | 1834422317.418 | 1982187000.8756 | 2167632653.8688 | 176062473.2506 | 584745539.3538 | 700766427.3516 | 901594364.4153 | 314591620.6282 | 490305750.2839 | 26455465.2046 | 108659052.0139 | 19832596.422 | 24289834.7394 | 914597822.8764 | 24437798.1207 | 1076699310.9618 | 5526315257.5665 | 676492570.2486 | 184663719.0863 | 1.5485e+12 | 2573006.2595 | 957073.5176 | 1576758.5192 |  |  | 1.7262e+12
1132 | 1032275224.5916 | 1072720268.5942 | 220396715.1364 | 153371945.4762 | 987748728.2986 | 23494021.4173 | 200784329.5872 | 322325344.1988 | 484058027.9302 | 125581760384.0124 | 1688894166.8162 | 1956938915.8285 | 2176120987.5976 | 193332460.1383 | 575328492.0813 | 617291334.8863 | 699210023.8405 | 292710034.9845 | 612425511.9459 | 26254824.228 | 125107461.6096 | 23403501.2629 | 19857727.9365 | 907091071.452 | 27031309.6456 | 1045087713.9029 | 6635908467.7301 | 641225014.1385 | 173195618.2123 | 1.9654e+12 | 2666786.8496 | 956168.3085 | 1535577.9849 |  |  | 2.1139e+12
1133 | 1222921775.2626 | 1188010781.79 | 221891003.2814 | 170831629.9288 | 1041853200.4591 | 21505691.756 | 192396496.5489 | 324052750.1172 | 491303349.9555 | 156776892244.1536 | 1717125721.3796 | 1807994479.7125 | 2051324866.8671 | 170655666.6758 | 613050547.7115 | 668806874.0567 | 842020734.1986 | 341695137.9534 | 607830576.3033 | 27717341.9897 | 128616534.1708 | 23501049.9892 | 22061514.2736 | 855889849.2446 | 26933195.4115 | 1192982848.763 | 5784145196.2076 | 662923538.4734 | 192122628.9909 | 2.0427e+12 | 2425771.4468 | 914863.0291 | 1722573.7878 |  |  | 2.2221e+12
1134 | 1175319413.8391 | 1161479256.996 | 214011230.147 | 170066681.1804 | 1072966181.3505 | 22440798.5652 | 200112886.5671 | 321439361.6555 | 476395327.1932 | 157721621426.5154 | 1998936366.2187 | 1718893747.4417 | 2142639589.9907 | 170203083.737 | 551776559.896 | 714396877.8142 | 779420975.9327 | 241746189.4761 | 467325097.6955 | 24163463.462 | 113541670.1325 | 23367777.3614 | 24442231.8074 | 803073639.0469 | 26739963.8188 | 1033225680.1684 | 6282187206.5465 | 618846754.457 | 190076585.0083 | 2.5527e+12 | 2288916.5124 | 917761.1487 | 1544784.836 |  |  | 2.7332e+12
1135 | 1163147953.964 | 1085734524.5749 | 206354780.9984 | 179550879.824 | 1012890453.4969 | 25562201.283 | 215137973.7075 | 305053819.8257 | 471760820.6104 | 130755977067.2913 | 1810450752.2464 | 1866823499.9547 | 1950477882.9759 | 198494756.5251 | 494567530.1781 | 649570664.0341 | 905322644.6515 | 307754103.8599 | 559568150.668 | 25991523.8875 | 103245697.0543 | 21191559.8749 | 23806383.023 | 821037850.7495 | 24182035.9002 | 994373072.9997 | 5918148508.904 | 606342222.0998 | 201390892.8503 | 2.2358e+12 | 2483869.2605 | 917388.3968 | 1841878.3238 |  |  | 2.3887e+12
1136 | 1170919243.9224 | 1189554753.6882 | 203044521.662 | 169600226.8407 | 1006924270.3443 | 25399725.0906 | 207679750.2738 | 306923361.922 | 499411408.3034 | 148137278712.455 | 1884919735.9846 | 1764872277.0447 | 2118761247.5635 | 198104057.6531 | 542719190.7453 | 710655058.5795 | 786546151.6799 | 317282402.0943 | 526029256.4885 | 25689981.9351 | 131487307.1365 | 23853422.688 | 25166891.3992 | 773824119.9862 | 24862075.1428 | 1130607614.5015 | 6267070809.0295 | 485590488.1697 | 152840411.381 | 2.1336e+12 | 2692955.3812 | 1021639.4581 | 1543855.4811 |  |  | 2.3044e+12
1137 | 1242476064.8389 | 1193451984.9003 | 210370589.2027 | 164336650.8175 | 1049839776.1592 | 23080999.414 | 203444809.6214 | 284411464.9218 | 493648347.2759 | 125452328290.4168 | 1614610081.1875 | 2011643291.6148 | 2150313887.1885 | 201553371.8063 | 638562259.1797 | 635787044.5843 | 908452088.9846 | 312596196.0587 | 597419005.0537 | 28176151.7991 | 106759136.0212 | 23805734.7353 | 21777212.2163 | 886094567.2223 | 28022174.0049 | 870321648.375 | 6712231399.2445 | 707166934.8968 | 144557869.4988 | 1.9895e+12 | 2473801.5251 | 936265.1196 | 1543796.4184 |  |  | 2.1384e+12
1138 | 1227976637.6064 | 1194122827.7437 | 184540876.147 | 180534046.4485 | 1016112133.3202 | 25126520.7094 | 227514768.5333 | 271612385.0737 | 455705313.5468 | 135238203633.3659 | 1741580157.8545 | 1899269347.8982 | 2002562630.8985 | 189039507.7904 | 502124531.9012 | 659774475.9198 | 847978241.6397 | 331361473.702 | 587486328.3999 | 27064960.918 | 124793566.4119 | 23154930.1655 | 23375821.5488 | 716015139.955 | 23713956.9485 | 930804743.1719 | 6659745109.2175 | 657334415.4785 | 185632498.5539 | 2.4547e+12 | 2553199.8736 | 980125.4529 | 1608948.9909 |  |  | 2.6129e+12
1139 | 1185657029.0766 | 1009797560.8944 | 222691031.9719 | 167240530.1704 | 1019202248.7905 | 22129347.8041 | 225274382.2915 | 317218725.3511 | 499384243.7174 | 150228084067.7587 | 1934347287.2502 | 1624882568.1895 | 1488344779.8462 | 192961811.568 | 528309621.2266 | 712645178.6115 | 703133562.6589 | 262124221.8056 | 600306771.3234 | 21186069.1557 | 121705121.7241 | 19480926.5422 | 24332648.2914 | 825565215.3926 | 24453949.095 | 1063148622.8252 | 6405233680.9478 | 593856399.108 | 198265848.6007 | 2.6043e+12 | 2439641.2898 | 985096.1668 | 1721037.7046 |  |  | 2.7766e+12
1140 | 1074148127.7911 | 1049952659.5694 | 220699160.0154 | 157213473.349 | 972135755.4464 | 22805217.2191 | 188114717.866 | 314902092.815 | 496312193.3558 | 155771125746.8824 | 1455074125.9133 | 1762613821.6636 | 2200302804.1219 | 170177241.6546 | 536412941.2492 | 619315995.778 | 766890174.4615 | 332568285.7786 | 579571122.7542 | 23741620.9571 | 123569608.5112 | 22023620.6546 | 25951636.2796 | 827890920.0019 | 27627393.7735 | 1033195415.8494 | 6360664685.9481 | 619145997.8602 | 175387758.1819 | 2.1429e+12 | 2478347.3391 | 927459.2862 | 1556772.0822 |  |  | 2.3208e+12
1141 | 1165398752.4023 | 1172927653.7998 | 223099207.0791 | 172167522.9349 | 1050123969.3643 | 22020306.9495 | 179757537.6952 | 316070362.9709 | 442646926.8063 | 152254323339.033 | 1901286130.4451 | 1904519226.991 | 2143310115.1805 | 197790638.9421 | 534859902.9398 | 507291275.8799 | 881148973.0318 | 313196465.1027 | 612882520.895 | 23189018.1705 | 122519486.9808 | 21495795.5038 | 21786494.8306 | 707956499.8886 | 22072632.6186 | 1060143119.2338 | 5537167575.7899 | 672290823.6482 | 185810646.8812 | 2.342e+12 | 2360372.6132 | 981623.0346 | 1557932.9572 |  |  | 2.5164e+12
1142 | 1232194982.8512 | 1156636503.7853 | 210433779.7179 | 171632102.6171 | 1020511887.1747 | 21049329.4946 | 215266662.0288 | 315015363.1623 | 494488099.6994 | 137585893436.0182 | 1560219069.7114 | 1783136325.5101 | 1901457992.6314 | 195046003.2358 | 621576856.3415 | 717015809.83 | 791563272.1055 | 256764658.4966 | 548493212.7465 | 23568170.8735 | 134440153.0801 | 20527475.7713 | 23247866.6396 | 714476451.697 | 23847431.4881 | 1168711117.8628 | 5731283129.2432 | 656018493.4368 | 179833736.6617 | 1.9741e+12 | 2463489.2423 | 939297.2569 | 1821419.3461 |  |  | 2.1336e+12
1143 | 1077339359.1564 | 1167565226.9847 | 174844884.1496 | 167351375.7066 | 1081485420.0227 | 23412635.8115 | 218786383.1471 | 314904838.5417 | 423204751.7146 | 142868933972.4705 | 2009118796.8753 | 1692817608.4097 | 2002187510.0808 | 165273744.613 | 603496469.5863 | 681644690.2035 | 685432263.3953 | 258997082.201 | 609480772.43 | 21274616.0758 | 130847027.975 | 21675062.1276 | 23912314.4173 | 882665476.9781 | 23305183.6218 | 1026624368.6884 | 5750351940.233 | 708850495.9456 | 198754508.8316 | 1.6672e+12 | 2508297.7738 | 892477.2446 | 1597474.4751 |  |  | 1.8322e+12
1144 | 1238795941.5767 | 1167713635.5195 | 212794722.6453 | 169322337.9867 | 977652888.7567 | 28135033.3725 | 182582144.6107 | 322450281.6879 | 485815953.2564 | 133519580136.1458 | 1742958845.0901 | 1706668751.2175 | 2184688986.5229 | 148842214.4082 | 651372697.7724 | 688833343.7977 | 879446483.5617 | 251536918.1031 | 556135461.5772 | 23951245.3882 | 132704980.3723 | 20030733.6387 | 25218745.0093 | 901081434.4206 | 21061477.9366 | 1052296168.9783 | 6482480581.824 | 596119872.8838 | 178618070.1452 | 1.3943e+12 | 2390654.2682 | 882915.7087 | 1629347.9463 |  |  | 1.5508e+12
1145 | 1005707956.4654 | 1079552147.3355 | 213523972.6195 | 160297533.9438 | 892622481.7926 | 24470393.5208 | 200481348.141 | 302968394.9608 | 499662627.1944 | 144591476161.4665 | 2067810628.8094 | 2032555169.8908 | 2037654964.5957 | 170537612.3656 | 479482822.7562 | 718017411.6418 | 927424949.8819 | 296780954.698 | 529457617.6024 | 24415709.0231 | 117110660.7841 | 20018355.9075 | 24744529.3753 | 881246128.0017 | 24976725.6935 | 1185511245.3957 | 6873131080.2864 | 646880180.644 | 178423695.7502 | 2.1328e+12 | 2621730.3436 | 1001806.4649 | 1622666.3948 |  |  | 2.301e+12
1146 | 1151994064.2681 | 1087278244.9067 | 219958002.2541 | 169390958.4323 | 845803643.4512 | 22618575.7114 | 225065416.598 | 324012411.5542 | 476826941.3638 | 158848177019.5943 | 1892438153.2933 | 1967948787.494 | 1766059029.648 | 167815113.9247 | 611844779.6547 | 531330266.0254 | 796199738.8268 | 276693781.7331 | 571912410.3096 | 26273079.5501 | 106090163.5175 | 22665781.0002 | 22460805.6228 | 878936603.2385 | 24525914.7781 | 1030418822.2599 | 6751030604.124 | 613351064.3451 | 194948575.815 | 1.781e+12 | 2379795.3116 | 934973.5978 | 1507878.3103 |  |  | 1.9626e+12
1147 | 1227281632.2981 | 1208700445.5823 | 201794386.6766 | 135728187.0765 | 1069503060.7804 | 21407453.7371 | 205344775.7655 | 317200233.8781 | 494683374.5471 | 157211482408.8618 | 1869602455.2237 | 1703267346.9613 | 2158844323.6854 | 192977980.5574 | 571058149.4556 | 586290645.6789 | 768536945.6477 | 328021254.6759 | 610047858.2319 | 22269259.7309 | 101580293.0173 | 20611996.8126 | 25694684.8261 | 872345390.3104 | 30156217.507 | 908236888.3975 | 5577314386.4217 | 653418615.2197 | 188060251.8022 | 2.343e+12 | 2517469.1685 | 893712.6969 | 1637829.8313 |  |  | 2.5223e+12
1148 | 1222024649.4514 | 1225931873.997 | 212640344.2445 | 143992280.303 | 1062662487.6926 | 23518098.2609 | 189095102.1188 | 308325671.0286 | 488302347.7045 | 152504866602.3669 | 1987244812.4938 | 1774807811.1726 | 1877502996.0778 | 202319795.5858 | 606070519.3006 | 674360473.4538 | 750593885.7734 | 287464930.2048 | 608580000.4346 | 25475334.6588 | 124715830.9977 | 20984129.684 | 24199946.1611 | 893941740.4389 | 28543900.398 | 1181946416.5615 | 5593549362.2699 | 702724583.0612 | 191631043.4152 | 2.4776e+12 | 2335643.5993 | 908687.2132 | 1623186.7499 |  |  | 2.6525e+12
1149 | 1227466028.1977 | 1199243853.4854 | 214375696.6236 | 171650776.971 | 998739857.0304 | 20135705.4258 | 196407391.2702 | 300589474.0957 | 498246215.9572 | 119262123844.7853 | 2008782893.6062 | 1907398816.8802 | 1704528942.1245 | 191852206.2105 | 645534765.97 | 708089631.0017 | 782731276.3413 | 312903318.6702 | 610852463.8527 | 26004449.9378 | 121636324.3086 | 21235167.7973 | 25053036.2999 | 930876950.9489 | 28904606.9428 | 936783610.9956 | 7037820725.9116 | 631126153.7753 | 186895867.6582 | 1.6674e+12 | 2481692.293 | 962622.0866 | 1524647.7159 |  |  | 1.8103e+12
1150 | 1218577661.7247 | 1168596345.5061 | 200241228.4658 | 170576745.9961 | 1039907822.2144 | 22183564.5313 | 194504415.6202 | 302666550.5386 | 497043142.0143 | 147094645962.2589 | 1962306117.7059 | 1889857199.9265 | 1987049852.7709 | 199436170.2084 | 496408938.7667 | 663979088.5758 | 805550500.7611 | 282156881.933 | 601626159.9092 | 25064313.7399 | 123900848.993 | 24278313.9022 | 25986821.9345 | 913830681.5425 | 26845075.1848 | 1149071273.2677 | 5602931691.6901 | 674847886.289 | 196608830.4086 | 2.0314e+12 | 2790991.5526 | 907969.4598 | 1538129.9697 |  |  | 2.201e+12
1151 | 1147530359.1106 | 1219101076.7605 | 211629663.0851 | 180048524.5063 | 1083270011.9938 | 22889819.3791 | 220821479.6512 | 296000722.6693 | 489393989.7835 | 122692410801.7035 | 1756191409.9116 | 1976293978.4185 | 2146146573.6535 | 176402613.5166 | 625231265.1881 | 661399429.5088 | 775822361.2161 | 309613412.6869 | 613228622.4878 | 25125631.3584 | 98520591.9888 | 17360001.7108 | 23630497.1009 | 790529985.2896 | 30627992.5746 | 1116951585.0796 | 4474041517.0568 | 641208223.9391 | 191846955.1999 | 2.2074e+12 | 2378125.8833 | 930391.5587 | 1490473.882 |  |  | 2.3515e+12
1152 | 1130825434.3095 | 1065968572.2966 | 204101878.3231 | 178759861.5228 | 1072486424.3816 | 20008692.2199 | 206036697.4228 | 324380827.6392 | 470396097.5645 | 153799864483.2974 | 2012867700.5382 | 2026196289.5816 | 2122993546.9068 | 184094604.7663 | 586623719.9351 | 692703745.5439 | 825362737.5719 | 237473065.9505 | 611928260.2431 | 25874541.0374 | 98792488.7424 | 19105173.2814 | 25701373.7352 | 834727285.4354 | 21612201.9609 | 1177019178.9848 | 6334583338.2253 | 587708580.7379 | 199020688.0133 | 1.9055e+12 | 2430543.4227 | 1010850.1359 | 1707767.3453 |  |  | 2.0826e+12
1153 | 1126499083.2682 | 1208943295.3915 | 188252547.1078 | 154699528.7127 | 876821412.6757 | 25163988.4648 | 190921148.909 | 295941404.2927 | 457958453.3178 | 138066014914.0478 | 1789316072.7258 | 1956901279.7242 | 2114768374.2987 | 148996295.7958 | 552589287.9855 | 706173672.2486 | 900306587.2181 | 297524266.7262 | 553996039.349 | 27774604.7174 | 86989202.3608 | 20430969.3061 | 25688230.7285 | 797429697.0297 | 30925248.7951 | 1023009362.5292 | 5956902611.5258 | 704610696.6454 | 196065224.4968 | 1.8021e+12 | 2516345.5237 | 954760.5323 | 1708861.3332 |  |  | 1.9626e+12
1154 | 1151154084.2564 | 1219697392.2862 | 208497761.3925 | 170133205.8513 | 945704760.0464 | 21057001.2827 | 220832398.6034 | 289167380.9307 | 499847884.9556 | 157683286790.8239 | 2061940687.5253 | 1868974257.4642 | 1958493494.6474 | 161201859.6394 | 401863517.0491 | 687969539.212 | 896337571.6681 | 296214523.7799 | 564469416.8503 | 25162630.407 | 122255328.9516 | 23516679.4015 | 25500374.0978 | 942264193.904 | 27935061.0438 | 1053780089.4643 | 6920567888.6323 | 657462613.2007 | 175176715.7438 | 2.6965e+12 | 2675873.3125 | 988804.0941 | 1652171.156 |  |  | 2.8778e+12
1155 | 1259191705.5124 | 1163332691.2821 | 210182670.9862 | 165907981.4595 | 1063384003.9819 | 20837612.9315 | 227129278.0099 | 274022329.1898 | 498650409.9752 | 141244608898.827 | 1872731787.7843 | 2195324745.0211 | 1987825258.8089 | 194802841.3397 | 654934653.5824 | 705490682.114 | 844633881.6829 | 328044467.3547 | 531556881.0251 | 21560076.6286 | 106087437.4267 | 22272755.934 | 20686886.7822 | 878449997.7952 | 26104191.0891 | 967909625.9667 | 5616109219.8643 | 568660427.11 | 197127704.8098 | 2.3403e+12 | 2399642.8841 | 933648.4171 | 1682611.7521 |  |  | 2.5041e+12
1156 | 1244977308.142 | 1090552601.6436 | 198846603.1985 | 169930170.2851 | 1068861818.2795 | 25841164.8338 | 210313046.3478 | 287583787.9365 | 460200950.5866 | 159918312760.8046 | 2012914040.3726 | 2018697625.3554 | 2156405899.6362 | 137273983.6388 | 548619585.6022 | 708203195.2979 | 880911021.2522 | 327922506.3882 | 488656016.8392 | 27969684.9876 | 130307304.3234 | 23040768.2646 | 19413186.1819 | 839495579.3072 | 28159618.9302 | 1154699230.9196 | 6560955149.2186 | 571848709.4483 | 189250133.9294 | 2.1282e+12 | 2214937.2394 | 945480.177 | 1881796.7296 |  |  | 2.3117e+12
1157 | 1182161202.997 | 1137471117.4686 | 208540799.0968 | 160471428.3828 | 1037595605.5016 | 22627078.617 | 187745022.9338 | 291162047.6494 | 443973922.3538 | 144984676993.5357 | 2052312763.9285 | 1772417815.7977 | 2177779144.7622 | 198969486.5715 | 573216730.9535 | 683677640.91 | 720900533.8723 | 257063109.9346 | 605025292.3328 | 27852530.4913 | 115621753.9052 | 24589601.1705 | 23026893.9635 | 868047862.3077 | 30076150.5737 | 985301958.973 | 5985168756.5113 | 708842069.7145 | 188576129.4108 | 2.3672e+12 | 2398384.3473 | 937958.8859 | 1591033.6168 |  |  | 2.5348e+12
1158 | 1206149605.5032 | 1183729988.8974 | 193728512.7012 | 172255364.9649 | 1073596843.487 | 21403886.6598 | 200574663.9181 | 323769553.5879 | 446616563.4565 | 135929815914.8978 | 1928729596.8954 | 2004742973.051 | 2209249065.5276 | 176704836.5646 | 560138620.0053 | 671854158.8576 | 729677680.2247 | 344454216.6018 | 615881705.7663 | 26216968.1675 | 106448530.1574 | 21919276.772 | 20218964.4153 | 823994077.666 | 26278336.65 | 1204576500.7793 | 5956185619.0731 | 658249292.8239 | 192711653.6936 | 1.4772e+12 | 2541172.0159 | 904801.2281 | 1559444.4301 |  |  | 1.6362e+12
1159 | 1177470097.1087 | 1078350839.6874 | 214451957.1019 | 154948272.7005 | 1053844482.0013 | 22805694.4527 | 219739495.3122 | 294708956.9683 | 500259060.3233 | 139734636555.171 | 2095446228.7178 | 1618907779.7154 | 1826690582.627 | 196325106.6262 | 577619469.6002 | 724812892.1506 | 812166896.148 | 281101456.5397 | 600475054.2716 | 24458635.64 | 103138270.9355 | 23129251.1286 | 25754500.6572 | 919547311.8902 | 27155266.93 | 1200661434.3316 | 6978137926.9023 | 686159999.036 | 194320807.4188 | 1.9532e+12 | 2299922.5972 | 964805.7501 | 1635882.4859 |  |  | 2.1166e+12
1160 | 1237513171.8008 | 1139433628.2327 | 216854825.5535 | 168442049.0936 | 993580104.4204 | 22038578.4003 | 209986570.8887 | 317420421.9432 | 499332843.8527 | 156181187930.546 | 1931194989.09 | 2095992956.7497 | 1863498143.0311 | 194049234.5449 | 647379374.8488 | 713998484.3752 | 840268808.6666 | 345183012.1379 | 559448743.8346 | 25167465.202 | 108023022.6246 | 21474895.0398 | 23213989.271 | 799510434.4167 | 29537538.0737 | 967757809.4731 | 6694759590.2407 | 621477450.0547 | 179655490.6827 | 1.8418e+12 | 2747087.005 | 982763.9693 | 1594000.8378 |  |  | 2.0215e+12
1161 | 1166023053.3744 | 1209567996.6532 | 199987255.7444 | 164978151.5857 | 1043851771.518 | 23971457.6828 | 221114316.6527 | 317026815.8567 | 482793887.2597 | 152116109741.3241 | 1935588181.7843 | 2017007396.5109 | 1726843721.7341 | 172975218.8026 | 618496086.5751 | 579390222.8059 | 863145403.3847 | 324951355.7831 | 607320840.3915 | 23735584.1667 | 106209912.3109 | 22279707.8101 | 24563700.4393 | 796421125.2774 | 25898450.1762 | 1117585413.9989 | 6675315713.231 | 639283724.6729 | 180272593.1366 | 2.2898e+12 | 2394253.8488 | 985891.7863 | 1498224.6564 |  |  | 2.4652e+12
1162 | 1217736119.587 | 1154188184.2974 | 188448738.1117 | 173272452.6545 | 1050482788.8788 | 25901374.3073 | 214812993.3433 | 309009961.572 | 446576127.3116 | 130468101662.9602 | 2052437379.9955 | 1741189789.4538 | 1943573106.6998 | 186262315.841 | 650075998.3393 | 683452986.053 | 689007574.4533 | 260814021.564 | 557070462.388 | 28991736.6041 | 105241669.7359 | 21816989.9226 | 23379337.6778 | 867443338.7772 | 28092116.7445 | 1040540090.4257 | 6538602356.8939 | 552715589.8256 | 188509343.8835 | 2.0648e+12 | 2525211.6799 | 899406.9131 | 1498148.6973 |  |  | 2.2182e+12
1163 | 1181029871.7724 | 963271120.4306 | 218606813.0613 | 162371825.1564 | 1063471206.5578 | 25360792.523 | 184682261.9594 | 304958403.135 | 493790858.6574 | 160384180986.3428 | 1842805063.5518 | 2065116880.074 | 2001124727.3787 | 185362665.1412 | 567015982.3614 | 629913244.0122 | 865704090.3169 | 313846108.3859 | 600772001.3969 | 26739544.7356 | 113452670.5059 | 19785294.8018 | 23844984.2019 | 879034695.3112 | 27456376.028 | 1146329516.3618 | 7070165490.57 | 701459150.8504 | 184904489.8273 | 2.3193e+12 | 2424817.601 | 973783.4634 | 1599461.3773 |  |  | 2.5035e+12
1164 | 1163676141.3184 | 1177923612.971 | 219187510.0514 | 164392364.6548 | 1077223677.9987 | 24972690.5546 | 197268717.8537 | 317315451.3629 | 491228974.7526 | 144753687385.7244 | 1478254689.2545 | 1875568334.8023 | 2089365554.9991 | 185614485.6833 | 492804173.4105 | 677153083.9151 | 689504702.0696 | 316047029.5274 | 605100477.1243 | 23967173.4365 | 94318115.6338 | 22423509.8074 | 22368556.8427 | 712867135.3901 | 29498222.6304 | 872598747.8114 | 6646601205.6909 | 687381731.5597 | 189912742.4334 | 2.069e+12 | 2469698.7586 | 958342.106 | 1647578.8997 |  |  | 2.2363e+12
1165 | 1174241700.6539 | 1187776052.1247 | 169170944.572 | 171339909.9198 | 1087310796.1685 | 25904687.3072 | 194943334.2125 | 326365425.4325 | 485683166.7355 | 149038667503.0745 | 1490127219.7694 | 1605862748.5206 | 2072041928.9858 | 201270655.7764 | 616011814.6675 | 685162707.1659 | 847706383.2557 | 244247025.9361 | 398550695.2063 | 23112018.6495 | 122765066.1789 | 22519290.399 | 20852749.0803 | 759138320.96 | 25300376.7717 | 1096783462.688 | 6263637837.9638 | 573286187.8911 | 188926779.4604 | 2.6032e+12 | 2544466.3866 | 879056.8453 | 1776811.2297 |  |  | 2.7743e+12
1166 | 1077660269.124 | 1138237178.5445 | 207049392.1254 | 169664102.0611 | 1069359122.9074 | 25100452.2255 | 211664672.4822 | 330005895.1251 | 434746337.1342 | 123832857627.3548 | 1968989477.7752 | 1892473299.1595 | 2177701797.0626 | 196055055.0466 | 632465605.7647 | 692923808.8661 | 725165093.059 | 316243607.107 | 611783868.7822 | 23094294.056 | 117619093.3022 | 24169581.3724 | 25776440.6475 | 894535585.0729 | 27912298.7467 | 1079250787.8763 | 5358022031.5518 | 590690843.3585 | 199168422.4718 | 2.3697e+12 | 2316373.0689 | 969170.0397 | 1741060.3074 |  |  | 2.5158e+12
1167 | 1099120514.0755 | 1212884034.3097 | 205329799.4667 | 141707764.4233 | 1061722163.4741 | 25396084.2412 | 201837427.7247 | 312947183.8255 | 446839807.0158 | 155508261489.2316 | 1965033652.5266 | 1464330820.6982 | 1999493795.6476 | 185756190.9856 | 649361815.4464 | 548135496.9438 | 690925739.8607 | 338907639.6242 | 577122105.91 | 27635875.9846 | 130791046.8181 | 22804433.1629 | 24078933.369 | 880473868.0725 | 25584198.1301 | 1083504970.9338 | 7343722529.7615 | 707483084.2557 | 197184447.1182 | 2.2375e+12 | 2370845.5291 | 945239.9476 | 1588518.1293 |  |  | 2.4166e+12
1168 | 1213707616.5605 | 1167740067.396 | 215159635.2258 | 154801757.7503 | 847629178.1245 | 25585083.7548 | 206174004.8155 | 326732830.3461 | 452013929.5557 | 136204336269.2779 | 1800767647.018 | 2107144062.1274 | 2040018638.0366 | 174027661.0991 | 504281950.6045 | 566198176.6735 | 886908727.483 | 283621148.6593 | 607672050.9149 | 23408235.5166 | 111694246.5683 | 21468177.4974 | 23911775.1495 | 857147222.3017 | 25753782.2806 | 855755792.8945 | 6036577962.468 | 713019486.1083 | 184810687.1385 | 1.3371e+12 | 2434457.2084 | 946247.554 | 1556530.9521 |  |  | 1.4958e+12
1169 | 1133486896.257 | 1212039603.0101 | 190433551.5861 | 150456966.777 | 1038837847.1241 | 24706109.5795 | 202070698.6714 | 325424181.8928 | 493791997.304 | 140027670509.1996 | 1692808124.1814 | 1706645566.1117 | 1987114354.2803 | 178606545.8219 | 654870074.4035 | 569417451.4885 | 789190628.7689 | 351945976.6613 | 592795097.6884 | 25504613.2078 | 105292388.5325 | 24029380.4817 | 24004007.4396 | 869581206.9667 | 31282504.9774 | 1071221408.2978 | 6355289677.9985 | 603840161.6429 | 165071951.6966 | 1.8041e+12 | 2259894.7265 | 924061.1336 | 1618764 |  |  | 1.9667e+12
1170 | 1086987229.9956 | 1170631604.6216 | 211417405.9949 | 154623611.3884 | 1044032390.2637 | 23615901.7611 | 195653629.6074 | 278215197.7957 | 491896283.3806 | 149731033293.2466 | 1936756083.3787 | 1773302111.0666 | 2180024705.8472 | 169987162.6931 | 573035724.479 | 537052651.0277 | 852719357.8714 | 289627859.3593 | 598883046.7115 | 26258927.0924 | 134853344.2814 | 22863140.0998 | 24810420.0773 | 772281057.5215 | 28344522.4202 | 875386598.2897 | 6934004394.6283 | 692025230.3316 | 182349557.7975 | 1.6651e+12 | 2251441.9935 | 977857.9827 | 1606842.8775 |  |  | 1.8381e+12
1171 | 1226356587.94 | 1083130497.1093 | 161554263.2813 | 145088741.5608 | 1014023817.9731 | 26699622.3948 | 214948550.7442 | 306288131.2981 | 489201945.9548 | 122252318397.3358 | 1824360613.9794 | 2076239670.9977 | 2179652517.0116 | 196355274.2095 | 672980783.8267 | 583737902.2831 | 886801307.5267 | 294056494.2096 | 610517283.5259 | 25417607.9761 | 127306109.1618 | 22319003.9612 | 24522425.6278 | 794124781.7541 | 28836629.8571 | 1002679027.6149 | 6278328972.258 | 597493076.8904 | 185714337.348 | 2.0571e+12 | 2477562.2536 | 980152.7243 | 1690193.8847 |  |  | 2.2025e+12
1172 | 1249771202.6555 | 1102206615.0519 | 204319729.6617 | 177545378.7906 | 1040050426.6273 | 20870803.4006 | 205266672.7693 | 310388059.8563 | 492602013.1023 | 148848769731.0695 | 1954096856.3735 | 1817248297.9481 | 2105091179.7935 | 199990702.5222 | 555049355.8331 | 711167097.433 | 815233973.7368 | 296233238.28 | 537184117.5947 | 22296322.4704 | 121200858.2953 | 23730876.9408 | 23530439.5393 | 937706746.572 | 23351357.2625 | 1150623644.4228 | 6456921737.14 | 702086504.3997 | 199645510.0038 | 2.3387e+12 | 2412303.9292 | 990241.9497 | 1571699.1959 |  |  | 2.511e+12
1173 | 1196589990.6073 | 1199052757.5466 | 191900183.8487 | 161914055.4382 | 990976393.2393 | 25423074.641 | 222365358.1789 | 317227701.4125 | 448591941.7479 | 128995010709.699 | 1572036576.8732 | 1704639630.4682 | 2151725166.7137 | 171598599.3445 | 669279843.2192 | 715521615.808 | 854727064.9994 | 341657737.8623 | 467140033.585 | 22608262.8787 | 121905148.1325 | 20442853.384 | 25844224.1848 | 835650743.5462 | 28403329.6833 | 986809692.4757 | 6763880523.0408 | 672632409.1102 | 190800562.3286 | 2.0128e+12 | 2492083.4959 | 992961.5881 | 1701023.3805 |  |  | 2.1649e+12
1174 | 1145345729.7222 | 1086780416.1669 | 186233663.4555 | 152297496.6755 | 1056084453.5827 | 24040273.9528 | 187927304.1127 | 325342806.6166 | 441912331.5554 | 152450276048.2579 | 1903337899.539 | 2041650112.0684 | 1881065622.549 | 190151483.0229 | 523405216.6844 | 687123454.2666 | 850622954.7283 | 342815407.2889 | 519773618.4265 | 25715653.6715 | 122691761.5602 | 23197733.8875 | 24543066.2702 | 892950599.0391 | 27642360.6165 | 841986107.2048 | 5925511443.562 | 673210121.5995 | 201509208.56 | 2.0817e+12 | 2457433.0623 | 933834.797 | 1689875.8783 |  |  | 2.2564e+12
1175 | 1178862181.5394 | 1106480966.4902 | 205012207.4999 | 174335656.0536 | 1043909962.0684 | 25293765.1834 | 217566872.4412 | 327943244.8325 | 422889744.6263 | 149253428270.1994 | 2025152614.3818 | 2171112164.89 | 2068800396.6237 | 177195405.6569 | 484955809.8939 | 698885226.0158 | 713559061.2348 | 296211746.8717 | 556069564.7934 | 27266419.1481 | 87585972.2054 | 23507474.2382 | 25851416.2396 | 824464238.1819 | 30366406.5856 | 1107137850.8239 | 6728061007.6712 | 705822447.7657 | 153817451.4155 | 2.5544e+12 | 2324975.8374 | 938838.2239 | 1646323.015 |  |  | 2.7273e+12
1176 | 1031641732.6842 | 1126655633.9763 | 205848251.3139 | 162427016.51 | 1073630662.378 | 26478249.6717 | 213281620.6147 | 326207923.3207 | 447125476.0007 | 158391484310.0874 | 1693655532.2865 | 2051807414.5902 | 2059992331.2433 | 163841402.4776 | 647854495.9682 | 720963405.6337 | 816045136.5942 | 276274182.9549 | 600077365.0144 | 24901135.7485 | 118705275.1736 | 25003885.3649 | 25685919.1954 | 755158104.726 | 22243464.9703 | 920875597.4501 | 5302185544.6541 | 639444112.7769 | 200324843.717 | 2.0952e+12 | 2511248.5051 | 923916.6189 | 1547322.3178 |  |  | 2.2753e+12
1177 | 1175676671.4998 | 1095750532.7402 | 210949412.3932 | 160401459.2869 | 1046930254.7512 | 24372357.05 | 210595674.2669 | 305303212.185 | 498482287.7517 | 148161962411.3436 | 1867146061.2802 | 2143896071.1163 | 2059180032.901 | 192988008.7541 | 491949796.9743 | 710156117.7239 | 925875624.6496 | 347674165.0737 | 587860916.6372 | 24776384.5507 | 127041593.0084 | 21768800.8787 | 24221989.7845 | 909687344.3826 | 27959461.3883 | 1127719873.2803 | 6640480754.2677 | 536326439.3844 | 187263748.7482 | 1.6624e+12 | 2355130.313 | 960606.9636 | 1569048.1 |  |  | 1.8343e+12
1178 | 1108065071.3029 | 1052220591.4413 | 203713174.3496 | 168852906.0286 | 1051777447.83 | 22853712.4014 | 211861968.0087 | 312003960.4629 | 496562513.3087 | 139692477971.1628 | 2064116498.6181 | 1808808846.5709 | 2130647631.0298 | 182087701.8816 | 465626316.8141 | 702089009.1565 | 892685739.4376 | 366780864.7428 | 559086218.8891 | 25813366.8246 | 118753467.8023 | 24782424.783 | 25267555.7051 | 896839868.0277 | 27863527.8324 | 1063356378.0758 | 6780713713.0789 | 687311561.8644 | 196718308.7055 | 1.9797e+12 | 2782752.3051 | 942558.0167 | 1820666.8846 |  |  | 2.1431e+12
1179 | 1126593157.2947 | 1039114174.7917 | 218405071.837 | 174822477.3056 | 977347936.4051 | 19052281.5803 | 190864613.9699 | 324075083.4668 | 437560420.1638 | 149468141840.952 | 2001638790.2331 | 1976518316.2638 | 1787280136.7451 | 193111120.0012 | 519063732.2208 | 643155852.342 | 778831496.8121 | 329867695.3629 | 492349129.5641 | 25747542.9445 | 113246437.6072 | 16088883.4916 | 25491032.233 | 843580759.2136 | 26137823.5016 | 1099621863.4978 | 6666959938.2555 | 622827489.5169 | 200924301.8994 | 2.6272e+12 | 2322623.4171 | 1022150.1987 | 1849635.6304 |  |  | 2.7996e+12
1180 | 1260718116.9787 | 1007723557.0537 | 200315933.3166 | 171114366.1742 | 893267802.1916 | 22588102.1246 | 204710241.2393 | 280671929.8346 | 443146376.9907 | 119751191747.9816 | 2048973084.0681 | 1599657134.5862 | 2147665434.3717 | 169647661.4806 | 644290656.9865 | 680642530.2988 | 873306914.7137 | 321750829.1935 | 589972104.1715 | 24985751.5 | 120545704.934 | 22540016.5468 | 22631946.2768 | 693507616.9465 | 28716001.1513 | 1028876490.4188 | 6425063805.0859 | 660079465.9236 | 173673166.0575 | 1.9057e+12 | 2446770.395 | 886476.0984 | 1833019.4834 |  |  | 2.0482e+12
1181 | 1247030071.6129 | 1185685374.5527 | 209221775.6526 | 170463830.7551 | 1040499430.4913 | 21528498.5042 | 217292338.5746 | 283574934.7813 | 443701814.1917 | 144560214848.0275 | 1906651603.1827 | 2173398606.3015 | 1878352024.6249 | 173840956.5653 | 558235953.9651 | 642560594.6087 | 896944444.6533 | 291859024.6042 | 509351607.6792 | 24888105.0149 | 109973313.1394 | 21690128.6295 | 25560942.8974 | 911942001.6728 | 23021535.8212 | 987296817.0489 | 7324803554.3179 | 622315465.4376 | 183088148.1337 | 1.6632e+12 | 2726606.0961 | 992347.4876 | 1796548.1895 |  |  | 1.8319e+12
1182 | 1080920321.6707 | 1174246739.9555 | 223411954.9788 | 156208750.7977 | 1048153548.9313 | 24618259.8714 | 205593425.6292 | 322995910.1823 | 466738911.7761 | 154390134897.2338 | 1825767527.4462 | 1664712129.8176 | 2193207368.0674 | 191300029.6791 | 497419280.7958 | 694023679.6227 | 772823982.3751 | 282260035.0932 | 578009378.8211 | 24141024.3069 | 105813792.1121 | 21098028.0981 | 21583077.5868 | 785898386.2476 | 28928955.3869 | 1068786826.7737 | 7016710027.5412 | 690067514.2509 | 180198106.386 | 1.7473e+12 | 2265905.4362 | 905227.5585 | 1760787.0422 |  |  | 1.9251e+12
1183 | 1218258237.9217 | 1061452802.4708 | 219034503.2505 | 175925882.2696 | 993106062.7871 | 22609653.1631 | 210911212.9669 | 293170892.7191 | 463305272.5107 | 148977504639.923 | 1991238557.2849 | 1969665143.7119 | 1989259991.8097 | 197855733.318 | 565546565.1598 | 653970206.6526 | 745588280.4688 | 351172560.7728 | 554020370.1685 | 26773523.5138 | 118689495.2389 | 22728460.5771 | 24475541.6913 | 811861027.6637 | 31003788.4369 | 964528643.6378 | 5854671615.5953 | 662701803.0192 | 201841237.3674 | 1.7257e+12 | 2409465.4883 | 941128.9661 | 1514078.8526 |  |  | 1.8971e+12
1184 | 1188327007.1894 | 1197131115.3732 | 218712963.9115 | 173020049.5431 | 1065720085.6372 | 21752753.5322 | 192886029.365 | 325233693.9297 | 491645328.6884 | 151985468933.8374 | 1845338933.553 | 2083199122.1625 | 2187143553.9638 | 200841087.411 | 501511894.286 | 687135808.3464 | 880772499.3648 | 279311533.8752 | 572743144.354 | 24292492.2548 | 122670163.5412 | 20949090.9012 | 24907966.667 | 904742339.625 | 21514417.9957 | 1020373782.5421 | 6063677808.1497 | 614018913.7905 | 190080970.7214 | 1.8752e+12 | 2312502.6545 | 980265.9402 | 1502805.0366 |  |  | 2.0503e+12
1185 | 1227357177.0534 | 1207431537.6677 | 207891904.0191 | 154800918.9926 | 1050359375.8178 | 20961605.0335 | 198262251.6352 | 307940946.4068 | 478498535.8771 | 138713683917.6475 | 2088623269.0642 | 1680607829.359 | 2158297468.9776 | 180406622.0078 | 597440745.7077 | 640378231.3682 | 841792993.899 | 312829103.7263 | 545839612.3628 | 25122782.3068 | 131524626.4632 | 22866439.6925 | 20984137.3356 | 935364063.2545 | 27171832.8226 | 988263017.6683 | 6597838041.22 | 641854597.7183 | 195194461.6554 | 1.9258e+12 | 2489399.9584 | 986833.2764 | 1519672.7393 |  |  | 2.088e+12
1186 | 1135459157.4277 | 1173483183.15 | 198277637.7618 | 177963501.3517 | 930719062.6926 | 25334831.6172 | 199499123.6146 | 298494815.8164 | 480606381.4716 | 157483417678.1147 | 1862029204.1962 | 1803938484.9201 | 2177965903.2496 | 198575978.1478 | 668642042.4597 | 620908822.4341 | 751797127.4452 | 289875115.824 | 542277564.8929 | 23184583.5789 | 135346516.7557 | 19078559.2394 | 22651433.0462 | 868252105.8277 | 27236009.4163 | 1005546624.2696 | 6305821144.7203 | 572297468.3533 | 181792342.2283 | 2.093e+12 | 2558463.8327 | 930658.5715 | 1695223.3849 |  |  | 2.2732e+12
1187 | 1150852866.5392 | 1213505143.7021 | 188737720.4611 | 167315181.4266 | 1082192517.8478 | 23826521.5975 | 191871166.6562 | 318212095.1407 | 489505677.4864 | 128570733685.8121 | 1981221618.9163 | 1620296386.0832 | 1628432076.5383 | 193715438.7114 | 514677789.8298 | 611001980.9945 | 852198961.3033 | 287755855.6964 | 558364414.2341 | 25949827.9155 | 124734970.5571 | 20908962.8412 | 24586685.5693 | 837983375.4187 | 25670510.624 | 974204698.6215 | 6106489764.8961 | 660520776.8978 | 158961014.8547 | 2.2333e+12 | 2343742.3611 | 908711.7147 | 1670719.3306 |  |  | 2.3839e+12
1188 | 1174748678.6421 | 1138238617.5651 | 200682189.2635 | 161051247.9164 | 1021851180.4714 | 24661209.518 | 215165749.043 | 259254583.4356 | 406408092.4604 | 134483468339.0108 | 2005143385.693 | 1998160411.3638 | 2056860178.1711 | 184253443.5357 | 648019420.0396 | 719043533.1735 | 762965562.692 | 364583795.5632 | 535319264.6604 | 26034617.1146 | 120080629.6297 | 21659111.9015 | 18938414.54 | 815591487.1716 | 29128449.335 | 1091779118.7223 | 6685175560.4691 | 611176758.7183 | 175799445.0112 | 1.6696e+12 | 2342400.2818 | 930512.1023 | 1815175.1888 |  |  | 1.8276e+12
1189 | 1258219462.2404 | 1123116389.1744 | 216951034.2006 | 173876796.2613 | 1087260513.5046 | 21150735.1676 | 220506194.748 | 319332603.5317 | 441400584.6846 | 152378219283.5072 | 1887012736.5779 | 2139346100.2645 | 2090611527.2227 | 157764782.1492 | 625168903.711 | 713162570.3396 | 913388243.4811 | 306853093.7941 | 556201707.5726 | 25358357.2947 | 102140518.7638 | 23136082.2481 | 24715569.6972 | 684097819.1942 | 31251214.9929 | 1136167971.1777 | 7209367798.119 | 591882063.064 | 196469024.4297 | 2.7764e+12 | 2325035.312 | 1011255.6143 | 1686401.1774 |  |  | 2.9531e+12
1190 | 1158374737.8433 | 999978486.3609 | 204349273.315 | 155114310.1735 | 1078728829.7517 | 23664879.2237 | 213657684.5327 | 315588399.8908 | 443545027.847 | 149054838143.8318 | 1982642909.7205 | 1481894672.4818 | 1833318274.6081 | 193275283.2914 | 590544262.4991 | 631111407.8016 | 662710564.6452 | 334208972.2482 | 611307938.0962 | 26245546.083 | 108460273.5936 | 21076761.7492 | 22652518.9528 | 932705212.2385 | 27507401.1939 | 1107224973.4569 | 5623783982.2876 | 617823578.7742 | 179595942.6146 | 1.7558e+12 | 2799839.0556 | 941196.7076 | 1719909.7796 |  |  | 1.9264e+12
1191 | 1150828236.0137 | 1099908691.5148 | 182159220.5015 | 175674102.7595 | 994107738.7625 | 26080828.545 | 204909233.21 | 326071302.0459 | 495540523.5796 | 117585564100.0679 | 1830187103.8532 | 1931565702.1239 | 1536813227.5847 | 153556307.2087 | 613866317.0309 | 696258959.2599 | 875499585.7048 | 340403942.263 | 580556061.1652 | 22246194.0568 | 117333426.6842 | 23799760.6097 | 26063929.9443 | 915540401.6486 | 29436614.2181 | 961062753.4358 | 6624234586.0906 | 705953725.4833 | 187730319.7816 | 1.8398e+12 | 2512258.0644 | 993672.5749 | 1527902.0371 |  |  | 1.9803e+12
1192 | 1182886291.6261 | 1006008513.719 | 197010305.6998 | 162576633.2493 | 907703413.7307 | 26556607.1936 | 207494088.5028 | 314706874.8667 | 439493893.0202 | 154279510298.2159 | 1683431656.4984 | 2163896194.743 | 1873721141.6554 | 191460669.5882 | 623880181.8555 | 684618330.1499 | 822129349.5022 | 341818584.1777 | 516002180.7574 | 25979286.8352 | 106407359.0544 | 24086539.5141 | 22002275.3597 | 790905705.0957 | 28350328.558 | 993762131.6513 | 6110584664.6741 | 701104847.7521 | 201334147.7906 | 1.8566e+12 | 2376038.8395 | 913752.4438 | 1815767.8415 |  |  | 2.0332e+12
1193 | 1211977987.0981 | 1223949385.6736 | 218593948.2535 | 178514558.3686 | 929679415.0218 | 26090938.1056 | 216266810.1746 | 311764971.8134 | 468845708.5001 | 150609452483.3159 | 1972730283.4938 | 2070450477.2346 | 1865428292.6825 | 174292537.6378 | 607366230.6588 | 707950549.1209 | 834548892.018 | 276875690.8964 | 562164099.0427 | 25519166.7705 | 108039541.9578 | 22525426.4326 | 22788393.2834 | 905633708.5982 | 29073662.1784 | 823821163.4892 | 5013990710.499 | 682578359.8607 | 175304108.9887 | 2.0899e+12 | 2689519.8553 | 1005953.6409 | 1583242.4865 |  |  | 2.2622e+12
1194 | 1180614530.9056 | 1178360385.8903 | 217485232.463 | 163544157.1025 | 1073773159.3695 | 23704137.5113 | 207288465.8207 | 307366931.1514 | 456901082.1359 | 146957505766.7019 | 1981821561.524 | 1885382412.4443 | 1983363663.4977 | 186318949.9342 | 606358320.4836 | 725275156.5748 | 750707251.997 | 350248648.4041 | 597075553.3205 | 25923678.7456 | 109628136.7235 | 22301464.8687 | 23688346.8277 | 697839065.3177 | 27997416.8979 | 1182089908.6625 | 6766372861.0865 | 636832845.9237 | 191223058.9371 | 1.8557e+12 | 2444557.6997 | 941834.0899 | 1638327.6509 |  |  | 2.0263e+12
1195 | 1098649909.2385 | 1162622129.0938 | 203875465.9083 | 141113368.6181 | 1038891725.5895 | 20331747.0676 | 224067041.4915 | 316581387.6885 | 494424167.6128 | 159113345122.126 | 1974610829.4507 | 2153317115.2591 | 2057277932.7469 | 198163298.8601 | 615477171.7067 | 692251912.9306 | 612531220.6292 | 358783523.5928 | 514223933.0107 | 24131849.4336 | 128911009.6127 | 24597644.1722 | 22559851.8878 | 739649874.2644 | 26681034.4548 | 1112527952.3693 | 5501716655.4873 | 658636869.6124 | 168631696.6743 | 1.3193e+12 | 2347718.5317 | 939682.5431 | 1640249.4678 |  |  | 1.5007e+12
1196 | 1028503772.1262 | 1025768160.5805 | 188872878.1597 | 164481557.7314 | 843443475.7774 | 22683685.834 | 194884453.3644 | 277735124.1967 | 462133409.8058 | 131255269323.0616 | 1987169760.2752 | 2129246894.0373 | 2151733882.292 | 196469182.976 | 625116357.2251 | 691230133.1684 | 581799165.9077 | 273974309.0764 | 553929562.8667 | 23774419.9518 | 131486152.1326 | 21695072.6192 | 21433480.3419 | 776827608.9768 | 28655484.1028 | 993358007.4261 | 7052203413.1983 | 534144778.8513 | 199394650.0404 | 2.0363e+12 | 2794644.1322 | 1002019.5464 | 1539127.4062 |  |  | 2.1908e+12
1197 | 1253731273.8094 | 1124159993.2169 | 222009447.5415 | 174890589.7148 | 1039680880.3035 | 23664281.1754 | 187821669.6876 | 281470949.1613 | 483886465.4085 | 144787340188.8597 | 1505784503.7594 | 2003685102.7765 | 1940151926.5207 | 196814208.3146 | 617374185.4649 | 710516074.3622 | 753793069.1088 | 300041886.4836 | 510911394.6712 | 26262435.895 | 106682989.264 | 20347553.0308 | 24285475.8832 | 892967806.1099 | 28107844.824 | 1089085501.8425 | 6149095727.6495 | 695785541.4186 | 170111616.4383 | 2.6925e+12 | 2401216.5981 | 955994.3149 | 1652466.6351 |  |  | 2.8598e+12
1198 | 1200432158.926 | 1201854664.6458 | 206017327.4432 | 181761878.8485 | 976670894.5693 | 23175155.753 | 205281499.5244 | 304296954.2857 | 494760082.3835 | 147984102202.8018 | 1984439908.3339 | 1891117618.0015 | 1738631549.9822 | 163471399.7892 | 646427016.9387 | 639656753.282 | 844657134.1707 | 311863903.1253 | 563944315.7266 | 25843175.4503 | 131468599.8499 | 21478051.5274 | 26083778.7808 | 788928657.5413 | 23368633.5954 | 949810363.3199 | 6840053134.8334 | 710948401.2593 | 164154404.8134 | 2.1868e+12 | 2401218.2762 | 904914.5114 | 1657207.2207 |  |  | 2.358e+12
1199 | 1199179928.7213 | 1220628266.4128 | 211520432.5857 | 179268810.2079 | 1024941366.2414 | 24811903.2319 | 205590187.723 | 317189792.1705 | 482377988.6607 | 143914134096.8445 | 1738963985.1974 | 2010091403.6376 | 1940887490.8326 | 194029546.505 | 556447986.1069 | 698688783.7338 | 897198996.4697 | 330381578.8026 | 514075676.5565 | 26191823.924 | 123539748.8301 | 23874112.4569 | 22839395.4971 | 724225545.1195 | 26475299.8973 | 1153293391.9844 | 5837767095.5796 | 600369834.972 | 198062461.0581 | 2.0117e+12 | 2568781.8091 | 952572.9839 | 1637102.8604 |  |  | 2.1781e+12
1200 | 1199718873.016 | 1134615566.0225 | 205931463.6009 | 154306083.7363 | 1073834621.0845 | 24544709.922 | 208084872.233 | 322858524.4534 | 498891750.8848 | 123464167476.8602 | 1846098858.062 | 1758468234.7198 | 2203365020.6031 | 169528240.3085 | 621579002.6181 | 676761847.2436 | 757596812.7135 | 315334438.4539 | 579783558.5188 | 22670457.5405 | 104016814.3803 | 19599873.8343 | 23810584.7892 | 885862241.9492 | 25560702.0928 | 1171022741.3946 | 6661062739.5304 | 686720821.9499 | 190890197.7332 | 2.0311e+12 | 2403316.5339 | 895588.0831 | 1600546.7462 |  |  | 2.1781e+12